## PDT
Project Code | Project Name | Plant | PP Description | Supplier | Po Number | Category Family | Sub Category | Project Currency | Total Budget | Currency | PO Amount | Calc. Variance | PO Variance Categorization | RFQ Baseline | RFQ Actual | BID Actual Date | TBE Baseline | TBE Actual | CBE Actual | PO Baseline | PO Actual | Delivery Baseline | Delivery Contractual | Delivery Actual | Supplier On Time Delivery (Days) | Warranty Period (Months) | Calc. GFI/GFO (Days)
503188 | Lake Manatee WTS | Oakville | Compressed Air System | MATTEI COMPRESSORS INC. | 4503353670 | Rotating Equipment | Compressors | USD | 46230 | USD | 47610 | -1380 | Proposed Supplier Incapable Of Executing | 2019-11-01 | 2019-12-12 | 2020-01-16 | 2019-11-15 | 2020-01-24 | 2020-01-07 | 2019-12-02 | 2020-02-02 | 2020-02-05 | 2020-03-15 | 2020-02-24 | 20 | 30 | 52
503188 | Lake Manatee WTS | Oakville | Angle Seat Valve | BURKERT-CONTROMATIC INC. | 4503393480 | Flow Control | Metal Isolation Valves | USD | 5829 | USD | 5829 | 0 | Market Impact | 2019-11-01 | 2020-03-06 | 2020-04-07 | 2019-11-15 | 2020-04-15 | 2020-03-18 | 2019-12-02 | 2020-04-21 | 2020-02-05 | 2020-08-03 | 2020-05-05 | 90 | 12 | 46
503188 | Lake Manatee WTS | Oakville | Ball Valve | CONBRACO INDUSTRIES INC | 4503400072 | Flow Control | Metal Isolation Valves | USD | 13067 | USD | 13067 | 0 | Design Optimizations | 2019-11-01 | 2019-03-19 | 2020-04-21 | 2019-11-15 | 2020-04-29 | 2019-10-11 | 2019-12-02 | 2020-05-05 | 2020-02-05 | 2020-05-05 | 2020-03-21 | 45 | 12 | 413
503188 | Lake Manatee WTS | Oakville | Blower | AERZEN CANADA INC. | 4503348784 | Rotating Equipment | Ele-Control Panels | USD | 88968 | USD | 61247 | 27721 | Supplier Competitions / Negotiation | 2020-02-12 | 2019-12-01 | 2020-01-07 | 2020-03-01 | 2020-01-14 | 2020-03-23 | 2020-03-15 | 2020-01-22 | 2020-07-15 | 2020-01-22 | 2020-04-18 | -87 | 30 | 52
503188 | Lake Manatee WTS | Oakville | Butterfly Valve | ROTORK CONTROLS, INC. | 4503266178 | Flow Control | Metal Isolation Valves | USD | 664454 | USD | 664454 | 0 | Design Optimizations | 2019-11-01 | 2019-06-12 | 2019-07-20 | 2019-11-15 | 2019-07-30 | 2019-10-09 | 2019-12-02 | 2019-08-05 | 2020-02-05 | 2019-08-05 | 2019-11-05 | -92 | 12 | 54
503188 | Lake Manatee WTS | Oakville | Butterfly Valve 2 | LAKESIDE PROCESS CONTROLS LTD. | 4503266459 | Flow Control | Metal Isolation Valves | USD | 229348 | USD | 296748 | -67400 | Not included in Proposal / RFQ | 2019-11-01 | 2019-06-19 | 2019-07-23 | 2019-11-15 | 2019-07-31 | 2019-10-12 | 2019-12-02 | 2019-08-07 | 2020-02-05 | 2020-01-15 | 2020-01-25 | -10 | 12 | 49
503188 | Lake Manatee WTS | Oakville | Check Valve | BRAY CONTROLS CANADA LTD. | 4503418530 | Flow Control | Metal Isolation Valves | USD | 47369 | USD | 48636 | -1267 | Not included in Proposal / RFQ | 2019-11-01 | 2020-04-28 | 2020-06-05 | 2019-11-15 | 2020-06-13 | 2020-04-17 | 2019-12-02 | 2020-06-19 | 2020-02-05 | 2020-10-02 | 2020-06-04 | 120 | 12 | 52
503188 | Lake Manatee WTS | Oakville | Anaylzers & Sensors | Hach Sales & Service Canada Ltd. | 4503397947 | Electrical & Instrumentation | Carbon Steel | USD | 41849 | USD | 31559 | 10290 | Design Optimizations | 2020-02-18 | 2020-04-10 | 2020-04-16 | 2020-03-01 | 2020-04-19 | 2020-04-17 | 2020-03-12 | 2020-04-26 | 2020-06-15 | 2020-04-26 | 2020-05-21 | -25 | 18 | 16
503188 | Lake Manatee WTS | Oakville | Control System Spare Parts and Licensing Software on Laptop | KELTOUR CONTROLS INC. | 4503352965 | Electrical & Instrumentation | Ele-Control Panels | USD | 432119 | USD | 432119 | 0 | Proposed Supplier Incapable Of Executing | 2020-02-18 | 2019-12-16 | 2020-01-14 | 2020-03-01 | 2020-01-25 | 2020-03-16 | 2020-03-12 | 2020-01-31 | 2020-06-15 | 2020-06-02 | 2020-06-08 | -6 | 18 | 46
503188 | Lake Manatee WTS | Oakville | Hot Water Back Pulse CIP Pumps | Flowserve US Inc. | 4503380733 | Rotating Equipment | Centrifugal Pumps | USD | 441964 | USD | 369895 | 72069 | Supplier Competitions / Negotiation | 2020-02-12 | 2020-02-03 | 2020-03-11 | 2020-03-01 | 2020-03-17 | 2020-06-02 | 2020-03-15 | 2020-03-24 | 2020-07-15 | 2020-09-30 | 2020-08-22 | 39 | 30 | 50
503188 | Lake Manatee WTS | Oakville | Frame 64/96M,1000V3 Bracket | 3D MECHANICAL | 4503301290 | Fabrication | Centrifugal Pumps | USD | 57411 | USD | 57411 | 0 | Design Optimizations | 2020-04-28 | 2019-09-03 | 2019-10-01 | 2020-05-13 | 2019-10-09 | 2020-02-17 | 2020-05-23 | 2019-10-16 | 2020-08-03 | 2019-12-04 | 2020-04-03 | -121 | 12 | 43
503188 | Lake Manatee WTS | Oakville | Permeate Pumps & Spare Parts Kit | GOULDS PUMPS | 4503293847 | Rotating Equipment | Centrifugal Pumps | USD | 994678 | USD | 915131 | 79547 | Frame Agreements | 2020-02-12 | 2019-08-07 | 2019-09-17 | 2020-03-01 | 2019-09-28 | 2020-01-25 | 2020-03-15 | 2019-10-01 | 2020-07-15 | 2019-10-01 | 2020-02-22 | -144 | 30 | 55
503188 | Lake Manatee WTS | Oakville | Pressure Gauge Instruments | CONVAL PROCESS SOLUTIONS INC | 4503401027 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 7050 | USD | 5067 | 1983 | Supplier Competitions / Negotiation | 2020-02-18 | 2019-05-01 | 2020-04-21 | 2020-03-01 | 2020-04-28 | 2019-11-22 | 2020-03-12 | 2020-05-06 | 2020-06-15 | 2020-05-06 | 2020-05-26 | -20 | 18 | 371
503188 | Lake Manatee WTS | Oakville | Air Header Permeate Header and Frame | NV PIPING SYSTEMS INC. | 4503294324 | Fabrication | Metal Isolation Valves | USD | 116107 | USD | 176527 | -60420 | Size/ Weight/ Quantity Underestimated | 2020-04-28 | 2019-08-22 | 2019-09-17 | 2020-05-13 | 2019-09-24 | 2020-02-11 | 2020-05-23 | 2019-10-02 | 2020-08-03 | 2019-12-19 | 2020-04-11 | -114 | 12 | 41
503188 | Lake Manatee WTS | Oakville | Instrument - Transmitters, level, Pressure, Temp & Sol & Btfly Lug Valve | LAKESIDE PROCESS CONTROLS LTD. | 4503391407 | Electrical & Instrumentation | Inst-Multiparam Transmitters, Controllers | USD | 219008 | USD | 199033 | 19975 | Supplier Competitions / Negotiation | 2020-02-18 | 2020-03-01 | 2020-03-31 | 2020-03-01 | 2020-04-07 | 2020-04-17 | 2020-03-12 | 2020-04-13 | 2020-06-15 | 2020-04-13 | 2020-05-14 | -31 | 18 | 43
503188 | Lake Manatee WTS | Oakville | Air Release, Back Pressure Valve, Injec Quil | PROCESS & STEAM SPECIALTIES | 4503417897 | Flow Control | Air Emissions Control (Scrubbers, ESP) | USD | 31661 | USD | 32817 | -1156 | Single Sourced | 2019-11-01 | 2020-05-07 | 2020-06-01 | 2019-11-15 | 2020-06-09 | 2020-02-23 | 2019-12-02 | 2020-06-16 | 2020-02-05 | 2020-06-16 | 2020-04-11 | 66 | 12 | 40
503188 | Lake Manatee WTS | Oakville | Sample Pump | MCPHEE ENTERPRISES | 4503354322 | Rotating Equipment | Centrifugal Pumps | USD | 11040 | USD | 11040 | 0 | Size/ Weight/ Quantity Underestimated | 2020-02-12 | 2020-01-05 | 2020-01-16 | 2020-03-01 | 2020-01-28 | 2020-04-10 | 2020-03-15 | 2020-02-04 | 2020-07-15 | 2020-04-02 | 2020-05-24 | -52 | 30 | 30
503188 | Lake Manatee WTS | Oakville | Instrument - Transmitter, Temperature | SPD Sales Limited | 4503400628 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 12915 | USD | 12915 | 0 | Size/ Weight/ Quantity Underestimated | 2020-05-08 | 2020-04-04 | 2020-04-18 | 2020-05-08 | 2020-04-28 | 2020-05-08 | 2020-05-08 | 2020-05-06 | 2020-05-08 | 2020-06-11 | 2020-05-25 | 17 | 18 | 32
503206 | CARLTON EDR PH 2 | Oakville | DC Power Supply Panel | Keltour US Inc. | 4503600241 | Electrical & Instrumentation | Ele-Electrical Supply (Inc Cable Tray) | USD | 319935 | USD | 436473 | -116538 | Size/ Weight/ Quantity Underestimated | 2021-05-28 | 2021-08-01 | 2021-06-11 | 2021-06-18 | 2021-08-01 | 2021-08-01 | 2021-07-06 | 2021-06-11 | 2021-10-05 | 2021-09-04 | 2021-09-19 | -15 | 18 | -51
503206 | CARLTON EDR PH 2 | Oakville | EDR Control Panel & JB | KELTOUR CONTROLS INC. | 4503589063 | Electrical & Instrumentation | Ele-Control Panels | USD | 110108 | USD | 107345 | 2763 | Frame Agreements | 2021-05-26 | 2021-04-24 | 2021-05-20 | 2021-06-16 | 2021-07-23 | 2021-07-23 | 2021-07-04 | 2021-05-21 | 2021-10-05 | 2021-10-21 | 2021-10-13 | 8 | 18 | 27
503206 | CARLTON EDR PH 2 | Oakville | Transformer | FRANKLIN EMPIRE INC. | 4503607643 | Electrical & Instrumentation | Ele-Transformers, Power Supplies | USD | 76275 | CAD | 65340 | 10935 | Supplier Competitions / Negotiation | 2021-05-25 | 2021-08-12 | 2021-05-20 | 2021-06-15 | 2021-08-12 | 2021-08-12 | 2021-07-02 | 2021-06-24 | 2021-10-04 | 2021-11-05 | 2021-10-20 | 16 | 18 | -49
503206 | CARLTON EDR PH 2 | Oakville | Disconnect Switch for Conc Pump vfd | ABB INC. | 4503588338 | Electrical & Instrumentation | Ele-Electrical Others | USD | 6515 | USD | 6776 | -261 | Single Sourced | 2021-05-28 | 2021-04-22 | 2021-05-05 | 2021-06-18 | 2021-07-14 | 2021-07-14 | 2021-07-06 | 2021-05-18 | 2021-10-05 | 2021-05-18 | 2021-07-27 | -70 | 18 | 26
503206 | CARLTON EDR PH 2 | Oakville | Inlet Module, Two Lines & Outlet Module & Catwalk | PLASFAB LIMITED | 4503582673 | Fabrication | Platform & Module | USD | 429675 | CAD | 201431 | 228244 | Supplier Competitions / Negotiation | 2021-05-12 | 2021-04-07 | 2021-05-05 | 2021-05-26 | 2021-06-26 | 2021-06-26 | 2021-06-16 | 2021-05-10 | 2021-09-15 | 2021-05-10 | 2021-07-13 | -64 | 12 | 33
503206 | CARLTON EDR PH 2 | Oakville | Concentrate Pump | PFC EQUIPMENT, INC | 4503586596 | Rotating Equipment | Centrifugal Pumps | USD | 64145 | USD | 64145 | 0 | Market Impact | 2021-05-25 | 2021-04-19 | 2021-04-29 | 2021-06-15 | 2021-05-10 | 2021-07-12 | 2021-07-02 | 2021-05-18 | 2021-10-04 | 2021-09-23 | 2021-09-28 | -5 | 30 | 29
504009 | San Luis Obispo | Oakville | Brackets/Frames | PLASFAB LIMITED | 4503513121 | Fabrication | Centrifugal Pumps | USD | 58942 | CAD | 72786 | -13844 | Single Sourced | 2020-12-07 | 2020-12-18 | 2021-01-07 | 2020-12-28 | 2021-01-08 | 2021-01-26 | 2021-01-04 | 2021-01-07 | 2021-03-18 | 2021-02-22 | 2021-03-06 | -12 | 12 | 20
504009 | San Luis Obispo | Oakville | Headers & Spools | NV PIPING SYSTEMS INC. | 4503509634 | Fabrication | Metal Isolation Valves | USD | 70912 | CAD | 62324 | 8588 | Design Optimizations | 2020-12-07 | 2021-12-18 | 2020-12-24 | 2020-12-28 | 2020-12-24 | 2021-06-13 | 2021-01-04 | 2020-12-30 | 2021-03-15 | 2021-02-21 | 2021-03-04 | -11 | 12 | -353
504009 | San Luis Obispo | Oakville | Intrumentation | ENDRESS + HAUSER CANADA LTD. | 4503537926 | Electrical & Instrumentation | Metal Isolation Valves | USD | 14899 | USD | 14899 | 0 | Design Optimizations | 2021-02-07 | 2021-01-27 | 2021-01-27 | 2021-02-07 | 2021-01-26 | 2021-02-07 | 2021-02-07 | 2021-02-19 | 2021-02-07 | 2021-02-19 | 2021-02-13 | 6 | 18 | 23
504009 | San Luis Obispo | Oakville | Pumps (Permeate, Backpulse, Drain) | FLOWSERVE | 4503477787 | Rotating Equipment | Centrifugal Pumps | USD | 102216 | USD | 111950 | -9734 | Estimate Without Market Reference(No Quote) | 2020-10-12 | 2020-10-14 | 2020-10-09 | 2020-11-02 | 2020-12-26 | 2020-12-26 | 2020-11-09 | 2020-10-23 | 2021-03-15 | 2021-03-06 | 2021-03-10 | -4 | 30 | 9
504009 | San Luis Obispo | Oakville | Membrane Blower Package | AERZEN CANADA INC. | 4503500799 | Rotating Equipment | Metal Isolation Valves | USD | 109884 | CAD | 117384 | -7500 | Specs / Requirements Misinterpreted in Proposal | 2020-10-12 | 2020-11-22 | 2020-11-25 | 2020-11-02 | 2021-01-12 | 2021-01-12 | 2020-11-09 | 2020-12-09 | 2021-03-15 | 2021-04-15 | 2021-03-30 | 16 | 30 | 17
504009 | San Luis Obispo | Oakville | Chemical Pump - Citric Acid | Prominent Fluid Controls Inc. | 4503552788 | Rotating Equipment | Centrifugal Pumps | USD | 192948 | CAD | 124460 | 68488 | Design Optimizations | 2020-11-02 | 2021-03-16 | 2021-03-16 | 2020-11-23 | 2021-03-16 | 2021-03-16 | 2020-11-30 | 2021-03-15 | 2021-03-15 | 2021-07-28 | 2021-05-21 | 68 | 30 | -1
504009 | San Luis Obispo | Oakville | Valves | BRAY CONTROLS CANADA LTD. | 4503538035 | Flow Control | Metal Isolation Valves | USD | 65812 | USD | 65812 | 0 | Single Sourced | 2021-01-24 | 2020-12-22 | 2021-02-26 | 2021-01-24 | 2021-02-25 | 2021-02-26 | 2021-01-24 | 2021-02-18 | 2021-01-24 | 2021-02-18 | 2021-02-05 | 13 | 12 | 58
504009 | San Luis Obispo | Oakville | Valves | BRAY CONTROLS CANADA LTD. | 4503542193 | Flow Control | Metal Isolation Valves | USD | 8532 | USD | 8532 | 0 | Supplier Competitions / Negotiation | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-03-26 | 2021-02-26 | 2021-03-26 | 2021-04-23 | 2021-04-09 | 14 | 12 | -28
504009 | San Luis Obispo | Oakville | Air Compressors | Compressor Science Inc. | 4503550047 | Rotating Equipment | Compressors | USD | 19376 | USD | 24184 | -4808 | Not included in Proposal / RFQ | 2020-11-23 | 2020-12-16 | 2021-02-02 | 2020-12-14 | 2021-02-02 | 2021-02-02 | 2020-12-21 | 2021-03-11 | 2021-03-15 | 2021-04-15 | 2021-03-30 | 16 | 30 | 85
504009 | San Luis Obispo | Oakville | Electrical Panels | KELTOUR CONTROLS INC. | 4503487476 | Electrical & Instrumentation | Ele-Electrical Others | USD | 152618 | CAD | 176438 | -23820 | Proposed Supplier Incapable Of Executing | 2020-11-23 | 2020-10-22 | 2020-11-02 | 2020-12-14 | 2020-11-09 | 2020-11-10 | 2020-12-21 | 2020-11-10 | 2021-03-15 | 2021-02-13 | 2021-02-28 | -15 | 18 | 19
504009 | San Luis Obispo | Oakville | Seismic Cals | The Leffler Group | 4503039887 | Fabrication | Metal Isolation Valves | USD | 6500 | USD | 6500 | 0 | Market Impact | 2018-04-10 | 2019-09-27 | 2019-09-27 | 2018-04-10 | 2019-09-27 | 2019-09-27 | 2018-04-10 | 2018-11-11 | 2021-03-15 | 2018-11-11 | 2020-01-12 | -427 | 12 | -320
504096 | San Mateo | Oakville | Tank Cover | CST Industries | 4503647941 | Fabrication | Platform & Module | USD | 875000 | USD | 875000 | 0 | Market Impact | 2022-04-26 | 2021-04-07 | 2021-07-20 | 2022-05-17 | 2021-09-07 | 2021-09-07 | 2022-05-24 | 2021-09-13 | 2022-11-01 | 2022-04-08 | 2022-07-20 | -103 | 12 | 159
504096 | San Mateo | Oakville | Blowers | AERZEN CANADA INC | 4503685081 | Rotating Equipment | Blowers & Fans | USD | 404799 | CAD | 417812 | -13013 | Market Impact | 2022-03-15 | 2021-11-01 | 2021-11-01 | 2022-04-05 | 2021-11-08 | 2021-11-08 | 2022-04-12 | 2021-11-11 | 2022-08-09 | 2021-11-11 | 2022-03-26 | -135 | 30 | 10
504096 | San Mateo | Oakville | Permeate Pumps | GOULDS PUMPS | 4503631050 | Rotating Equipment | Centrifugal Pumps | USD | 353312 | USD | 372841 | -19529 | Market Impact | 2021-05-18 | 2021-06-08 | 2021-07-29 | 2021-06-08 | 2021-07-29 | 2021-07-30 | 2021-06-15 | 2021-07-31 | 2022-01-25 | 2021-07-31 | 2021-10-28 | -89 | 30 | 53
504096 | San Mateo | Oakville | Backpulse Pumps | GOULDS PUMPS | 4503631064 | Rotating Equipment | Centrifugal Pumps | USD | 94050 | USD | 70830 | 23220 | Supplier Competitions / Negotiation | 2021-06-25 | 2021-06-08 | 2021-07-29 | 2021-07-16 | 2021-07-29 | 2021-07-29 | 2021-07-23 | 2021-08-01 | 2022-03-04 | 2021-08-01 | 2021-11-16 | -107 | 30 | 54
504096 | San Mateo | Oakville | Instruments (E&H) | ENDRESS & HAUSER | 4503680474 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 24431 | USD | 24431 | 0 | Proposed Supplier Incapable Of Executing | 2021-09-21 | 2021-09-20 | 2021-10-20 | 2021-10-12 | 2021-11-03 | 2021-11-04 | 2021-10-19 | 2021-11-04 | 2022-02-01 | 2022-01-20 | 2022-01-26 | -6 | 18 | 45
504096 | San Mateo | Oakville | Flow Transmitter (E&H) | ENDRESS & HAUSER | 4503699790 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 47255 | USD | 30757 | 16498 | Supplier Competitions / Negotiation | 2022-01-13 | 2021-11-10 | 2021-11-15 | 2022-01-13 | 2021-12-08 | 2021-12-08 | 2022-01-13 | 2021-12-08 | 2022-01-13 | 2022-03-18 | 2022-02-14 | 32 | 18 | 28
504096 | San Mateo | Oakville | Manual Valves - Ball | Sylvan Automation Ltd. | 4503656578 | Flow Control | Metal Control Valves | USD | 5241 | CAD | 5241 | 0 | Single Sourced | 2021-08-10 | 2021-08-16 | 2021-09-20 | 2021-08-31 | 2021-09-22 | 2021-09-23 | 2021-09-07 | 2021-09-23 | 2022-02-01 | 2021-09-23 | 2021-11-27 | -65 | 12 | 38
504096 | San Mateo | Oakville | Manual Valves - Check | CONVAL PROCESS SOLUTIONS INC | 4503644496 | Flow Control | Metal Control Valves | USD | 50654 | CAD | 51719 | -1065 | Market Impact | 2021-05-18 | 2021-08-16 | 2021-09-01 | 2021-06-08 | 2021-09-01 | 2021-09-01 | 2021-06-15 | 2021-09-01 | 2022-02-01 | 2021-11-22 | 2021-12-27 | -35 | 12 | 16
504096 | San Mateo | Oakville | Manual Valves - Butterfly | BRAY CONTROLS CANADA LTD. | 4503658128 | Flow Control | Metal Control Valves | USD | 42094 | USD | 42094 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-12-10 | 2021-09-10 | 2021-09-27 | 2021-12-10 | 2021-09-27 | 2021-09-27 | 2021-12-10 | 2021-09-27 | 2021-12-10 | 2022-03-11 | 2022-01-24 | 46 | 12 | 17
504096 | San Mateo | Oakville | AutoValves - Butterfly | BRAY CONTROLS CANADA LTD. | 4503650464 | Flow Control | Metal Control Valves | USD | 38176 | USD | 38176 | 0 | Design Optimizations | 2021-07-27 | 2021-08-16 | 2021-09-10 | 2021-08-17 | 2021-09-10 | 2021-09-12 | 2021-08-24 | 2021-09-12 | 2022-02-01 | 2021-09-12 | 2021-11-22 | -71 | 12 | 27
504096 | San Mateo | Oakville | Fabrication- Spools | NV PIPING SYSTEMS INC. | 4503718430 | Fabrication | Stainless Steel | USD | 502616 | CAD | 380272 | 122344 | Supplier Competitions / Negotiation | 2022-05-18 | 2021-11-08 | 2021-11-24 | 2022-06-08 | 2021-12-16 | 2022-01-06 | 2022-06-15 | 2022-01-12 | 2022-10-05 | 2022-08-14 | 2022-09-09 | -26 | 12 | 65
504096 | San Mateo | Oakville | Electrical Panels | KELTOUR CONTROLS INC. | 4503725809 | Electrical & Instrumentation | Ele-PLCs, HMIs | USD | 227744 | CAD | 227744 | 0 | Design Optimizations | 2021-12-02 | 2021-11-20 | 2022-01-20 | 2021-12-23 | 2022-01-20 | 2022-01-21 | 2021-12-30 | 2022-01-24 | 2022-05-26 | 2022-05-30 | 2022-05-28 | 2 | 18 | 65
504096 | San Mateo | Oakville | Compressor | Compressor Science | 450378401 | Rotating Equipment | Compressors | USD | 24377 | USD | 23377 | 1000 | Supplier Competitions / Negotiation | 2022-01-07 | 2022-01-04 | 2022-01-25 | 2022-04-11 | 2022-04-28 | 2022-04-29 | 2022-02-04 | 2022-05-01 | 2022-07-01 | 2022-05-01 | 2022-05-31 | -30 | 30 | 117
504096 | San Mateo | Oakville | Fabrication- Frames | 3D MECHANICAL | 4503718920 | Fabrication | Carbon Steel | USD | 205538 | CAD | 456764 | -251226 | Size/ Weight/ Quantity Underestimated | 2022-03-23 | 2021-11-08 | 2021-11-22 | 2022-04-13 | 2021-12-13 | 2022-01-06 | 2022-04-20 | 2022-01-10 | 2022-08-10 | 2022-08-12 | 2022-08-11 | 1 | 12 | 63
504096 | San Mateo | Oakville | Chemical Skid/Pump | PROMINENT FLUID CONTROLS LTD. | 4503702844 | Rotating Equipment | Dosing Pump | USD | 108130 | CAD | 49872 | 58258 | Supplier Competitions / Negotiation | 2022-01-28 | 2021-11-30 | 2021-12-07 | 2022-02-18 | 2021-12-07 | 2021-12-08 | 2022-02-25 | 2021-12-11 | 2022-07-01 | 2022-03-12 | 2022-05-06 | -55 | 30 | 11
504280 | Dalton GA WTP | Oakville | Cleaning Solution Electric Heater & Drain Valve | ASB HEATING ELEMENTS LIMITED | 4503315973 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | USD | 44356 | USD | 37996 | 6360 | Supplier Competitions / Negotiation | 2020-01-02 | 2019-09-13 | 2019-10-23 | 2020-01-12 | 2019-10-31 | 2019-12-27 | 2020-01-22 | 2019-11-15 | 2020-04-10 | 2020-02-03 | 2020-03-07 | -33 | 18 | 63
504280 | Dalton GA WTP | Oakville | Valve Rack Skid - PIPING | NV PIPING SYSTEMS INC. | 4503316660 | Fabrication | Skid Assembly Outsourced | USD | 379226 | USD | 412420 | -33194 | Estimate Without Market Reference(No Quote) | 2020-04-05 | 2019-09-15 | 2019-10-31 | 2020-04-15 | 2019-11-12 | 2020-02-21 | 2020-04-22 | 2019-11-18 | 2020-07-29 | 2020-01-15 | 2020-04-22 | -98 | 12 | 64
504280 | Dalton GA WTP | Oakville | Valve Rack Skid - FRAME | Baumeier Corp. | 4503315332 | Fabrication | Skid Assembly Outsourced | USD | 114961 | USD | 131559 | -16598 | Proposed Supplier Incapable Of Executing | 2020-04-05 | 2019-09-05 | 2019-10-26 | 2020-04-15 | 2019-11-04 | 2020-02-16 | 2020-04-22 | 2019-11-13 | 2020-07-29 | 2019-11-13 | 2020-03-21 | -129 | 12 | 69
504280 | Dalton GA WTP | Oakville | CIP Tank (with all fittings) & Permeate Storage/Backpulse Tank | Augusta Fiberglass | 4503291603 | Fabrication | Carbon Steel | USD | 64281 | USD | 91152 | -26871 | Proposed Supplier Incapable Of Executing | 2020-04-05 | 2019-08-02 | 2019-09-12 | 2020-04-15 | 2019-09-19 | 2020-01-30 | 2020-04-22 | 2019-09-26 | 2020-07-29 | 2020-04-20 | 2020-06-09 | -50 | 12 | 55
504280 | Dalton GA WTP | Oakville | Presure Transmitter manifolds Isolation & Vent abilities | ENDRESS & HAUSER | 4503313248 | Fabrication | Metal Isolation Valves | USD | 23413 | USD | 23756 | -343 | Market Impact | 2020-04-05 | 2019-09-03 | 2019-10-29 | 2020-04-15 | 2019-11-04 | 2020-02-15 | 2020-04-22 | 2019-11-10 | 2020-07-29 | 2019-11-10 | 2020-03-20 | -131 | 12 | 68
504280 | Dalton GA WTP | Oakville | Pressure Manifold - Iso Valve & Vent Abilities | CONVAL EQUIPMENT LIMITED | 4503313780 | Flow Control | Metal Isolation Valves | USD | 15110 | USD | 11071 | 4039 | Supplier Competitions / Negotiation | 2020-05-15 | 2019-09-06 | 2019-10-22 | 2020-05-25 | 2019-11-01 | 2020-03-14 | 2020-06-01 | 2019-11-08 | 2020-09-21 | 2019-11-08 | 2020-04-15 | -159 | 12 | 63
504280 | Dalton GA WTP | Oakville | VE One PLC Controls System | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503323017 | Electrical & Instrumentation | Ele-Control Panels | USD | 191401 | USD | 169659 | 21742 | Supplier Competitions / Negotiation | 2020-01-11 | 2019-10-03 | 2019-11-15 | 2020-01-25 | 2019-11-20 | 2020-01-22 | 2020-02-04 | 2019-11-27 | 2020-05-12 | 2019-11-27 | 2020-02-18 | -83 | 18 | 55
504280 | Dalton GA WTP | Oakville | Feed Magnetic Flowmeter | ENDRESS & HAUSER | 4503316887 | Electrical & Instrumentation | Ele-Control Panels | USD | 36087 | USD | 36087 | 0 | Single Sourced | 2020-01-11 | 2019-08-18 | 2019-11-01 | 2020-01-25 | 2019-11-11 | 2019-12-30 | 2020-02-04 | 2019-11-18 | 2020-05-12 | 2020-02-11 | 2020-03-27 | -45 | 18 | 92
504280 | Dalton GA WTP | Oakville | Temp Air Scour Feed and BW Switch High | WAJAX INDUSTRIAL COMPONENTS LP. | 4503311303 | Electrical & Instrumentation | Carbon Steel | USD | 5732 | USD | 6660 | -928 | Single Sourced | 2020-01-11 | 2019-09-01 | 2019-10-23 | 2020-01-25 | 2019-10-31 | 2020-01-06 | 2020-02-04 | 2019-11-06 | 2020-05-12 | 2019-12-12 | 2020-02-26 | -76 | 18 | 66
504280 | Dalton GA WTP | Oakville | Feed Self Cleaning Auto Strainer with Pressure Differential Switch & Drain Valve | AMIAD USA INC. | 4503295821 | Rotating Equipment | Chem. Feed Skids (TurnKey) | USD | 236250 | USD | 270845 | -34595 | Proposed Supplier Incapable Of Executing | 2020-03-15 | 2019-08-01 | 2019-09-27 | 2020-03-21 | 2019-10-30 | 2020-01-20 | 2020-04-02 | 2019-10-08 | 2020-07-11 | 2019-10-08 | 2020-02-23 | -138 | 30 | 68
504280 | Dalton GA WTP | Oakville | CIP Pump c/w Motor & Backwash Pump Goulds c/w Motor | Flowserve US Inc. | 4503287910 | Rotating Equipment | Centrifugal Pumps | USD | 76940 | USD | 57441 | 19499 | Frame Agreements | 2020-03-15 | 2019-06-19 | 2019-08-31 | 2020-03-21 | 2019-09-10 | 2019-12-30 | 2020-04-02 | 2019-09-19 | 2020-07-11 | 2020-05-04 | 2020-06-07 | -34 | 30 | 92
504280 | Dalton GA WTP | Oakville | CIP tank mixers | DYNAMIX | 4503311155 | Rotating Equipment | Mixers | USD | 21000 | USD | 16358 | 4642 | Frame Agreements | 2020-03-15 | 2019-09-02 | 2019-10-22 | 2020-03-21 | 2019-10-31 | 2020-02-05 | 2020-04-02 | 2019-11-06 | 2020-07-11 | 2020-03-06 | 2020-05-08 | -63 | 30 | 65
504280 | Dalton GA WTP | Oakville | Air Scour Blower & Acoustic Enclosure (VFD Operated) w/ Line Flow & Temp Switch | AERZEN CANADA INC. | 4503288266 | Rotating Equipment | Carbon Steel | USD | 19380 | USD | 31348 | -11968 | Size/ Weight/ Quantity Underestimated | 2020-03-15 | 2019-07-18 | 2019-09-03 | 2020-03-21 | 2019-09-13 | 2020-01-13 | 2020-04-02 | 2019-09-20 | 2020-07-11 | 2020-05-04 | 2020-06-07 | -34 | 30 | 64
504280 | Dalton GA WTP | Oakville | Air Compressor (Simplex 10HP) Mounted on 250 US gal Horizontal Air Reciever Tank | MATTEI COMPRESSORS INC. | 4503292473 | Rotating Equipment | Vapor Compressor | USD | 16000 | USD | 26343 | -10343 | Specs / Requirements Misinterpreted in Proposal | 2020-03-15 | 2019-07-19 | 2019-09-07 | 2020-03-21 | 2019-09-17 | 2020-01-14 | 2020-04-02 | 2019-09-27 | 2020-07-11 | 2019-09-27 | 2020-02-18 | -144 | 30 | 70
504280 | Dalton GA WTP | Oakville | Turbidity Panel Assembly & Adder Input Output (i/o) for Common Equipment | Hach Company | 4503332866 | Electrical & Instrumentation | Ele-Control Panels | USD | 74147 | USD | 75813 | -1666 | Market Impact | 2020-01-11 | 2019-10-08 | 2019-11-28 | 2020-01-25 | 2019-11-13 | 2020-01-24 | 2020-02-04 | 2019-12-17 | 2020-05-12 | 2019-12-17 | 2020-02-28 | -73 | 18 | 70
504280 | Dalton GA WTP | Oakville | Isolation Inlet Outlet CIP Ricirculation Valves | BRAY CONTROLS CANADA LTD. | 4503316045 | Flow Control | Metal Isolation Valves | USD | 139034 | USD | 145268 | -6234 | Proposed Supplier Incapable Of Executing | 2020-03-10 | 2019-09-01 | 2019-10-23 | 2020-03-20 | 2019-11-03 | 2020-02-02 | 2020-03-30 | 2019-11-09 | 2020-07-05 | 2019-11-09 | 2020-03-07 | -119 | 12 | 69
504280 | Dalton GA WTP | Oakville | Permeate Discharge Valve | CONBRACO INDUSTRIES INC | 4503313835 | Flow Control | Metal Isolation Valves | USD | 7037 | USD | 8293 | -1256 | Market Impact | 2020-03-10 | 2019-08-30 | 2019-10-29 | 2020-03-20 | 2019-11-04 | 2020-02-01 | 2020-03-30 | 2019-11-11 | 2020-07-05 | 2019-11-11 | 2020-03-08 | -118 | 12 | 73
504280 | Dalton GA WTP | Oakville | Permeate Reject Line Vent Air Release Valves | BURKERT-CONTROMATIC INC. | 4503311306 | Flow Control | Air Emissions Control (Scrubbers, ESP) | USD | 32800 | USD | 33044 | -244 | Size/ Weight/ Quantity Underestimated | 2020-03-10 | 2019-09-04 | 2019-10-30 | 2020-03-20 | 2019-11-11 | 2020-02-03 | 2020-03-30 | 2019-11-05 | 2020-07-05 | 2019-11-05 | 2020-03-05 | -121 | 12 | 62
504280 | Dalton GA WTP | Oakville | Manufacturing / Third Party Assembly | TITAN PIPING SYSTEMS INC. | 4503362406 | Fabrication | Carbon Steel | USD | 191360 | USD | 100284 | 91076 | Supplier Competitions / Negotiation | 2020-01-26 | 2020-01-04 | 2020-01-16 | 2020-01-26 | 2020-02-09 | 2020-01-26 | 2020-01-26 | 2020-02-17 | 2020-01-26 | 2020-02-17 | 2020-02-06 | 11 | 12 | 44
504327 | Valencia | Oakville | Skid Frame Fabrication | PLASFAB LIMITED | 4503335138 | Fabrication | Skid Assembly Outsourced | USD | 141355 | CAD | 141356 | -1 | Specs / Requirements Misinterpreted in Proposal | 2019-08-12 | 2019-12-27 | 2019-12-24 | 2019-09-02 | 2019-12-27 | 2019-12-27 | 2019-09-09 | 2019-12-24 | 2020-05-13 | 2020-02-04 | 2020-03-24 | -49 | 12 | -3
504327 | Valencia | Oakville | Skid Frame Painting | BRANT CORROSION CONTROL, | 4503346044 | Fabrication | Skid Assembly Outsourced | USD | 69942 | CAD | 69942 | 0 | Proposed Supplier Incapable Of Executing | 2019-08-12 | 2019-12-27 | 2020-01-07 | 2019-09-02 | 2020-01-07 | 2019-12-27 | 2019-09-09 | 2020-01-18 | 2020-05-13 | 2020-02-15 | 2020-03-30 | -44 | 12 | 22
504327 | Valencia | Oakville | Skid Fabrication & Painting | PLASFAB LIMITED | 4503381646 | Fabrication | Skid Assembly Outsourced | USD | 8438 | CAD | 8438 | 0 | Proposed Supplier Incapable Of Executing | 2019-08-12 | 2019-12-27 | 2019-12-27 | 2019-09-02 | 2019-12-27 | 2019-12-27 | 2019-09-09 | 2020-03-25 | 2020-05-13 | 2020-03-25 | 2020-04-18 | -24 | 12 | 89
504327 | Valencia | Oakville | Skid Frame Painting | PLASFAB LIMITED | 4503396483 | Fabrication | Skid Assembly Outsourced | USD | 46583 | CAD | 46583 | 0 | Proposed Supplier Incapable Of Executing | 2019-08-12 | 2020-01-10 | 2020-04-22 | 2019-09-02 | 2020-01-10 | 2020-01-10 | 2019-09-09 | 2020-04-27 | 2020-02-15 | 2020-06-10 | 2020-04-13 | 58 | 12 | 108
504327 | Valencia | Oakville | Skid Frame Fabrication & Paining | PLASFAB LIMITED | 4503378311 | Fabrication | Skid Assembly Outsourced | USD | 16060 | CAD | 16060 | 0 | Single Sourced | 2019-08-12 | 2019-12-27 | 2019-12-27 | 2019-09-02 | 2019-12-27 | 2019-12-27 | 2019-09-09 | 2020-03-19 | 2020-05-13 | 2020-03-19 | 2020-04-15 | -27 | 12 | 83
504327 | Valencia | Oakville | Skid Fabrication & Painting | PLASFAB LIMITED | 4503405335 | Fabrication | Skid Assembly Outsourced | USD | 31156 | CAD | 31157 | -1 | Estimate Without Market Reference(No Quote) | 2019-08-12 | 2020-01-21 | 2020-05-13 | 2019-09-02 | 2020-01-21 | 2020-01-21 | 2019-09-09 | 2020-01-21 | 2020-01-21 | 2020-07-02 | 2020-04-11 | 82 | 12 | 0
504327 | Valencia | Oakville | WAC Vessel Frames & Brackets | SOUTH GATE ENGINEERING | 450338814 | Fabrication | Carbon Steel | USD | 154660 | USD | 154660 | 0 | Size/ Weight/ Quantity Underestimated | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 2020-04-07 | 0 | 12 | 0
504327 | Valencia | Oakville | Piping | Bell Camp | 4503346691 | Flow Control | Centrifugal Pumps | USD | 329356 | CAD | 368490 | -39134 | Not included in Proposal / RFQ | 2019-08-12 | 2019-12-09 | 2020-01-17 | 2019-09-02 | 2020-01-17 | 2019-12-09 | 2019-09-09 | 2020-01-20 | 2020-04-03 | 2020-04-06 | 2020-04-04 | 2 | 12 | 42
504327 | Valencia | Oakville | Pump (Flowserve API) | Flowserve S.A.DE C.V | 4503306797 | Rotating Equipment | Centrifugal Pumps | USD | 649964 | USD | 325962 | 324002 | Design Optimizations | 2019-12-22 | 2019-12-22 | 2019-10-02 | 2019-04-01 | 2019-10-02 | 2019-12-22 | 2019-04-08 | 2019-10-27 | 2020-03-23 | 2020-09-12 | 2020-06-17 | 87 | 30 | -56
504327 | Valencia | Oakville | Pump (Sulzer API) | SULZER PUMPS (CANADA) INC. | 4503355268 | Rotating Equipment | Centrifugal Pumps | USD | 242953 | CAD | 242953 | 0 | Not included in Proposal / RFQ | 2020-01-14 | 2020-01-14 | 2020-01-20 | 2019-04-01 | 2020-02-05 | 2020-01-14 | 2019-04-08 | 2020-02-05 | 2020-03-23 | 2020-10-28 | 2020-07-10 | 110 | 30 | 22
504327 | Valencia | Oakville | Pump (Danfoss) | DANFROSS LLC | 4503332154 | Rotating Equipment | Centrifugal Pumps | USD | 66207 | USD | 66207 | 0 | Specs / Requirements Misinterpreted in Proposal | 2019-10-12 | 2019-10-12 | 2019-12-04 | 2019-04-01 | 2019-12-03 | 2019-10-12 | 2019-04-08 | 2019-12-17 | 2020-03-23 | 2020-04-24 | 2020-04-08 | 16 | 30 | 66
504327 | Valencia | Oakville | Pump (Milton Roy) | Milton Roy Company | 4503356704 | Rotating Equipment | Centrifugal Pumps | USD | 87869 | USD | 87869 | 0 | Supplier Competitions / Negotiation | 2019-09-26 | 2019-09-26 | 2020-01-15 | 2019-04-01 | 2020-02-04 | 2019-09-26 | 2019-04-08 | 2020-03-11 | 2020-03-23 | 2020-03-11 | 2020-03-17 | -6 | 30 | 167
504327 | Valencia | Oakville | Pump (Fedco) | FLUID EQUIPMENT DEVELOPMENT | 4503319540 | Rotating Equipment | Centrifugal Pumps | USD | 116245 | USD | 116245 | 0 | Size/ Weight/ Quantity Underestimated | 2019-10-10 | 2020-01-15 | 2019-11-20 | 2019-10-27 | 2019-11-21 | 2020-01-15 | 2019-11-20 | 2019-11-22 | 2020-04-21 | 2019-11-22 | 2020-02-05 | -75 | 30 | -54
504327 | Valencia | Oakville | WAC Vessel (S) | SOUTH GATE ENGINEERING | 4503388141 | Fabrication | Carbon Steel | USD | 625758 | USD | 732636 | -106878 | Market Impact | 2019-02-25 | 2019-09-15 | 2019-09-15 | 2019-03-18 | 2019-09-15 | 2019-09-15 | 2019-03-25 | 2020-04-04 | 2020-01-31 | 2020-04-04 | 2020-03-03 | 32 | 12 | 202
504327 | Valencia | Oakville | Painting & Lining | F.D.Thomas | 4503457870 | Fabrication | Centrifugal Pumps | USD | 369600 | USD | 360350 | 9250 | Supplier Competitions / Negotiation | 2019-09-23 | 2020-03-19 | 2020-05-26 | 2019-10-14 | 2020-03-19 | 2020-03-19 | 2019-10-21 | 2020-09-14 | 2020-02-28 | 2020-09-14 | 2020-06-06 | 100 | 12 | 179
504327 | Valencia | Oakville | WAC Vessel Internal | BELL-CAMP MANUFACTURING | 4503388323 | Fabrication | Carbon Steel | USD | 358087 | CAD | 358088 | -1 | Proposed Supplier Incapable Of Executing | 2019-02-25 | 2019-09-17 | 2020-04-07 | 2019-03-18 | 2019-09-17 | 2019-09-17 | 2019-03-25 | 2020-04-08 | 2020-01-31 | 2020-04-08 | 2020-03-05 | 34 | 12 | 204
504327 | Valencia | Oakville | WAC Vessel Internal Installation | F.D.Thomas | 450345787 | Fabrication | Metal Isolation Valves | USD | 97283 | USD | 33690 | 63593 | Design Optimizations | 2020-11-01 | 2020-11-01 | 2020-11-01 | 2020-11-01 | 2020-11-01 | 2020-11-01 | 2020-11-01 | 2020-09-14 | 2020-11-01 | 2020-12-20 | 2020-11-25 | 25 | 12 | -48
504327 | Valencia | Oakville | Hero Feed Tank (Fiberglass) | DIAMOND FIBERGLASS | 4503398038 | Fabrication | Carbon Steel | USD | 31925 | USD | 46705 | -14780 | Market Impact | 2019-07-29 | 2020-04-06 | 2020-04-27 | 2019-08-19 | 2020-04-06 | 2020-04-06 | 2019-08-26 | 2020-05-01 | 2020-03-13 | 2020-12-15 | 2020-07-29 | 139 | 12 | 25
504327 | Valencia | Oakville | Decarbonator Vessel (Fiberglass) | DIAMOND FIBERGLASS | 4503370391 | Fabrication | Carbon Steel | USD | 168030 | USD | 217335 | -49305 | Proposed Supplier Incapable Of Executing | 2019-07-29 | 2020-04-06 | 2020-02-18 | 2019-08-19 | 2020-04-06 | 2020-04-06 | 2019-08-26 | 2020-03-05 | 2020-05-25 | 2020-12-15 | 2020-09-04 | 102 | 12 | -32
504327 | Valencia | Oakville | Filter (Cartridge) | FIL-TREK CORPORATION | 4503344294 | Flow Control | Carbon Steel | USD | 85145 | USD | 87290 | -2145 | Not included in Proposal / RFQ | 2019-09-09 | 2019-12-09 | 2020-01-08 | 2019-09-30 | 2020-01-13 | 2019-12-09 | 2019-10-07 | 2020-03-10 | 2020-03-03 | 2020-03-10 | 2020-03-06 | 4 | 12 | 92
504327 | Valencia | Oakville | Butterfly Valves (Bray) | BRAY CONTROLS CANADA LTD. | 4503322015 | Flow Control | Metal Isolation Valves | USD | 421210 | USD | 421210 | 0 | Size/ Weight/ Quantity Underestimated | 2019-08-12 | 2019-11-25 | 2019-11-26 | 2019-09-02 | 2019-11-25 | 2019-11-25 | 2019-09-09 | 2019-11-26 | 2020-03-09 | 2019-11-26 | 2020-01-17 | -52 | 12 | 1
504327 | Valencia | Oakville | Ball Valves (Bray) | BRAY CONTROLS CANADA LTD. | 4503329557 | Flow Control | Metal Isolation Valves | USD | 35952 | USD | 35952 | 0 | Proposed Supplier Incapable Of Executing | 2019-08-12 | 2020-01-24 | 2019-12-17 | 2019-09-02 | 2019-12-16 | 2020-01-24 | 2019-09-09 | 2019-11-12 | 2020-03-09 | 2020-07-08 | 2020-05-08 | 61 | 12 | -73
504327 | Valencia | Oakville | Check Valves (Crane) | CRANE SUPPLY | 4503334890 | Flow Control | Metal Isolation Valves | USD | 112665 | CAD | 112665 | 0 | Proposed Supplier Incapable Of Executing | 2019-08-12 | 2019-12-13 | 2019-12-19 | 2019-09-02 | 2019-12-15 | 2019-12-13 | 2019-09-09 | 2019-12-23 | 2020-03-09 | 2020-04-15 | 2020-03-27 | 19 | 12 | 10
504327 | Valencia | Oakville | Valves (Fisher) | LAKESIDE PROCESS CONTROLS LTD. | 4503340866 | Flow Control | Metal Isolation Valves | USD | 153114 | USD | 340548 | -187434 | Size/ Weight/ Quantity Underestimated | 2019-08-12 | 2019-11-25 | 2020-01-08 | 2019-09-02 | 2020-01-08 | 2019-11-25 | 2019-09-09 | 2020-01-09 | 2020-03-09 | 2020-01-09 | 2020-02-08 | -30 | 12 | 45
504327 | Valencia | Oakville | Instruments (Rosemount) | LAKESIDE PROCESS CONTROLS LTD. | 4503342580 | Electrical & Instrumentation | Ele-Control Panels | USD | 66363 | USD | 66363 | 0 | Single Sourced | 2019-08-12 | 2019-11-20 | 2020-01-08 | 2019-09-02 | 2020-01-08 | 2019-11-20 | 2019-09-09 | 2020-01-17 | 2020-02-25 | 2020-02-28 | 2020-02-26 | 2 | 18 | 58
504327 | Valencia | Oakville | Instruments (Ashcroft) | CONVAL EQUIPMENT LIMITED | 4503343243 | Electrical & Instrumentation | Carbon Steel | USD | 43424 | USD | 35108 | 8316 | Supplier Competitions / Negotiation | 2019-08-12 | 2019-11-18 | 2020-01-14 | 2019-09-02 | 2020-01-13 | 2019-11-18 | 2019-09-09 | 2020-01-13 | 2020-02-25 | 2020-01-13 | 2020-02-03 | -21 | 18 | 56
504327 | Valencia | Oakville | Instruments (E&H) | ENDRESS & HAUSER | 4503344037 | Electrical & Instrumentation | Centrifugal Pumps | USD | 247594 | USD | 218286 | 29308 | Design Optimizations | 2019-08-12 | 2020-01-28 | 2020-01-28 | 2019-09-02 | 2020-01-28 | 2020-01-28 | 2019-09-09 | 2020-07-16 | 2020-02-25 | 2020-07-16 | 2020-05-06 | 71 | 18 | 170
504327 | Valencia | Oakville | Instruments (FCI) | AVENSYS | 4503363962 | Electrical & Instrumentation | Centrifugal Pumps | USD | 59426 | CAD | 48622 | 10804 | Supplier Competitions / Negotiation | 2019-08-12 | 2019-11-18 | 2020-02-24 | 2019-09-02 | 2019-11-18 | 2019-11-18 | 2019-09-09 | 2020-02-21 | 2020-02-25 | 2020-02-21 | 2020-02-23 | -2 | 18 | 95
504327 | Valencia | Oakville | Instruments (Hach) | Hach Company | 4503373944 | Electrical & Instrumentation | Centrifugal Pumps | USD | 239057 | USD | 239057 | 0 | Not included in Proposal / RFQ | 2019-08-12 | 2019-11-26 | 2019-11-27 | 2019-09-02 | 2019-11-26 | 2019-11-26 | 2019-09-09 | 2020-03-11 | 2020-02-25 | 2020-03-11 | 2020-03-03 | 8 | 18 | 106
504327 | Valencia | Oakville | Instruments | CONVAL EQUIPMENT LIMITED | 4503379256 | Electrical & Instrumentation | Centrifugal Pumps | USD | 61507 | USD | 61508 | -1 | Specs / Requirements Misinterpreted in Proposal | 2019-08-12 | 2019-12-01 | 2019-12-01 | 2019-09-02 | 2019-12-01 | 2019-12-01 | 2019-09-09 | 2020-03-21 | 2020-03-09 | 2020-03-21 | 2020-03-15 | 6 | 18 | 111
504327 | Valencia | Oakville | Variable frequency Drive | WESCO DISTRIBUTION CANADA INC. | 4503311922 | Electrical & Instrumentation | Carbon Steel | USD | 408528 | CAD | 538388 | -129860 | Estimate Without Market Reference(No Quote) | 2019-07-15 | 2019-12-11 | 2019-10-18 | 2019-08-05 | 2019-11-08 | 2019-12-11 | 2019-08-12 | 2019-12-11 | 2020-05-08 | 2019-12-11 | 2020-02-23 | -74 | 18 | 0
504327 | Valencia | Oakville | Junction Box | MACHINE CONTROL SYSTEMS | 4503377058 | Electrical & Instrumentation | Metal Isolation Valves | USD | 11883 | CAD | 25049 | -13166 | Size/ Weight/ Quantity Underestimated | 2019-07-15 | 2019-12-11 | 2019-12-11 | 2019-08-05 | 2019-12-11 | 2019-12-11 | 2019-08-12 | 2020-03-16 | 2020-05-08 | 2020-03-16 | 2020-04-11 | -26 | 18 | 96
504327 | Valencia | Oakville | Resin | DDP Specialty Electronics Materials | 4503476177 | Flow Control | Metal Isolation Valves | USD | 687189 | USD | 621060 | 66129 | Supplier Competitions / Negotiation | 2019-09-23 | 2020-05-10 | 2020-05-10 | 2019-10-07 | 2020-05-10 | 2020-05-10 | 2019-10-21 | 2020-10-21 | 2020-04-30 | 2020-12-26 | 2020-08-28 | 120 | 12 | 164
504327 | Valencia | Oakville | Duct Work | DIAMOND FIBERGLASS | 4503441170 | Fabrication | Metal Isolation Valves | USD | 35088 | USD | 26550 | 8538 | Frame Agreements | 2019-12-18 | 2020-04-12 | 2020-04-12 | 2020-01-02 | 2020-04-12 | 2020-04-12 | 2020-01-17 | 2020-08-07 | 2020-02-28 | 2020-08-07 | 2020-05-18 | 81 | 12 | 117
504327 | Valencia | Oakville | Decarbonator Fan | GENERAL AIR PRODUCTS | 4503426294 | Rotating Equipment | Ele-Control Panels | USD | 98778 | USD | 158862 | -60084 | Proposed Supplier Incapable Of Executing | 2019-11-24 | 2020-03-16 | 2020-03-16 | 2019-12-07 | 2020-03-16 | 2020-03-16 | 2019-12-22 | 2020-07-07 | 2020-02-28 | 2020-07-07 | 2020-05-03 | 65 | 30 | 113
504327 | Valencia | Oakville | RIO | MACHINE CONTROL SYSTEMS | 4503406317 | Flow Control | Metal Isolation Valves | USD | 375064 | CAD | 360168 | 14896 | Frame Agreements | 2019-12-18 | 2020-06-08 | 2020-06-08 | 2020-01-02 | 2020-06-08 | 2020-06-08 | 2020-01-17 | 2020-05-21 | 2020-02-28 | 2020-11-28 | 2020-07-14 | 137 | 12 | -18
504327 | Valencia | Oakville | Assembly of Skids | ASLAN TECHNOLOGIES | 4503421534 | Fabrication | Metal Isolation Valves | USD | 783656 | CAD | 853543 | -69887 | Size/ Weight/ Quantity Underestimated | 2020-09-02 | 2020-08-18 | 2020-08-18 | 2020-09-17 | 2020-08-18 | 2020-08-18 | 2020-09-19 | 2020-06-25 | 2020-09-30 | 2020-10-11 | 2020-10-05 | 6 | 12 | -54
504671 | LOUDOUN COUNTY WWTP | Oakville | Fabrication Frames | 3D MECHANICAL | 4503690471 | Fabrication | Stainless Steel | USD | 48883 | CAD | 70941 | -22058 | Estimate Without Market Reference(No Quote) | 2021-10-05 | 2021-10-19 | 2021-10-21 | 2021-10-29 | 2021-09-18 | 2021-11-27 | 2021-11-07 | 2021-11-19 | 2022-02-02 | 2022-02-06 | 2022-02-04 | 2 | 12 | 31
504671 | LOUDOUN COUNTY WWTP | Oakville | Fabrication Spools | NV PIPING SYSTEMS INC. | 4503687927 | Fabrication | Stainless Steel | USD | 65000 | CAD | 24122 | 40878 | Supplier Competitions / Negotiation | 2021-10-05 | 2021-11-15 | 2021-11-17 | 2021-10-29 | 2021-11-14 | 2021-12-04 | 2021-11-07 | 2021-11-15 | 2022-02-02 | 2022-01-24 | 2022-01-28 | -4 | 12 | 0
504671 | LOUDOUN COUNTY WWTP | Oakville | Flow Tranmsitter | ENDRESS + HAUSER CANADA LTD. | 4503677772 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 50000 | USD | 45001 | 4999 | Supplier Competitions / Negotiation | 2021-10-05 | 2021-09-23 | 2021-09-29 | 2021-10-29 | 2021-09-28 | 2021-11-28 | 2021-11-07 | 2021-10-28 | 2022-02-02 | 2022-01-06 | 2022-01-19 | -13 | 18 | 35
504671 | LOUDOUN COUNTY WWTP | Oakville | Turbidity Analyzer | HACH SALES & SERVICE CANADA LTD-REM | 4503713081 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 50000 | CAD | 46270 | 3730 | Supplier Competitions / Negotiation | 2021-10-05 | 2021-11-22 | 2021-11-24 | 2021-10-29 | 2022-01-02 | 2021-12-04 | 2021-11-07 | 2022-01-03 | 2022-02-02 | 2022-02-01 | 2022-02-01 | 0 | 18 | 42
504671 | LOUDOUN COUNTY WWTP | Oakville | Butterfly Valve | BRAY CONTROLS CANADA LTD. | 4503684338 | Flow Control | Metal Control Valves | USD | 40000 | USD | 36967 | 3033 | Frame Agreements | 2021-10-05 | 2021-09-19 | 2021-09-21 | 2021-10-29 | 2021-11-10 | 2021-12-21 | 2021-11-07 | 2021-11-11 | 2022-02-02 | 2022-03-25 | 2022-02-27 | 26 | 12 | 53
504671 | LOUDOUN COUNTY WWTP | Oakville | Diaphragm and solenoid valve | BURKERT-CONTROMATIC INC. | 4503684519 | Flow Control | Plastic Valves (All) | USD | 15000 | CAD | 10374 | 4626 | Supplier Competitions / Negotiation | 2021-10-05 | 2021-09-14 | 2021-09-16 | 2021-10-29 | 2021-09-13 | 2021-11-23 | 2021-11-07 | 2021-11-08 | 2022-02-02 | 2022-01-21 | 2022-01-27 | -6 | 12 | 55
504671 | LOUDOUN COUNTY WWTP | Oakville | Ball Valve and check valve | Duncan Co. | 4503672797 | Flow Control | Plastic Valves (All) | USD | 10000 | USD | 6608 | 3392 | Design Optimizations | 2021-10-05 | 2021-09-14 | 2021-09-16 | 2021-10-29 | 2021-09-14 | 2021-11-23 | 2021-11-07 | 2021-10-19 | 2022-02-02 | 2022-01-11 | 2022-01-22 | -11 | 12 | 35
504765 | Upper Trinity Expansion | Oakville | VFD For Permeate Pump | VFD Solutions Inc. | 4503332665 | Electrical & Instrumentation | Centrifugal Pumps | USD | 176392 | USD | 176392 | 0 | Size/ Weight/ Quantity Underestimated | 2019-10-01 | 2019-10-12 | 2019-11-12 | 2019-10-11 | 2019-11-25 | 2019-11-14 | 2019-10-19 | 2019-12-17 | 2019-12-28 | 2019-12-17 | 2019-12-22 | -5 | 18 | 66
504765 | Upper Trinity Expansion | Oakville | RIO Panel - Control Panel | KELTOUR CONTROLS INC. | 4503321366 | Electrical & Instrumentation | Ele-Control Panels | USD | 10200 | USD | 13072 | -2872 | Size/ Weight/ Quantity Underestimated | 2019-10-01 | 2019-12-15 | 2019-12-26 | 2019-10-11 | 2020-01-08 | 2019-11-19 | 2019-10-19 | 2019-12-25 | 2019-12-28 | 2019-12-25 | 2019-12-26 | -1 | 18 | 10
504765 | Upper Trinity Expansion | Oakville | Modicon Conversion Main Control Panel & Nema 4X Panel AC Instruments Panel AP-17 | GRAYBAR CANADA | 4503309739 | Electrical & Instrumentation | Ele-Control Panels | USD | 204602 | USD | 223069 | -18467 | Estimate Without Market Reference(No Quote) | 2019-10-01 | 2019-09-25 | 2019-10-19 | 2019-10-11 | 2019-10-27 | 2019-11-11 | 2019-10-19 | 2019-11-02 | 2019-12-28 | 2019-11-02 | 2019-11-30 | -28 | 18 | 38
504765 | Upper Trinity Expansion | Oakville | Level Trans (Neutra Tank) Flow Transmitter Magmeter | ENDRESS + HAUSER CANADA LTD. | 4503315931 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 16414 | USD | 16667 | -253 | Specs / Requirements Misinterpreted in Proposal | 2019-10-19 | 2019-10-10 | 2019-10-29 | 2019-10-29 | 2019-11-05 | 2019-12-02 | 2019-11-06 | 2019-11-14 | 2020-01-25 | 2019-11-14 | 2019-12-20 | -36 | 18 | 35
504765 | Upper Trinity Expansion | Oakville | Piping Supports | DOUGLAS BARWICK INC. | 4503331052 | Fabrication | Centrifugal Pumps | USD | 254833 | USD | 320193 | -65360 | Single Sourced | 2020-02-13 | 2019-10-07 | 2019-11-23 | 2020-02-23 | 2019-11-29 | 2020-02-07 | 2020-03-02 | 2019-12-15 | 2020-06-10 | 2019-12-15 | 2020-03-13 | -89 | 12 | 69
504765 | Upper Trinity Expansion | Oakville | Permeate Pumps 100 HP 1200 RPM | GOULDS PUMPS | 4503285857 | Rotating Equipment | Centrifugal Pumps | USD | 378399 | USD | 396238 | -17839 | Single Sourced | 2019-11-14 | 2019-08-02 | 2019-08-31 | 2019-11-24 | 2019-09-07 | 2019-12-01 | 2019-12-02 | 2019-09-14 | 2020-03-31 | 2019-09-14 | 2019-12-22 | -99 | 30 | 43
504765 | Upper Trinity Expansion | Oakville | Drain/Recirc Pump - AP-10 Goulds 3180, 20HP 6x8-14 M | GOULDS PUMPS | 4503333299 | Rotating Equipment | Centrifugal Pumps | USD | 131569 | USD | 133802 | -2233 | Proposed Supplier Incapable Of Executing | 2019-10-20 | 2019-11-16 | 2019-12-03 | 2019-10-30 | 2019-12-10 | 2019-12-28 | 2019-11-07 | 2019-12-17 | 2020-03-06 | 2019-12-17 | 2020-01-26 | -40 | 30 | 31
504765 | Upper Trinity Expansion | Oakville | Keystone Btfly & Acutated Btfly Valves | LAKESIDE PROCESS CONTROLS LTD. | 4503313614 | Flow Control | Metal Isolation Valves | USD | 91279 | USD | 91279 | 0 | Supplier Competitions / Negotiation | 2019-10-15 | 2019-10-06 | 2019-10-29 | 2019-10-25 | 2019-11-04 | 2019-12-18 | 2019-11-02 | 2019-11-11 | 2020-03-01 | 2019-11-11 | 2020-01-05 | -55 | 12 | 36
504765 | Upper Trinity Expansion | Oakville | Neutralization Feed and Pump Swing Check Valves | BRAY CONTROLS CANADA LTD. | 4503318240 | Flow Control | Metal Isolation Valves | USD | 10406 | USD | 11881 | -1475 | Size/ Weight/ Quantity Underestimated | 2019-10-15 | 2019-10-09 | 2019-11-02 | 2019-10-25 | 2019-11-11 | 2019-12-20 | 2019-11-02 | 2019-11-19 | 2020-03-01 | 2019-11-19 | 2020-01-09 | -51 | 12 | 41
504765 | Upper Trinity Expansion | Oakville | Plug Vavle Bodies for Actoator Keystone and Handvalve | ROTORK CONTROLS, INC. | 4503332795 | Flow Control | Metal Isolation Valves | USD | 12760 | USD | 15938 | -3178 | Specs / Requirements Misinterpreted in Proposal | 2019-10-15 | 2019-10-10 | 2019-12-04 | 2019-10-25 | 2019-12-09 | 2019-12-20 | 2019-11-02 | 2019-12-16 | 2020-03-01 | 2019-12-16 | 2020-01-23 | -38 | 12 | 67
504903 | Monsanto | Guelph | FRP Tanks with Piping, Trough, Platforms, Walkways and ladder | THORPE PLANT SERVICES | 4503328287 | Fabrication | Centrifugal Pumps | USD | 643509 | USD | 751411 | -107902 | Specs / Requirements Misinterpreted in Proposal | 2018-11-23 | 2019-08-10 | 2019-08-10 | 2018-12-14 | 2019-11-10 | 2019-08-10 | 2019-01-25 | 2019-11-11 | 2019-07-26 | 2020-04-27 | 2019-12-11 | 138 | 12 | 93
504903 | Monsanto | Guelph | Centrifugal Pumps | SULZER PUMPS (CANADA) INC. | 4503243509 | Rotating Equipment | Centrifugal Pumps | USD | 118422 | USD | 79251 | 39171 | Frame Agreements | 2018-11-23 | 2019-04-28 | 2019-04-16 | 2018-12-14 | 2019-06-23 | 2019-04-28 | 2019-01-11 | 2019-06-25 | 2019-05-31 | 2019-10-01 | 2019-07-31 | 62 | 30 | 58
504903 | Monsanto | Guelph | Chemical Feed Pumps/ Skids | Prominent Fluid Controls Inc. | 4503286374 | Rotating Equipment | Chem. Feed Skids (TurnKey) | USD | 23257 | USD | 13872 | 9385 | Design Optimizations | 2018-12-14 | 2019-05-30 | 2019-03-20 | 2019-02-01 | 2019-09-12 | 2019-05-30 | 2019-02-22 | 2019-09-18 | 2019-07-12 | 2019-11-13 | 2019-09-12 | 62 | 30 | 111
504903 | Monsanto | Guelph | VFD (Drive Only) | ABB INSTRUMENTATION | 4503284204 | Electrical & Instrumentation | Metal Isolation Valves | USD | 52919 | USD | 37006 | 15913 | Design Optimizations | 2019-01-18 | 2019-05-30 | 2019-04-01 | 2019-02-01 | 2019-08-19 | 2019-05-30 | 2019-03-01 | 2019-09-12 | 2019-06-28 | 2019-10-10 | 2019-08-19 | 52 | 18 | 105
504903 | Monsanto | Guelph | Level transmitter and Temperature transmitter | LAKESIDE PROCESS CONTROLS LTD. | 4503317568 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 52830 | USD | 29220 | 23610 | Design Optimizations | 2019-01-25 | 2019-08-15 | 2019-03-08 | 2019-02-22 | 2020-01-08 | 2019-08-15 | 2019-03-22 | 2020-01-08 | 2019-05-31 | 2020-03-04 | 2019-10-17 | 139 | 18 | 146
504903 | Monsanto | Guelph | pH and ORP analyzer (Mettler Toledo) | METTLER TOLEDO THORNTON INC. | 4503252088 | Electrical & Instrumentation | Metal Isolation Valves | USD | 34282 | USD | 65736 | -31454 | Proposed Supplier Incapable Of Executing | 2019-02-01 | 2019-05-12 | 2019-02-14 | 2019-03-01 | 2019-05-31 | 2019-05-12 | 2019-04-05 | 2019-07-09 | 2019-07-12 | 2019-08-20 | 2019-07-31 | 20 | 18 | 58
504903 | Monsanto | Guelph | Flowmeter | LAKESIDE PROCESS CONTROLS LTD. | 4503246260 | Electrical & Instrumentation | Ele-Control Panels | USD | 60617 | USD | 27545 | 33072 | Design Optimizations | 2019-01-11 | 2019-04-15 | 2019-01-16 | 2019-02-01 | 2019-04-15 | 2019-04-15 | 2019-02-15 | 2019-05-24 | 2019-05-31 | 2019-07-19 | 2019-06-24 | 25 | 18 | 39
504903 | Monsanto | Guelph | Skid Fabrication with Painting | 3D MECHANICAL | 4503273689 | Fabrication | Skid Assembly Outsourced | USD | 40000 | USD | 27506 | 12494 | Design Optimizations | 2019-02-15 | 2019-06-04 | 2019-01-21 | 2019-03-01 | 2019-08-06 | 2019-06-04 | 2019-03-22 | 2019-08-22 | 2019-05-31 | 2019-10-17 | 2019-08-08 | 70 | 12 | 79
504903 | Monsanto | Guelph | Check Valve - Centreline | CRANE SUPPLY | 4503239467 | Flow Control | Ele-Control Panels | USD | 16741 | USD | 9764 | 6977 | Design Optimizations | 2018-12-21 | 2019-04-08 | 2019-04-17 | 2019-02-01 | 2019-05-30 | 2019-04-08 | 2019-03-08 | 2019-06-14 | 2019-05-31 | 2019-07-26 | 2019-06-28 | 28 | 12 | 67
504903 | Monsanto | Guelph | HDPE PIPE (Tank Internals) | PLASTIC FUSION FABRICATORS | 4503264482 | Fabrication | Carbon Steel | USD | 70000 | USD | 39250 | 30750 | Frame Agreements | 2019-02-08 | 2019-06-08 | 2019-03-07 | 2019-03-01 | 2019-07-18 | 2019-06-08 | 2019-03-29 | 2019-08-12 | 2019-07-19 | 2019-10-07 | 2019-08-28 | 40 | 12 | 65
504903 | Monsanto | Guelph | Butterfly Valves Actuated from Lakeside + PVC Automated | LAKESIDE PROCESS CONTROLS LTD. | 4503250742 | Flow Control | Metal Isolation Valves | USD | 32631 | USD | 26133 | 6498 | Frame Agreements | 2018-12-21 | 2019-05-02 | 2019-06-06 | 2019-02-08 | 2019-07-04 | 2019-05-02 | 2019-03-15 | 2019-07-04 | 2019-05-31 | 2019-09-12 | 2019-07-22 | 52 | 12 | 63
505197 | COUNTY OF SPOTSYLVANIA | Oakville | Process Pump +Permeate spares parts | BOERGER LLC | 4503580983 | Rotating Equipment | Centrifugal Pumps | USD | 129575 | USD | 123318 | 6257 | Supplier Competitions / Negotiation | 2021-03-10 | 2021-03-10 | 2021-04-14 | 2021-04-14 | 2021-04-23 | 2021-05-11 | 2021-05-06 | 2021-05-06 | 2021-07-12 | 2021-07-12 | 2021-07-12 | 0 | 30 | 57
505197 | COUNTY OF SPOTSYLVANIA | Oakville | Blower +Blower spare parts | AERZEN CANADA INC. | 4503579351 | Rotating Equipment | Ele-Control Panels | USD | 96525 | CAD | 85778 | 10747 | Design Optimizations | 2021-03-10 | 2021-03-10 | 2021-04-23 | 2021-04-14 | 2021-04-23 | 2021-05-19 | 2021-05-06 | 2021-05-04 | 2021-07-12 | 2021-07-28 | 2021-07-20 | 8 | 30 | 55
505197 | COUNTY OF SPOTSYLVANIA | Oakville | Membrane lifting parts | 3D MECHANICAL | 450358096 | Fabrication | Metal Isolation Valves | USD | 26297 | CAD | 38363 | -12066 | Specs / Requirements Misinterpreted in Proposal | 2021-03-10 | 2021-03-10 | 2021-05-04 | 2021-04-14 | 2021-05-04 | 2021-05-12 | 2021-05-06 | 2021-05-06 | 2021-07-12 | 2021-07-14 | 2021-07-13 | 1 | 12 | 57
505197 | COUNTY OF SPOTSYLVANIA | Oakville | Chemical dosing system | PROMINENT FLUID CONTROLS LTD. | 4503584623 | Rotating Equipment | Dosing Pump | USD | 19836 | CAD | 24606 | -4770 | Single Sourced | 2021-03-10 | 2020-12-12 | 2020-12-12 | 2021-04-14 | 2021-05-11 | 2021-03-28 | 2021-05-06 | 2021-05-13 | 2021-07-12 | 2021-06-01 | 2021-06-21 | -20 | 30 | 152
505197 | COUNTY OF SPOTSYLVANIA | Oakville | Electrical panel | MACHINE CONTROL SYSTEMS | 4503668321 | Electrical & Instrumentation | Ele-Electrical Others | USD | 80340 | CAD | 103421 | -23081 | Single Sourced | 2021-03-10 | 2021-09-21 | 2021-10-07 | 2021-04-14 | 2021-10-14 | 2021-07-25 | 2021-05-06 | 2021-10-14 | 2021-07-12 | 2021-12-10 | 2021-09-25 | 76 | 18 | 23
505197 | COUNTY OF SPOTSYLVANIA | Oakville | Air Compressor | Compressor Science Inc. | 4503581341 | Rotating Equipment | Vapor Compressor | USD | 24810 | USD | 29558 | -4748 | Single Sourced | 2021-03-10 | 2020-12-30 | 2020-12-30 | 2021-04-14 | 2021-04-23 | 2021-04-08 | 2021-05-06 | 2021-05-07 | 2021-07-12 | 2021-07-16 | 2021-07-14 | 2 | 30 | 128
505197 | COUNTY OF SPOTSYLVANIA | Oakville | Butterfly Valve | BRAY CONTROLS CANADA LTD. | 4503581404 | Flow Control | Metal Isolation Valves | USD | 5725 | USD | 22606 | -16881 | Estimate Without Market Reference(No Quote) | 2021-03-10 | 2020-03-10 | 2021-05-06 | 2021-04-14 | 2021-05-07 | 2020-11-13 | 2021-05-10 | 2021-05-07 | 2021-07-12 | 2021-07-19 | 2021-07-15 | 4 | 12 | 423
505197 | COUNTY OF SPOTSYLVANIA | Oakville | Flow Transmitter | ENDRESS + HAUSER CANADA LTD. | 4503584753 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 18120 | USD | 22840 | -4720 | Specs / Requirements Misinterpreted in Proposal | 2021-03-10 | 2020-03-10 | 2021-03-12 | 2021-04-15 | 2021-04-22 | 2020-11-28 | 2021-05-15 | 2021-05-12 | 2021-07-15 | 2021-08-18 | 2021-08-01 | 17 | 18 | 428
505202 | IEUA - MBR | Oakville | Spools & Header - SS | NV PIPING SYSTEMS INC. | 4503728209 | Fabrication | Stainless Steel | USD | 296647 | CAD | 373440 | -76793 | Size/ Weight/ Quantity Underestimated | 2022-02-02 | 2022-01-14 | 2022-01-27 | 2022-02-23 | 2022-01-27 | 2022-01-27 | 2022-03-02 | 2022-01-28 | 2022-05-18 | 2022-05-06 | 2022-05-12 | -6 | 12 | 14
505202 | IEUA - MBR | Oakville | Frames & Hanger Arms | BURKES MECHANICAL | 4503729158 | Fabrication | Carbon Steel | USD | 300031 | USD | 466000 | -165969 | Size/ Weight/ Quantity Underestimated | 2022-02-02 | 2022-01-13 | 2022-04-01 | 2022-02-23 | 2022-04-05 | 2022-04-06 | 2022-04-13 | 2022-04-05 | 2022-07-05 | 2022-04-05 | 2022-05-20 | -45 | 12 | 82
505202 | IEUA - MBR | Oakville | Membrane Aeration Blower Package including VFD | AERZEN | 4503498515 | Rotating Equipment | Blowers & Fans | USD | 520470 | USD | 543518 | -23048 | Market Impact | 2021-12-01 | 2020-11-27 | 2020-11-27 | 2021-12-22 | 2020-11-27 | 2020-11-27 | 2021-12-29 | 2020-12-05 | 2022-06-01 | 2022-04-16 | 2022-05-09 | -23 | 30 | 8
505202 | IEUA - MBR | Oakville | Manual Valves - Ball (Apollo) | Sylvan Automation Ltd. | 4503720755 | Flow Control | Metal Control Valves | USD | 5469 | CAD | 5469 | 0 | Proposed Supplier Incapable Of Executing | 2022-01-12 | 2022-01-04 | 2022-01-04 | 2022-02-02 | 2022-01-17 | 2022-01-17 | 2022-02-09 | 2022-01-18 | 2022-05-18 | 2022-05-23 | 2022-05-20 | 3 | 12 | 14
505202 | IEUA - MBR | Oakville | Manual Valves - Butterfly (Bray) | BRAY CONTROLS CANADA LTD. | 4503718437 | Flow Control | Metal Control Valves | USD | 102295 | USD | 102295 | 0 | Design Optimizations | 2022-01-12 | 2022-01-03 | 2022-01-07 | 2022-02-02 | 2022-01-10 | 2022-01-10 | 2022-02-09 | 2022-01-13 | 2022-05-18 | 2022-06-09 | 2022-05-29 | 11 | 12 | 10
505202 | IEUA - MBR | Oakville | Auto Valves - Butterfly (Bray) | BRAY CONTROLS CANADA LTD. | 4503707689 | Flow Control | Metal Control Valves | USD | 123944 | USD | 104065 | 19879 | Supplier Competitions / Negotiation | 2021-12-15 | 2021-12-15 | 2021-12-22 | 2022-01-05 | 2021-12-22 | 2021-12-22 | 2022-01-12 | 2021-12-22 | 2022-05-18 | 2022-05-25 | 2022-05-21 | 4 | 12 | 7
505202 | IEUA - MBR | Oakville | Transmitters (Flow, Level, Pressure) | LAKESIDE PROCESS CONTROLS LTD. | 4503752938 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 20894 | USD | 20894 | 0 | Design Optimizations | 2021-12-29 | 2021-12-10 | 2022-01-07 | 2022-01-19 | 2022-03-04 | 2022-03-04 | 2022-01-26 | 2022-03-06 | 2022-05-18 | 2022-05-02 | 2022-05-10 | -8 | 18 | 86
505202 | IEUA - MBR | Oakville | Transmitters (E&H) | ENDRESS + HAUSER CANADA LTD. | 4503776530 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 13885 | USD | 13885 | 0 | Design Optimizations | 2022-01-12 | 2022-01-12 | 2022-02-15 | 2022-02-02 | 2022-04-12 | 2022-04-13 | 2022-02-09 | 2022-04-17 | 2022-05-18 | 2022-06-19 | 2022-06-03 | 16 | 18 | 95
505202 | IEUA - MBR | Oakville | Level Switches (Flygt) | XYLEM CANADA COMPANY | 4503775964 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 5332 | CAD | 5332 | 0 | Market Impact | 2021-12-15 | 2022-01-04 | 2022-02-04 | 2022-01-05 | 2022-03-17 | 2022-04-06 | 2022-01-12 | 2022-04-18 | 2022-05-18 | 2022-05-05 | 2022-05-11 | -6 | 18 | 104
505202 | IEUA - MBR | Oakville | Filtrate + Backpulse Pumps including Spare Bare Pumps | SULZER PUMPS (CANADA) INC. | 4503713727 | Rotating Equipment | Centrifugal Pumps | USD | 569217 | CAD | 389570 | 179647 | Supplier Competitions / Negotiation | 2021-10-27 | 2021-11-15 | 2022-01-04 | 2021-11-17 | 2022-01-05 | 2022-01-05 | 2021-11-24 | 2022-01-04 | 2022-05-18 | 2022-05-30 | 2022-05-24 | 6 | 30 | 50
505202 | IEUA - MBR | Oakville | VFD for Permeate & Backpulse pump | DAVIS CONTROLS LTD. | 4503816404 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 372048 | USD | 334200 | 37848 | Supplier Competitions / Negotiation | 2022-01-26 | 2022-03-07 | 2022-06-03 | 2022-06-07 | 2022-06-14 | 2022-06-15 | 2022-06-28 | 2022-06-20 | 2022-07-22 | 2023-01-30 | 2022-10-26 | 96 | 18 | 105
505202 | IEUA - MBR | Oakville | Control Panel including HMI Software + PLC Software | KELTOUR CONTROLS INC. | 4503765618 | Electrical & Instrumentation | Ele-Control Panels | USD | 305727 | CAD | 274385 | 31342 | Supplier Competitions / Negotiation | 2021-12-15 | 2022-02-16 | 2022-03-18 | 2022-01-05 | 2022-03-28 | 2022-03-28 | 2022-01-12 | 2022-03-30 | 2022-06-01 | 2022-09-15 | 2022-07-24 | 53 | 18 | 42
505202 | IEUA - MBR | Oakville | Air Compressors and Dryers | Pump Engineering Company | 4503709158 | Rotating Equipment | Compressors | USD | 43440 | USD | 59770 | -16330 | Supplier Competitions / Negotiation | 2022-01-19 | 2021-10-20 | 2021-10-28 | 2022-02-09 | 2021-12-20 | 2021-12-24 | 2022-02-16 | 2021-12-26 | 2022-06-01 | 2022-03-20 | 2022-04-25 | -36 | 30 | 67
505337 | Mountain House | Oakville | Membrane Blower + Spares (Aerzen) - DS | AERZEN CANADA INC | 4503697162 | Rotating Equipment | Blowers & Fans | USD | 90447 | USD | 82814 | 7633 | Supplier Competitions / Negotiation | 2021-09-18 | 2021-10-05 | 2021-10-25 | 2021-02-24 | 2021-12-01 | 2021-09-18 | 2021-03-17 | 2021-11-30 | 2021-03-24 | 2022-04-13 | 2021-10-02 | 193 | 30 | 56
505337 | Mountain House | Oakville | Permeate Pump + Spare(Volgesang )-DS | Vogelsang | 4503715876 | Rotating Equipment | PD Pumps | USD | 63621 | USD | 54814 | 8807 | Frame Agreements | 2021-09-26 | 2021-09-25 | 2021-10-05 | 2021-03-24 | 2022-01-06 | 2021-09-26 | 2021-04-14 | 2022-01-06 | 2021-04-21 | 2022-03-31 | 2021-10-10 | 172 | 30 | 103
505337 | Mountain House | Oakville | Air Compressors (GD) | Compressor Science Inc. | 4503705955 | Rotating Equipment | Compressors | USD | 15888 | USD | 21715 | -5827 | Size/ Weight/ Quantity Underestimated | 2021-08-31 | 2021-09-25 | 2021-09-29 | 2021-03-19 | 2021-12-16 | 2021-08-31 | 2021-04-09 | 2021-12-19 | 2021-04-16 | 2022-02-13 | 2021-09-14 | 152 | 30 | 85
505337 | Mountain House | Oakville | Chemical Pump +Spare - Sodium Hypochlorite (Prominent) | PROMINENT FLUID CONTROLS LTD. | 4503705923 | Rotating Equipment | Dosing Pump | USD | 29310 | USD | 26616 | 2694 | Supplier Competitions / Negotiation | 2021-08-09 | 2021-06-05 | 2021-06-11 | 2021-01-22 | 2021-12-15 | 2021-08-09 | 2021-02-12 | 2021-12-15 | 2021-02-19 | 2022-02-24 | 2021-08-23 | 185 | 30 | 193
505337 | Mountain House | Oakville | VFD (Danfoss) | DAVIS CONTROLS LTD. | 4503706594 | Electrical & Instrumentation | Ele-Control Panels | USD | 49977 | USD | 32926 | 17051 | Design Optimizations | 2021-10-02 | 2021-10-24 | 2021-12-18 | 2021-02-26 | 2021-12-12 | 2021-10-02 | 2021-03-19 | 2021-12-20 | 2021-03-26 | 2022-05-09 | 2021-10-16 | 205 | 18 | 57
505337 | Mountain House | Oakville | Valves | BRAY CONTROLS CANADA LTD. | 4503718348 | Flow Control | Metal Isolation Valves | USD | 29000 | USD | 28456 | 544 | Design Optimizations | 2021-09-06 | 2021-01-06 | 2022-01-20 | 2021-09-06 | 2022-01-16 | 2021-09-06 | 2021-09-06 | 2022-01-16 | 2021-09-06 | 2022-05-08 | 2022-01-06 | 122 | 12 | 375
505337 | Mountain House | Oakville | Instruments | Hach Company | 4503719139 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 32491 | USD | 15173 | 17318 | Supplier Competitions / Negotiation | 2021-09-19 | 2021-12-15 | 2022-01-15 | 2021-03-19 | 2022-01-12 | 2021-09-19 | 2021-04-09 | 2022-01-12 | 2021-04-16 | 2022-03-23 | 2021-10-03 | 171 | 18 | 28
505337 | Mountain House | Oakville | Headers & Spools - DS | NV PIPING SYSTEMS INC. | 4503714540 | Fabrication | Stainless Steel | USD | 70768 | USD | 53801 | 16967 | Frame Agreements | 2021-09-10 | 2021-10-01 | 2021-10-15 | 2021-04-07 | 2021-12-14 | 2021-09-10 | 2021-04-28 | 2021-12-20 | 2021-05-05 | 2022-02-14 | 2021-09-24 | 143 | 12 | 80
505337 | Mountain House | Oakville | Control Panel | MACHINE CONTROL SYSTEMS | 4503708382 | Electrical & Instrumentation | Ele-Control Panels | USD | 84498 | USD | 90517 | -6019 | Estimate Without Market Reference(No Quote) | 2021-09-15 | 2021-12-09 | 2021-12-23 | 2021-02-19 | 2021-12-17 | 2021-09-15 | 2021-03-12 | 2021-12-23 | 2021-03-19 | 2022-04-12 | 2021-09-29 | 195 | 18 | 14
505337 | Mountain House | Oakville | Frames | 3D MECHANICAL | 4503718059 | Fabrication | Stainless Steel | USD | 58822 | USD | 149781 | -90959 | Not included in Proposal / RFQ | 2021-09-09 | 2021-10-21 | 2021-11-05 | 2021-03-05 | 2022-01-11 | 2021-09-09 | 2021-03-26 | 2022-01-11 | 2021-04-02 | 2022-03-16 | 2021-09-23 | 174 | 12 | 82
505525 | Fairlife Western Facilities LLC | Minnetonka | AC TOWER VESSEL | Arrow Tanks | 4503336371 | Fabrication | Carbon Steel | USD | 69000 | USD | 52883 | 16117 | Frame Agreements | 2019-12-30 | 2019-12-30 | 2019-12-30 | 2019-12-30 | 2019-12-29 | 2020-02-06 | 2019-12-30 | 2019-12-30 | 2020-03-17 | 2020-03-17 | 2020-03-17 | 0 | 12 | 0
505525 | Fairlife Western Facilities LLC | Minnetonka | CITY WATER PUMP SKID | PFC EQUIPMENT | 4503338829 | Fabrication | Skid Assembly Outsourced | USD | 13500 | USD | 20412 | -6912 | Size/ Weight/ Quantity Underestimated | 2020-03-03 | 2020-02-26 | 2020-01-06 | 2020-03-04 | 2020-01-06 | 2020-02-26 | 2020-03-10 | 2020-01-06 | 2020-04-17 | 2020-02-17 | 2020-03-18 | -30 | 12 | -51
505525 | Fairlife Western Facilities LLC | Minnetonka | BAG FILTER HOUSING | Duncan Co. | 4503350739 | Flow Control | Carbon Steel | USD | 7000 | USD | 9395 | -2395 | Estimate Without Market Reference(No Quote) | 2020-03-03 | 2020-02-17 | 2019-12-20 | 2020-03-04 | 2020-01-27 | 2020-02-17 | 2020-03-10 | 2020-01-27 | 2020-04-17 | 2020-03-23 | 2020-04-04 | -12 | 12 | -21
505525 | Fairlife Western Facilities LLC | Minnetonka | MOTOR CONTROL ENCLOSURE | WERNER ELECTRIC | 4503348626 | Electrical & Instrumentation | Carbon Steel | USD | 50000 | USD | 46179 | 3821 | Design Optimizations | 2020-03-03 | 2020-03-15 | 2020-01-23 | 2020-03-04 | 2020-01-23 | 2020-03-15 | 2020-03-10 | 2020-01-23 | 2020-04-17 | 2020-05-06 | 2020-04-26 | 10 | 18 | -52
505525 | Fairlife Western Facilities LLC | Minnetonka | PRE RO UV | AQUIONICS, INC. | 4513348054 | Fabrication | Metal Isolation Valves | USD | 20000 | USD | 20003 | -3 | Market Impact | 2020-03-03 | 2020-06-23 | 2020-05-15 | 2020-03-04 | 2020-01-22 | 2020-06-23 | 2020-03-10 | 2020-09-21 | 2020-04-17 | 2020-11-23 | 2020-08-05 | 110 | 12 | 90
505525 | Fairlife Western Facilities LLC | Minnetonka | REMOTE PC | WERNER ELECTRIC | 4503398004 | Electrical & Instrumentation | Ele-Control Panels | USD | 9000 | USD | 10227 | -1227 | Specs / Requirements Misinterpreted in Proposal | 2020-03-03 | 2020-04-04 | 2020-05-01 | 2020-03-04 | 2020-04-29 | 2020-04-04 | 2020-03-10 | 2020-04-29 | 2020-04-17 | 2020-05-06 | 2020-04-26 | 10 | 18 | 25
505525 | Fairlife Western Facilities LLC | Minnetonka | TANK, CITY WATER 10000GAL | DIAMOND FIBERGLASS | 4503334134 | Fabrication | Carbon Steel | USD | 17000 | USD | 26055 | -9055 | Size/ Weight/ Quantity Underestimated | 2020-03-03 | 2019-11-01 | 2019-11-13 | 2020-03-04 | 2019-12-19 | 2020-01-27 | 2020-03-10 | 2019-12-20 | 2020-04-17 | 2020-04-24 | 2020-04-20 | 4 | 12 | 49
505525 | Fairlife Western Facilities LLC | Minnetonka | PERMEATE STORAGE TANK 25000GAL | FELDMEIER EQUIPMENT INC | 4503310490 | Fabrication | Carbon Steel | USD | 85000 | USD | 85755 | -755 | Specs / Requirements Misinterpreted in Proposal | 2020-03-03 | 2019-10-15 | 2019-10-19 | 2020-03-04 | 2019-11-04 | 2020-01-17 | 2020-03-10 | 2019-11-05 | 2020-04-17 | 2020-04-21 | 2020-04-19 | 2 | 12 | 21
505525 | Fairlife Western Facilities LLC | Minnetonka | FINAL UV STERILIZER | AQUIONICS, INC. | 4503348054 | Fabrication | Metal Isolation Valves | USD | 27000 | USD | 26922 | 78 | Supplier Competitions / Negotiation | 2020-03-03 | 2019-11-01 | 2019-11-15 | 2020-03-04 | 2020-01-20 | 2020-01-24 | 2020-03-10 | 2020-01-21 | 2020-04-17 | 2020-04-14 | 2020-04-15 | -1 | 12 | 81
505525 | Fairlife Western Facilities LLC | Minnetonka | ELECTRICAL PANELS (AC & RO) | WERNER ELECTRIC | 4503365226 | Electrical & Instrumentation | Ele-Electrical Others | USD | 24650 | USD | 24650 | 0 | Proposed Supplier Incapable Of Executing | 2020-06-20 | 2020-06-20 | 2020-02-22 | 2020-06-20 | 2020-02-21 | 2020-06-20 | 2020-06-20 | 2020-09-14 | 2020-06-20 | 2020-10-19 | 2020-08-19 | 61 | 18 | 86
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Storage Tank CS incl. Painting | TANK CONNECTION | 4503385160 | Fabrication | Carbon Steel | USD | 320200 | USD | 321219 | -1019 | Single Sourced | 2020-01-23 | 2020-01-08 | 2020-01-22 | 2020-01-30 | 2020-02-06 | 2020-03-26 | 2020-02-14 | 2020-02-08 | 2020-06-12 | 2020-05-23 | 2020-06-02 | -10 | 12 | 31
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Centrifuge | Andritz Separation Technologies Inc. | 4503367523 | Rotating Equipment | Centrifuge | USD | 207500 | USD | 252529 | -45029 | Estimate Without Market Reference(No Quote) | 2020-01-09 | 2020-01-08 | 2020-01-16 | 2020-01-27 | 2020-01-26 | 2020-05-17 | 2020-02-12 | 2020-02-07 | 2020-09-24 | 2020-09-04 | 2020-09-14 | -10 | 30 | 30
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Chemical Feed Systems | PROMINENT FLUID CONTROLS LTD. | 4503429639 | Rotating Equipment | Chem. Feed Skids (TurnKey) | USD | 75000 | CAD | 85992 | -10992 | Not included in Proposal / RFQ | 2020-03-19 | 2020-03-17 | 2020-06-04 | 2020-04-08 | 2020-06-15 | 2020-06-25 | 2020-04-22 | 2020-07-12 | 2020-07-22 | 2020-10-04 | 2020-08-28 | 37 | 30 | 117
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Local Disconnects | ELECTRICAL EQUIPMENT COMP | 4503463818 | Electrical & Instrumentation | Metal Isolation Valves | USD | 5500 | USD | 8600 | -3100 | Not included in Proposal / RFQ | 2020-04-02 | 2020-08-10 | 2020-09-17 | 2020-04-22 | 2020-09-21 | 2020-06-28 | 2020-05-06 | 2020-09-24 | 2020-07-15 | 2020-09-24 | 2020-08-19 | 36 | 18 | 45
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | MCC | ELECTRICAL EQUIPMENT COMP | 4503415270 | Electrical & Instrumentation | Centrifugal Pumps | USD | 205893 | USD | 173244 | 32649 | Design Optimizations | 2020-03-18 | 2020-05-04 | 2020-05-29 | 2020-03-25 | 2020-06-07 | 2020-07-01 | 2020-04-08 | 2020-06-07 | 2020-08-05 | 2020-10-15 | 2020-09-09 | 36 | 18 | 34
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503455151 | Electrical & Instrumentation | Ele-Control Panels | USD | 50000 | CAD | 73940 | -23940 | Size/ Weight/ Quantity Underestimated | 2020-03-18 | 2020-05-04 | 2020-08-28 | 2020-03-25 | 2020-08-31 | 2020-07-02 | 2020-04-08 | 2020-09-04 | 2020-08-05 | 2020-10-16 | 2020-09-10 | 36 | 18 | 123
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Odor Control System | AMBIO BIOFILTRATION LTD | 4503385588 | Rotating Equipment | Carbon Steel | USD | 87340 | USD | 86000 | 1340 | Design Optimizations | 2020-03-02 | 2020-02-18 | 2020-03-31 | 2019-07-01 | 2020-03-30 | 2020-01-22 | 2020-04-03 | 2020-04-02 | 2020-08-14 | 2020-08-06 | 2020-08-10 | -4 | 30 | 44
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Lab Equipments | LUMINULTRA TECHNOLOGOES L | 4503486014 | Electrical & Instrumentation | Ele-Control Panels | USD | 30000 | USD | 21447 | 8553 | Frame Agreements | 2020-06-15 | 2020-11-04 | 2020-11-04 | 2020-07-03 | 2020-11-07 | 2020-09-02 | 2020-07-17 | 2020-11-07 | 2020-09-18 | 2020-11-21 | 2020-10-20 | 32 | 18 | 3
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Tekleen Screen | TEKLEEN | 4503387939 | Flow Control | Carbon Steel | USD | 20000 | USD | 26400 | -6400 | Single Sourced | 2020-03-19 | 2020-03-23 | 2020-03-23 | 2020-04-08 | 2020-04-28 | 2020-06-05 | 2020-04-22 | 2020-05-03 | 2020-07-22 | 2020-08-23 | 2020-08-07 | 16 | 12 | 41
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | BRAY VALVES | BRAY CONTROLS CANADA LTD. | 4503411912 | Flow Control | Metal Isolation Valves | USD | 18750 | USD | 11440 | 7310 | Frame Agreements | 2020-03-19 | 2020-05-22 | 2020-05-08 | 2020-04-08 | 2020-05-16 | 2020-05-22 | 2020-04-22 | 2020-06-06 | 2020-07-22 | 2020-07-25 | 2020-07-23 | 2 | 12 | 15
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Coarse Bubble Diffuser System | EDI | 4503393644 | Fabrication | Carbon Steel | USD | 45895 | USD | 55286 | -9391 | Proposed Supplier Incapable Of Executing | 2020-02-24 | 2020-02-17 | 2020-02-21 | 2020-03-13 | 2020-04-16 | 2020-05-13 | 2020-03-27 | 2020-04-21 | 2020-08-07 | 2020-07-31 | 2020-08-03 | -3 | 12 | 64
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | pH Adjustment System | WASTECH CONTROLS & ENGINEERING, INC | 4503340212 | Rotating Equipment | Carbon Steel | USD | 650549 | USD | 634000 | 16549 | Design Optimizations | 2019-12-05 | 2019-11-15 | 2019-11-26 | 2019-07-01 | 2019-12-03 | 2020-01-05 | 2019-07-15 | 2020-01-04 | 2020-02-14 | 2020-07-11 | 2020-04-28 | 74 | 30 | 50
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Instruments - P Gauge | CONVAL PROCESS SOLUTIONS INC | 4503447070 | Electrical & Instrumentation | Centrifugal Pumps | USD | 6952 | USD | 7290 | -338 | Market Impact | 2020-03-19 | 2020-08-12 | 2020-08-19 | 2020-04-08 | 2020-08-19 | 2020-06-11 | 2020-04-22 | 2020-08-19 | 2020-02-28 | 2020-09-23 | 2020-06-11 | 104 | 18 | 7
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Instruments - E&H | ENDRESS + HAUSER CANADA LTD. | 4503458223 | Electrical & Instrumentation | Centrifugal Pumps | USD | 23902 | USD | 40765 | -16863 | Size/ Weight/ Quantity Underestimated | 2020-03-19 | 2020-08-14 | 2020-08-20 | 2020-04-08 | 2020-09-11 | 2020-06-29 | 2020-04-22 | 2020-09-11 | 2020-07-15 | 2020-10-09 | 2020-08-27 | 43 | 18 | 28
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | MBBR Media 345m3 | PEXCO | 4503395954 | Flow Control | Centrifugal Pumps | USD | 131625 | USD | 99877 | 31748 | Design Optimizations | 2020-04-20 | 2020-03-16 | 2020-03-31 | 2020-05-08 | 2020-03-31 | 2020-06-03 | 2020-05-22 | 2020-04-27 | 2020-08-21 | 2020-07-24 | 2020-08-07 | -14 | 12 | 42
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Platforms - Primary and Secondary DAF | ISC Industrial Services Company | 4503400627 | Fabrication | Carbon Steel | USD | 40000 | USD | 42000 | -2000 | Single Sourced | 2020-04-02 | 2020-03-31 | 2020-03-31 | 2020-04-22 | 2020-04-05 | 2020-05-30 | 2020-05-06 | 2020-04-22 | 2020-07-29 | 2020-04-22 | 2020-06-10 | -49 | 12 | 22
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Compressors | ATLAS COPCO COMPRESSORS | 4503404188 | Rotating Equipment | Compressors | USD | 20000 | CAD | 7742 | 12258 | Design Optimizations | 2020-03-05 | 2020-03-11 | 2020-03-25 | 2020-03-13 | 2020-05-12 | 2020-06-10 | 2020-03-27 | 2020-06-10 | 2020-07-24 | 2020-09-16 | 2020-08-20 | 27 | 30 | 91
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Pumps - Sludge & Centrifuge Feed | SEEPEX | 4503398013 | Rotating Equipment | Chem. Feed Skids (TurnKey) | USD | 33175 | USD | 10550 | 22625 | Frame Agreements | 2020-03-05 | 2020-03-11 | 2020-04-04 | 2020-03-25 | 2020-04-29 | 2020-05-10 | 2020-04-08 | 2020-05-01 | 2020-07-15 | 2020-06-26 | 2020-07-05 | -9 | 30 | 51
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Pumps - Centrifugal | SULZER PUMPS (CANADA) INC. | 4503398729 | Rotating Equipment | Centrifugal Pumps | USD | 23999 | USD | 19782 | 4217 | Frame Agreements | 2020-03-05 | 2020-03-11 | 2020-04-07 | 2020-03-25 | 2020-04-29 | 2020-05-23 | 2020-04-08 | 2020-05-04 | 2020-07-15 | 2020-08-10 | 2020-07-28 | 13 | 30 | 54
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Blowers | AERZEN CANADA INC. | 4503398721 | Rotating Equipment | Blowers & Fans | USD | 34844 | CAD | 94708 | -59864 | Proposed Supplier Incapable Of Executing | 2020-02-24 | 2020-03-12 | 2020-03-18 | 2020-03-13 | 2020-04-21 | 2020-06-01 | 2020-03-27 | 2020-04-22 | 2020-07-31 | 2020-09-08 | 2020-08-19 | 20 | 30 | 41
505564 | Western Facilities, LLC (Pierce WWTP) | Oakville | Mixer - EQ Tank | GRUNDFOS CANADA INC. | 4503397998 | Rotating Equipment | Ele-Control Panels | USD | 7642 | USD | 10404 | -2762 | Not included in Proposal / RFQ | 2020-03-05 | 2020-03-25 | 2020-03-27 | 2020-03-25 | 2020-04-15 | 2020-05-26 | 2020-03-27 | 2020-05-01 | 2020-07-15 | 2020-08-17 | 2020-07-31 | 17 | 30 | 37
505625 | City of Sturgis MBR | Oakville | Knife Gate Valves | WOLSELEY INDUSTRIAL | 4503463125 | Flow Control | Metal Isolation Valves | USD | 13157 | CAD | 7387 | 5770 | Design Optimizations | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-09-07 | 2020-09-16 | 2020-10-24 | 2020-09-30 | 2020-09-22 | 2020-12-15 | 2020-12-14 | 2020-12-14 | 0 | 12 | 19
505625 | City of Sturgis MBR | Oakville | Level,Pressure ,Flow Meter,Temperature Transmitter ,DO/PH/ORP Probe | ENDRESS + HAUSER CANADA LTD. | 4503459270 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 27776 | USD | 36285 | -8509 | Market Impact | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-09-10 | 2020-09-14 | 2020-10-24 | 2020-09-16 | 2020-09-15 | 2020-12-15 | 2020-11-24 | 2020-12-04 | -10 | 18 | 12
505625 | City of Sturgis MBR | Oakville | Blower with Spares | AERZEN CANADA INC. | 4503456062 | Rotating Equipment | Ele-Control Panels | USD | 101782 | CAD | 95648 | 6134 | Supplier Competitions / Negotiation | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-09-07 | 2020-09-08 | 2020-10-24 | 2020-09-10 | 2020-09-10 | 2020-12-15 | 2020-12-03 | 2020-12-09 | -6 | 30 | 7
505625 | City of Sturgis MBR | Oakville | Air Compressor | Compressor Science Inc. | 4503459381 | Rotating Equipment | Vapor Compressor | USD | 15949 | USD | 12986 | 2963 | Design Optimizations | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-09-10 | 2020-09-15 | 2020-10-24 | 2020-09-16 | 2020-09-16 | 2020-12-15 | 2020-12-15 | 2020-12-15 | 0 | 30 | 13
505625 | City of Sturgis MBR | Oakville | Control Panel | KELTOUR CONTROLS INC. | 4503474348 | Electrical & Instrumentation | Ele-Control Panels | USD | 123194 | USD | 107465 | 15729 | Design Optimizations | 2020-09-03 | 2020-10-06 | 2020-10-14 | 2020-09-03 | 2020-10-16 | 2020-11-09 | 2020-11-05 | 2020-10-16 | 2021-01-15 | 2020-12-08 | 2020-12-27 | -19 | 18 | 10
505625 | City of Sturgis MBR | Oakville | Frames & Spools | 3D MECHANICAL | 4503470836 | Fabrication | Metal Isolation Valves | USD | 19188 | USD | 28044 | -8856 | Estimate Without Market Reference(No Quote) | 2020-09-03 | 2020-09-21 | 2020-10-06 | 2020-09-03 | 2020-10-01 | 2020-10-24 | 2020-09-28 | 2020-10-08 | 2020-12-15 | 2020-11-22 | 2020-12-03 | -11 | 12 | 17
505625 | City of Sturgis MBR | Oakville | Chemical Skid with Spares | FLOMOTION SYSTEMS INC | 4503458215 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 21990 | USD | 21656 | 334 | Frame Agreements | 2020-09-03 | 2020-09-10 | 2020-09-10 | 2020-09-09 | 2020-09-10 | 2020-10-24 | 2020-09-14 | 2020-09-19 | 2020-12-15 | 2020-11-10 | 2020-11-27 | -17 | 30 | 9
505625 | City of Sturgis MBR | Oakville | Diffuser | ENVIRONMENTAL DYNAMICS | 4503454176 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 34235 | USD | 33392 | 843 | Supplier Competitions / Negotiation | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-10-24 | 2020-09-04 | 2020-09-04 | 2020-12-15 | 2020-12-15 | 2020-12-15 | 0 | 12 | 1
505625 | City of Sturgis MBR | Oakville | Diffuser -Additional requirement | ENVIRONMENTAL DYNAMICS | 4503543836 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 5791 | USD | 8990 | -3199 | Not included in Proposal / RFQ | 2021-04-16 | 2021-04-16 | 2021-02-04 | 2021-04-16 | 2021-02-04 | 2021-04-16 | 2021-04-16 | 2021-03-02 | 2021-04-16 | 2021-06-26 | 2021-05-21 | 36 | 12 | -45
505625 | City of Sturgis MBR | Oakville | RAS Pump | SULZER PUMPS (CANADA) INC. | 4503457286 | Rotating Equipment | Centrifugal Pumps | USD | 52300 | CAD | 60760 | -8460 | Estimate Without Market Reference(No Quote) | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-09-14 | 2020-09-15 | 2020-11-07 | 2020-09-16 | 2020-09-16 | 2021-01-12 | 2020-12-21 | 2021-01-01 | -11 | 30 | 13
505625 | City of Sturgis MBR | Oakville | Process Pump | BOERGER, INC | 4503456035 | Rotating Equipment | Centrifugal Pumps | USD | 56273 | USD | 45879 | 10394 | Design Optimizations | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-09-07 | 2020-09-08 | 2020-10-24 | 2020-09-09 | 2020-09-09 | 2020-12-15 | 2020-11-20 | 2020-12-02 | -12 | 30 | 6
505625 | City of Sturgis MBR | Oakville | Spools | NV PIPING SYSTEMS INC. | 4503476408 | Fabrication | Centrifugal Pumps | USD | 8203 | CAD | 10678 | -2475 | Proposed Supplier Incapable Of Executing | 2020-10-02 | 2020-10-16 | 2020-10-19 | 2020-10-09 | 2020-10-18 | 2020-11-08 | 2020-10-16 | 2020-10-20 | 2020-12-15 | 2020-11-24 | 2020-12-04 | -10 | 12 | 4
505703 | Eramet | Oakville | Modules (Design, Manufacture, Assy & Testing) (Incl. supply of Manual Valves) + Pipping + Fitting + Frames | Morimatsu (Jiangsu) Heavy Industry | 4503335165 | Fabrication | Metal Isolation Valves | USD | 4716154 | USD | 5096200 | -380046 | Size/ Weight/ Quantity Underestimated | 2019-09-19 | 2019-11-04 | 2019-11-05 | 2019-10-10 | 2019-11-09 | 2019-12-09 | 2019-10-24 | 2019-12-17 | 2020-10-09 | 2023-01-20 | 2021-11-29 | 417 | 12 | 43
505703 | Eramet | Oakville | Skid frame & Spool supply and Fab, Incl. Mech and Elec Bulk, Incl. Victaullic, Pneumaic Tubings, Tags etc | Morimatsu (Jiangsu) Heavy Industry | 4503353420 | Fabrication | Skid Assembly Outsourced | USD | 3114747 | USD | 3320000 | -205253 | Specs / Requirements Misinterpreted in Proposal | 2020-01-20 | 2019-11-13 | 2019-11-29 | 2020-02-03 | 2020-02-20 | 2020-02-14 | 2020-02-10 | 2020-02-27 | 2020-10-09 | 2023-01-20 | 2021-11-29 | 417 | 12 | 106
505703 | Eramet | Oakville | Valves Package - Manual | Morimatsu (Jiangsu) Heavy Industry | 4503800406 | Flow Control | Metal Isolation Valves | USD | 590000 | USD | 631361 | -41361 | Estimate Without Market Reference(No Quote) | 2019-10-04 | 2019-11-04 | 2022-04-11 | 2019-11-01 | 2022-04-15 | 2020-02-07 | 2019-11-15 | 2022-04-22 | 2020-06-15 | 2022-04-22 | 2021-05-19 | 338 | 12 | 900
505703 | Eramet | Oakville | Valves Package - Control | BRAY CONTROLS CANADA LTD. | 4503775061 | Flow Control | Ele-Control Panels | USD | 980000 | USD | 723202 | 256798 | Supplier Competitions / Negotiation | 2019-11-29 | 2022-03-17 | 2022-03-31 | 2019-12-27 | 2022-04-05 | 2022-04-07 | 2020-01-10 | 2022-04-12 | 2021-02-03 | 2022-04-12 | 2021-09-07 | 217 | 12 | 26
505703 | Eramet | Oakville | Valves Package - Manual | BRAY CONTROLS CANADA LTD | 4503795107 | Flow Control | Metal Isolation Valves | USD | 300000 | USD | 254537 | 45463 | Frame Agreements | 2019-11-29 | 2022-04-29 | 2022-05-06 | 2019-12-27 | 2022-05-13 | 2022-05-13 | 2020-01-09 | 2022-05-20 | 2021-02-22 | 2022-05-20 | 2021-10-06 | 226 | 12 | 21
505703 | Eramet | Oakville | Valves Package - Manual | Morimatsu (Jiangsu) Heavy Industry | 4503800409 | Flow Control | Metal Isolation Valves | USD | 300000 | USD | 530561 | -230561 | Size/ Weight/ Quantity Underestimated | 2019-11-29 | 2022-04-04 | 2022-04-11 | 2019-12-27 | 2022-04-16 | 2022-04-18 | 2020-01-09 | 2022-04-23 | 2021-02-09 | 2022-04-23 | 2021-09-16 | 219 | 12 | 19
505703 | Eramet | Oakville | Valves Package - Control | SAMSON CONTROLS PVT LTD | 4503794738 | Flow Control | Ele-Control Panels | USD | 150000 | USD | 33508 | 116492 | Frame Agreements | 2019-11-29 | 2022-04-29 | 2022-05-06 | 2019-12-27 | 2022-05-13 | 2022-05-13 | 2020-01-09 | 2022-05-20 | 2021-02-22 | 2022-05-20 | 2021-10-06 | 226 | 12 | 21
505703 | Eramet | Oakville | Valves Package - Control | Aalberts Integrated Piping Systems | 4503796649 | Flow Control | Ele-Control Panels | USD | 100000 | USD | 80949 | 19051 | Supplier Competitions / Negotiation | 2022-05-13 | 2022-05-03 | 2022-05-10 | 2022-05-13 | 2022-05-17 | 2022-05-17 | 2022-05-13 | 2022-05-24 | 2022-05-13 | 2022-05-24 | 2022-05-18 | 6 | 12 | 21
505703 | Eramet | Oakville | Valves Package - PSV/PRV | Great Lakes Industrial Controls | 4503796782 | Flow Control | Metal Isolation Valves | USD | 50000 | USD | 32857 | 17143 | Design Optimizations | 2022-05-13 | 2022-05-03 | 2022-05-10 | 2022-05-13 | 2022-05-17 | 2022-05-17 | 2022-05-13 | 2022-05-24 | 2022-05-13 | 2022-05-24 | 2022-05-18 | 6 | 12 | 21
505703 | Eramet | Oakville | Pressure Safety Valves / Pressure Releif Valves | PROCESS & STEAM SPECIALTIES | 4503359744 | Flow Control | Metal Safety(relief) Valves | USD | 82562 | USD | 81412 | 1150 | Frame Agreements | 2019-11-29 | 2019-12-02 | 2019-12-19 | 2019-12-27 | 2020-02-05 | 2020-02-14 | 2020-01-10 | 2020-02-12 | 2020-06-15 | 2022-04-29 | 2021-05-22 | 342 | 12 | 72
505703 | Eramet | Oakville | Valves Package - Control (incl. ON/OFF) | PROCESS & STEAM SPECIALTIES | 4503367514 | Flow Control | Metal Isolation Valves | USD | 27562 | USD | 28380 | -818 | Not included in Proposal / RFQ | 2019-11-29 | 2019-12-12 | 2019-12-19 | 2019-12-27 | 2020-02-19 | 2020-02-26 | 2020-01-10 | 2020-02-26 | 2020-08-31 | 2022-04-29 | 2021-06-30 | 303 | 12 | 76
505703 | Eramet | Oakville | Valves Package - Control (incl. ON/OFF) | Great Lakes Industrial Controls | 4503369208 | Flow Control | Metal Isolation Valves | USD | 85000 | USD | 85489 | -489 | Not included in Proposal / RFQ | 2019-11-29 | 2020-02-17 | 2020-02-24 | 2019-12-27 | 2020-02-23 | 2020-03-05 | 2020-01-10 | 2020-03-05 | 2020-08-31 | 2022-07-15 | 2021-08-07 | 342 | 12 | 17
505703 | Eramet | Oakville | Valves Package - Control (incl. ON/OFF) | Samson Controls Inc. | 4503810762 | Flow Control | Metal Isolation Valves | USD | 15000 | USD | 24185 | -9185 | Not included in Proposal / RFQ | 2022-09-10 | 2022-09-10 | 2022-05-23 | 2022-09-10 | 2022-06-11 | 2022-09-10 | 2022-09-10 | 2022-06-17 | 2022-09-10 | 2022-12-30 | 2022-11-04 | 56 | 12 | -85
505703 | Eramet | Oakville | NF/RO Housing | Wave Cyber (Shanghai) Co., Ltd. | 4503371564 | Fabrication | Metal Isolation Valves | USD | 348217 | USD | 287808 | 60409 | Design Optimizations | 2019-11-29 | 2019-12-02 | 2019-12-10 | 2019-12-27 | 2020-01-01 | 2019-12-31 | 2020-01-10 | 2020-03-08 | 2020-06-15 | 2022-07-29 | 2021-07-07 | 387 | 12 | 97
505703 | Eramet | Oakville | WAC Vessel incl. Painting and Lining | Kunshan Bexcelle Special Equipment | 4503369998 | Fabrication | Carbon Steel | USD | 594182 | USD | 583800 | 10382 | Frame Agreements | 2019-12-02 | 2019-12-10 | 2019-12-20 | 2019-12-30 | 2019-12-30 | 2020-01-15 | 2020-01-13 | 2020-02-29 | 2020-06-15 | 2022-09-30 | 2021-08-07 | 419 | 12 | 81
505703 | Eramet | Oakville | Cartidge Filters incl. Element | Fluytec Filtration Technology | 4503334695 | Fabrication | Carbon Steel | USD | 129475 | USD | 136426 | -6951 | Market Impact | 2019-11-29 | 2019-10-07 | 2019-10-15 | 2019-12-27 | 2019-11-24 | 2019-12-05 | 2020-01-10 | 2019-12-19 | 2020-06-15 | 2022-05-27 | 2021-06-05 | 356 | 12 | 73
505703 | Eramet | Oakville | Pumps - RO High Pressure | Sulzer (Dalian) Pumps & Compressors Ltd | 4503320541 | Rotating Equipment | Centrifugal Pumps | USD | 1154860 | USD | 521481 | 633379 | Design Optimizations | 2019-11-29 | 2019-11-04 | 2019-11-11 | 2019-12-27 | 2019-11-16 | 2019-11-24 | 2020-01-09 | 2019-11-23 | 2021-03-30 | 2022-08-25 | 2021-12-11 | 257 | 30 | 19
505703 | Eramet | Oakville | Pump - Centrifugal (Qty 24) | Sulzer (Dalian) Pumps & Compressors Ltd | 4503333516 | Rotating Equipment | Centrifugal Pumps | USD | 815309 | USD | 436639 | 378670 | Frame Agreements | 2019-10-18 | 2019-10-23 | 2019-11-11 | 2019-11-15 | 2019-11-25 | 2019-12-02 | 2019-11-29 | 2019-12-18 | 2020-06-15 | 2022-08-12 | 2021-07-14 | 394 | 30 | 56
505703 | Eramet | Oakville | Pump - Axial (Qty 3) | SULZER PUMPS (CANADA) INC. | 4503333570 | Rotating Equipment | Centrifugal Pumps | USD | 557410 | USD | 359958 | 197452 | Supplier Competitions / Negotiation | 2019-09-04 | 2019-10-22 | 2019-11-07 | 2019-09-25 | 2019-12-14 | 2019-12-20 | 2019-10-02 | 2019-12-18 | 2020-09-10 | 2022-11-25 | 2021-10-18 | 403 | 30 | 57
505703 | Eramet | Oakville | Pump - Vacuum | Flowserve Canada Corp. | 4503343564 | Rotating Equipment | Centrifugal Pumps | USD | 37243 | USD | 61575 | -24332 | Size/ Weight/ Quantity Underestimated | 2019-10-18 | 2019-11-11 | 2019-11-21 | 2019-11-15 | 2020-01-08 | 2020-01-17 | 2019-11-29 | 2020-01-25 | 2020-07-31 | 2022-09-23 | 2021-08-27 | 392 | 30 | 75
505703 | Eramet | Oakville | Pump - Membrane Turbo Booster | FLUID EQUIPMENT DEVELOPMENT | 4503341757 | Rotating Equipment | Carbon Steel | USD | 811816 | USD | 309190 | 502626 | Supplier Competitions / Negotiation | 2019-11-01 | 2019-10-29 | 2019-11-19 | 2019-11-29 | 2020-01-03 | 2020-01-13 | 2019-12-13 | 2020-01-10 | 2020-06-15 | 2022-10-21 | 2021-08-18 | 429 | 30 | 73
505703 | Eramet | Oakville | Centrifuge | Andritz Separation Technologies Inc. | 4503357403 | Rotating Equipment | Centrifuge | USD | 161596 | USD | 192557 | -30961 | Single Sourced | 2019-11-29 | 2020-01-20 | 2020-01-27 | 2019-12-27 | 2020-02-02 | 2020-02-09 | 2020-01-09 | 2020-02-09 | 2021-06-13 | 2022-12-27 | 2022-03-21 | 281 | 30 | 20
505703 | Eramet | Oakville | Evaporator incl. L&P | Kunshan Bexcelle Special Equipment | 4503322941 | Fabrication | Ele-Control Panels | USD | 1926090 | USD | 2232600 | -306510 | Single Sourced | 2019-08-26 | 2019-10-09 | 2019-10-30 | 2019-09-16 | 2019-11-01 | 2019-11-06 | 2019-09-30 | 2019-11-29 | 2020-10-09 | 2022-12-09 | 2021-11-08 | 396 | 12 | 51
505703 | Eramet | Oakville | Cleaning Tank | Kunshan Bexcelle Special Equipment | 4503346025 | Fabrication | Metal Isolation Valves | USD | 131215 | USD | 159600 | -28385 | Estimate Without Market Reference(No Quote) | 2019-09-23 | 2019-11-26 | 2019-12-10 | 2019-10-21 | 2019-12-14 | 2019-12-26 | 2019-11-04 | 2020-01-31 | 2020-10-09 | 2022-11-18 | 2021-10-29 | 385 | 12 | 66
505703 | Eramet | Oakville | Non metallic Tank (HDPE) | ACO CONTAINER SYSTEMS LTD. | 4503796667 | Fabrication | Non-Metal Equipment | USD | 89826 | USD | 64647 | 25179 | Frame Agreements | 2020-01-27 | 2022-04-25 | 2022-05-10 | 2020-02-24 | 2022-05-17 | 2021-03-26 | 2020-03-09 | 2022-05-24 | 2020-10-09 | 2022-05-24 | 2021-08-01 | 296 | 12 | 29
505703 | Eramet | Oakville | Evaporator Separator | Coastal Technologies, Inc. | 4503352931 | Fabrication | Carbon Steel | USD | 264069 | USD | 381322 | -117253 | Market Impact | 2020-01-03 | 2019-12-19 | 2020-01-30 | 2020-01-31 | 2020-01-29 | 2020-02-13 | 2020-02-14 | 2020-02-01 | 2020-10-09 | 2022-10-31 | 2021-10-20 | 376 | 12 | 44
505703 | Eramet | Oakville | Duct (incl. H/W) to ship to Morimatsu | Kunshan Bexcelle Special Equipment | 4503352989 | Fabrication | Metal Isolation Valves | USD | 483994 | USD | 839000 | -355006 | Specs / Requirements Misinterpreted in Proposal | 2019-11-22 | 2019-12-13 | 2019-12-20 | 2019-12-20 | 2020-01-07 | 2020-01-24 | 2020-01-03 | 2020-01-31 | 2020-08-31 | 2022-08-19 | 2021-08-25 | 359 | 12 | 49
505703 | Eramet | Oakville | Guard Filter Internal+skid mounted+piping+valves and instrumentation, Junction boxes, wired | Gaudfrin | 4503334651 | Fabrication | Carbon Steel | USD | 233385 | USD | 412355 | -178970 | Size/ Weight/ Quantity Underestimated | 2019-10-09 | 2019-10-30 | 2019-11-22 | 2019-10-30 | 2019-12-06 | 2019-12-13 | 2019-11-06 | 2019-12-19 | 2020-09-16 | 2022-12-02 | 2021-10-24 | 404 | 12 | 50
505703 | Eramet | Oakville | Heat Exchanger | SPX FLOW TECHNOLOGY | 4503753855 | Fabrication | Ele-Control Panels | USD | 159824 | USD | 152036 | 7788 | Frame Agreements | 2019-09-09 | 2019-10-28 | 2019-10-29 | 2019-10-07 | 2019-12-15 | 2019-12-23 | 2019-10-21 | 2019-12-17 | 2020-06-15 | 2022-07-28 | 2021-07-06 | 387 | 12 | 50
505703 | Eramet | Oakville | Thermocompressor | Croll Reynolds | 4503343556 | Fabrication | Centrifugal Pumps | USD | 53950 | USD | 68570 | -14620 | Not included in Proposal / RFQ | 2019-11-18 | 2019-12-02 | 2019-12-16 | 2019-12-16 | 2020-01-03 | 2020-01-06 | 2019-12-30 | 2020-01-24 | 2020-07-13 | 2020-01-24 | 2020-04-18 | -85 | 12 | 53
505703 | Eramet | Oakville | Hydrocyclone | FLSmidth Krebs | 4503349416 | Fabrication | Ele-Control Panels | USD | 40640 | USD | 47936 | -7296 | Specs / Requirements Misinterpreted in Proposal | 2019-10-21 | 2019-12-17 | 2019-12-17 | 2019-11-18 | 2020-01-13 | 2020-01-14 | 2019-12-02 | 2020-03-04 | 2020-10-09 | 2022-08-12 | 2021-09-10 | 336 | 12 | 78
505703 | Eramet | Oakville | Ti Tubes | Hunan Xiangtou Goldsky New Materials | 4503375472 | Fabrication | Centrifugal Pumps | USD | 678262 | USD | 725896 | -47634 | Market Impact | 2019-08-17 | 2019-08-13 | 2019-08-22 | 2019-09-14 | 2019-09-10 | 2019-09-10 | 2019-09-28 | 2019-10-14 | 2020-04-11 | 2019-10-14 | 2020-03-31 | -169 | 12 | 62
505703 | Eramet | Oakville | Vapor Compressor incl. VFD | Piller Blowers & Compressors GMBH | 4503333577 | Rotating Equipment | Vapor Compressor | USD | 1665771 | USD | 1808171 | -142400 | Estimate Without Market Reference(No Quote) | 2019-10-11 | 2019-12-05 | 2019-12-12 | 2019-11-08 | 2019-12-17 | 2019-12-31 | 2019-11-22 | 2019-12-31 | 2020-10-09 | 2022-12-30 | 2021-11-19 | 406 | 30 | 26
505703 | Eramet | Oakville | Instrumentation - Pressure | ENDRESS & HAUSER | 4503809923 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 120915 | USD | 91248 | 29667 | Design Optimizations | 2019-11-29 | 2022-04-25 | 2022-06-16 | 2019-12-27 | 2022-06-16 | 2021-05-10 | 2020-01-10 | 2022-06-16 | 2020-06-15 | 2022-10-20 | 2021-08-17 | 429 | 18 | 52
505703 | Eramet | Oakville | Instrumentation - Level | ENDRESS & HAUSER | 4503847575 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 200000 | USD | 178251 | 21749 | Supplier Competitions / Negotiation | 2019-11-29 | 2022-04-25 | 2022-08-19 | 2019-12-27 | 2022-08-24 | 2021-06-20 | 2020-01-10 | 2022-08-24 | 2020-06-15 | 2023-01-11 | 2021-09-28 | 470 | 18 | 121
505703 | Eramet | Oakville | Mixers - Rotary | DYNAMEX CANADA CORP | 4503833327 | Rotating Equipment | Mixers | USD | 13135 | USD | 31636 | -18501 | Specs / Requirements Misinterpreted in Proposal | 2019-12-30 | 2021-06-08 | 2022-06-29 | 2020-01-27 | 2022-07-06 | 2021-06-08 | 2020-02-10 | 2022-07-27 | 2020-10-09 | 2022-11-16 | 2021-10-28 | 384 | 30 | 414
505703 | Eramet | Oakville | Pump - Centrifugal (Qty 2) | SULZER PUMPS (CANADA) INC. | 4503341202 | Rotating Equipment | Centrifugal Pumps | USD | 291608 | USD | 330918 | -39310 | Proposed Supplier Incapable Of Executing | 2019-10-18 | 2019-11-06 | 2019-11-18 | 2019-11-15 | 2019-12-28 | 2019-12-24 | 2019-11-29 | 2020-01-10 | 2020-10-09 | 2022-09-23 | 2021-10-01 | 357 | 30 | 65
505703 | Eramet | Oakville | Pump - Centrifugal (Qty 11) | Sulzer (Dalian) Pumps & Compressors Ltd | 4503341210 | Rotating Equipment | Centrifugal Pumps | USD | 235433 | USD | 204698 | 30735 | Supplier Competitions / Negotiation | 2019-10-18 | 2019-11-25 | 2019-12-04 | 2019-11-15 | 2020-01-04 | 2020-01-15 | 2019-11-29 | 2020-01-10 | 2020-07-27 | 2022-08-12 | 2021-08-04 | 373 | 30 | 46
505739 | Highland Creek | Oakville | Roof Spray Pumps | Roth Pump Company | 4503366123 | Rotating Equipment | Centrifugal Pumps | CAD | 90432 | USD | 80807 | 9625 | Supplier Competitions / Negotiation | 2019-09-27 | 2019-10-23 | 2019-11-07 | 2019-10-11 | 2019-12-09 | 2021-10-13 | 2019-10-25 | 2020-02-26 | 2023-10-31 | 2023-08-16 | 2023-09-23 | -38 | 30 | 126
505739 | Highland Creek | Oakville | Fluidization Air Blower | GARDNER DENVER NASH LLC | 4503352043 | Rotating Equipment | Metal Isolation Valves | CAD | 759928 | USD | 720607 | 39321 | Supplier Competitions / Negotiation | 2019-09-13 | 2019-11-11 | 2019-12-05 | 2019-09-27 | 2020-01-30 | 2021-10-06 | 2019-10-11 | 2020-01-29 | 2023-10-31 | 2020-07-15 | 2022-03-08 | -601 | 30 | 79
505739 | Highland Creek | Oakville | Purge Air Blowers | BEST BLOWER | 4503369211 | Rotating Equipment | Blowers & Fans | CAD | 86043 | USD | 63731 | 22312 | Supplier Competitions / Negotiation | 2019-09-27 | 2019-01-03 | 2019-01-14 | 2019-10-11 | 2019-12-08 | 2021-06-02 | 2019-10-25 | 2020-03-02 | 2023-10-31 | 2020-03-02 | 2021-12-31 | -669 | 30 | 424
505739 | Highland Creek | Oakville | ID Fan | ROBINSON FANS INC | 4503347261 | Rotating Equipment | Ele-Control Panels | CAD | 734558 | USD | 1042490 | -307932 | Size/ Weight/ Quantity Underestimated | 2019-09-13 | 2019-11-25 | 2020-12-09 | 2019-09-27 | 2019-12-07 | 2021-10-06 | 2019-10-11 | 2020-01-19 | 2023-10-31 | 2020-05-10 | 2022-02-03 | -634 | 30 | 55
505739 | Highland Creek | Oakville | Urea Dosing Pump Skids & Oil Injection Pump Skids | SPD Sales Limited | 4503353732 | Rotating Equipment | Chem. Feed Skids (TurnKey) | CAD | 293093 | CAD | 133210 | 159883 | Frame Agreements | 2019-09-13 | 2020-01-20 | 2020-02-03 | 2019-09-27 | 2020-01-28 | 2021-09-21 | 2019-10-11 | 2020-01-31 | 2023-09-30 | 2020-04-24 | 2022-01-11 | -627 | 30 | 11
505739 | Highland Creek | Oakville | Stack | FOX EQUIPMENT LLC | 4503356670 | Fabrication | Metal Isolation Valves | CAD | 381264 | USD | 339431 | 41833 | Frame Agreements | 2019-09-16 | 2019-11-18 | 2019-12-02 | 2019-09-30 | 2020-01-31 | 2021-10-08 | 2019-10-14 | 2020-02-04 | 2023-10-31 | 2023-08-13 | 2023-09-21 | -39 | 12 | 78
505739 | Highland Creek | Oakville | Electrical Mv VFD (ID Fans) | GERRIE ELECTRIC LIMITED | 4503366130 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 443316 | CAD | 443144 | 172 | Frame Agreements | 2019-09-13 | 2021-02-11 | 2020-02-25 | 2019-09-27 | 2020-02-16 | 2021-08-29 | 2019-10-11 | 2020-02-25 | 2023-08-16 | 2023-08-15 | 2023-08-15 | 0 | 18 | -352
505739 | Highland Creek | Oakville | Bentley Nevada Panel | BENTLEY SYSTEMS INC | 4503369712 | Electrical & Instrumentation | Ele-Control Panels | CAD | 51000 | CAD | 191544 | -140544 | Not included in Proposal / RFQ | 2019-09-13 | 2020-02-12 | 2020-02-26 | 2019-09-27 | 2020-02-24 | 2021-09-02 | 2019-10-11 | 2020-03-02 | 2023-08-23 | 2020-05-25 | 2022-01-07 | -592 | 18 | 19
505745 | Port Deposit WWTP | Oakville | Control Panel | KELTOUR CONTROLS INC. | 4503426348 | Electrical & Instrumentation | Ele-Control Panels | USD | 94534 | CAD | 59053 | 35481 | Frame Agreements | 2020-04-17 | 2020-06-12 | 2020-06-12 | 2020-05-01 | 2020-06-12 | 2020-06-12 | 2020-05-01 | 2020-07-07 | 2020-08-07 | 2020-07-07 | 2020-07-22 | -15 | 18 | 25
505745 | Port Deposit WWTP | Oakville | Mixers | XYLEM CANADA COMPANY | 4503399238 | Rotating Equipment | Mixers | USD | 50999 | CAD | 34728 | 16271 | Design Optimizations | 2020-04-17 | 2020-06-03 | 2020-06-03 | 2020-05-01 | 2020-06-03 | 2020-06-03 | 2020-05-01 | 2020-05-05 | 2020-07-20 | 2020-07-20 | 2020-07-20 | 0 | 30 | -29
505745 | Port Deposit WWTP | Oakville | Pumps | BOERGER, INC | 4503400635 | Rotating Equipment | Centrifugal Pumps | USD | 26051 | USD | 26051 | 0 | Frame Agreements | 2020-04-17 | 2020-06-01 | 2020-06-01 | 2020-05-01 | 2020-06-01 | 2020-06-01 | 2020-05-01 | 2020-05-07 | 2020-07-17 | 2020-05-07 | 2020-06-11 | -35 | 30 | -25
505745 | Port Deposit WWTP | Oakville | Pumps | SULZER PUMPS (CANADA) INC. | 4503398192 | Rotating Equipment | Centrifugal Pumps | USD | 30294 | CAD | 49521 | -19227 | Proposed Supplier Incapable Of Executing | 2020-04-17 | 2020-06-19 | 2020-06-19 | 2020-05-01 | 2020-06-19 | 2020-06-19 | 2020-05-01 | 2020-05-01 | 2020-08-21 | 2020-08-21 | 2020-08-21 | 0 | 30 | -49
505745 | Port Deposit WWTP | Oakville | Valves | FLOVAL EQUIPMENT LIMITED | 4503398795 | Flow Control | Metal Isolation Valves | USD | 27128 | CAD | 27128 | 0 | Supplier Competitions / Negotiation | 2020-04-17 | 2020-05-31 | 2020-05-31 | 2020-05-01 | 2020-05-31 | 2020-05-31 | 2020-05-01 | 2020-05-04 | 2020-07-13 | 2020-07-15 | 2020-07-14 | 1 | 12 | -27
505745 | Port Deposit WWTP | Oakville | Blower | AERZEN CANADA INC. | 4503398209 | Rotating Equipment | Ele-Control Panels | USD | 34534 | CAD | 38555 | -4021 | Not included in Proposal / RFQ | 2020-04-17 | 2020-06-12 | 2020-06-12 | 2020-05-01 | 2020-06-12 | 2020-06-12 | 2020-05-01 | 2020-05-01 | 2020-08-07 | 2020-08-07 | 2020-08-07 | 0 | 30 | -42
505745 | Port Deposit WWTP | Oakville | Instruments | Hach Sales & Service Canada Ltd. | 4503398845 | Electrical & Instrumentation | Centrifugal Pumps | USD | 6381 | CAD | 6381 | 0 | Market Impact | 2020-04-17 | 2020-05-09 | 2020-05-09 | 2020-05-01 | 2020-05-09 | 2020-05-09 | 2020-05-01 | 2020-05-04 | 2020-06-01 | 2020-06-01 | 2020-06-01 | 0 | 18 | -5
505745 | Port Deposit WWTP | Oakville | Instruments | ENDRESS + HAUSER CANADA LTD. | 4503398854 | Electrical & Instrumentation | Centrifugal Pumps | USD | 12740 | USD | 12740 | 0 | Proposed Supplier Incapable Of Executing | 2020-04-17 | 2020-05-14 | 2020-05-14 | 2020-05-01 | 2020-05-14 | 2020-05-14 | 2020-05-01 | 2020-05-04 | 2020-06-01 | 2020-06-10 | 2020-06-05 | 5 | 18 | -10
505745 | Port Deposit WWTP | Oakville | Chemical Metering Pump Package | Prominent Fluid Controls Inc. | 4503398242 | Rotating Equipment | Centrifugal Pumps | USD | 19215 | CAD | 19215 | 0 | Design Optimizations | 2020-04-17 | 2020-05-23 | 2020-05-23 | 2020-05-01 | 2020-05-23 | 2020-05-23 | 2020-05-01 | 2020-05-02 | 2020-06-29 | 2020-05-02 | 2020-05-31 | -29 | 30 | -21
505745 | Port Deposit WWTP | Oakville | Chemical Metering Pump Package | Prominent Fluid Controls Inc. | 4503310695 | Rotating Equipment | Centrifugal Pumps | USD | 10839 | CAD | 9550 | 1289 | Supplier Competitions / Negotiation | 2020-04-05 | 2020-05-17 | 2020-05-17 | 2020-04-19 | 2020-05-17 | 2020-05-17 | 2020-04-19 | 2020-05-03 | 2020-06-29 | 2020-05-13 | 2020-06-05 | -23 | 30 | -14
505745 | Port Deposit WWTP | Oakville | Compressor | Compressor Science Inc. | 4503398851 | Rotating Equipment | Vapor Compressor | USD | 19376 | USD | 13545 | 5831 | Frame Agreements | 2020-04-17 | 2020-05-06 | 2020-05-06 | 2020-05-01 | 2020-05-06 | 2020-05-06 | 2020-05-01 | 2020-05-04 | 2020-05-25 | 2020-05-04 | 2020-05-14 | -10 | 30 | -2
505745 | Port Deposit WWTP | Oakville | UV Product for Disinfection - Hallett 1000 | UV Pure | 4503399891 | Electrical & Instrumentation | Metal Isolation Valves | USD | 14478 | CAD | 19237 | -4759 | Single Sourced | 2020-04-17 | 2020-05-10 | 2020-05-10 | 2020-05-01 | 2020-05-10 | 2020-05-10 | 2020-05-01 | 2020-05-06 | 2020-06-03 | 2020-06-03 | 2020-06-03 | 0 | 18 | -4
505745 | Port Deposit WWTP | Oakville | Skids/Beam/Brackets/Supports | 3D MECHANICAL | 4503416536 | Fabrication | Centrifugal Pumps | USD | 5567 | CAD | 5567 | 0 | Frame Agreements | 2020-04-17 | 2020-05-16 | 2020-05-16 | 2020-05-01 | 2020-05-16 | 2020-05-16 | 2020-05-01 | 2020-06-14 | 2020-05-25 | 2020-06-14 | 2020-06-04 | 10 | 12 | 29
505745 | Port Deposit WWTP | Oakville | Skids/Beam/Brackets/Supports | 3D MECHANICAL | 4503418331 | Fabrication | Centrifugal Pumps | USD | 5354 | CAD | 10672 | -5318 | Size/ Weight/ Quantity Underestimated | 2020-04-17 | 2020-06-03 | 2020-06-03 | 2020-04-24 | 2020-06-03 | 2020-06-03 | 2020-05-01 | 2020-06-18 | 2020-05-25 | 2020-07-21 | 2020-06-22 | 29 | 12 | 15
505809 | Tate & Lyle Decatur MBR | Minnetonka | HDPE TANK | ACO CONTAINER SYSTEMS LTD. | 4503295580 | Fabrication | Ele-Control Panels | USD | 13791 | USD | 25140 | -11349 | Proposed Supplier Incapable Of Executing | 2019-09-02 | 2019-11-12 | 2019-09-17 | 2019-09-09 | 2019-10-03 | 2019-11-12 | 2019-09-11 | 2019-10-03 | 2019-11-27 | 2020-01-23 | 2019-12-25 | 29 | 12 | -40
505809 | Tate & Lyle Decatur MBR | Minnetonka | Chemical Skids | LOC PUMP | 4503301280 | Fabrication | Centrifugal Pumps | USD | 29454 | USD | 24372 | 5082 | Design Optimizations | 2019-10-11 | 2019-10-11 | 2019-07-06 | 2019-10-11 | 2019-10-15 | 2019-10-11 | 2019-10-11 | 2019-10-16 | 2019-10-11 | 2020-01-17 | 2019-11-29 | 49 | 12 | 5
505809 | Tate & Lyle Decatur MBR | Minnetonka | Blowers & Silencers | AERZEN | 4503290865 | Rotating Equipment | Blowers & Fans | USD | 45622 | USD | 45764 | -142 | Size/ Weight/ Quantity Underestimated | 2019-08-26 | 2019-10-22 | 2019-09-19 | 2019-09-02 | 2019-09-25 | 2019-10-22 | 2019-09-04 | 2019-09-25 | 2019-11-27 | 2019-12-18 | 2019-12-07 | 11 | 30 | -27
505809 | Tate & Lyle Decatur MBR | Minnetonka | Electrical Panels - RIO | ICSE | 4503365760 | Electrical & Instrumentation | Ele-Electrical Others | USD | 26528 | USD | 12910 | 13618 | Design Optimizations | 2019-09-02 | 2020-01-01 | 2020-01-11 | 2019-09-09 | 2020-02-26 | 2020-01-01 | 2019-09-11 | 2020-02-26 | 2019-11-27 | 2020-05-01 | 2020-02-13 | 78 | 18 | 56
505893 | Loyalist Bath WTP | Oakville | Strainer | BOLL FILTER CORPORATION | 4503333225 | Rotating Equipment | Ele-Control Panels | CAD | 64840 | CAD | 50367 | 14473 | Design Optimizations | 2019-11-13 | 2019-10-16 | 2019-11-21 | 2019-11-26 | 2019-12-04 | 2020-02-10 | 2019-12-10 | 2019-12-19 | 2020-04-06 | 2020-06-06 | 2020-05-06 | 31 | 30 | 64
505893 | Loyalist Bath WTP | Oakville | Dosing Pump | PROMINENT FLUID CONTROLS LTD. | 4503366746 | Rotating Equipment | Dosing Pump | CAD | 19074 | CAD | 16078 | 2996 | Frame Agreements | 2020-04-25 | 2020-03-02 | 2020-03-19 | 2020-05-05 | 2020-03-29 | 2020-05-03 | 2020-05-20 | 2020-04-06 | 2020-07-04 | 2020-04-06 | 2020-05-20 | -44 | 30 | 35
505893 | Loyalist Bath WTP | Oakville | Flow Transmitter | ACI Instrumentation Limited | 4503357525 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | CAD | 13732 | CAD | 14850 | -1118 | Size/ Weight/ Quantity Underestimated | 2020-04-28 | 2020-01-04 | 2020-01-18 | 2020-05-05 | 2020-01-31 | 2020-04-12 | 2020-06-28 | 2020-02-11 | 2020-07-20 | 2020-03-19 | 2020-05-19 | -61 | 18 | 38
505893 | Loyalist Bath WTP | Oakville | Air Compressor | Compressor Science Inc. | 4503356676 | Rotating Equipment | Vapor Compressor | CAD | 7815 | CAD | 7690 | 125 | Design Optimizations | 2020-01-20 | 2019-12-28 | 2020-01-15 | 2020-02-02 | 2020-01-25 | 2020-03-12 | 2020-02-06 | 2020-02-07 | 2020-04-27 | 2020-05-26 | 2020-05-11 | 15 | 30 | 41
505893 | Loyalist Bath WTP | Oakville | Membrane Lifting Module | MARCON CUSTOM METALS, INC. | 4503366671 | Fabrication | Platform & Module | CAD | 6030 | CAD | 10644 | -4614 | Size/ Weight/ Quantity Underestimated | 2020-04-29 | 2020-01-28 | 2020-02-11 | 2020-05-27 | 2020-02-25 | 2020-04-22 | 2020-06-19 | 2020-03-02 | 2020-07-16 | 2020-05-22 | 2020-06-18 | -27 | 12 | 34
505893 | Loyalist Bath WTP | Oakville | Fabrication | PANDA PIPING LTD | 4503366113 | Fabrication | Metal Isolation Valves | CAD | 10687 | CAD | 23808 | -13121 | Not included in Proposal / RFQ | 2020-04-24 | 2020-01-16 | 2020-02-05 | 2020-06-05 | 2020-02-19 | 2020-04-09 | 2020-05-19 | 2020-02-26 | 2020-07-02 | 2020-04-24 | 2020-05-28 | -34 | 12 | 41
505893 | Loyalist Bath WTP | Oakville | Actuators Rotork | Rotork Controls (Canada) Ltd | 4503352385 | Flow Control | Actuators (Pneumatic And Electric) | CAD | 69250 | CAD | 59058 | 10192 | Design Optimizations | 2020-01-24 | 2019-12-27 | 2020-01-09 | 2020-01-25 | 2020-01-23 | 2020-03-13 | 2020-01-27 | 2020-01-30 | 2020-05-29 | 2020-05-29 | 2020-05-29 | 0 | 12 | 34
505893 | Loyalist Bath WTP | Oakville | ACTUATOR - AUMA | TROY-ONTOR INC. | 4503422265 | Flow Control | Ele-Control Panels | CAD | 8023 | CAD | 7096 | 927 | Supplier Competitions / Negotiation | 2020-06-02 | 2020-05-30 | 2020-06-01 | 2020-06-13 | 2020-07-06 | 2020-06-29 | 2020-07-04 | 2020-06-28 | 2020-07-30 | 2020-07-10 | 2020-07-20 | -10 | 12 | 29
505967 | Marathon Dickson North Dakota | Oakville | Control Panels | Keltour Controls Inc. | 4503347049 | Electrical & Instrumentation | Ele-Control Panels | USD | 57969 | CAD | 38532 | 19437 | Design Optimizations | 2019-11-01 | 2020-01-15 | 2020-01-02 | 2019-11-22 | 2020-01-14 | 2020-01-15 | 2019-11-29 | 2020-01-21 | 2020-01-24 | 2020-03-31 | 2020-02-26 | 34 | 18 | 6
505967 | Marathon Dickson North Dakota | Oakville | Pumps | FLOWSERVE INC. | 4503325122 | Rotating Equipment | Centrifugal Pumps | USD | 13714 | USD | 15270 | -1556 | Market Impact | 2019-10-04 | 2020-01-02 | 2019-11-19 | 2019-11-01 | 2019-11-26 | 2020-01-02 | 2019-11-01 | 2019-12-04 | 2020-02-21 | 2020-04-01 | 2020-03-12 | 20 | 30 | -29
505967 | Marathon Dickson North Dakota | Oakville | CIP Tank (PE) | ACO CONTAINER SYSTEMS LTD. | 4503328983 | Fabrication | Carbon Steel | USD | 5849 | CAD | 8859 | -3010 | Proposed Supplier Incapable Of Executing | 2019-11-01 | 2020-01-29 | 2019-11-21 | 2019-11-08 | 2019-12-04 | 2020-01-29 | 2019-11-29 | 2019-12-11 | 2020-03-20 | 2020-04-27 | 2020-04-08 | 19 | 12 | -49
505967 | Marathon Dickson North Dakota | Oakville | Fabrications - Frames | PLASFAB LIMITED | 4503341769 | Fabrication | Metal Isolation Valves | USD | 30989 | CAD | 16236 | 14753 | Supplier Competitions / Negotiation | 2019-11-15 | 2020-01-16 | 2020-01-16 | 2019-12-06 | 2020-01-08 | 2020-01-16 | 2019-12-13 | 2020-01-10 | 2020-02-21 | 2020-03-19 | 2020-03-05 | 14 | 12 | -6
505967 | Marathon Dickson North Dakota | Oakville | Membrane Tank (Stainless Steel) - | D & R FABRICATION INC - BELDING TANKS | 4503338544 | Fabrication | Stainless Steel | USD | 35794 | CAD | 30552 | 5242 | Supplier Competitions / Negotiation | 2019-11-15 | 2020-01-31 | 2019-12-06 | 2019-12-06 | 2019-12-20 | 2020-01-31 | 2019-12-13 | 2020-01-06 | 2020-02-21 | 2020-04-17 | 2020-03-20 | 28 | 12 | -25
505975 | Husky Spruce Lake East | Guelph | Lakeside - Keystone Valves | LAKESIDE PROCESS CONTROLS LTD. | 4503349931 | Flow Control | Metal Isolation Valves | CAD | 26507 | USD | 37881 | -11374 | Not included in Proposal / RFQ | 2019-11-01 | 2019-11-11 | 2019-11-04 | 2019-11-08 | 2019-12-20 | 2020-02-28 | 2019-11-20 | 2020-01-04 | 2020-05-13 | 2020-06-27 | 2020-06-04 | 23 | 12 | 54
505975 | Husky Spruce Lake East | Guelph | Lakeside - Fisher Valves | LAKESIDE PROCESS CONTROLS LTD. | 4503354560 | Flow Control | Metal Isolation Valves | CAD | 132327 | USD | 131468 | 859 | Supplier Competitions / Negotiation | 2019-11-01 | 2019-11-11 | 2019-11-04 | 2019-11-22 | 2019-11-19 | 2020-01-17 | 2019-12-06 | 2020-01-08 | 2020-04-03 | 2020-03-31 | 2020-03-30 | 1 | 12 | 58
505975 | Husky Spruce Lake East | Guelph | Valves - Ball & Check Valve Metal | WOLSELEY INDUSTRIAL | 4503369094 | Flow Control | Metal Safety(relief) Valves | CAD | 10328 | CAD | 11766 | -1438 | Market Impact | 2019-11-11 | 2019-11-11 | 2020-03-03 | 2019-12-02 | 2020-03-10 | 2020-03-21 | 2019-12-09 | 2020-03-24 | 2020-03-23 | 2020-07-31 | 2020-04-07 | 115 | 12 | 134
505975 | Husky Spruce Lake East | Guelph | Valves - Manifold / 5 Way Manifold | LAKESIDE PROCESS CONTROLS LTD. | 4503381629 | Flow Control | Metal Isolation Valves | CAD | 16130 | USD | 19711 | -3581 | Specs / Requirements Misinterpreted in Proposal | 2019-11-15 | 2019-11-19 | 2020-03-24 | 2019-12-06 | 2020-03-24 | 2020-03-04 | 2019-12-13 | 2020-03-25 | 2020-02-28 | 2020-06-22 | 2020-06-17 | 5 | 12 | 127
505975 | Husky Spruce Lake East | Guelph | Pressure Vessels Metal Fabrication, Painting, Lining | LESENA STEEL DIVISION | 4503323020 | Fabrication | Non-Metal Equipment | CAD | 717927 | CAD | 706090 | 11837 | Frame Agreements | 2019-11-01 | 2019-10-02 | 2019-10-31 | 2019-11-15 | 2019-11-11 | 2020-02-15 | 2019-11-22 | 2019-11-17 | 2020-05-25 | 2020-06-30 | 2020-06-12 | 18 | 12 | 46
505975 | Husky Spruce Lake East | Guelph | Paint for Grating, Handrails, Ladders & Platorms | BRANT CORROSION CONTROL, | 4503385107 | Fabrication | Ele-Control Panels | CAD | 49361 | CAD | 47250 | 2111 | Supplier Competitions / Negotiation | 2019-12-02 | 2019-12-12 | 2020-03-25 | 2019-12-23 | 2020-03-18 | 2020-03-05 | 2019-12-30 | 2020-04-01 | 2020-03-17 | 2020-06-08 | 2020-04-27 | 42 | 12 | 111
505975 | Husky Spruce Lake East | Guelph | Polishing internals welding, Media Trap Cover, Vessel Internals, Resin Traps | TITAN PIPING SYSTEMS INC. | 4503458837 | Fabrication | Metal Isolation Valves | CAD | 232079 | CAD | 265611 | -33532 | Not included in Proposal / RFQ | 2019-11-19 | 2019-11-19 | 2020-03-30 | 2019-12-10 | 2020-08-24 | 2020-05-13 | 2019-12-17 | 2020-08-28 | 2020-04-15 | 2020-11-06 | 2020-07-26 | 103 | 12 | 283
505975 | Husky Spruce Lake East | Guelph | Pipe Spools -Steel Fabrication with Painting | Liquid Flow | 4503354544 | Fabrication | Alloy Steel | CAD | 230062 | CAD | 216461 | 13601 | Design Optimizations | 2019-11-25 | 2019-11-25 | 2020-01-15 | 2019-12-09 | 2020-01-31 | 2020-02-15 | 2019-12-12 | 2020-01-30 | 2020-05-08 | 2020-05-07 | 2020-05-07 | 0 | 12 | 66
505975 | Husky Spruce Lake East | Guelph | Centrifugal Pumps Vertical - Clyde Union | Clyde Union Canada Ltd. | 4503322507 | Rotating Equipment | Centrifugal Pumps | CAD | 361757 | CAD | 351679 | 10078 | Supplier Competitions / Negotiation | 2019-11-01 | 2019-09-27 | 2019-10-22 | 2019-11-13 | 2019-11-11 | 2020-01-22 | 2019-11-18 | 2019-11-27 | 2020-05-18 | 2019-11-27 | 2020-02-21 | -86 | 30 | 61
505975 | Husky Spruce Lake East | Guelph | Centrifugal Pumps Vertical - Gould | GOULDS PUMPS | 4503360326 | Rotating Equipment | Centrifugal Pumps | CAD | 22637 | USD | 17677 | 4960 | Design Optimizations | 2019-11-01 | 2019-10-25 | 2020-02-14 | 2019-11-15 | 2020-02-14 | 2019-12-30 | 2019-11-22 | 2020-02-13 | 2020-03-06 | 2020-02-13 | 2020-02-24 | -11 | 30 | 111
505975 | Husky Spruce Lake East | Guelph | Vacuum Pumps - Flowserve | Flowserve Canada Corp. | 4503334124 | Rotating Equipment | Centrifugal Pumps | CAD | 143300 | CAD | 135000 | 8300 | Supplier Competitions / Negotiation | 2019-11-01 | 2019-10-24 | 2019-11-22 | 2019-11-15 | 2019-12-20 | 2020-03-09 | 2019-11-22 | 2019-12-19 | 2020-07-24 | 2019-12-19 | 2020-04-06 | -109 | 30 | 56
505975 | Husky Spruce Lake East | Guelph | FRP Tank- Brine Maker Tank (FRP GRATING TO SOME TO GUELPH) 84500 | PRECISIONEERING | 4503366131 | Fabrication | Carbon Steel | CAD | 67600 | CAD | 61736 | 5864 | Frame Agreements | 2019-11-22 | 2019-12-18 | 2020-02-25 | 2019-12-06 | 2020-02-18 | 2020-04-02 | 2019-12-11 | 2020-02-26 | 2020-08-12 | 2020-02-26 | 2020-05-20 | -84 | 12 | 70
505975 | Husky Spruce Lake East | Guelph | Plastic Tank | RTS PLASTICS INC. | 4500267159 | Fabrication | Metal Isolation Valves | CAD | 8608 | CAD | 7425 | 1183 | Frame Agreements | 2019-11-22 | 2019-12-18 | 2020-01-16 | 2019-12-06 | 2020-03-17 | 2020-03-30 | 2019-12-11 | 2020-03-31 | 2020-05-20 | 2020-08-07 | 2020-06-28 | 40 | 12 | 104
505975 | Husky Spruce Lake East | Guelph | Skid, Ladders, Platform, Gratings (Fab only) | 3D MECHANICAL | 4503354223 | Fabrication | Skid Assembly Outsourced | CAD | 127600 | CAD | 131500 | -3900 | Single Sourced | 2019-11-26 | 2019-12-12 | 2020-01-06 | 2019-12-10 | 2020-01-16 | 2020-02-16 | 2019-12-12 | 2020-01-30 | 2020-05-08 | 2020-01-30 | 2020-03-19 | -49 | 12 | 49
505975 | Husky Spruce Lake East | Guelph | Junction Boxes | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503401827 | Electrical & Instrumentation | Metal Isolation Valves | CAD | 15514 | CAD | 13990 | 1524 | Supplier Competitions / Negotiation | 2019-11-26 | 2020-05-04 | 2020-05-08 | 2019-12-17 | 2020-05-10 | 2020-03-09 | 2019-12-31 | 2020-05-10 | 2020-04-14 | 2020-06-21 | 2020-05-18 | 34 | 18 | 6
505975 | Husky Spruce Lake East | Guelph | Pressure Gauge/Diaphragm Seal | WIKA INSTRUMENTS LTD. | 4503389202 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | CAD | 8141 | CAD | 8712 | -571 | Not included in Proposal / RFQ | 2019-11-22 | 2020-01-08 | 2020-04-20 | 2019-12-13 | 2020-04-20 | 2020-02-26 | 2019-12-20 | 2020-04-21 | 2020-03-06 | 2020-06-02 | 2020-04-19 | 44 | 18 | 104
505975 | Husky Spruce Lake East | Guelph | Lakeside Instruments | LAKESIDE PROCESS CONTROLS LTD. | 4503383707 | Electrical & Instrumentation | Metal Isolation Valves | CAD | 95571 | USD | 98224 | -2653 | Estimate Without Market Reference(No Quote) | 2019-11-22 | 2020-02-07 | 2020-02-19 | 2019-12-13 | 2020-03-26 | 2020-01-25 | 2019-12-20 | 2020-03-30 | 2020-03-20 | 2020-03-30 | 2020-03-25 | 5 | 18 | 52
505975 | Husky Spruce Lake East | Guelph | Valves - ASCO Solenoid and Speed Control Valves | ASCO NUMATICS CANADA | 4503387851 | Flow Control | Metal Isolation Valves | CAD | 14113 | USD | 12966 | 1147 | Supplier Competitions / Negotiation | 2019-11-29 | 2020-01-09 | 2020-03-10 | 2019-12-20 | 2020-03-17 | 2020-02-20 | 2019-12-27 | 2020-04-07 | 2020-02-28 | 2020-05-11 | 2020-05-13 | -2 | 12 | 89
505975 | Husky Spruce Lake East | Guelph | Heat Tracing | Thermon Canada Inc. | 4503387623 | Electrical & Instrumentation | Metal Isolation Valves | CAD | 17288 | CAD | 15717 | 1571 | Design Optimizations | 2019-12-16 | 2020-03-23 | 2020-03-23 | 2020-01-06 | 2020-03-26 | 2020-03-25 | 2020-01-13 | 2020-04-07 | 2020-04-13 | 2020-07-03 | 2020-04-16 | 78 | 18 | 15
506003 | Morro Bay MBR | Oakville | Main Control Panel | KELTOUR CONTROLS INC. | 4503552641 | Electrical & Instrumentation | Ele-Control Panels | USD | 146854 | USD | 127364 | 19490 | Frame Agreements | 2021-02-12 | 2021-02-10 | 2021-02-21 | 2021-02-28 | 2021-03-06 | 2021-03-27 | 2021-03-10 | 2021-03-13 | 2021-05-12 | 2021-03-13 | 2021-04-12 | -30 | 18 | 31
506003 | Morro Bay MBR | Oakville | Turbidity Ammonia Sensors | Hach Sales & Service Canada Ltd. | 4503535817 | Electrical & Instrumentation | Carbon Steel | USD | 16972 | USD | 27876 | -10904 | Not included in Proposal / RFQ | 2021-03-03 | 2021-01-04 | 2021-01-14 | 2021-03-17 | 2021-01-22 | 2021-03-10 | 2021-03-27 | 2021-02-15 | 2021-05-15 | 2021-02-15 | 2021-03-31 | -44 | 18 | 42
506003 | Morro Bay MBR | Oakville | 500D Hanger-Arm & Brace & Lifting Module - Fabricated Component + Hardware | 3D MECHANICAL | 4503525423 | Fabrication | Platform & Module | USD | 21696 | USD | 31214 | -9518 | Not included in Proposal / RFQ | 2021-02-22 | 2020-12-26 | 2021-01-07 | 2021-03-08 | 2021-01-17 | 2021-03-05 | 2021-03-18 | 2021-01-25 | 2021-05-13 | 2021-01-25 | 2021-03-20 | -54 | 12 | 30
506003 | Morro Bay MBR | Oakville | InSight Pro + Hardware for 1 year InSight Pro for 1 Year;hardware + Pro | Wonderware Canada | 4503576079 | Electrical & Instrumentation | Carbon Steel | USD | 5000 | USD | 8940 | -3940 | Market Impact | 2021-02-16 | 2021-04-02 | 2021-04-13 | 2021-03-04 | 2021-04-19 | 2021-04-01 | 2021-03-14 | 2021-04-27 | 2021-05-16 | 2021-04-27 | 2021-05-06 | -9 | 18 | 25
506003 | Morro Bay MBR | Oakville | SS Pipe Permeate Spool | Liquid Flow | 4503526296 | Fabrication | Carbon Steel | USD | 25436 | USD | 9245 | 16191 | Supplier Competitions / Negotiation | 2021-02-22 | 2020-12-21 | 2021-01-08 | 2021-03-08 | 2021-01-20 | 2021-03-02 | 2021-03-18 | 2021-01-29 | 2021-05-13 | 2021-03-24 | 2021-04-18 | -25 | 12 | 39
506003 | Morro Bay MBR | Oakville | Boerger Permeate Pumps for 2 train system | BOERGER, INC | 4503515691 | Rotating Equipment | Centrifugal Pumps | USD | 23142 | USD | 46112 | -22970 | Specs / Requirements Misinterpreted in Proposal | 2021-02-10 | 2020-12-08 | 2020-12-26 | 2021-02-22 | 2021-01-04 | 2021-02-26 | 2021-03-01 | 2021-01-12 | 2021-05-17 | 2021-01-12 | 2021-03-15 | -62 | 30 | 35
506003 | Morro Bay MBR | Oakville | Aerzen Blower GM 25S DN 125 @ 30 HP @ 1800 RPM (with hood) | AERZEN CANADA INC. | 4503515674 | Rotating Equipment | Carbon Steel | USD | 16255 | USD | 30356 | -14101 | Estimate Without Market Reference(No Quote) | 2021-02-09 | 2020-12-06 | 2020-12-23 | 2021-02-21 | 2021-01-04 | 2021-02-24 | 2021-02-28 | 2021-01-12 | 2021-05-16 | 2021-01-12 | 2021-03-15 | -62 | 30 | 37
506003 | Morro Bay MBR | Oakville | Air compressor system 1+1 compressor system | Compressor Science Inc. | 4503525625 | Rotating Equipment | Vapor Compressor | USD | 15073 | USD | 23975 | -8902 | Specs / Requirements Misinterpreted in Proposal | 2021-02-27 | 2020-12-29 | 2021-01-08 | 2021-03-11 | 2021-01-19 | 2021-03-09 | 2021-03-23 | 2021-01-27 | 2021-05-18 | 2021-01-27 | 2021-03-23 | -55 | 30 | 29
506003 | Morro Bay MBR | Oakville | Drain Pump (Flowserve) | FLOWSERVE INC. | 4503515667 | Rotating Equipment | Centrifugal Pumps | USD | 13444 | USD | 11938 | 1506 | Frame Agreements | 2020-11-25 | 2020-12-09 | 2020-12-23 | 2020-12-05 | 2021-01-05 | 2021-02-20 | 2020-12-15 | 2021-01-13 | 2021-05-18 | 2021-05-15 | 2021-05-16 | -1 | 30 | 35
506003 | Morro Bay MBR | Oakville | Spare parts - Blower - Belts/Filter | BOERGER LLC | 4503675371 | Rotating Equipment | Filter Press | USD | 5273 | USD | 5273 | 0 | Proposed Supplier Incapable Of Executing | 2021-02-05 | 2021-10-06 | 2021-10-12 | 2021-02-17 | 2021-10-22 | 2021-07-01 | 2021-02-24 | 2021-10-26 | 2021-05-19 | 2021-11-25 | 2021-08-22 | 95 | 30 | 20
506003 | Morro Bay MBR | Oakville | PLUG VALVES | FLOVAL EQUIPMENT LIMITED | 4503518974 | Flow Control | Metal Isolation Valves | USD | 9366 | USD | 15737 | -6371 | Single Sourced | 2021-02-12 | 2020-12-28 | 2021-01-05 | 2021-02-24 | 2021-01-11 | 2021-03-09 | 2021-03-03 | 2021-01-18 | 2021-05-19 | 2021-04-30 | 2021-05-09 | -9 | 12 | 21
506003 | Morro Bay MBR | Oakville | Tank Covers, FRP, Assembly & Supports 316 | ACCESS INDUSTRIAL INC | 4503540049 | Fabrication | Centrifugal Pumps | USD | 28000 | USD | 23760 | 4240 | Frame Agreements | 2021-02-07 | 2021-01-23 | 2021-02-01 | 2021-02-07 | 2021-02-09 | 2021-02-07 | 2021-02-07 | 2021-02-22 | 2021-02-07 | 2021-02-22 | 2021-02-14 | 8 | 12 | 30
506028 | Husky Edam Central | Oakville | Lakeside - Valves FISHER | LAKESIDE PROCESS CONTROLS LTD. | 4503380040 | Flow Control | Metal Isolation Valves | CAD | 40614 | CAD | 43811 | -3197 | Specs / Requirements Misinterpreted in Proposal | 2019-11-01 | 2019-10-28 | 2020-03-17 | 2019-11-22 | 2019-12-29 | 2020-02-26 | 2019-12-06 | 2020-01-03 | 2020-06-26 | 2020-01-03 | 2020-03-30 | -87 | 12 | 67
506028 | Husky Edam Central | Oakville | Pressure Vessels Metal Fabrication, Painting, Lining | LESENA STEEL DIVISION | 4503324357 | Fabrication | Non-Metal Equipment | CAD | 304365 | CAD | 295500 | 8865 | Supplier Competitions / Negotiation | 2019-11-01 | 2019-10-15 | 2019-10-16 | 2019-11-15 | 2019-10-30 | 2020-02-26 | 2019-12-06 | 2019-11-16 | 2020-07-10 | 2019-11-16 | 2020-03-13 | -118 | 12 | 32
506028 | Husky Edam Central | Oakville | Centrifugal Pumps Vertical - Clyde Union | Clyde Union Canada Ltd. | 4503322945 | Rotating Equipment | Centrifugal Pumps | CAD | 364890 | CAD | 351679 | 13211 | Frame Agreements | 2019-11-01 | 2019-10-18 | 2019-10-22 | 2019-11-13 | 2019-11-11 | 2020-02-21 | 2019-11-18 | 2019-11-29 | 2020-06-23 | 2020-06-26 | 2020-06-24 | 2 | 30 | 42
506028 | Husky Edam Central | Oakville | Skid, Ladders, Platform, Gratings (Fab only) | 3D MECHANICAL | 4503354540 | Fabrication | Skid Assembly Outsourced | CAD | 7073 | CAD | 13313 | -6240 | Size/ Weight/ Quantity Underestimated | 2019-11-26 | 2020-01-08 | 2020-01-13 | 2019-12-10 | 2020-01-19 | 2020-03-09 | 2019-12-12 | 2020-01-29 | 2020-06-22 | 2020-01-29 | 2020-04-10 | -72 | 12 | 21
506041 | Saint Joseph | Richmond | Air Scour Blower | AERZEN | 4503459532 | Rotating Equipment | Carbon Steel | CAD | 82858 | CAD | 9648 | 73210 | Frame Agreements | 2020-09-14 | 2020-09-04 | 2020-09-04 | 2020-09-28 | 2020-09-13 | 2020-09-04 | 2020-10-01 | 2020-09-15 | 2020-12-03 | 2020-11-24 | 2020-11-28 | -4 | 30 | 11
506041 | Saint Joseph | Richmond | Compressor | ATLAS COPCO COMPRESSORS | 4503459480 | Rotating Equipment | Vapor Compressor | CAD | 32599 | CAD | 26420 | 6179 | Frame Agreements | 2020-09-14 | 2020-09-04 | 2020-09-04 | 2020-09-28 | 2020-09-12 | 2020-09-04 | 2020-10-01 | 2020-09-14 | 2020-12-03 | 2020-11-23 | 2020-11-28 | -5 | 30 | 10
506041 | Saint Joseph | Richmond | Tank - Mangazur | LES ACIERS SOFATEC INC. | 4503468406 | Fabrication | Ele-Control Panels | CAD | 180224 | CAD | 196480 | -16256 | Not included in Proposal / RFQ | 2020-09-15 | 2020-12-24 | 2020-11-03 | 2020-09-28 | 2020-11-02 | 2020-12-24 | 2020-10-01 | 2021-01-24 | 2020-12-10 | 2021-04-04 | 2021-02-05 | 58 | 12 | 31
506041 | Saint Joseph | Richmond | Flowmeters | ENDRESS & HAUSER | 4503485669 | Electrical & Instrumentation | Metal Isolation Valves | CAD | 21916 | CAD | 12559 | 9357 | Frame Agreements | 2020-09-18 | 2020-12-11 | 2020-11-03 | 2020-09-28 | 2020-10-31 | 2020-12-11 | 2020-10-01 | 2021-01-22 | 2020-12-10 | 2021-03-05 | 2021-01-21 | 43 | 18 | 42
506041 | Saint Joseph | Richmond | Electrical Panels | ICSE | 4503483107 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 47020 | CAD | 32684 | 14336 | Design Optimizations | 2020-09-21 | 2020-09-04 | 2020-11-02 | 2020-09-28 | 2020-11-02 | 2020-09-04 | 2020-10-01 | 2020-11-02 | 2020-12-31 | 2021-01-11 | 2021-01-05 | 6 | 18 | 59
506041 | Saint Joseph | Richmond | Butterfly Valves | HAJOCA CORP | 4503488592 | Flow Control | Metal Isolation Valves | CAD | 19637 | CAD | 12388 | 7249 | Supplier Competitions / Negotiation | 2020-09-15 | 2020-09-04 | 2020-11-03 | 2020-09-28 | 2020-11-01 | 2020-09-04 | 2020-10-01 | 2020-11-01 | 2020-12-31 | 2020-12-13 | 2020-12-22 | -9 | 12 | 58
506041 | Saint Joseph | Richmond | Ball Valves | BRAY CONTROLS CANADA LTD. | 4503483940 | Flow Control | Metal Isolation Valves | CAD | 21434 | CAD | 14254 | 7180 | Frame Agreements | 2020-09-15 | 2020-09-04 | 2020-11-03 | 2020-09-28 | 2020-11-01 | 2020-09-04 | 2020-10-01 | 2020-11-01 | 2020-12-31 | 2020-12-13 | 2020-12-22 | -9 | 12 | 58
506048 | Montreal Biomethanation Plant | Oakville | Grit Tank | D&R CUSTOM STEEL | 4503560215 | Fabrication | Stainless Steel | CAD | 309016 | CAD | 168000 | 141016 | Supplier Competitions / Negotiation | 2020-04-03 | 2020-08-07 | 2021-01-15 | 2020-05-04 | 2021-04-18 | 2020-12-01 | 2020-05-25 | 2021-04-24 | 2021-04-15 | 2021-07-31 | 2021-06-07 | 54 | 12 | 260
506048 | Montreal Biomethanation Plant | Oakville | FRP & HDPE Tanks | Augusta Fiberglass | 4503502867 | Fabrication | Non-Metal Equipment | CAD | 130742 | USD | 260124 | -129382 | Single Sourced | 2020-04-10 | 2020-05-13 | 2020-11-03 | 2020-05-11 | 2020-11-15 | 2020-10-04 | 2020-06-01 | 2020-12-09 | 2020-12-01 | 2021-03-31 | 2021-01-30 | 60 | 12 | 210
506048 | Montreal Biomethanation Plant | Oakville | Site Erected Tanks (Supply) | TANK CONNECTION | 4503412730 | Fabrication | Carbon Steel | CAD | 2899585 | USD | 3223838 | -324253 | Market Impact | 2020-01-24 | 2020-03-10 | 2020-05-21 | 2020-02-24 | 2020-04-22 | 2020-06-28 | 2020-03-16 | 2020-04-27 | 2020-12-01 | 2020-06-22 | 2020-09-11 | -81 | 12 | 48
506048 | Montreal Biomethanation Plant | Oakville | Activated Carbon Vessel | BIOCONSERVACION | 4503556553 | Fabrication | Carbon Steel | CAD | 80000 | USD | 659500 | -579500 | Market Impact | 2020-02-28 | 2020-02-27 | 2020-11-18 | 2020-03-30 | 2021-05-13 | 2020-10-27 | 2020-04-20 | 2021-03-21 | 2021-02-15 | 2021-06-27 | 2021-04-22 | 66 | 12 | 388
506048 | Montreal Biomethanation Plant | Oakville | Centrifugal Pumps (JOHN BROOKS/VAUGHAN) | JOHN BROOKS COMPANY LTD. | 4503479909 | Rotating Equipment | Centrifugal Pumps | CAD | 435642 | USD | 435642 | 0 | Specs / Requirements Misinterpreted in Proposal | 2020-03-13 | 2020-04-14 | 2020-08-01 | 2020-04-13 | 2020-09-09 | 2020-09-05 | 2020-05-04 | 2020-10-28 | 2020-12-01 | 2021-03-01 | 2021-01-15 | 45 | 30 | 197
506048 | Montreal Biomethanation Plant | Oakville | Positive Displacement Pumps (Skidded) | BOERGER, INC | 4503474297 | Rotating Equipment | Dosing Pump | CAD | 91394 | USD | 91394 | 0 | Specs / Requirements Misinterpreted in Proposal | 2020-02-28 | 2020-04-14 | 2020-08-07 | 2020-03-30 | 2020-09-07 | 2020-08-17 | 2020-04-20 | 2020-10-15 | 2020-12-01 | 2021-02-04 | 2021-01-02 | 33 | 30 | 184
506048 | Montreal Biomethanation Plant | Oakville | Positive Displacement Pumps (Loose) | BOERGER, INC | 4503474306 | Rotating Equipment | Dosing Pump | CAD | 173404 | USD | 31273 | 142131 | Design Optimizations | 2020-11-28 | 2020-09-21 | 2020-09-28 | 2020-11-28 | 2020-10-12 | 2020-11-28 | 2020-11-28 | 2020-10-15 | 2020-11-28 | 2021-02-04 | 2021-01-01 | 34 | 30 | 24
506048 | Montreal Biomethanation Plant | Oakville | Air Blower | AERZEN CANADA INC. | 4503465289 | Rotating Equipment | Blowers & Fans | CAD | 199207 | CAD | 161700 | 37507 | Design Optimizations | 2020-03-06 | 2020-05-14 | 2020-05-20 | 2020-04-06 | 2020-09-01 | 2020-08-11 | 2020-04-27 | 2020-09-27 | 2020-12-01 | 2021-01-17 | 2020-12-24 | 24 | 30 | 136
506048 | Montreal Biomethanation Plant | Oakville | Recessed Impeller Pumps | HAYWARD GORDON LIMITED | 4503474266 | Rotating Equipment | Centrifugal Pumps | CAD | 75450 | CAD | 226351 | -150901 | Size/ Weight/ Quantity Underestimated | 2020-03-20 | 2020-04-14 | 2020-08-06 | 2020-04-20 | 2020-10-11 | 2020-10-01 | 2020-05-11 | 2020-10-16 | 2021-04-15 | 2021-03-05 | 2021-03-25 | -20 | 30 | 185
506048 | Montreal Biomethanation Plant | Oakville | Submersible Pumps (JOHN BROOKS) | JOHN BROOKS COMPANY LTD. | 4503494718 | Rotating Equipment | Centrifugal Pumps | CAD | 83861 | USD | 73069 | 10792 | Frame Agreements | 2020-03-20 | 2020-04-14 | 2020-04-25 | 2020-04-20 | 2020-04-30 | 2020-10-01 | 2020-05-11 | 2020-11-27 | 2021-04-15 | 2021-03-19 | 2021-04-01 | -13 | 30 | 227
506048 | Montreal Biomethanation Plant | Oakville | Digester Heat Exchanger | HRS | 4503450767 | Fabrication | Carbon Steel | CAD | 52900 | USD | 65027 | -12127 | Single Sourced | 2020-03-06 | 2020-04-14 | 2020-07-09 | 2020-04-06 | 2020-08-20 | 2020-08-05 | 2020-04-27 | 2020-09-08 | 2020-12-01 | 2021-01-05 | 2020-12-18 | 18 | 12 | 147
506048 | Montreal Biomethanation Plant | Oakville | Dewatering Centrifuge | ALFA LAVAL | 4503445171 | Rotating Equipment | Centrifuge | CAD | 608950 | CAD | 750074 | -141124 | Estimate Without Market Reference(No Quote) | 2020-02-28 | 2020-03-25 | 2020-04-16 | 2020-03-30 | 2020-07-28 | 2020-09-21 | 2020-04-20 | 2020-08-13 | 2021-04-15 | 2021-03-25 | 2021-04-04 | -10 | 30 | 141
506048 | Montreal Biomethanation Plant | Oakville | Flare | AIR SCIENCE | 4503442041 | Fabrication | Process Equipment | CAD | 290335 | CAD | 418265 | -127930 | Not included in Proposal / RFQ | 2020-02-28 | 2020-03-13 | 2020-06-22 | 2020-03-30 | 2020-07-18 | 2020-08-22 | 2020-04-20 | 2020-08-04 | 2021-02-15 | 2020-12-22 | 2021-01-18 | -27 | 12 | 144
506048 | Montreal Biomethanation Plant | Oakville | Gas Mix Compressor | Busch Vacuum Technics Inc. | 4503453983 | Rotating Equipment | Compressors | CAD | 150156 | USD | 150656 | -500 | Size/ Weight/ Quantity Underestimated | 2020-03-06 | 2020-04-28 | 2020-07-10 | 2020-04-06 | 2020-08-24 | 2020-08-26 | 2020-04-27 | 2020-09-03 | 2021-02-15 | 2021-02-04 | 2021-02-09 | -5 | 30 | 128
506048 | Montreal Biomethanation Plant | Oakville | Conveyors | Spirac | 4503445000 | Rotating Equipment | Material Handling-ADT | CAD | 474696 | USD | 474444 | 252 | Design Optimizations | 2020-03-13 | 2020-04-10 | 2020-07-13 | 2020-04-13 | 2020-08-11 | 2020-09-28 | 2020-05-04 | 2020-08-15 | 2021-04-15 | 2021-01-16 | 2021-03-01 | -44 | 30 | 127
506048 | Montreal Biomethanation Plant | Oakville | Shredder | ACG – Envirocan | 4503457518 | Rotating Equipment | Material Handling-ADT | CAD | 390231 | CAD | 415725 | -25494 | Specs / Requirements Misinterpreted in Proposal | 2020-03-13 | 2020-03-25 | 2020-07-07 | 2020-04-13 | 2020-06-20 | 2020-09-28 | 2020-05-04 | 2020-11-16 | 2021-04-15 | 2021-02-22 | 2021-03-20 | -26 | 30 | 236
506048 | Montreal Biomethanation Plant | Oakville | Push Compactor | HUSMANN | 4503482040 | Rotating Equipment | Dehydration | CAD | 150000 | EUR | 207379 | -57379 | Market Impact | 2020-03-06 | 2020-03-26 | 2020-09-24 | 2020-04-06 | 2020-07-12 | 2020-09-24 | 2020-04-27 | 2020-10-29 | 2021-04-15 | 2021-02-18 | 2021-03-18 | -28 | 30 | 217
506048 | Montreal Biomethanation Plant | Oakville | Hydrocyclone | Salter Cyclones Ltd | 4503440044 | Fabrication | Process Equipment | CAD | 18685 | GBP | 19726 | -1041 | Market Impact | 2020-03-13 | 2020-04-10 | 2020-05-05 | 2020-04-13 | 2020-06-24 | 2020-09-28 | 2020-05-04 | 2020-08-03 | 2021-04-15 | 2020-10-12 | 2021-01-12 | -92 | 12 | 115
506048 | Montreal Biomethanation Plant | Oakville | Grit Classifier | Enviro-Care Company - WAM | 4503442052 | Fabrication | Process Equipment | CAD | 123260 | USD | 127605 | -4345 | Proposed Supplier Incapable Of Executing | 2020-03-13 | 2020-04-20 | 2020-06-17 | 2020-04-13 | 2020-06-10 | 2020-09-28 | 2020-05-04 | 2020-08-07 | 2021-04-15 | 2021-01-22 | 2021-03-04 | -41 | 12 | 109
506048 | Montreal Biomethanation Plant | Oakville | Gas Upgrading Membrane Skid (Engineering Prodeval) | PRODEVAL | 4503422033 | Fabrication | Skid Assembly Outsourced | CAD | 332930 | CAD | 343928 | -10998 | Single Sourced | 2020-02-28 | 2020-02-27 | 2020-05-27 | 2020-03-30 | 2020-06-18 | 2020-08-22 | 2020-04-20 | 2020-06-24 | 2021-02-15 | 2020-06-24 | 2020-10-20 | -118 | 12 | 118
506048 | Montreal Biomethanation Plant | Oakville | Gas Upgrading Membrane Skid (Fabrication) | GRANITEFUEL ENGINEERING | 4503546175 | Fabrication | Skid Assembly Outsourced | CAD | 2254046 | CAD | 980833 | 1273213 | Design Optimizations | 2021-04-26 | 2020-10-20 | 2020-10-27 | 2021-04-26 | 2021-02-22 | 2021-04-26 | 2021-04-26 | 2021-02-28 | 2021-04-26 | 2021-10-31 | 2021-07-29 | 94 | 12 | 131
506048 | Montreal Biomethanation Plant | Oakville | Master Control Panel | GERRIE ELECTRIC LIMITED | 4503734237 | Electrical & Instrumentation | Ele-Control Panels | CAD | 326707 | CAD | 561851 | -235144 | Specs / Requirements Misinterpreted in Proposal | 2022-01-25 | 2022-01-11 | 2022-01-18 | 2022-01-25 | 2022-02-01 | 2022-01-25 | 2022-01-25 | 2022-02-08 | 2022-01-25 | 2022-02-08 | 2022-02-01 | 7 | 18 | 28
506048 | Montreal Biomethanation Plant | Oakville | Depackaging Machine | TMA | 4503469070 | Rotating Equipment | Material Handling-ADT | CAD | 1057934 | EUR | 954186 | 103748 | Design Optimizations | 2020-03-06 | 2020-03-25 | 2020-07-09 | 2020-04-06 | 2020-10-16 | 2020-09-24 | 2020-04-27 | 2020-10-24 | 2021-04-15 | 2021-03-13 | 2021-03-29 | -16 | 30 | 213
506048 | Montreal Biomethanation Plant | Oakville | Dual Fuel Boiler | Groupe Simoneau | 4503493780 | Fabrication | Process Equipment | CAD | 443918 | CAD | 563100 | -119182 | Single Sourced | 2020-03-20 | 2020-05-11 | 2020-07-03 | 2020-04-20 | 2020-08-30 | 2020-11-03 | 2020-05-11 | 2020-11-22 | 2020-12-01 | 2021-06-20 | 2021-03-11 | 101 | 12 | 195
506048 | Montreal Biomethanation Plant | Oakville | Double Membrane Gas Holder | Tecon | 4503456736 | Fabrication | Process Equipment | CAD | 182590 | EUR | 150321 | 32269 | Frame Agreements | 2020-03-13 | 2020-04-20 | 2020-08-21 | 2020-04-13 | 2020-08-16 | 2020-08-29 | 2020-05-04 | 2020-09-10 | 2021-02-15 | 2020-12-03 | 2021-01-09 | -37 | 12 | 143
506048 | Montreal Biomethanation Plant | Oakville | Gas Analyzer | AVENSYS | 4503589743 | Electrical & Instrumentation | Inst-Analytical Instruments | CAD | 90000 | CAD | 69250 | 20750 | Supplier Competitions / Negotiation | 2020-04-03 | 2020-10-16 | 2021-02-01 | 2020-05-04 | 2021-04-20 | 2020-12-09 | 2020-05-25 | 2021-04-26 | 2021-02-15 | 2021-08-16 | 2021-05-17 | 91 | 18 | 192
506048 | Montreal Biomethanation Plant | Oakville | Instruments - Transmitters - E&H (to site) | ENDRESS + HAUSER CANADA LTD. | 4503622900 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | CAD | 100000 | USD | 305053 | -205053 | Size/ Weight/ Quantity Underestimated | 2020-04-17 | 2020-08-31 | 2020-10-20 | 2020-05-18 | 2021-06-30 | 2021-02-10 | 2020-06-08 | 2021-07-19 | 2021-02-02 | 2021-12-06 | 2021-07-05 | 154 | 18 | 322
506048 | Montreal Biomethanation Plant | Oakville | UPS | WESCO DISTRIBUTION CANADA INC. | 4503788000 | Electrical & Instrumentation | Inst-Gauges | CAD | 30000 | CAD | 31084 | -1084 | Not included in Proposal / RFQ | 2022-04-28 | 2022-04-18 | 2022-04-25 | 2022-04-28 | 2022-05-02 | 2022-04-28 | 2022-04-28 | 2022-05-09 | 2022-04-28 | 2022-05-09 | 2022-05-03 | 6 | 18 | 21
506048 | Montreal Biomethanation Plant | Oakville | Instruments (for Biofilter-Odor Control) | ENDRESS + HAUSER CANADA LTD. | 4503705133 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | CAD | 123497 | CAD | 67741 | 55756 | Design Optimizations | 2020-04-17 | 2020-08-31 | 2021-12-02 | 2020-05-18 | 2021-12-09 | 2021-02-15 | 2020-06-08 | 2021-12-16 | 2020-10-15 | 2021-12-16 | 2021-05-16 | 214 | 18 | 472
506048 | Montreal Biomethanation Plant | Oakville | Manual Valves - Non-Metallic PVC - Georg Fisher (Loose) | GEORG FISCHER LLC | 4503577551 | Flow Control | Plastic Valves (All) | CAD | 60468 | CAD | 6771 | 53697 | Frame Agreements | 2020-04-17 | 2020-10-22 | 2021-04-01 | 2020-05-18 | 2021-04-23 | 2020-11-26 | 2020-06-08 | 2021-04-29 | 2021-02-02 | 2021-07-08 | 2021-04-21 | 78 | 12 | 189
506048 | Montreal Biomethanation Plant | Oakville | PVRVs | Protego | 4503444319 | Flow Control | Metal Safety(relief) Valves | CAD | 152000 | USD | 290921 | -138921 | Size/ Weight/ Quantity Underestimated | 2020-03-06 | 2020-03-25 | 2020-05-28 | 2020-04-06 | 2020-08-03 | 2020-07-24 | 2020-04-27 | 2020-08-22 | 2020-12-01 | 2020-12-12 | 2020-12-06 | 6 | 12 | 150
506048 | Montreal Biomethanation Plant | Oakville | Auto Valves - On-Off and Modulation Control and 3 way - Bray | BRAY CONTROLS CANADA LTD. | 4503646644 | Flow Control | Metal Control Valves | CAD | 57476 | USD | 292363 | -234887 | Single Sourced | 2020-04-17 | 2020-09-04 | 2021-08-17 | 2020-05-18 | 2021-08-22 | 2021-03-14 | 2020-06-08 | 2021-09-07 | 2020-10-15 | 2022-02-08 | 2021-06-12 | 241 | 12 | 368
506048 | Montreal Biomethanation Plant | Oakville | WWTP Electrical Panels & JBs - part of main control PLC line | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503635530 | Electrical & Instrumentation | Ele-Control Panels | CAD | 7042 | CAD | 27990 | -20948 | Specs / Requirements Misinterpreted in Proposal | 2020-03-20 | 2020-03-16 | 2021-08-04 | 2020-04-20 | 2021-08-08 | 2021-01-03 | 2020-05-11 | 2021-08-14 | 2020-12-01 | 2021-10-23 | 2021-05-13 | 163 | 18 | 516
506048 | Montreal Biomethanation Plant | Oakville | Chemical Feed - Polymer Makedown System | PROMINENT FLUID CONTROLS LTD. | 4503488692 | Rotating Equipment | Chem. Feed Skids (Turnkey) | CAD | 244022 | CAD | 266558 | -22536 | Market Impact | 2020-04-10 | 2020-05-12 | 2020-10-30 | 2020-05-11 | 2020-11-01 | 2020-09-28 | 2020-06-01 | 2020-11-15 | 2020-12-01 | 2021-03-19 | 2021-01-24 | 54 | 30 | 187
506048 | Montreal Biomethanation Plant | Oakville | Chemical Feeds - Skids | PROMINENT FLUID CONTROLS LTD. | 4503489425 | Rotating Equipment | Chem. Feed Skids (Turnkey) | CAD | 43596 | CAD | 78148 | -34552 | Size/ Weight/ Quantity Underestimated | 2020-04-10 | 2020-05-12 | 2020-10-22 | 2020-05-11 | 2020-10-31 | 2020-09-19 | 2020-06-01 | 2020-11-16 | 2020-12-01 | 2021-02-28 | 2021-01-14 | 45 | 30 | 188
506048 | Montreal Biomethanation Plant | Oakville | Condensate Trap | FIL-TREK CORPORATION | 4503546066 | Fabrication | Process Equipment | CAD | 15000 | USD | 34360 | -19360 | Size/ Weight/ Quantity Underestimated | 2020-05-01 | 2021-02-27 | 2021-02-26 | 2020-06-01 | 2021-03-02 | 2020-10-01 | 2020-06-22 | 2021-03-03 | 2021-02-15 | 2021-03-03 | 2021-02-23 | 8 | 12 | 4
506048 | Montreal Biomethanation Plant | Oakville | Air Compressor, Air Dryer, Air Filter | ATLAS COPCO COMPRESSORS | 4503493771 | Rotating Equipment | Compressors | CAD | 33457 | CAD | 28040 | 5417 | Frame Agreements | 2020-04-03 | 2020-10-23 | 2020-10-30 | 2020-05-04 | 2020-11-18 | 2020-09-15 | 2020-05-25 | 2020-11-24 | 2020-12-01 | 2021-02-28 | 2021-01-14 | 45 | 30 | 32
506048 | Montreal Biomethanation Plant | Oakville | Screw Compactor | RUNI Inc | 4503468380 | Rotating Equipment | Dehydration | CAD | 197549 | EUR | 313046 | -115497 | Proposed Supplier Incapable Of Executing | 2020-03-20 | 2020-04-24 | 2020-07-14 | 2020-04-20 | 2020-08-29 | 2020-10-01 | 2020-05-11 | 2020-10-01 | 2021-04-15 | 2021-01-21 | 2021-03-04 | -42 | 30 | 160
506048 | Montreal Biomethanation Plant | Oakville | Post Digestion Screen Press | Huber Technology | 4503438966 | Rotating Equipment | Filter Press | CAD | 292107 | USD | 350297 | -58190 | Proposed Supplier Incapable Of Executing | 2020-03-13 | 2020-04-10 | 2020-06-01 | 2020-04-13 | 2020-07-26 | 2020-09-28 | 2020-05-04 | 2020-08-01 | 2021-04-15 | 2021-02-27 | 2021-03-22 | -23 | 30 | 113
506048 | Montreal Biomethanation Plant | Oakville | Brackets-Frames (Brackets Frames) | Plasfab Inc | 4503546939 | Fabrication | Platform & Module | CAD | 70598 | CAD | 10716 | 59882 | Design Optimizations | 2020-05-01 | 2021-03-04 | 2021-03-11 | 2020-06-01 | 2021-02-28 | 2020-10-05 | 2020-06-22 | 2021-03-06 | 2020-10-15 | 2021-03-06 | 2020-12-25 | 71 | 12 | 2
506048 | Montreal Biomethanation Plant | Oakville | Biogas Compressor Package (Biogas Blowers, Compressors,Chiller) | ACS | 4503502018 | Rotating Equipment | Compressors | CAD | 1069196 | USD | 2071161 | -1001965 | Single Sourced | 2020-02-28 | 2020-02-27 | 2020-12-01 | 2020-03-30 | 2020-11-30 | 2020-10-30 | 2020-04-20 | 2020-12-06 | 2021-02-15 | 2021-07-04 | 2021-04-25 | 70 | 30 | 283
506048 | Montreal Biomethanation Plant | Oakville | Biogas Compressor Package (C/O) | ACS | 4503776881 | Rotating Equipment | Compressors | CAD | 40000 | USD | 39004 | 996 | Supplier Competitions / Negotiation | 2022-04-08 | 2022-03-29 | 2022-04-05 | 2022-04-08 | 2022-04-12 | 2022-04-08 | 2022-04-08 | 2022-04-19 | 2022-04-08 | 2022-04-19 | 2022-04-13 | 6 | 30 | 21
506048 | Montreal Biomethanation Plant | Oakville | Cake Distribution Conveyors | Con-V-Air | 4503471474 | Rotating Equipment | Material Handling-ADT | CAD | 495287 | CAD | 199827 | 295460 | Frame Agreements | 2020-10-02 | 2020-09-09 | 2020-08-01 | 2020-10-02 | 2020-10-10 | 2020-10-02 | 2020-10-02 | 2020-10-23 | 2020-10-02 | 2020-12-04 | 2020-11-02 | 32 | 30 | 44
506048 | Montreal Biomethanation Plant | Oakville | MBR Membrane Tank | D&R CUSTOM STEEL | 4503471715 | Fabrication | Stainless Steel | CAD | 98600 | CAD | 80300 | 18300 | Design Optimizations | 2020-04-03 | 2020-05-13 | 2020-09-08 | 2020-05-04 | 2020-09-29 | 2020-09-01 | 2020-05-25 | 2020-10-10 | 2020-12-01 | 2021-01-30 | 2020-12-31 | 30 | 12 | 150
506138 | Crosby TX Accelator | Richmond | Rotor Drives | SEW EURODRIVE | 4503400604 | Rotating Equipment | Metal Isolation Valves | USD | 9157 | USD | 9158 | -1 | Not included in Proposal / RFQ | 2020-04-20 | 2020-06-09 | 2020-05-07 | 2020-04-30 | 2020-04-30 | 2020-06-09 | 2020-05-04 | 2020-05-02 | 2020-07-30 | 2020-07-11 | 2020-07-20 | -9 | 30 | -38
506138 | Crosby TX Accelator | Richmond | Filter Valves | DEZURIK | 4503437657 | Flow Control | Metal Isolation Valves | USD | 120452 | USD | 206498 | -86046 | Not included in Proposal / RFQ | 2020-04-20 | 2020-08-30 | 2020-05-01 | 2020-04-30 | 2020-07-29 | 2020-08-30 | 2020-05-04 | 2020-08-23 | 2020-07-30 | 2021-01-10 | 2020-10-20 | 82 | 12 | -7
506138 | Crosby TX Accelator | Richmond | Control Panels | ICSE | 4503460785 | Electrical & Instrumentation | Ele-Control Panels | USD | 56472 | USD | 42698 | 13774 | Frame Agreements | 2020-04-20 | 2020-07-07 | 2020-03-14 | 2020-04-30 | 2020-09-16 | 2020-07-07 | 2020-05-04 | 2020-09-18 | 2020-07-30 | 2020-10-30 | 2020-09-14 | 46 | 18 | 73
506138 | Crosby TX Accelator | Richmond | Accelator | RICHLAND LLC. | 4503399879 | Fabrication | Metal Isolation Valves | USD | 147574 | USD | 149010 | -1436 | Estimate Without Market Reference(No Quote) | 2020-06-21 | 2020-06-21 | 2020-05-01 | 2020-06-21 | 2020-05-04 | 2020-06-21 | 2020-06-21 | 2020-05-05 | 2020-06-21 | 2020-08-11 | 2020-07-16 | 26 | 12 | -47
506186 | Hespeler WWTP | Oakville | Hanger Arms, Wall Mounting Bracket End & Between Cassettes | MARCON CUSTOM METALS, INC. | 4503505604 | Fabrication | Alloy Steel | CAD | 102649 | CAD | 121712 | -19063 | Single Sourced | 2021-01-05 | 2020-11-19 | 2020-11-28 | 2021-01-15 | 2020-12-10 | 2021-01-20 | 2021-01-23 | 2020-12-18 | 2021-03-24 | 2021-03-05 | 2021-03-14 | -9 | 12 | 29
506186 | Hespeler WWTP | Oakville | Process Air Header | NV PIPING SYSTEMS INC. | 4503519099 | Fabrication | Carbon Steel | CAD | 26189 | CAD | 46980 | -20791 | Market Impact | 2021-01-03 | 2020-12-22 | 2021-01-06 | 2021-01-13 | 2021-01-13 | 2021-02-05 | 2021-01-21 | 2021-01-20 | 2021-03-22 | 2021-03-15 | 2021-03-18 | -3 | 12 | 29
506186 | Hespeler WWTP | Oakville | Lifting Bracket | Plasfab Inc | 4503542153 | Fabrication | Alloy Steel | CAD | 13309 | CAD | 13309 | 0 | Design Optimizations | 2021-01-05 | 2021-01-29 | 2021-02-09 | 2021-01-15 | 2021-02-17 | 2021-02-13 | 2021-01-23 | 2021-02-24 | 2021-03-24 | 2021-02-24 | 2021-03-10 | -14 | 12 | 26
506186 | Hespeler WWTP | Oakville | Solenoid Valve For Cassettes | ASCO NUMATICS | 4503454312 | Flow Control | Metal Control Valves | CAD | 36009 | CAD | 12278 | 23731 | Design Optimizations | 2021-01-13 | 2020-08-08 | 2020-08-19 | 2021-01-23 | 2020-08-24 | 2020-12-09 | 2021-02-01 | 2020-09-03 | 2021-04-12 | 2020-09-03 | 2020-12-22 | -110 | 12 | 26
506186 | Hespeler WWTP | Oakville | Main Control Panel | KELTOUR CONTROLS INC. | 4503661915 | Electrical & Instrumentation | Ele-Control Panels | CAD | 55000 | CAD | 63427 | -8427 | Estimate Without Market Reference(No Quote) | 2021-03-24 | 2021-08-25 | 2021-09-17 | 2021-04-02 | 2021-09-25 | 2021-08-15 | 2021-04-10 | 2021-10-04 | 2021-06-12 | 2022-01-07 | 2021-09-24 | 105 | 18 | 40
506186 | Hespeler WWTP | Oakville | Oxygen Monitor & Oxygen Monitor - hand held | VERONICS INSTRUMENTS INC. | 4503454793 | Electrical & Instrumentation | Inst-Gauges | CAD | 22406 | CAD | 25782 | -3376 | Estimate Without Market Reference(No Quote) | 2021-01-29 | 2020-08-12 | 2020-08-22 | 2021-02-07 | 2020-08-28 | 2020-12-11 | 2021-02-15 | 2020-09-06 | 2021-04-12 | 2020-09-06 | 2020-12-24 | -109 | 18 | 25
506186 | Hespeler WWTP | Oakville | Blower | AERZEN CANADA INC. | 4503472354 | Rotating Equipment | Blowers & Fans | CAD | 30680 | CAD | 27328 | 3352 | Supplier Competitions / Negotiation | 2021-01-17 | 2020-09-19 | 2020-09-29 | 2021-01-26 | 2020-10-05 | 2020-12-30 | 2021-02-03 | 2020-10-12 | 2021-04-11 | 2020-10-12 | 2021-01-10 | -90 | 30 | 23
506222 | INTEL RA WaTR Phase 2 | Guelph | Pressure Vessel (Includes Painting + Internal) | LESENA STEEL DIVISION | 4503381243 | Fabrication | Metal Isolation Valves | USD | 90979 | CAD | 90979 | 0 | Specs / Requirements Misinterpreted in Proposal | 2020-03-11 | 2020-03-17 | 2020-03-17 | 2020-03-28 | 2020-03-20 | 2020-05-25 | 2020-04-02 | 2020-03-24 | 2020-08-08 | 2020-07-28 | 2020-08-02 | -5 | 12 | 7
506222 | INTEL RA WaTR Phase 2 | Guelph | IX Vessel Lining | BRANT CORROSION CONTROL, | 4503394639 | Fabrication | Metal Isolation Valves | USD | 40109 | CAD | 43475 | -3366 | Not included in Proposal / RFQ | 2020-03-11 | 2020-03-17 | 2020-04-01 | 2020-03-28 | 2020-04-26 | 2020-06-28 | 2020-04-02 | 2020-04-27 | 2020-10-15 | 2020-07-06 | 2020-08-25 | -50 | 12 | 41
506222 | INTEL RA WaTR Phase 2 | Guelph | Squeezer RO Housing -Model 80S120-3 | CODELINE | 4503379207 | Fabrication | Carbon Steel | USD | 78746 | USD | 76348 | 2398 | Frame Agreements | 2020-03-17 | 2020-03-03 | 2020-03-06 | 2020-04-03 | 2020-03-15 | 2020-06-06 | 2020-04-08 | 2020-03-19 | 2020-09-09 | 2020-06-11 | 2020-07-26 | -45 | 12 | 16
506222 | INTEL RA WaTR Phase 2 | Guelph | Feed Pump - Centrifugal | FLOWSERVE INC. | 4503380596 | Rotating Equipment | Chem. Feed Skids (TurnKey) | USD | 33619 | USD | 43393 | -9774 | Single Sourced | 2020-03-03 | 2020-02-24 | 2020-03-16 | 2020-03-20 | 2020-03-21 | 2020-06-09 | 2020-03-25 | 2020-03-22 | 2020-09-23 | 2020-08-16 | 2020-09-04 | -19 | 30 | 27
506222 | INTEL RA WaTR Phase 2 | Guelph | HPRO Booster Pump - Centrifugal | FLUID EQUIPMENT DEVELOPMENT | 4503386297 | Rotating Equipment | Centrifugal Pumps | USD | 97703 | USD | 102742 | -5039 | Proposed Supplier Incapable Of Executing | 2020-03-03 | 2020-03-06 | 2020-03-11 | 2020-03-20 | 2020-04-01 | 2020-06-06 | 2020-03-25 | 2020-04-03 | 2020-09-09 | 2020-08-21 | 2020-08-30 | -9 | 30 | 28
506222 | INTEL RA WaTR Phase 2 | Guelph | Squeezer RO Pump - Centrifugal | FLUID EQUIPMENT DEVELOPMENT | 450338629 | Rotating Equipment | Centrifugal Pumps | USD | 70259 | USD | 75947 | -5688 | Market Impact | 2020-05-05 | 2020-03-01 | 2020-03-11 | 2020-05-22 | 2020-03-29 | 2020-07-06 | 2020-05-27 | 2020-03-31 | 2020-11-11 | 2020-08-04 | 2020-09-22 | -49 | 30 | 30
506222 | INTEL RA WaTR Phase 2 | Guelph | VFD's + Panels (PLC) | Integrated Systems Group | 4503390150 | Electrical & Instrumentation | Ele-Control Panels | USD | 333746 | USD | 204895 | 128851 | Supplier Competitions / Negotiation | 2020-04-01 | 2020-04-01 | 2020-04-10 | 2020-04-18 | 2020-04-09 | 2020-06-07 | 2020-04-23 | 2020-04-12 | 2020-08-13 | 2020-06-21 | 2020-07-17 | -26 | 18 | 11
506222 | INTEL RA WaTR Phase 2 | Guelph | Plastic Box/Fittings | BETA PLASTICS INC | 4503427605 | Electrical & Instrumentation | Metal Isolation Valves | USD | 12657 | USD | 10785 | 1872 | Frame Agreements | 2020-04-15 | 2020-05-08 | 2020-05-14 | 2020-05-02 | 2020-07-04 | 2020-07-12 | 2020-05-07 | 2020-07-08 | 2020-08-13 | 2020-10-08 | 2020-09-10 | 28 | 18 | 61
506222 | INTEL RA WaTR Phase 2 | Guelph | Flow/Press-Transmitter | ENDRESS + HAUSER CANADA LTD. | 4503432763 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 30165 | USD | 50044 | -19879 | Size/ Weight/ Quantity Underestimated | 2020-04-29 | 2020-06-01 | 2020-06-08 | 2020-05-16 | 2020-07-13 | 2020-07-05 | 2020-05-21 | 2020-07-18 | 2020-09-10 | 2020-07-18 | 2020-08-14 | -27 | 18 | 47
506222 | INTEL RA WaTR Phase 2 | Oakville | Flow/Press-Transmitter-II | ENDRESS + HAUSER CANADA LTD. | 4503450739 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 23960 | USD | 28610 | -4650 | Market Impact | 2020-07-28 | 2020-07-01 | 2020-07-16 | 2020-08-13 | 2020-07-18 | 2020-08-12 | 2020-07-17 | 2020-07-20 | 2020-09-24 | 2020-07-20 | 2020-08-22 | -33 | 18 | 19
506222 | INTEL RA WaTR Phase 2 | Guelph | Pressure- Gauge/Switch | CONVAL EQUIPMENT LIMITED | 4503417207 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 6900 | USD | 6702 | 198 | Supplier Competitions / Negotiation | 2020-04-29 | 2020-06-01 | 2020-06-10 | 2020-05-16 | 2020-06-14 | 2020-07-05 | 2020-05-21 | 2020-06-15 | 2020-09-10 | 2020-06-15 | 2020-07-28 | -43 | 18 | 14
506222 | INTEL RA WaTR Phase 2 | Guelph | Frames | PLASFAB LIMITED | 4503399181 | Fabrication | Metal Isolation Valves | USD | 180162 | CAD | 175369 | 4793 | Frame Agreements | 2020-03-24 | 2020-04-17 | 2020-04-02 | 2020-04-10 | 2020-04-28 | 2020-06-13 | 2020-04-15 | 2020-04-29 | 2020-09-02 | 2020-04-29 | 2020-07-01 | -63 | 12 | 12
506222 | INTEL RA WaTR Phase 2 | Guelph | Spools | NV PIPING SYSTEMS INC. | 4503399882 | Fabrication | Centrifugal Pumps | USD | 377168 | USD | 407003 | -29835 | Single Sourced | 2020-03-24 | 2020-04-17 | 2020-04-12 | 2020-04-10 | 2020-04-26 | 2020-06-13 | 2020-04-15 | 2020-04-27 | 2020-09-02 | 2020-04-27 | 2020-06-30 | -64 | 12 | 10
506222 | INTEL RA WaTR Phase 2 | Guelph | UF Cassette hanger Arms + Brace | 3D MECHANICAL | 4503403678 | Fabrication | Ele-Control Panels | USD | 72689 | CAD | 32027 | 40662 | Design Optimizations | 2020-04-15 | 2020-05-07 | 2020-05-12 | 2020-05-02 | 2020-05-14 | 2020-07-05 | 2020-05-07 | 2020-05-14 | 2020-09-24 | 2020-08-28 | 2020-09-10 | -13 | 12 | 7
506222 | INTEL RA WaTR Phase 2 | Guelph | Tank-Decarb | Design Tanks, LLC | 4503384261 | Fabrication | Ele-Control Panels | USD | 94155 | USD | 94155 | 0 | Market Impact | 2020-03-18 | 2020-03-01 | 2020-03-26 | 2020-04-04 | 2020-03-31 | 2020-05-12 | 2020-04-09 | 2020-03-30 | 2020-07-23 | 2020-03-30 | 2020-05-26 | -57 | 12 | 29
506222 | INTEL RA WaTR Phase 2 | Guelph | VALVE-BTFLY | BRAY CONTROLS CANADA LTD. | 4503401218 | Flow Control | Ele-Control Panels | USD | 33784 | USD | 33784 | 0 | Not included in Proposal / RFQ | 2020-04-15 | 2020-04-28 | 2020-04-15 | 2020-05-02 | 2020-05-05 | 2020-07-26 | 2020-05-07 | 2020-05-07 | 2020-11-05 | 2020-05-07 | 2020-08-06 | -91 | 12 | 9
506222 | INTEL RA WaTR Phase 2 | Guelph | VALVE-RELIEF | Great Lakes Industrial Controls | 4503418480 | Flow Control | Metal Safety(relief) Valves | USD | 6075 | CAD | 10826 | -4751 | Proposed Supplier Incapable Of Executing | 2020-04-15 | 2020-06-01 | 2020-06-12 | 2020-05-02 | 2020-06-16 | 2020-06-28 | 2020-05-07 | 2020-06-18 | 2020-09-10 | 2020-06-18 | 2020-07-30 | -42 | 12 | 17
506222 | INTEL RA WaTR Phase 2 | Guelph | VALVE-CHECK | SWAGELOK SOUTHWESTERN ONTARIO | 4503395305 | Flow Control | Ele-Control Panels | USD | 5540 | CAD | 8352 | -2812 | Single Sourced | 2020-04-15 | 2020-04-02 | 2020-04-16 | 2020-05-02 | 2020-04-21 | 2020-06-21 | 2020-05-07 | 2020-04-24 | 2020-09-10 | 2020-05-21 | 2020-07-16 | -56 | 12 | 22
506222 | INTEL RA WaTR Phase 2 | Guelph | CARTRIDGE FILTER | FIL-TREK CORPORATION | 4503382706 | Fabrication | Carbon Steel | USD | 17900 | USD | 17900 | 0 | Not included in Proposal / RFQ | 2020-04-15 | 2020-03-11 | 2020-03-20 | 2020-05-02 | 2020-03-24 | 2020-06-03 | 2020-05-07 | 2020-03-26 | 2020-08-26 | 2020-03-26 | 2020-06-10 | -76 | 12 | 15
506222 | INTEL RA WaTR Phase 2 | Guelph | LINED STEEL SPOOL | BAUM AMERICA CORP | 4503417003 | Fabrication | Alloy Steel | USD | 49503 | USD | 52461 | -2958 | Single Sourced | 2020-04-22 | 2020-07-01 | 2020-07-10 | 2020-05-09 | 2020-07-16 | 2020-07-12 | 2020-05-14 | 2020-07-16 | 2020-10-01 | 2020-08-16 | 2020-09-08 | -23 | 12 | 15
506222 | INTEL RA WaTR Phase 2 | Guelph | HRH RACK | LAUREN ENGINEERS & CONSTRUCTORS INC | 4503499823 | Flow Control | Centrifugal Pumps | USD | 58052 | USD | 30337 | 27715 | Supplier Competitions / Negotiation | 2020-04-15 | 2020-12-01 | 2020-12-01 | 2020-05-02 | 2021-01-06 | 2020-09-21 | 2020-05-07 | 2020-12-08 | 2020-09-10 | 2021-02-28 | 2020-12-04 | 86 | 12 | 7
506222 | INTEL RA WaTR Phase 2 | Oakville | Ball Valves | BRAY CONTROLS CANADA LTD. | 4503458789 | Flow Control | Metal Isolation Valves | USD | 12891 | USD | 12100 | 791 | Supplier Competitions / Negotiation | 2020-03-19 | 2020-08-30 | 2020-09-10 | 2020-04-02 | 2020-09-14 | 2020-06-24 | 2020-05-14 | 2020-09-15 | 2020-08-21 | 2020-09-29 | 2020-09-09 | 20 | 12 | 16
506222 | INTEL RA WaTR Phase 2 | Oakville | Butterfly Valves | LAKESIDE PROCESS CONTROLS LTD. | 4503428348 | Flow Control | Metal Isolation Valves | USD | 48252 | USD | 41482 | 6770 | Frame Agreements | 2020-03-20 | 2020-07-01 | 2020-07-01 | 2020-04-03 | 2020-07-01 | 2020-06-05 | 2020-05-08 | 2020-07-09 | 2020-08-21 | 2020-08-16 | 2020-08-18 | -2 | 12 | 8
506222 | INTEL RA WaTR Phase 2 | Oakville | Automated Valves | PROCESS & STEAM SPECIALTIES | 4503456174 | Flow Control | Metal Isolation Valves | USD | 111077 | USD | 100164 | 10913 | Design Optimizations | 2020-09-01 | 2020-08-30 | 2020-09-04 | 2020-09-04 | 2020-09-07 | 2020-10-15 | 2020-09-08 | 2020-09-09 | 2020-11-05 | 2020-11-30 | 2020-11-17 | 13 | 12 | 10
506222 | INTEL RA WaTR Phase 2 | Oakville | HDPE Tanks (PILOT) | ACO CONTAINER SYSTEMS LTD. | 4503562937 | Fabrication | Ele-Control Panels | USD | 30000 | CAD | 12324 | 17676 | Design Optimizations | 2021-03-05 | 2021-03-17 | 2021-03-23 | 2021-03-26 | 2021-03-29 | 2021-04-23 | 2021-04-02 | 2021-04-03 | 2021-06-11 | 2021-05-19 | 2021-05-30 | -11 | 12 | 17
506222 | INTEL RA WaTR Phase 2 | Oakville | FRP Towers (Forced Draft Degasifier/ Clearwell) (PILOT) | Augusta Fiberglass | 4503598101 | Fabrication | Carbon Steel | USD | 30000 | USD | 23716 | 6284 | Frame Agreements | 2021-04-09 | 2021-04-16 | 2021-06-08 | 2021-04-30 | 2021-06-09 | 2021-06-25 | 2021-05-07 | 2021-06-09 | 2021-09-10 | 2021-09-09 | 2021-09-09 | 0 | 12 | 54
506222 | INTEL RA WaTR Phase 2 | Oakville | Close Coupled Pumps (PILOT) | PROSPEC TECHNOLOGIES INC. | 4503562946 | Rotating Equipment | Centrifugal Pumps | USD | 15000 | CAD | 5417 | 9583 | Frame Agreements | 2021-03-12 | 2021-02-05 | 2021-03-07 | 2021-04-09 | 2021-04-01 | 2021-04-09 | 2021-04-16 | 2021-04-05 | 2021-06-11 | 2021-05-14 | 2021-05-28 | -14 | 30 | 59
506222 | INTEL RA WaTR Phase 2 | Oakville | High Pressure Pump (PILOT) | Danfoss LLC | 4503547385 | Rotating Equipment | Centrifugal Pumps | USD | 30000 | USD | 10771 | 19229 | Design Optimizations | 2021-01-29 | 2021-02-05 | 2021-02-23 | 2021-02-26 | 2021-02-25 | 2021-04-05 | 2021-03-05 | 2021-03-09 | 2021-06-11 | 2021-06-01 | 2021-06-06 | -5 | 30 | 32
506222 | INTEL RA WaTR Phase 2 | Oakville | Metallic Tank (MBR Tank and Lid) (PILOT) | INTUITEC | 4503560370 | Fabrication | Metal Isolation Valves | USD | 30000 | USD | 26459 | 3541 | Supplier Competitions / Negotiation | 2021-02-26 | 2021-03-03 | 2021-03-15 | 2021-03-26 | 2021-03-30 | 2021-04-19 | 2021-04-02 | 2021-03-30 | 2021-06-11 | 2021-05-12 | 2021-05-27 | -15 | 12 | 27
506222 | INTEL RA WaTR Phase 2 | Oakville | GLOBE Valve (Lakeside) (PILOT) | LAKESIDE PROCESS CONTROLS LTD. | 4503559707 | Flow Control | Ele-Control Panels | USD | 33233 | USD | 20121 | 13112 | Frame Agreements | 2021-05-01 | 2021-03-13 | 2021-03-29 | 2021-05-01 | 2021-03-28 | 2021-05-01 | 2021-05-01 | 2021-03-28 | 2021-05-01 | 2021-06-20 | 2021-05-26 | 25 | 12 | 15
506222 | INTEL RA WaTR Phase 2 | Oakville | Plastic Ball Valves (PILOT) | GEORG FISCHER LLC | 4503563639 | Flow Control | Plastic Works, Spools | USD | 7031 | USD | 7031 | 0 | Size/ Weight/ Quantity Underestimated | 2021-04-03 | 2021-03-10 | 2021-03-31 | 2021-04-03 | 2021-04-01 | 2021-04-03 | 2021-04-03 | 2021-04-06 | 2021-04-03 | 2021-04-27 | 2021-04-15 | 12 | 12 | 27
506222 | INTEL RA WaTR Phase 2 | Oakville | Instruments (E&H) (PILOT) | ENDRESS & HAUSER | 4503566593 | Electrical & Instrumentation | Centrifugal Pumps | USD | 72000 | USD | 25621 | 46379 | Design Optimizations | 2021-02-15 | 2021-02-17 | 2021-03-11 | 2021-04-09 | 2021-04-06 | 2021-04-14 | 2021-04-16 | 2021-04-11 | 2021-06-11 | 2021-05-11 | 2021-05-26 | -15 | 18 | 53
506222 | INTEL RA WaTR Phase 2 | Oakville | Instruments (Ashcroft) (PILOT) | CONVAL EQUIPMENT LIMITED | 4503569460 | Electrical & Instrumentation | Centrifugal Pumps | USD | 10000 | USD | 8097 | 1903 | Design Optimizations | 2021-02-15 | 2021-02-17 | 2021-02-24 | 2021-04-23 | 2021-04-09 | 2021-04-14 | 2021-04-30 | 2021-04-15 | 2021-06-11 | 2021-05-20 | 2021-05-31 | -11 | 18 | 57
506222 | INTEL RA WaTR Phase 2 | Oakville | Instruments (HACH) (PILOT) | Hach Company | 4503565816 | Electrical & Instrumentation | Centrifugal Pumps | USD | 45000 | CAD | 50619 | -5619 | Size/ Weight/ Quantity Underestimated | 2021-02-24 | 2021-02-17 | 2021-03-23 | 2021-05-07 | 2021-04-09 | 2021-04-15 | 2021-05-14 | 2021-04-09 | 2021-06-11 | 2021-05-21 | 2021-05-31 | -10 | 18 | 51
506222 | INTEL RA WaTR Phase 2 | Oakville | Metallic Spools (PILOT) | PANDA PIPING LTD | 4503562546 | Fabrication | Metal Isolation Valves | USD | 50000 | CAD | 6712 | 43288 | Design Optimizations | 2021-02-12 | 2021-03-24 | 2021-03-30 | 2021-03-12 | 2021-04-01 | 2021-04-12 | 2021-03-19 | 2021-04-01 | 2021-06-11 | 2021-05-13 | 2021-05-27 | -14 | 12 | 8
506222 | INTEL RA WaTR Phase 2 | Oakville | Frames (PILOT) | 3D MECHANICAL | 4503562121 | Fabrication | Metal Isolation Valves | USD | 40000 | CAD | 50694 | -10694 | Proposed Supplier Incapable Of Executing | 2021-02-12 | 2021-03-23 | 2021-03-30 | 2021-03-12 | 2021-03-28 | 2021-04-12 | 2021-03-19 | 2021-03-28 | 2021-06-11 | 2021-05-09 | 2021-05-25 | -16 | 12 | 5
506222 | INTEL RA WaTR Phase 2 | Oakville | VFDs and Junction Boxed (PILOT) | Integrated Systems Group | 4503562106 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 55000 | USD | 73198 | -18198 | Not included in Proposal / RFQ | 2021-02-26 | 2021-02-12 | 2021-03-30 | 2021-03-26 | 2021-03-31 | 2021-04-12 | 2021-04-02 | 2021-04-01 | 2021-06-11 | 2021-05-28 | 2021-06-04 | -7 | 18 | 48
506222 | INTEL RA WaTR Phase 2 | Oakville | CIP Heater (PILOT) | Chromalox Inc. | 4503573225 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | USD | 173000 | CAD | 16456 | 156544 | Frame Agreements | 2021-03-12 | 2021-04-02 | 2021-04-16 | 2021-04-09 | 2021-04-21 | 2021-04-26 | 2021-04-16 | 2021-04-21 | 2021-06-11 | 2021-06-02 | 2021-06-06 | -4 | 18 | 19
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | CITY WATER PUMPS | PFC EQUIPMENT | 4503352025 | Rotating Equipment | Carbon Steel | USD | 27630 | USD | 21683 | 5947 | Design Optimizations | 2020-01-17 | 2020-03-06 | 2019-11-21 | 2020-01-30 | 2020-01-29 | 2020-03-06 | 2020-01-30 | 2020-04-19 | 2020-03-06 | 2020-06-21 | 2020-04-28 | 54 | 30 | 44
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | CITY WATER TANK | Augusta Fiberglass | 4503352332 | Fabrication | Metal Isolation Valves | USD | 42826 | USD | 32004 | 10822 | Supplier Competitions / Negotiation | 2020-01-17 | 2020-03-18 | 2020-01-17 | 2020-01-30 | 2020-01-26 | 2020-03-18 | 2020-01-30 | 2020-01-26 | 2020-05-18 | 2020-05-17 | 2020-05-17 | 0 | 12 | -52
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | TEKLEEN STRAINER | TEKLEEN | 4503356370 | Flow Control | Carbon Steel | USD | 59400 | USD | 53550 | 5850 | Frame Agreements | 2020-01-23 | 2020-03-12 | 2020-01-23 | 2020-01-23 | 2020-02-06 | 2020-03-12 | 2020-01-23 | 2020-02-06 | 2020-02-28 | 2020-04-30 | 2020-03-30 | 31 | 12 | -35
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | BEV AC TOWERS | Arrow Tanks | 4503341120 | Fabrication | Carbon Steel | USD | 216024 | USD | 179973 | 36051 | Frame Agreements | 2020-01-09 | 2020-03-15 | 2020-01-09 | 2020-01-09 | 2020-01-09 | 2020-03-15 | 2020-01-09 | 2020-01-09 | 2020-05-20 | 2020-04-23 | 2020-05-06 | -13 | 12 | -66
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | BEV AC TOWERS ELECTRICAL PANELS | ICSE | 4503369941 | Electrical & Instrumentation | Ele-Electrical Others | USD | 41064 | USD | 41066 | -2 | Market Impact | 2020-03-24 | 2020-03-24 | 2020-03-04 | 2020-03-24 | 2020-03-03 | 2020-03-24 | 2020-03-24 | 2020-03-03 | 2020-03-24 | 2020-04-14 | 2020-04-03 | 11 | 18 | -21
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | DISTRIBUTION PUMPS | ALFA LAVAL | 4503352023 | Rotating Equipment | Carbon Steel | USD | 57833 | USD | 61025 | -3192 | Single Sourced | 2020-02-11 | 2020-01-28 | 2019-11-26 | 2020-02-11 | 2020-01-29 | 2020-01-28 | 2020-02-11 | 2020-01-29 | 2020-03-17 | 2020-04-01 | 2020-03-24 | 8 | 30 | 1
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | BEV RO | R&R Metalworks | 4533373858 | Fabrication | Ele-Control Panels | USD | 23900 | USD | 23900 | 0 | Market Impact | 2020-03-28 | 2020-03-28 | 2020-03-05 | 2020-03-28 | 2020-03-04 | 2020-03-28 | 2020-03-28 | 2020-03-10 | 2020-03-28 | 2020-04-21 | 2020-04-09 | 12 | 12 | -18
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | SPOOLS | A&B Process | 4503000406 | Fabrication | Carbon Steel | USD | 116743 | USD | 133299 | -16556 | Not included in Proposal / RFQ | 2020-03-25 | 2020-03-25 | 2020-03-05 | 2020-03-25 | 2020-03-04 | 2020-03-25 | 2020-03-25 | 2020-03-04 | 2020-03-25 | 2020-04-15 | 2020-04-04 | 11 | 12 | -21
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | BEV CIP TANKS | Preferred Stainless Holdings | 4503348463 | Fabrication | Carbon Steel | USD | 29960 | USD | 33468 | -3508 | Single Sourced | 2020-01-17 | 2020-03-02 | 2020-01-17 | 2020-01-23 | 2020-01-23 | 2020-03-02 | 2020-01-23 | 2020-01-23 | 2020-04-06 | 2020-04-16 | 2020-04-11 | 5 | 12 | -39
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | DISTRIBUTION & RECIRCULATION UV | AQUIONICS, INC. | 4503357106 | Fabrication | Carbon Steel | USD | 42443 | USD | 82696 | -40253 | Not included in Proposal / RFQ | 2020-01-17 | 2020-03-19 | 2020-02-06 | 2020-01-30 | 2020-02-10 | 2020-03-19 | 2020-01-30 | 2020-02-10 | 2020-05-20 | 2020-03-23 | 2020-04-21 | -29 | 12 | -38
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | CARTRIDGE FILTER HOUSINGS | PENTAIR FILTRATION SOLUTIONS, LLC | 4503374446 | Flow Control | RO Membrane Housings | USD | 13000 | USD | 42560 | -29560 | Proposed Supplier Incapable Of Executing | 2020-03-03 | 2020-04-18 | 2020-03-12 | 2020-03-03 | 2020-03-11 | 2020-04-18 | 2020-03-03 | 2020-03-11 | 2020-05-20 | 2020-06-03 | 2020-05-27 | 7 | 12 | -38
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | PRE RO UV | ANDERSON & DAHLGREEN | 4533377732 | Fabrication | Metal Isolation Valves | USD | 26843 | USD | 12090 | 14753 | Frame Agreements | 2020-02-06 | 2020-03-17 | 2020-03-18 | 2020-02-06 | 2020-03-15 | 2020-03-17 | 2020-02-10 | 2020-03-15 | 2020-03-17 | 2020-04-26 | 2020-04-06 | 20 | 12 | -2
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | CONSERVATION VALVES | Duncan Co. | 4503368374 | Flow Control | Carbon Steel | USD | 13300 | USD | 9878 | 3422 | Supplier Competitions / Negotiation | 2020-03-15 | 2020-04-09 | 2020-05-06 | 2020-03-15 | 2020-02-24 | 2020-04-09 | 2020-03-15 | 2020-03-01 | 2020-05-20 | 2020-05-24 | 2020-05-22 | 2 | 12 | -39
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | MCE | WERNER ELECTRIC | 4503362228 | Electrical & Instrumentation | Ele-Control Panels | USD | 130000 | USD | 111235 | 18765 | Frame Agreements | 2020-03-01 | 2020-03-23 | 2020-02-05 | 2020-03-08 | 2020-02-18 | 2020-03-23 | 2020-03-08 | 2020-02-18 | 2020-05-10 | 2020-04-14 | 2020-04-27 | -13 | 18 | -34
506226 | Mark Anthony Brewing Hillside NJ | Minnetonka | RO PERMEATE TANK | Preferred Stainless Holdings | 4503340141 | Fabrication | Centrifugal Pumps | USD | 77900 | USD | 61197 | 16703 | Design Optimizations | 2019-12-17 | 2020-02-25 | 2019-12-17 | 2020-01-06 | 2020-01-08 | 2020-02-25 | 2020-01-06 | 2020-01-08 | 2020-05-05 | 2020-05-06 | 2020-05-05 | 1 | 12 | -48
506254 | LAURENS COUNTY SC DWAM | Richmond | Core,Vac Tank, BW&Inlet Siphon, Annular Flume, Waste Funnel, INlet Baffle, Weir Plates | POSEIDON, INC | 4503452619 | Fabrication | Ele-Control Panels | USD | 105435 | USD | 88271 | 17164 | Frame Agreements | 2020-05-07 | 2020-08-05 | 2020-08-26 | 2020-05-21 | 2020-08-19 | 2020-08-17 | 2020-06-04 | 2020-08-24 | 2020-07-30 | 2020-11-30 | 2020-12-17 | -17 | 12 | 19
506254 | LAURENS COUNTY SC DWAM | Richmond | Upper Vacuum Tank & Piping | BE PETERSON | 4503450277 | Fabrication | Centrifugal Pumps | USD | 7617 | USD | 19350 | -11733 | Not included in Proposal / RFQ | 2020-11-01 | 2020-11-01 | 2020-08-25 | 2020-11-01 | 2020-08-13 | 2020-11-01 | 2020-11-01 | 2020-11-11 | 2020-11-01 | 2021-01-20 | 2020-11-11 | 70 | 12 | 10
506254 | LAURENS COUNTY SC DWAM | Richmond | Vacuum Pumps - GL | GARDNER DENVER NASH LLC | 4503446809 | Rotating Equipment | Centrifugal Pumps | USD | 15620 | USD | 13573 | 2047 | Frame Agreements | 2020-04-30 | 2020-06-24 | 2020-02-03 | 2020-05-14 | 2020-07-27 | 2020-08-31 | 2020-05-28 | 2020-08-17 | 2020-07-30 | 2020-08-31 | 2020-11-14 | -75 | 30 | 54
506254 | LAURENS COUNTY SC DWAM | Richmond | Compressor - Super P | QUINCY COMPRESSORS | 4503446732 | Rotating Equipment | Vapor Compressor | USD | 6533 | USD | 6953 | -420 | Estimate Without Market Reference(No Quote) | 2020-04-23 | 2020-07-04 | 2020-03-10 | 2020-05-07 | 2020-08-05 | 2020-08-31 | 2020-05-21 | 2020-08-19 | 2020-07-30 | 2020-10-28 | 2020-10-16 | 12 | 30 | 46
506254 | LAURENS COUNTY SC DWAM | Richmond | Air Scour Blower | BEST BLOWER | 4503446722 | Rotating Equipment | Carbon Steel | USD | 27116 | USD | 27018 | 98 | Design Optimizations | 2020-04-16 | 2020-07-11 | 2020-02-13 | 2020-04-30 | 2020-08-11 | 2020-09-01 | 2020-05-14 | 2020-08-18 | 2020-07-30 | 2020-12-08 | 2020-10-12 | 57 | 30 | 38
506254 | LAURENS COUNTY SC DWAM | Richmond | Electrical Panels - GL | ICSE | 4503461557 | Electrical & Instrumentation | Ele-Electrical Others | USD | 72100 | USD | 61463 | 10637 | Design Optimizations | 2020-04-16 | 2020-08-16 | 2020-08-13 | 2020-04-30 | 2020-09-14 | 2020-09-20 | 2020-05-14 | 2020-11-04 | 2020-07-30 | 2020-12-16 | 2020-11-02 | 44 | 18 | 80
506254 | LAURENS COUNTY SC DWAM | Richmond | Washtroughs | MFG CONSTRUCTION | 4503458696 | Fabrication | Centrifugal Pumps | USD | 20020 | USD | 15245 | 4775 | Supplier Competitions / Negotiation | 2020-05-28 | 2020-08-05 | 2020-06-27 | 2020-06-11 | 2020-09-10 | 2020-08-24 | 2020-06-18 | 2020-09-14 | 2020-07-30 | 2020-11-02 | 2020-11-20 | -18 | 12 | 40
506254 | LAURENS COUNTY SC DWAM | Richmond | Embedded Items | JOB SHOP FABRICATORS | 4503406109 | Fabrication | Metal Isolation Valves | USD | 10242 | USD | 9624 | 618 | Frame Agreements | 2020-05-28 | 2020-06-23 | 2020-05-21 | 2020-06-11 | 2020-05-18 | 2020-06-23 | 2020-06-18 | 2020-05-17 | 2020-07-30 | 2020-05-31 | 2020-05-31 | 0 | 12 | -37
506254 | LAURENS COUNTY SC DWAM | Richmond | Platforms,walkways | RICHLAND LLC | 4503450519 | Fabrication | Metal Isolation Valves | USD | 30018 | USD | 31050 | -1032 | Size/ Weight/ Quantity Underestimated | 2020-04-23 | 2020-07-31 | 2020-08-27 | 2020-05-07 | 2020-08-26 | 2020-08-17 | 2020-05-21 | 2020-11-17 | 2020-07-30 | 2020-12-22 | 2020-11-20 | 32 | 12 | 109
506254 | LAURENS COUNTY SC DWAM | Richmond | Manual Valves | ROBERT E. MASON CO. | 4503441731 | Flow Control | Metal Isolation Valves | USD | 12311 | USD | 11224 | 1087 | Design Optimizations | 2020-04-23 | 2020-07-01 | 2020-05-11 | 2020-05-07 | 2020-07-17 | 2020-07-18 | 2020-05-21 | 2020-08-10 | 2020-07-30 | 2020-08-31 | 2020-12-01 | -92 | 12 | 40
506254 | LAURENS COUNTY SC DWAM | Richmond | Valves - Super P | HENRY PRATT | 4503446728 | Flow Control | Metal Isolation Valves | USD | 129550 | USD | 148430 | -18880 | Estimate Without Market Reference(No Quote) | 2020-04-23 | 2020-07-01 | 2020-03-13 | 2020-05-07 | 2020-08-07 | 2020-07-31 | 2020-05-21 | 2020-08-19 | 2020-07-30 | 2020-09-16 | 2020-12-01 | -76 | 12 | 49
506259 | BASF Freeport Watewater Treatment System | Guelph | Blowers | AERZEN CANADA INC | 4503708427 | Rotating Equipment | Blowers & Fans | USD | 74380 | CAD | 73195 | 1185 | Supplier Competitions / Negotiation | 2021-12-03 | 2021-11-16 | 2021-12-09 | 2021-12-31 | 2021-12-16 | 2022-02-09 | 2022-01-14 | 2021-12-23 | 2022-05-06 | 2022-04-15 | 2022-04-25 | -10 | 36 | 37
506259 | BASF Freeport Watewater Treatment System | Guelph | Centrifugal Pumps | FLOWSERVE INC. | 4503678427 | Rotating Equipment | Centrifugal Pumps | USD | 97828 | USD | 89347 | 8481 | Supplier Competitions / Negotiation | 2021-11-05 | 2021-09-23 | 2021-10-19 | 2021-11-19 | 2021-10-30 | 2021-12-20 | 2021-12-10 | 2021-10-30 | 2022-03-18 | 2022-03-19 | 2022-03-18 | 1 | 36 | 37
506259 | BASF Freeport Watewater Treatment System | Guelph | Chemical Dosing Pumps | JOHN BROOKS COMPANY LTD. | 4503701276 | Rotating Equipment | Dosing Pump | USD | 165484 | CAD | 140126 | 25358 | Supplier Competitions / Negotiation | 2021-10-29 | 2021-11-05 | 2021-12-03 | 2021-11-12 | 2021-12-02 | 2022-02-10 | 2021-11-19 | 2021-12-09 | 2022-05-06 | 2022-05-25 | 2022-05-15 | 10 | 24 | 34
506259 | BASF Freeport Watewater Treatment System | Guelph | Control Panels/Junction Box | ENGINEERING ELECTRIC CONTROLS | 4503696418 | Electrical & Instrumentation | Ele-Control Panels | USD | 58256 | CAD | 51158 | 7098 | Supplier Competitions / Negotiation | 2021-12-24 | 2021-11-11 | 2021-12-01 | 2022-01-07 | 2021-11-10 | 2022-01-13 | 2022-01-21 | 2021-11-30 | 2022-03-18 | 2022-01-25 | 2022-02-20 | -26 | 12 | 19
506259 | BASF Freeport Watewater Treatment System | Guelph | AB Components | WESTBURNE INDUSTRIAL ONTARIO | 4503685173 | Electrical & Instrumentation | Ele-Control Panels | USD | 51639 | CAD | 42241 | 9398 | Supplier Competitions / Negotiation | 2021-10-15 | 2021-10-15 | 2021-11-11 | 2021-12-09 | 2021-11-09 | 2021-12-09 | 2021-12-09 | 2021-11-10 | 2021-12-09 | 2022-02-02 | 2022-01-05 | 28 | 18 | 26
506259 | BASF Freeport Watewater Treatment System | Minnetonka | Tanks - FRP | DIAMOND FIBERGLASS | 4503700672 | Fabrication | Non-Metal Equipment | USD | 46820 | USD | 46820 | 0 | Size/ Weight/ Quantity Underestimated | 2021-11-19 | 2021-10-29 | 2021-11-19 | 2021-12-03 | 2021-11-16 | 2022-02-12 | 2021-12-24 | 2021-12-08 | 2022-05-06 | 2022-05-30 | 2022-05-18 | 12 | 12 | 40
506259 | BASF Freeport Watewater Treatment System | Guelph | Tanks - SS | POSEIDON, INC | 4503689436 | Fabrication | Stainless Steel | USD | 314269 | USD | 369075 | -54806 | Single Sourced | 2021-12-31 | 2021-10-28 | 2021-11-15 | 2022-01-14 | 2021-11-17 | 2022-01-31 | 2022-01-28 | 2021-11-20 | 2022-05-06 | 2021-11-20 | 2022-02-11 | -83 | 30 | 23
506259 | BASF Freeport Watewater Treatment System | Guelph | FRP Covers | Fiberglass Fabricators, INc | 4503717082 | Fabrication | Stainless Steel | USD | 35200 | USD | 35200 | 0 | Supplier Competitions / Negotiation | 2021-11-10 | 2021-11-10 | 2022-01-04 | 2022-02-01 | 2022-01-07 | 2022-02-01 | 2022-02-01 | 2022-01-12 | 2022-02-01 | 2022-04-25 | 2022-03-14 | 42 | 12 | 63
506259 | BASF Freeport Watewater Treatment System | Guelph | Skid Frame - Metal, including painting | 3D MECHANICAL | 4503696406 | Fabrication | Carbon Steel | USD | 68106 | CAD | 72077 | -3971 | Design Optimizations | 2021-11-05 | 2021-10-28 | 2021-11-23 | 2021-11-19 | 2021-11-17 | 2022-01-06 | 2021-12-10 | 2021-11-18 | 2022-03-18 | 2021-11-18 | 2022-01-17 | -60 | 12 | 21
506259 | BASF Freeport Watewater Treatment System | Guelph | Pipe Spooling - SS | PANDA PIPING LTD | 4503692818 | Fabrication | Stainless Steel | USD | 103376 | CAD | 103376 | 0 | Supplier Competitions / Negotiation | 2021-12-24 | 2021-10-29 | 2021-11-23 | 2022-01-07 | 2021-11-16 | 2022-01-07 | 2022-01-21 | 2021-11-21 | 2022-03-18 | 2021-11-21 | 2022-01-18 | -58 | 12 | 23
506259 | BASF Freeport Watewater Treatment System | Guelph | RAS Pumps | BOERGER LLC | 4503679209 | Rotating Equipment | Others | USD | 124681 | USD | 92514 | 32167 | Supplier Competitions / Negotiation | 2021-11-12 | 2021-10-04 | 2021-10-28 | 2021-12-10 | 2021-11-01 | 2021-12-25 | 2021-12-24 | 2021-11-02 | 2022-03-18 | 2022-03-18 | 2022-03-18 | 0 | 36 | 29
506259 | BASF Freeport Watewater Treatment System | Minnetonka | Screens/Conveyor & Compactor | JWC Environmental Canada | 4503695600 | Fabrication | Stainless Steel | USD | 431306 | CAD | 367307 | 63999 | Supplier Competitions / Negotiation | 2021-12-21 | 2021-11-08 | 2021-11-23 | 2021-12-31 | 2021-12-22 | 2022-02-05 | 2022-01-14 | 2021-11-30 | 2022-05-06 | 2022-03-08 | 2022-04-06 | -29 | 36 | 22
506259 | BASF Freeport Watewater Treatment System | Guelph | Valves - Ball | WOLSELEY INDUSTRIAL CANADA INC | 4503708434 | Flow Control | Metal Control Valves | USD | 34349 | CAD | 5333 | 29016 | Supplier Competitions / Negotiation | 2021-11-19 | 2021-11-23 | 2021-12-14 | 2021-12-10 | 2021-12-19 | 2022-01-17 | 2021-12-24 | 2021-12-22 | 2022-03-18 | 2022-03-02 | 2022-03-10 | -8 | 12 | 29
506259 | BASF Freeport Watewater Treatment System | Guelph | Valves - Ball (SW) | WOLSELEY INDUSTRIAL CANADA INC | 4503706877 | Flow Control | Metal Control Valves | USD | 10319 | CAD | 10319 | 0 | Not included in Proposal / RFQ | 2022-12-20 | 2022-12-20 | 2021-12-14 | 2021-12-10 | 2021-12-19 | 2022-06-15 | 2022-06-15 | 2021-12-19 | 2022-06-15 | 2022-02-14 | 2022-04-15 | -60 | 12 | -366
506259 | BASF Freeport Watewater Treatment System | Guelph | Valves - Butterfly | LAKESIDE PROCESS CONTROLS LTD. | 4503692844 | Flow Control | Metal Control Valves | USD | 177254 | USD | 161766 | 15488 | Supplier Competitions / Negotiation | 2021-11-19 | 2021-10-14 | 2021-11-25 | 2021-12-10 | 2021-11-04 | 2021-12-30 | 2021-12-24 | 2021-11-26 | 2022-03-18 | 2022-03-18 | 2022-03-18 | 0 | 24 | 43
506259 | BASF Freeport Watewater Treatment System | Guelph | Vavles - Swing Check | WOLSELEY INDUSTRIAL CANADA INC | 4503700402 | Flow Control | Metal Control Valves | USD | 13072 | CAD | 13072 | 0 | Market Impact | 2021-11-19 | 2021-12-01 | 2021-12-01 | 2021-12-10 | 2021-12-08 | 2022-01-17 | 2021-12-24 | 2021-12-09 | 2022-03-18 | 2022-03-18 | 2022-03-18 | 0 | 12 | 8
506259 | BASF Freeport Watewater Treatment System | Guelph | Valves - Pressure Relief | Great Lakes Industrial Controls | 4503700452 | Flow Control | Metal Safety(relief) Valves | USD | 7876 | CAD | 7477 | 399 | Supplier Competitions / Negotiation | 2021-11-19 | 2021-12-01 | 2021-11-17 | 2021-12-10 | 2021-12-08 | 2022-01-16 | 2021-12-24 | 2021-12-09 | 2022-03-18 | 2022-03-18 | 2022-03-18 | 0 | 12 | 8
506259 | BASF Freeport Watewater Treatment System | Guelph | Instrumentation - Transmitters | LAKESIDE PROCESS CONTROLS LTD. | 4503699691 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 71655 | USD | 57249 | 14406 | Supplier Competitions / Negotiation | 2022-01-07 | 2025-10-29 | 2021-11-25 | 2022-01-21 | 2021-11-08 | 2023-11-03 | 2022-02-04 | 2021-12-08 | 2022-03-18 | 2022-03-18 | 2022-03-18 | 0 | 24 | -1421
506259 | BASF Freeport Watewater Treatment System | Guelph | Instrumentation - Radar Level ransmitters | VEGA AMERICAS INC | 4503697563 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 5530 | CAD | 5530 | 0 | Size/ Weight/ Quantity Underestimated | 2021-10-29 | 2021-10-29 | 2021-11-04 | 2022-01-07 | 2021-11-04 | 2022-01-07 | 2022-01-07 | 2021-12-06 | 2022-01-07 | 2022-03-18 | 2022-02-11 | 35 | 24 | 38
506259 | BASF Freeport Watewater Treatment System | Guelph | Instrumentation - Turbidity | Hach Company | 4503699433 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 13716 | CAD | 13716 | 0 | Estimate Without Market Reference(No Quote) | 2021-12-24 | 2021-10-27 | 2021-11-30 | 2022-01-07 | 2021-12-01 | 2022-01-06 | 2022-01-21 | 2021-12-08 | 2022-03-18 | 2022-02-23 | 2022-03-06 | -11 | 12 | 42
506259 | BASF Freeport Watewater Treatment System | Guelph | Instrumentation - pH Meter | ENDRESS & HAUSER | 4503697148 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 7161 | USD | 7161 | 0 | Market Impact | 2021-10-27 | 2021-10-27 | 2021-11-25 | 2021-12-02 | 2021-11-23 | 2021-12-02 | 2021-12-02 | 2021-12-03 | 2021-12-02 | 2022-01-07 | 2021-12-20 | 18 | 36 | 37
506265 | Imperial WWTP MBR Equipment Procurement | Oakville | Rotary Lobe Pump (Boerger) | BOERGER, INC | 4503412720 | Rotating Equipment | Centrifugal Pumps | USD | 61500 | USD | 61824 | -324 | Estimate Without Market Reference(No Quote) | 2020-04-24 | 2020-07-12 | 2020-07-12 | 2020-05-15 | 2020-07-12 | 2020-07-12 | 2020-05-22 | 2020-06-05 | 2020-08-07 | 2020-09-30 | 2020-09-03 | 27 | 30 | -37
506265 | Imperial WWTP MBR Equipment Procurement | Oakville | Butterfly Valves (Crane Supply) | CRANE SUPPLY | 4503415141 | Flow Control | Carbon Steel | USD | 11696 | CAD | 11696 | 0 | Proposed Supplier Incapable Of Executing | 2020-05-29 | 2020-07-03 | 2020-07-03 | 2020-06-19 | 2020-07-03 | 2020-07-03 | 2020-06-26 | 2020-06-11 | 2020-08-07 | 2020-07-09 | 2020-07-23 | -14 | 12 | -22
506265 | Imperial WWTP MBR Equipment Procurement | Oakville | Chemical system (Prominent) | PROMINENT FLUID CONTROLS LTD. | 4503422765 | Rotating Equipment | Centrifugal Pumps | USD | 13222 | CAD | 17645 | -4423 | Proposed Supplier Incapable Of Executing | 2020-04-24 | 2020-06-17 | 2020-06-17 | 2020-05-15 | 2020-06-17 | 2020-06-17 | 2020-05-22 | 2020-06-29 | 2020-08-07 | 2020-08-10 | 2020-08-08 | 2 | 30 | 12
506265 | Imperial WWTP MBR Equipment Procurement | Oakville | Frames | 3D MECHANICAL | 4503413959 | Fabrication | Metal Isolation Valves | USD | 69997 | CAD | 51428 | 18569 | Frame Agreements | 2020-05-08 | 2020-06-25 | 2020-06-25 | 2020-05-29 | 2020-06-25 | 2020-06-25 | 2020-06-05 | 2020-06-09 | 2020-08-07 | 2020-08-12 | 2020-08-09 | 3 | 12 | -16
506266 | Nutrien Demo Plant | Oakville | Control Panel and Enclosures | KELTOUR CONTROLS INC. | 4503594792 | Electrical & Instrumentation | Ele-Control Panels | USD | 89804 | USD | 51731 | 38073 | Supplier Competitions / Negotiation | 2020-12-11 | 2021-04-30 | 2021-05-20 | 2020-12-25 | 2021-05-25 | 2021-03-24 | 2021-01-08 | 2021-05-24 | 2021-03-19 | 2021-07-05 | 2021-05-12 | 54 | 18 | 24
506266 | Nutrien Demo Plant | Oakville | VFD'S and Starters | KELTOUR CONTROLS INC. | 4503581646 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 22269 | USD | 43845 | -21576 | Specs / Requirements Misinterpreted in Proposal | 2021-01-15 | 2021-03-29 | 2021-04-29 | 2021-01-29 | 2021-05-06 | 2021-04-03 | 2021-02-12 | 2021-05-09 | 2021-04-23 | 2021-06-20 | 2021-05-22 | 29 | 18 | 41
506266 | Nutrien Demo Plant | Oakville | Painted Frames | PLASFAB LIMITED | 4503566074 | Fabrication | Carbon Steel | USD | 173907 | USD | 70992 | 102915 | Supplier Competitions / Negotiation | 2020-12-18 | 2021-03-18 | 2021-03-31 | 2021-01-04 | 2021-04-05 | 2021-03-18 | 2021-01-18 | 2021-04-07 | 2021-04-12 | 2021-06-16 | 2021-05-14 | 33 | 12 | 20
506266 | Nutrien Demo Plant | Oakville | Spools (DSS / 2205 Nutrien Spec) | PANDA PIPING LTD | 4503570848 | Fabrication | Alloy Steel | USD | 180077 | USD | 103425 | 76652 | Supplier Competitions / Negotiation | 2020-12-18 | 2021-03-19 | 2021-04-01 | 2021-01-04 | 2021-03-27 | 2021-02-20 | 2021-01-18 | 2021-04-17 | 2021-04-26 | 2021-04-17 | 2021-04-21 | -4 | 12 | 29
506266 | Nutrien Demo Plant | Oakville | Heater and Panel | Chromalox Inc. | 4503583797 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | USD | 10275 | USD | 20581 | -10306 | Market Impact | 2020-12-18 | 2020-11-22 | 2021-05-06 | 2021-01-11 | 2021-05-06 | 2021-03-08 | 2021-01-25 | 2021-05-11 | 2021-03-29 | 2021-06-22 | 2021-05-10 | 43 | 18 | 170
506266 | Nutrien Demo Plant | Oakville | Instruments - Krohne - Flow, Level, Pressure | KROHNE | 4503563772 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 19278 | USD | 17392 | 1886 | Design Optimizations | 2020-11-20 | 2020-12-09 | 2021-04-05 | 2020-12-04 | 2021-04-05 | 2021-02-20 | 2020-12-18 | 2021-04-05 | 2021-04-12 | 2021-05-24 | 2021-05-03 | 21 | 18 | 117
506266 | Nutrien Demo Plant | Oakville | Instruments - Pressure Gauges+ Diaphragm Seals | WIKA INSTRUMENTS LTD. | 4503558933 | Electrical & Instrumentation | Inst-Gauges | USD | 22644 | USD | 6163 | 16481 | Design Optimizations | 2020-11-20 | 2020-12-09 | 2020-12-17 | 2020-12-04 | 2021-03-18 | 2021-02-11 | 2020-12-18 | 2021-03-25 | 2021-03-29 | 2021-05-06 | 2021-04-17 | 19 | 18 | 106
506266 | Nutrien Demo Plant | Oakville | Centrifugal Pumps - Sulzer | SULZER PUMPS (CANADA) INC. | 4503510476 | Rotating Equipment | Centrifugal Pumps | USD | 138467 | USD | 102089 | 36378 | Frame Agreements | 2020-11-13 | 2020-11-22 | 2021-01-04 | 2020-11-27 | 2021-01-02 | 2021-03-16 | 2020-12-11 | 2021-01-02 | 2021-06-30 | 2021-07-17 | 2021-07-08 | 9 | 30 | 41
506266 | Nutrien Demo Plant | Oakville | Bray Auto Valve | BRAY CONTROLS CANADA LTD. | 4503523944 | Flow Control | Metal Control Valves | USD | 111716 | USD | 27279 | 84437 | Supplier Competitions / Negotiation | 2020-11-20 | 2020-12-07 | 2021-01-15 | 2020-12-04 | 2021-01-23 | 2021-03-02 | 2020-12-18 | 2021-01-24 | 2021-05-21 | 2021-06-13 | 2021-06-01 | 12 | 12 | 48
506266 | Nutrien Demo Plant | Oakville | Bray Manual | BRAY CONTROLS CANADA LTD. | 4503542946 | Flow Control | Metal Isolation Valves | USD | 38441 | USD | 38118 | 323 | Frame Agreements | 2020-11-20 | 2021-02-11 | 2021-02-22 | 2020-11-27 | 2021-02-20 | 2021-04-08 | 2020-12-11 | 2021-02-27 | 2021-08-25 | 2021-07-31 | 2021-08-12 | -12 | 12 | 16
506266 | Nutrien Demo Plant | Oakville | Globe Control | LAKESIDE PROCESS CONTROLS LTD. | 4503532590 | Flow Control | Metal Control Valves | USD | 21587 | USD | 26387 | -4800 | Market Impact | 2020-11-20 | 2020-12-07 | 2021-01-20 | 2020-12-04 | 2021-01-25 | 2021-04-08 | 2020-12-18 | 2021-02-08 | 2021-08-25 | 2021-04-26 | 2021-06-25 | -60 | 12 | 63
506266 | Nutrien Demo Plant | Oakville | HFZ Vessels | FIL-TREK CORPORATION | 4503524445 | Fabrication | Metal Isolation Valves | USD | 30906 | USD | 13500 | 17406 | Supplier Competitions / Negotiation | 2020-12-18 | 2020-11-22 | 2020-12-11 | 2021-01-12 | 2021-01-14 | 2021-02-04 | 2021-01-26 | 2021-01-26 | 2021-04-20 | 2021-03-16 | 2021-04-02 | -17 | 12 | 65
506266 | Nutrien Demo Plant | Oakville | LP Flowserve Pumps | Flowserve Canada Corp. | 4503537446 | Rotating Equipment | Centrifugal Pumps | USD | 41989 | USD | 32978 | 9011 | Design Optimizations | 2020-11-20 | 2020-11-22 | 2021-02-19 | 2020-12-23 | 2021-02-18 | 2021-03-01 | 2021-01-14 | 2021-02-18 | 2021-05-28 | 2021-06-10 | 2021-06-03 | 7 | 30 | 88
506266 | Nutrien Demo Plant | Oakville | Victaulic Coupling | WOLSELEY INDUSTRIAL CANADA INC | 4503597545 | Flow Control | Metal Isolation Valves | USD | 20000 | USD | 10768 | 9232 | Frame Agreements | 2021-03-04 | 2021-05-13 | 2021-06-08 | 2021-03-25 | 2021-06-07 | 2021-05-19 | 2021-04-15 | 2021-06-07 | 2021-06-15 | 2021-08-04 | 2021-07-10 | 25 | 12 | 25
506274 | Niagara Vegas | Minnetonka | AC Tower | Arrow Tanks | 4503377032 | Fabrication | Centrifugal Pumps | USD | 142900 | USD | 142900 | 0 | Supplier Competitions / Negotiation | 2020-03-12 | 2020-04-14 | 2020-01-22 | 2020-03-17 | 2020-03-17 | 2020-04-14 | 2020-03-17 | 2020-03-17 | 2020-07-01 | 2020-07-07 | 2020-07-04 | 3 | 12 | -28
506274 | Niagara Vegas | Minnetonka | CIP SKID | Preferred Stainless Holdings | 4503381335 | Fabrication | Skid Assembly Outsourced | USD | 19841 | USD | 19841 | 0 | Proposed Supplier Incapable Of Executing | 2020-03-12 | 2020-05-11 | 2020-05-01 | 2020-03-25 | 2020-03-25 | 2020-05-11 | 2020-03-25 | 2020-05-25 | 2020-07-10 | 2020-07-10 | 2020-07-10 | 0 | 12 | 14
506274 | Niagara Vegas | Minnetonka | TEKLEEN SKID | TEKLEEN | 4503376256 | Fabrication | Skid Assembly Outsourced | USD | 33207 | USD | 48450 | -15243 | Not included in Proposal / RFQ | 2020-03-16 | 2020-03-15 | 2020-03-16 | 2020-03-16 | 2020-03-16 | 2020-05-03 | 2020-03-16 | 2020-03-16 | 2020-06-16 | 2020-06-22 | 2020-06-19 | 3 | 12 | 1
506290 | Buford Water Works | Oakville | Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503707969 | Electrical & Instrumentation | Ele-Control Panels | USD | 93922 | CAD | 77767 | 16155 | Frame Agreements | 2021-10-04 | 2021-11-29 | 2021-11-29 | 2021-10-11 | 2021-12-20 | 2021-09-07 | 2021-10-21 | 2021-12-21 | 2021-03-30 | 2022-02-15 | 2021-09-07 | 161 | 18 | 22
506290 | Buford Water Works | Oakville | Backpulse /CIP Pumps | FLOWSERVE INC. | 4503685074 | Rotating Equipment | Centrifugal Pumps | USD | 42745 | USD | 39284 | 3461 | Design Optimizations | 2021-10-04 | 2021-09-22 | 2021-09-24 | 2021-10-11 | 2021-09-24 | 2021-09-27 | 2021-10-21 | 2021-11-12 | 2021-03-30 | 2022-03-28 | 2021-09-27 | 182 | 30 | 51
506290 | Buford Water Works | Oakville | Valve rack skid - Piping | NV PIPING SYSTEMS INC. | 4503687491 | Fabrication | Carbon Steel | USD | 74445 | CAD | 44197 | 30248 | Supplier Competitions / Negotiation | 2021-10-04 | 2021-10-28 | 2021-11-02 | 2021-10-11 | 2021-10-31 | 2021-09-01 | 2021-10-21 | 2021-11-15 | 2021-03-30 | 2022-02-03 | 2021-09-01 | 155 | 12 | 18
506290 | Buford Water Works | Oakville | Butterfly Valves | BRAY CONTROLS 102 PVT LTD | 4503684648 | Flow Control | Metal Isolation Valves | USD | 13520 | USD | 13245 | 275 | Frame Agreements | 2021-10-04 | 2021-10-25 | 2021-10-28 | 2021-10-11 | 2021-10-26 | 2021-08-23 | 2021-10-21 | 2021-11-08 | 2021-03-30 | 2022-01-17 | 2021-08-23 | 147 | 12 | 14
506290 | Buford Water Works | Oakville | Blower | AERZEN | 4503685046 | Rotating Equipment | Blowers & Fans | USD | 13243 | CAD | 16505 | -3262 | Market Impact | 2021-10-04 | 2021-10-25 | 2021-11-04 | 2021-10-11 | 2021-11-04 | 2021-09-27 | 2021-10-21 | 2021-11-12 | 2021-03-30 | 2022-03-28 | 2021-09-27 | 182 | 30 | 18
506290 | Buford Water Works | Oakville | Air Compressor | Compressor Science Inc. | 4503712820 | Rotating Equipment | Compressors | USD | 13235 | USD | 16671 | -3436 | Proposed Supplier Incapable Of Executing | 2021-10-04 | 2021-12-15 | 2022-01-04 | 2021-10-11 | 2022-01-04 | 2021-09-21 | 2021-10-21 | 2022-01-05 | 2021-03-30 | 2022-03-16 | 2021-09-21 | 176 | 30 | 21
506290 | Buford Water Works | Oakville | Valve rack frames | 3D MECHANICAL | 4503690202 | Fabrication | Carbon Steel | USD | 13433 | CAD | 17576 | -4143 | Estimate Without Market Reference(No Quote) | 2021-10-04 | 2021-10-25 | 2021-11-02 | 2021-10-11 | 2021-11-22 | 2021-08-30 | 2021-10-21 | 2021-11-22 | 2021-03-30 | 2022-01-31 | 2021-08-30 | 154 | 12 | 28
506290 | Buford Water Works | Oakville | Flow Transmitter | ENDRESS & HAUSER | 4503680791 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 13084 | USD | 13245 | -161 | Market Impact | 2021-10-04 | 2021-10-25 | 2021-11-03 | 2021-10-11 | 2021-10-31 | 2021-09-09 | 2021-10-21 | 2021-11-01 | 2021-03-30 | 2022-02-20 | 2021-09-09 | 164 | 18 | 7
506290 | Buford Water Works | Oakville | Valves | BRAY CONTROLS CANADA LTD. | 4503719085 | Flow Control | Metal Control Valves | USD | 6675 | USD | 7098 | -423 | Specs / Requirements Misinterpreted in Proposal | 2022-03-03 | 2022-01-14 | 2022-01-14 | 2022-03-03 | 2022-01-13 | 2022-03-03 | 2022-03-03 | 2022-01-13 | 2022-03-03 | 2022-04-21 | 2022-03-27 | 25 | 12 | -1
506324 | Mark Anthony Brewing Glendale | Minnetonka | 506324B City Water Tank | DIAMOND FIBERGLASS | 4503370733 | Fabrication | Carbon Steel | USD | 29000 | USD | 39880 | -10880 | Single Sourced | 2020-02-07 | 2020-02-07 | 2020-02-07 | 2020-02-07 | 2020-02-05 | 2020-04-08 | 2020-03-05 | 2020-03-03 | 2020-06-11 | 2020-06-09 | 2020-06-10 | -1 | 12 | 25
506324 | Mark Anthony Brewing Glendale | Minnetonka | 506324B City Water Pumps SKID | PFC EQUIPMENT | 4503365194 | Rotating Equipment | Centrifugal Pumps | USD | 74000 | USD | 43260 | 30740 | Frame Agreements | 2020-03-05 | 2019-11-21 | 2019-11-21 | 2020-03-05 | 2020-02-18 | 2020-01-30 | 2020-03-09 | 2020-02-25 | 2020-04-10 | 2020-04-07 | 2020-04-08 | -1 | 30 | 96
506324 | Mark Anthony Brewing Glendale | Minnetonka | 506324E Tekleen Screens | TEKLEEN | 4503369026 | Flow Control | Carbon Steel | USD | 137000 | USD | 74100 | 62900 | Supplier Competitions / Negotiation | 2020-03-05 | 2020-03-02 | 2020-03-02 | 2020-03-05 | 2020-03-03 | 2020-04-21 | 2020-03-09 | 2020-03-03 | 2020-06-11 | 2020-06-09 | 2020-06-10 | -1 | 12 | 1
506324 | Mark Anthony Brewing Glendale | Minnetonka | 506324C AC Media | CALGON CARBON CORPORATION | 4503403693 | Flow Control | Centrifugal Pumps | USD | 157400 | USD | 156316 | 1084 | Supplier Competitions / Negotiation | 2020-03-11 | 2020-04-01 | 2020-04-07 | 2020-03-11 | 2020-05-13 | 2020-06-06 | 2020-03-16 | 2020-05-14 | 2020-06-11 | 2020-09-01 | 2020-07-22 | 41 | 12 | 43
506324 | Mark Anthony Brewing Glendale | Minnetonka | 506324K Cartridge Filter Housings | FIL-TREK CORPORATION | 4503370801 | Flow Control | RO Membrane Housings | USD | 45600 | USD | 39600 | 6000 | Frame Agreements | 2020-03-11 | 2020-03-02 | 2020-03-03 | 2020-03-11 | 2020-03-05 | 2020-04-21 | 2020-03-16 | 2020-03-05 | 2020-06-11 | 2020-05-28 | 2020-06-04 | -7 | 12 | 3
506324 | Mark Anthony Brewing Glendale | Minnetonka | 506324C Activated Carbon Unit | Arrow Tanks | 4503370760 | Fabrication | Carbon Steel | USD | 412000 | USD | 303880 | 108120 | Frame Agreements | 2020-03-05 | 2020-03-02 | 2020-03-03 | 2020-03-05 | 2020-03-03 | 2020-03-28 | 2020-03-05 | 2020-03-05 | 2020-04-23 | 2020-04-23 | 2020-04-23 | 0 | 12 | 3
506324 | Mark Anthony Brewing Glendale | Minnetonka | 506324J Pre-RO UV | AQUIONICS, INC. | 4503368409 | Fabrication | Metal Isolation Valves | USD | 42500 | USD | 31167 | 11333 | Supplier Competitions / Negotiation | 2020-02-07 | 2020-02-07 | 2020-02-28 | 2020-02-07 | 2020-02-26 | 2020-04-09 | 2020-02-07 | 2020-03-01 | 2020-06-11 | 2020-04-26 | 2020-05-19 | -23 | 12 | 23
506324 | Mark Anthony Brewing Glendale | Minnetonka | 506324F CIP TANK | Preferred Stainless Holdings | 4503358827 | Fabrication | Metal Isolation Valves | USD | 49000 | USD | 33703 | 15297 | Frame Agreements | 2020-03-05 | 2020-01-16 | 2020-01-17 | 2020-03-09 | 2020-02-11 | 2020-03-29 | 2020-03-09 | 2020-02-12 | 2020-06-11 | 2020-04-29 | 2020-05-20 | -21 | 12 | 27
506324 | Mark Anthony Brewing Glendale | Minnetonka | 506324M MCE | WERNER ELECTRIC | 4503372813 | Electrical & Instrumentation | Metal Isolation Valves | USD | 134349 | USD | 134349 | 0 | Specs / Requirements Misinterpreted in Proposal | 2020-02-24 | 2020-02-07 | 2020-02-27 | 2020-02-28 | 2020-02-27 | 2020-04-06 | 2020-03-02 | 2020-03-10 | 2020-05-25 | 2020-06-05 | 2020-05-30 | 6 | 18 | 32
506324 | Mark Anthony Brewing Glendale | Minnetonka | ELECTRICAL PANELS | PTS Products | 4503382015 | Electrical & Instrumentation | Ele-Electrical Others | USD | 35651 | USD | 70610 | -34959 | Proposed Supplier Incapable Of Executing | 2020-03-14 | 2020-03-14 | 2020-03-24 | 2020-03-24 | 2020-03-23 | 2020-04-23 | 2020-03-24 | 2020-03-25 | 2020-06-02 | 2020-05-13 | 2020-05-23 | -10 | 18 | 11
506324 | Mark Anthony Brewing Glendale | Minnetonka | Frames and Spools | A&B Process | 4503371406 | Fabrication | Ele-Control Panels | USD | 12066 | USD | 80442 | -68376 | Estimate Without Market Reference(No Quote) | 2020-02-26 | 2020-02-26 | 2020-02-25 | 2020-02-27 | 2020-02-24 | 2020-03-18 | 2020-02-28 | 2020-03-02 | 2020-04-10 | 2020-04-06 | 2020-04-08 | -2 | 12 | 5
506357 | City of Canton Water Pollution Control Plant | Oakville | Process pump | BOERGER, INC | 4503680157 | Rotating Equipment | Centrifugal Pumps | USD | 164410 | USD | 153150 | 11260 | Frame Agreements | 2021-10-25 | 2021-09-25 | 2021-09-29 | 2021-10-27 | 2021-11-02 | 2021-09-29 | 2021-11-01 | 2021-11-02 | 2021-02-24 | 2022-05-05 | 2021-09-29 | 218 | 30 | 38
506357 | City of Canton Water Pollution Control Plant | Oakville | RAS Pump | SULZER PUMPS (CANADA) INC. | 4503680142 | Rotating Equipment | Centrifugal Pumps | USD | 134697 | CAD | 134876 | -179 | Estimate Without Market Reference(No Quote) | 2021-10-25 | 2021-04-10 | 2021-04-13 | 2021-10-27 | 2021-11-03 | 2021-08-18 | 2021-11-01 | 2021-11-03 | 2021-02-24 | 2022-02-09 | 2021-08-18 | 175 | 30 | 207
506357 | City of Canton Water Pollution Control Plant | Oakville | Main Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503708252 | Electrical & Instrumentation | Ele-Control Panels | USD | 121262 | CAD | 59444 | 61818 | Frame Agreements | 2021-11-22 | 2021-12-01 | 2021-12-10 | 2021-11-24 | 2021-12-17 | 2021-10-20 | 2021-11-27 | 2021-12-23 | 2021-05-24 | 2022-03-18 | 2021-10-20 | 149 | 18 | 22
506357 | City of Canton Water Pollution Control Plant | Oakville | Spools | NV PIPING SYSTEMS INC. | 4503734083 | Fabrication | Stainless Steel | USD | 96403 | CAD | 108904 | -12501 | Market Impact | 2021-11-22 | 2022-02-18 | 2022-02-25 | 2021-10-24 | 2022-02-07 | 2021-09-25 | 2021-11-27 | 2022-02-07 | 2021-03-24 | 2022-03-30 | 2021-09-25 | 186 | 12 | -11
506357 | City of Canton Water Pollution Control Plant | Oakville | Blower | AERZEN CANADA INC | 4503684760 | Rotating Equipment | Blowers & Fans | USD | 77058 | CAD | 77160 | -102 | Single Sourced | 2021-10-25 | 2021-10-15 | 2021-10-20 | 2021-10-27 | 2021-11-11 | 2021-08-26 | 2021-11-01 | 2021-11-11 | 2021-02-24 | 2022-02-25 | 2021-08-26 | 183 | 30 | 27
506357 | City of Canton Water Pollution Control Plant | Oakville | Membrane lifting devices | PLASFAB LIMITED | 4503729225 | Fabrication | Stainless Steel | USD | 79474 | CAD | 109536 | -30062 | Market Impact | 2021-11-22 | 2022-02-18 | 2022-02-24 | 2021-10-24 | 2022-01-23 | 2021-09-13 | 2021-11-27 | 2022-01-30 | 2021-03-24 | 2022-03-06 | 2021-09-13 | 174 | 12 | -19
506357 | City of Canton Water Pollution Control Plant | Oakville | Knife gate valves | COMMONWEALTH CONTROLS CORPORATION | 4503709582 | Flow Control | Metal Control Valves | USD | 82730 | USD | 48742 | 33988 | Frame Agreements | 2021-11-22 | 2021-12-18 | 2021-12-21 | 2021-10-24 | 2021-12-20 | 2021-09-14 | 2021-11-27 | 2021-12-27 | 2021-03-24 | 2022-03-07 | 2021-09-14 | 174 | 12 | 9
506357 | City of Canton Water Pollution Control Plant | Oakville | Chemical dosing skid | PROMINENT FLUID CONTROLS LTD. | 4503707864 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 27720 | CAD | 21612 | 6108 | Design Optimizations | 2021-11-22 | 2021-01-25 | 2021-01-28 | 2021-10-24 | 2021-12-21 | 2021-08-21 | 2021-11-27 | 2021-12-21 | 2021-03-24 | 2022-03-17 | 2021-09-19 | 179 | 30 | 330
506357 | City of Canton Water Pollution Control Plant | Oakville | Flow Transmitter | ENDRESS + HAUSER CANADA LTD. | 4503699737 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 17036 | USD | 18756 | -1720 | Market Impact | 2021-11-22 | 2021-12-06 | 2021-12-08 | 2021-10-24 | 2021-12-08 | 2021-09-11 | 2021-11-27 | 2021-12-08 | 2021-03-24 | 2022-03-02 | 2021-09-11 | 172 | 18 | 2
506357 | City of Canton Water Pollution Control Plant | Oakville | Air Compressor + Dryer | Compressor Science Inc. | 4503730685 | Rotating Equipment | Compressors | USD | 15089 | USD | 16971 | -1882 | Specs / Requirements Misinterpreted in Proposal | 2021-11-22 | 2021-03-19 | 2021-03-23 | 2021-10-24 | 2022-02-01 | 2021-09-06 | 2021-11-27 | 2022-02-02 | 2021-03-24 | 2022-02-24 | 2021-09-08 | 169 | 30 | 320
506372 | CSU Mountain Campus | Oakville | Blower | Aerzen Canada Inc. | 4503428459 | Rotating Equipment | Ele-Control Panels | USD | 12069 | CAD | 11318 | 751 | Supplier Competitions / Negotiation | 2020-04-17 | 2020-06-23 | 2020-06-23 | 2020-04-24 | 2020-06-23 | 2020-06-23 | 2020-05-01 | 2020-07-06 | 2020-08-30 | 2020-07-06 | 2020-08-02 | -27 | 30 | 13
506372 | CSU Mountain Campus | Oakville | Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503425702 | Electrical & Instrumentation | Ele-Control Panels | USD | 31010 | CAD | 28433 | 2577 | Design Optimizations | 2020-04-17 | 2020-06-23 | 2020-06-23 | 2020-04-24 | 2020-06-23 | 2020-06-23 | 2020-05-02 | 2020-07-02 | 2020-08-30 | 2020-07-02 | 2020-07-31 | -29 | 18 | 9
506372 | CSU Mountain Campus | Oakville | Frame + Tank + Assembly | ASLAN TECHNOLOGIES | 4503420398 | Fabrication | Carbon Steel | USD | 72738 | CAD | 91730 | -18992 | Not included in Proposal / RFQ | 2020-04-17 | 2020-06-23 | 2020-06-23 | 2020-04-24 | 2020-06-23 | 2020-06-23 | 2020-05-06 | 2020-06-21 | 2020-08-30 | 2020-06-21 | 2020-07-26 | -35 | 12 | -2
506372 | CSU Mountain Campus | Oakville | Mixer | Philadelphia Mixing Solutions | 4503426518 | Rotating Equipment | Metal Isolation Valves | USD | 29935 | USD | 14432 | 15503 | Frame Agreements | 2020-04-17 | 2020-06-23 | 2020-06-23 | 2020-04-24 | 2020-06-23 | 2020-06-23 | 2020-05-01 | 2020-07-07 | 2020-08-30 | 2020-07-07 | 2020-08-03 | -27 | 30 | 14
506372 | CSU Mountain Campus | Oakville | Bioreactor Tank | Burke's Mechanical, Inc. | 4503418926 | Fabrication | Ele-Control Panels | USD | 56925 | USD | 76916 | -19991 | Specs / Requirements Misinterpreted in Proposal | 2020-04-17 | 2020-06-23 | 2020-06-23 | 2020-04-24 | 2020-06-23 | 2020-06-23 | 2020-05-01 | 2020-06-17 | 2020-08-30 | 2020-06-17 | 2020-07-24 | -37 | 12 | -6
506377 | Shintech LEX4 | Oakville | Decarbonator Tower (Air Seal/Overflow Pipe included) | PRECISIONEERING | 4503408198 | Fabrication | Carbon Steel | USD | 45338 | USD | 49257 | -3919 | Size/ Weight/ Quantity Underestimated | 2020-03-20 | 2020-03-26 | 2020-04-06 | 2020-04-24 | 2020-04-27 | 2020-06-20 | 2020-05-08 | 2020-05-24 | 2020-08-28 | 2020-09-20 | 2020-09-08 | 12 | 12 | 59
506377 | Shintech LEX4 | Oakville | Automatic and Flow Control Valves (Proximity Limit Switches Included) | BRAY CONTROLS CANADA LTD. | 4503422670 | Flow Control | Metal Isolation Valves | USD | 97291 | USD | 17715 | 79576 | Design Optimizations | 2020-03-20 | 2020-04-08 | 2020-06-27 | 2020-04-24 | 2020-06-25 | 2020-06-08 | 2020-05-08 | 2020-06-28 | 2020-08-28 | 2020-08-09 | 2020-08-18 | -9 | 12 | 81
506377 | Shintech LEX4 | Oakville | Flow Control and Automatic Ball Valves (Proximity Limit Switches Included) | M.A. STEWART & SONS LTD. | 4503421821 | Flow Control | Metal Isolation Valves | USD | 24236 | CAD | 19610 | 4626 | Design Optimizations | 2020-04-17 | 2020-04-08 | 2020-05-14 | 2020-05-22 | 2020-06-11 | 2020-06-18 | 2020-06-05 | 2020-06-29 | 2020-08-28 | 2020-08-17 | 2020-08-22 | -5 | 12 | 82
506377 | Shintech LEX4 | Oakville | Flow Control Valves (Lined) (Proximity Limit Switches Included) | AMRI INC. | 4503409395 | Flow Control | Metal Isolation Valves | USD | 43477 | USD | 46560 | -3083 | Market Impact | 2020-03-20 | 2020-04-08 | 2020-05-15 | 2020-04-24 | 2020-05-15 | 2020-06-08 | 2020-05-08 | 2020-05-25 | 2020-08-28 | 2020-07-27 | 2020-08-12 | -16 | 12 | 47
506377 | Shintech LEX4 | Oakville | Automatic Lined Ball Valves (Proximity Limit Switches Included) | PEERLESS | 4503419586 | Flow Control | Metal Isolation Valves | USD | 22513 | USD | 24710 | -2197 | Market Impact | 2020-05-15 | 2020-04-08 | 2020-05-29 | 2020-06-19 | 2020-06-14 | 2020-06-18 | 2020-07-03 | 2020-06-21 | 2020-08-28 | 2020-07-26 | 2020-08-11 | -16 | 12 | 74
506377 | Shintech LEX4 | Oakville | Junction Boxes | KELTOUR CONTROLS INC. | 4503454120 | Electrical & Instrumentation | Metal Isolation Valves | USD | 6335 | USD | 8569 | -2234 | Specs / Requirements Misinterpreted in Proposal | 2020-05-15 | 2020-07-02 | 2020-07-13 | 2020-06-19 | 2020-07-30 | 2020-07-24 | 2020-07-03 | 2020-09-04 | 2020-08-28 | 2020-10-02 | 2020-09-14 | 18 | 18 | 64
506377 | Shintech LEX4 | Oakville | Decarbonator Fans | LAWSON-TAYLOR LTD. | 4503407158 | Rotating Equipment | Blowers & Fans | USD | 5186 | USD | 5672 | -486 | Market Impact | 2020-05-22 | 2020-03-24 | 2020-04-02 | 2020-06-26 | 2020-04-05 | 2020-06-10 | 2020-07-10 | 2020-05-07 | 2020-08-28 | 2020-07-16 | 2020-08-06 | -21 | 30 | 44
506377 | Shintech LEX4 | Oakville | Skid Manufacturing Sub-Out (Mechanical Bulk & Electrical Bulk Included) | TITAN PIPING SYSTEMS INC. | 4503449430 | Fabrication | Skid Assembly Outsourced | USD | 253163 | CAD | 154554 | 98609 | Frame Agreements | 2020-05-15 | 2020-05-29 | 2020-07-14 | 2020-06-19 | 2020-07-14 | 2020-07-30 | 2020-07-03 | 2020-07-22 | 2020-08-28 | 2020-10-14 | 2020-09-20 | 24 | 12 | 54
506377 | Shintech LEX4 | Oakville | Instrumentation - Flowmeters & Magmeters | LAKESIDE PROCESS CONTROLS LTD. | 4503431135 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 27128 | USD | 28705 | -1577 | Not included in Proposal / RFQ | 2020-03-27 | 2020-06-23 | 2020-07-03 | 2020-06-05 | 2020-07-07 | 2020-06-21 | 2020-06-19 | 2020-07-14 | 2020-08-28 | 2020-09-15 | 2020-09-06 | 9 | 18 | 21
506377 | Shintech LEX4 | Oakville | Instrumentation - Conductivity | YOKOGAWA | 4503451265 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 10785 | USD | 24422 | -13637 | Size/ Weight/ Quantity Underestimated | 2020-03-27 | 2020-06-23 | 2020-07-23 | 2020-06-05 | 2020-08-28 | 2020-07-25 | 2020-06-19 | 2020-08-30 | 2020-08-28 | 2020-11-22 | 2020-10-10 | 43 | 18 | 68
506377 | Shintech LEX4 | Oakville | Pressure Relief Valves | Great Lakes Industrial Controls | 4503425082 | Flow Control | Metal Safety(relief) Valves | USD | 12201 | CAD | 7521 | 4680 | Design Optimizations | 2020-03-20 | 2020-04-08 | 2020-07-02 | 2020-04-24 | 2020-06-30 | 2020-06-22 | 2020-05-08 | 2020-07-03 | 2020-08-28 | 2020-09-25 | 2020-09-11 | 14 | 12 | 86
506377 | Shintech LEX4 | Oakville | Pumps | SULZER PUMPS (CANADA) INC. | 4503406139 | Rotating Equipment | Centrifugal Pumps | USD | 29366 | USD | 29366 | 0 | Single Sourced | 2020-03-20 | 2020-03-23 | 2020-03-31 | 2020-04-24 | 2020-04-07 | 2020-06-08 | 2020-05-08 | 2020-04-19 | 2020-08-28 | 2020-07-12 | 2020-07-27 | -15 | 30 | 27
506377 | Shintech LEX4 | Oakville | Pressure Vessels | LESENA STEEL DIVISION | 4503406805 | Fabrication | Carbon Steel | USD | 112665 | CAD | 112665 | 0 | Size/ Weight/ Quantity Underestimated | 2020-03-20 | 2020-03-05 | 2020-03-12 | 2020-04-24 | 2020-03-16 | 2020-06-01 | 2020-05-08 | 2020-03-20 | 2020-08-28 | 2020-03-20 | 2020-06-08 | -80 | 12 | 15
506377 | Shintech LEX4 | Oakville | Pressure Vessels Painting & Lining | BRANT CORROSION CONTROL, | 4503406201 | Fabrication | Carbon Steel | USD | 39138 | CAD | 39138 | 0 | Market Impact | 2020-05-15 | 2020-03-17 | 2020-03-19 | 2020-06-19 | 2020-04-28 | 2020-06-07 | 2020-07-03 | 2020-05-10 | 2020-08-28 | 2020-06-07 | 2020-07-18 | -41 | 12 | 54
506377 | Shintech LEX4 | Oakville | Internals (Hastelloy) | PANDA PIPING LTD | 4503418491 | Fabrication | Ele-Control Panels | USD | 89980 | CAD | 116579 | -26599 | Not included in Proposal / RFQ | 2020-02-21 | 2020-05-05 | 2020-05-15 | 2020-03-27 | 2020-05-31 | 2020-05-25 | 2020-04-10 | 2020-06-16 | 2020-08-28 | 2020-06-16 | 2020-07-22 | -36 | 12 | 42
506377 | Shintech LEX4 | Oakville | PP Lined Pipes & Fittings | BAUM AMERICA CORP | 4503444327 | Fabrication | Metal Isolation Valves | USD | 45000 | USD | 40109 | 4891 | Supplier Competitions / Negotiation | 2020-07-17 | 2020-07-17 | 2020-07-27 | 2020-08-02 | 2020-07-27 | 2020-08-14 | 2020-08-07 | 2020-08-15 | 2020-08-28 | 2020-09-12 | 2020-09-04 | 8 | 12 | 29
506393 | Mayfield Springs | Richmond | Bio Tank | POSEIDON, INC | 4503430897 | Fabrication | Metal Isolation Valves | USD | 128193 | USD | 108750 | 19443 | Design Optimizations | 2020-06-29 | 2020-09-05 | 2020-06-30 | 2020-09-30 | 2020-09-05 | 2020-09-05 | 2020-08-20 | 2020-07-16 | 2020-11-12 | 2020-10-22 | 2020-11-01 | -10 | 12 | -51
506393 | Mayfield Springs | Richmond | Screens | JWC Environmental Canada | 4503461640 | Rotating Equipment | Carbon Steel | USD | 163232 | CAD | 162258 | 974 | Design Optimizations | 2020-06-26 | 2020-09-12 | 2020-05-29 | 2020-09-30 | 2020-09-12 | 2020-09-12 | 2020-08-20 | 2020-09-21 | 2020-11-13 | 2020-12-28 | 2020-12-05 | 23 | 30 | 9
506393 | Mayfield Springs | Richmond | Compressors | PNEU AIR COMPRESSORS LTD | 4503484175 | Rotating Equipment | Compressors | USD | 15140 | CAD | 7315 | 7825 | Design Optimizations | 2020-06-26 | 2020-11-01 | 2020-11-04 | 2020-09-30 | 2020-11-01 | 2020-11-01 | 2020-08-20 | 2020-11-01 | 2020-11-13 | 2021-03-10 | 2021-01-10 | 59 | 30 | 0
506393 | Mayfield Springs | Richmond | Blowers | AERZEN | 4503540397 | Rotating Equipment | Blowers & Fans | USD | 48000 | CAD | 26840 | 21160 | Supplier Competitions / Negotiation | 2020-06-26 | 2020-09-27 | 2020-07-01 | 2020-06-26 | 2020-09-27 | 2020-09-27 | 2020-06-26 | 2020-10-07 | 2020-11-13 | 2020-12-30 | 2020-12-06 | 24 | 30 | 10
506393 | Mayfield Springs | Richmond | Mag. Meters | ENDRESS & HAUSER | 4503470911 | Electrical & Instrumentation | Metal Isolation Valves | USD | 8000 | USD | 8604 | -604 | Proposed Supplier Incapable Of Executing | 2020-06-26 | 2020-09-04 | 2020-07-01 | 2020-06-26 | 2020-09-04 | 2020-09-04 | 2020-06-26 | 2020-10-07 | 2020-11-13 | 2020-10-21 | 2020-11-01 | -11 | 18 | 33
506393 | Mayfield Springs | Richmond | RAS Pumps | FLOWSERVE INC. | 4503436697 | Rotating Equipment | Centrifugal Pumps | USD | 11000 | USD | 10594 | 406 | Supplier Competitions / Negotiation | 2020-06-26 | 2020-09-04 | 2020-07-01 | 2020-06-26 | 2020-09-04 | 2020-09-04 | 2020-06-26 | 2020-09-04 | 2020-11-13 | 2020-09-04 | 2020-10-09 | -35 | 30 | 0
506393 | Mayfield Springs | Richmond | Diffuser Grid | EDI | 4503429460 | Flow Control | Centrifugal Pumps | USD | 8000 | USD | 7362 | 638 | Design Optimizations | 2020-06-30 | 2020-09-06 | 2020-07-01 | 2020-07-06 | 2020-07-08 | 2020-09-06 | 2020-07-06 | 2020-07-14 | 2020-11-13 | 2020-10-06 | 2020-10-25 | -19 | 12 | -54
506393 | Mayfield Springs | Richmond | Mixer | SULZER PUMP SOLUTIONS - USA | 4503484179 | Rotating Equipment | Metal Isolation Valves | USD | 14100 | CAD | 14004 | 96 | Frame Agreements | 2020-07-01 | 2020-09-23 | 2020-09-23 | 2020-07-31 | 2020-09-23 | 2020-09-23 | 2020-07-20 | 2020-11-05 | 2020-11-13 | 2020-12-17 | 2020-11-30 | 17 | 30 | 43
506393 | Mayfield Springs | Richmond | Membrane Tank and Skid Frame | D&R CUSTOM STEEL | 4503437778 | Fabrication | Skid Assembly Outsourced | USD | 48000 | CAD | 49206 | -1206 | Specs / Requirements Misinterpreted in Proposal | 2021-05-06 | 2021-05-06 | 2020-07-08 | 2021-05-06 | 2020-07-31 | 2021-05-06 | 2021-05-06 | 2021-11-26 | 2021-05-06 | 2022-03-04 | 2021-10-04 | 151 | 12 | 204
506393 | Mayfield Springs | Richmond | Additional Tank | POSEIDON, INC | 4503494061 | Fabrication | Metal Isolation Valves | USD | 41000 | CAD | 40700 | 300 | Design Optimizations | 2021-01-02 | 2021-01-02 | 2020-11-02 | 2021-01-02 | 2020-11-25 | 2021-01-02 | 2021-01-02 | 2020-11-26 | 2021-01-02 | 2021-03-04 | 2021-02-01 | 31 | 12 | -37
506393 | Mayfield Springs | Richmond | Electrical Panels | ENGINEERING ELECTRIC CONTROLS | 4503499672 | Electrical & Instrumentation | Ele-Electrical Others | USD | 25746 | CAD | 31435 | -5689 | Single Sourced | 2020-12-23 | 2020-12-23 | 2020-11-27 | 2020-12-23 | 2020-12-04 | 2020-12-23 | 2020-12-23 | 2020-12-08 | 2020-12-23 | 2021-01-19 | 2021-01-05 | 14 | 18 | -15
506394 | Plumsted WWTP | Oakville | Pump Rotary Lobe (Boerger) | BOERGER LLC | 4503432858 | Rotating Equipment | Centrifugal Pumps | USD | 14900 | USD | 14900 | 0 | Not included in Proposal / RFQ | 2020-10-13 | 2020-09-08 | 2020-09-08 | 2020-10-27 | 2020-09-08 | 2020-09-08 | 2020-10-27 | 2020-07-21 | 2020-09-26 | 2020-10-10 | 2020-10-03 | 7 | 30 | -49
506394 | Plumsted WWTP | Oakville | RAS pumps | SULZER PUMPS (CANADA) INC. | 4503435921 | Rotating Equipment | Centrifugal Pumps | USD | 9186 | CAD | 9186 | 0 | Market Impact | 2020-06-23 | 2020-08-28 | 2020-08-28 | 2020-07-07 | 2020-08-28 | 2020-08-28 | 2020-07-07 | 2020-07-28 | 2020-11-03 | 2020-07-28 | 2020-09-15 | -49 | 30 | -31
506394 | Plumsted WWTP | Oakville | Chemical Pump | PROMINENT FLUID CONTROLS LTD. | 4503441264 | Rotating Equipment | Centrifugal Pumps | USD | 14944 | CAD | 14822 | 122 | Supplier Competitions / Negotiation | 2020-07-03 | 2020-08-21 | 2020-08-21 | 2020-07-17 | 2020-08-21 | 2020-08-21 | 2020-07-17 | 2020-08-07 | 2020-09-26 | 2020-10-10 | 2020-10-03 | 7 | 30 | -14
506394 | Plumsted WWTP | Oakville | Piping Headers | NV PIPING SYSTEMS INC. | 4503481024 | Fabrication | Metal Isolation Valves | USD | 8863 | CAD | 8864 | -1 | Single Sourced | 2020-11-03 | 2020-06-09 | 2020-06-09 | 2020-11-17 | 2020-06-09 | 2020-06-09 | 2020-11-17 | 2020-10-30 | 2020-01-01 | 2020-10-30 | 2020-05-31 | 152 | 12 | 143
506394 | Plumsted WWTP | Oakville | Control Panels | Keltour Controls Inc. | 4503513348 | Electrical & Instrumentation | Ele-Control Panels | USD | 74763 | CAD | 51640 | 23123 | Frame Agreements | 2020-10-09 | 2020-12-10 | 2020-12-10 | 2020-10-23 | 2020-12-10 | 2020-12-10 | 2020-10-23 | 2021-01-08 | 2020-12-01 | 2021-02-10 | 2021-01-05 | 36 | 18 | 29
506394 | Plumsted WWTP | Oakville | Blowers | AERZEN CANADA INC. | 4503436043 | Rotating Equipment | Blowers & Fans | USD | 17770 | CAD | 17123 | 647 | Design Optimizations | 2020-09-09 | 2020-09-18 | 2020-09-18 | 2020-09-23 | 2020-09-18 | 2020-09-18 | 2020-09-23 | 2020-08-28 | 2020-09-30 | 2020-10-10 | 2020-10-05 | 5 | 30 | -21
506394 | Plumsted WWTP | Oakville | Compressor System | Compressor Science Inc. | 4503436477 | Rotating Equipment | Vapor Compressor | USD | 11628 | USD | 12985 | -1357 | Single Sourced | 2020-06-23 | 2020-08-08 | 2020-08-08 | 2020-07-07 | 2020-08-08 | 2020-08-08 | 2020-09-23 | 2020-07-29 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 0 | 30 | -10
506394 | Plumsted WWTP | Oakville | Assembly of Skids | ASLAN TECHNOLOGIES | 4503474243 | Fabrication | Metal Isolation Valves | USD | 20240 | CAD | 12038 | 8202 | Supplier Competitions / Negotiation | 2020-06-23 | 2020-10-06 | 2020-10-06 | 2020-07-07 | 2020-10-06 | 2020-10-06 | 2020-09-23 | 2020-10-16 | 2020-11-16 | 2021-01-20 | 2020-12-18 | 33 | 12 | 10
506397 | Table Mountain Rancheria | Oakville | Control Panel -Terminals | ENGINEERING ELECTRIC CONTROLS | 4503397910 | Electrical & Instrumentation | Ele-Control Panels | USD | 16440 | CAD | 9075 | 7365 | Supplier Competitions / Negotiation | 2020-04-27 | 2020-04-06 | 2020-04-14 | 2020-05-18 | 2020-04-10 | 2020-05-18 | 2020-05-25 | 2020-04-30 | 2020-06-29 | 2020-05-28 | 2020-06-13 | -16 | 18 | 24
506397 | Table Mountain Rancheria | Oakville | Flow Gauge | ENDRESS & HAUSER | 4503395932 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 5427 | USD | 5038 | 389 | Supplier Competitions / Negotiation | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-05-04 | 2020-04-24 | 2020-05-21 | 2020-05-11 | 2020-04-27 | 2020-06-29 | 2020-05-18 | 2020-06-08 | -21 | 18 | 13
506444 | DRUMBO MBR | Oakville | Electrical Panels | MACHINE CONTROL SYSTEMS | 4503708626 | Electrical & Instrumentation | Ele-Control Panels | CAD | 134774 | CAD | 83887 | 50887 | Supplier Competitions / Negotiation | 2021-09-22 | 2021-11-03 | 2021-12-20 | 2021-10-13 | 2021-12-22 | 2021-12-22 | 2021-10-20 | 2021-12-24 | 2022-02-02 | 2021-12-28 | 2022-01-15 | -18 | 18 | 51
506444 | DRUMBO MBR | Oakville | Submersible RAS pump including Tests | XYLEM CANADA COMPANY | 4503772134 | Rotating Equipment | Centrifugal Pumps | CAD | 12652 | CAD | 18942 | -6290 | Market Impact | 2021-09-22 | 2021-12-05 | 2022-01-26 | 2021-10-13 | 2022-04-04 | 2022-04-04 | 2021-10-20 | 2022-04-11 | 2022-02-02 | 2022-07-25 | 2022-04-29 | 87 | 30 | 127
506444 | DRUMBO MBR | Oakville | Process Pump (Rotary Lobe) with tests | BOERGER LLC | 4503718357 | Rotating Equipment | PD Pumps | CAD | 35497 | USD | 44014 | -8517 | Market Impact | 2021-10-06 | 2021-11-28 | 2022-01-10 | 2021-10-27 | 2022-01-09 | 2022-01-11 | 2021-11-03 | 2022-01-12 | 2022-02-02 | 2022-01-12 | 2022-01-22 | -10 | 30 | 45
506444 | DRUMBO MBR | Oakville | Chemical Dosing System | PROMINENT FLUID CONTROLS LTD. | 4503696732 | Rotating Equipment | Chem. Feed Skids (Turnkey) | CAD | 10661 | CAD | 10661 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-10-20 | 2021-11-29 | 2021-12-03 | 2021-11-10 | 2021-12-03 | 2021-12-03 | 2021-11-17 | 2021-12-03 | 2022-02-02 | 2022-09-20 | 2022-05-28 | 115 | 30 | 4
506444 | DRUMBO MBR | Oakville | Harmonic Filters | Proax Technologies Ltd | 4503708419 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 28599 | CAD | 27680 | 919 | Supplier Competitions / Negotiation | 2021-12-01 | 2021-11-28 | 2021-12-23 | 2021-12-22 | 2021-12-23 | 2021-12-23 | 2021-12-29 | 2021-12-23 | 2022-02-02 | 2022-03-17 | 2022-02-23 | 22 | 18 | 25
506444 | DRUMBO MBR | Oakville | Blower | FPZ INC | 4503766067 | Rotating Equipment | Blowers & Fans | CAD | 19362 | USD | 12056 | 7306 | Supplier Competitions / Negotiation | 2021-10-20 | 2021-11-28 | 2022-02-01 | 2021-11-10 | 2022-03-25 | 2022-03-25 | 2021-11-17 | 2022-03-31 | 2022-02-02 | 2022-07-01 | 2022-04-17 | 75 | 30 | 123
506444 | DRUMBO MBR | Oakville | Air Compressors | PNEU AIR COMPRESSORS LTD | 4503706160 | Rotating Equipment | Compressors | CAD | 17092 | CAD | 12692 | 4400 | Supplier Competitions / Negotiation | 2021-11-17 | 2021-11-29 | 2021-11-30 | 2021-12-08 | 2021-12-16 | 2021-12-17 | 2021-12-15 | 2021-12-19 | 2022-02-02 | 2022-04-06 | 2022-03-05 | 32 | 30 | 20
506444 | DRUMBO MBR | Oakville | Fab (Beam + Hanger) | PLASFAB LIMITED | 4503772145 | Fabrication | Carbon Steel | CAD | 13102 | CAD | 37644 | -24542 | Size/ Weight/ Quantity Underestimated | 2021-10-20 | 2021-11-28 | 2022-04-08 | 2021-11-10 | 2022-04-04 | 2022-01-11 | 2021-11-17 | 2022-04-11 | 2022-02-02 | 2022-05-23 | 2022-03-29 | 55 | 12 | 134
506444 | DRUMBO MBR | Oakville | Pipe Spools | NV PIPING SYSTEMS INC. | 4503706573 | Fabrication | Stainless Steel | CAD | 13102 | CAD | 9350 | 3752 | Supplier Competitions / Negotiation | 2021-10-20 | 2021-11-28 | 2021-12-20 | 2021-11-10 | 2021-12-20 | 2021-12-20 | 2021-11-17 | 2021-12-20 | 2022-02-02 | 2022-02-20 | 2022-02-11 | 9 | 12 | 22
506444 | DRUMBO MBR | Oakville | Flow Transmitter | ENDRESS + HAUSER CANADA LTD. | 4503710902 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | CAD | 5288 | USD | 10522 | -5234 | Market Impact | 2021-09-04 | 2021-12-15 | 2021-12-30 | 2021-09-25 | 2022-01-03 | 2022-01-03 | 2021-10-02 | 2022-01-03 | 2021-12-18 | 2022-03-03 | 2022-01-24 | 38 | 18 | 19
506444 | DRUMBO MBR | Oakville | VFD, DV/DT Filter | DAVIS CONTROLS LTD. | 4503710117 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | CAD | 18766 | USD | 18766 | 0 | Single Sourced | 2022-02-12 | 2021-12-24 | 2021-12-29 | 2022-02-12 | 2021-12-29 | 2021-12-29 | 2022-02-12 | 2021-12-30 | 2022-02-12 | 2022-04-03 | 2022-03-09 | 25 | 18 | 6
506476 | COCA COLA GRAND RAPIDS | Minnetonka | CITY WATER/ RO FEED/ TRICKLE (FRP) | DIAMOND FIBERGLASS | 4503406018 | Fabrication | Ele-Control Panels | USD | 117636 | USD | 81768 | 35868 | Supplier Competitions / Negotiation | 2020-04-24 | 2020-05-18 | 2020-05-20 | 2020-05-01 | 2020-05-20 | 2020-07-06 | 2020-05-04 | 2020-05-21 | 2020-09-18 | 2020-08-20 | 2020-09-03 | -14 | 12 | 3
506476 | COCA COLA GRAND RAPIDS | Minnetonka | TANKS - RO PERMEATE/CIP | Preferred Stainless Holdings | 4503406116 | Fabrication | Carbon Steel | USD | 101845 | USD | 90270 | 11575 | Frame Agreements | 2020-05-15 | 2020-05-12 | 2020-05-15 | 2020-05-20 | 2020-05-20 | 2020-07-13 | 2020-05-22 | 2020-06-08 | 2020-09-01 | 2020-09-14 | 2020-09-07 | 7 | 12 | 27
506476 | COCA COLA GRAND RAPIDS | Minnetonka | AC TOWER TANKS | Arrow Tanks | 4503405089 | Fabrication | Carbon Steel | USD | 185203 | USD | 185203 | 0 | Frame Agreements | 2020-04-24 | 2020-04-24 | 2020-05-05 | 2020-05-01 | 2020-05-17 | 2020-07-06 | 2020-05-04 | 2020-05-17 | 2020-09-18 | 2020-08-16 | 2020-09-01 | -16 | 12 | 23
506476 | COCA COLA GRAND RAPIDS | Minnetonka | UV STERILIZER, FINAL DIST, PRE PRO | AQUIONICS, INC. | 4503405111 | Electrical & Instrumentation | Ele-Control Panels | USD | 81345 | USD | 77348 | 3997 | Frame Agreements | 2020-04-24 | 2020-05-07 | 2020-05-10 | 2020-05-01 | 2020-05-19 | 2020-07-06 | 2020-05-04 | 2020-05-19 | 2020-09-18 | 2020-08-25 | 2020-09-01 | -7 | 18 | 12
506476 | COCA COLA GRAND RAPIDS | Minnetonka | PUMPS - DIST/RO/CITY WATER | ALFA LAVAL | 4503402429 | Rotating Equipment | Carbon Steel | USD | 55791 | USD | 23256 | 32535 | Supplier Competitions / Negotiation | 2020-05-04 | 2020-05-04 | 2020-05-12 | 2020-05-07 | 2020-05-08 | 2020-06-26 | 2020-05-12 | 2020-05-08 | 2020-08-18 | 2020-08-14 | 2020-08-16 | -2 | 30 | 4
506476 | COCA COLA GRAND RAPIDS | Minnetonka | PUMPS CIP/DISTR PUMP | ALFA LAVAL | 4503413904 | Rotating Equipment | Metal Isolation Valves | USD | 46535 | USD | 46535 | 0 | Frame Agreements | 2020-06-01 | 2020-06-01 | 2020-06-05 | 2020-05-07 | 2020-06-05 | 2020-06-27 | 2020-05-12 | 2020-06-09 | 2020-08-18 | 2020-08-11 | 2020-08-14 | -3 | 30 | 8
506476 | COCA COLA GRAND RAPIDS | Minnetonka | Electrical Panels | BW Systems | 4503437326 | Electrical & Instrumentation | Ele-Electrical Others | USD | 26995 | USD | 98264 | -71269 | Not included in Proposal / RFQ | 2020-07-01 | 2020-07-24 | 2020-07-24 | 2020-07-02 | 2020-07-30 | 2020-08-09 | 2020-07-02 | 2020-07-30 | 2020-09-18 | 2020-09-03 | 2020-09-10 | -7 | 18 | 6
506476 | COCA COLA GRAND RAPIDS | Minnetonka | MCE | BW Systems | 4503410526 | Electrical & Instrumentation | Ele-Control Panels | USD | 123005 | USD | 123005 | 0 | Design Optimizations | 2020-05-18 | 2020-05-18 | 2020-05-26 | 2020-05-23 | 2020-05-28 | 2020-07-11 | 2020-06-04 | 2020-06-02 | 2020-09-03 | 2020-08-25 | 2020-08-29 | -4 | 18 | 15
506476 | COCA COLA GRAND RAPIDS | Minnetonka | TEKLEEN | TEKLEEN | 4503401822 | Flow Control | Ele-Control Panels | USD | 17100 | USD | 17100 | 0 | Design Optimizations | 2020-03-23 | 2020-03-23 | 2020-03-23 | 2020-05-11 | 2020-05-09 | 2020-05-02 | 2020-05-11 | 2020-05-11 | 2020-06-11 | 2020-06-08 | 2020-06-09 | -1 | 12 | 49
506476 | COCA COLA GRAND RAPIDS | Minnetonka | SS FRAMES 506476A/F/G/H | R&R Metalworks | 4503436317 | Fabrication | Carbon Steel | USD | 8827 | USD | 58280 | -49453 | Single Sourced | 2020-07-21 | 2020-07-21 | 2020-07-30 | 2020-07-24 | 2020-07-29 | 2020-08-04 | 2020-07-24 | 2020-07-29 | 2020-08-17 | 2020-08-19 | 2020-08-18 | 1 | 12 | 8
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | MCC's+VFDs | GRAYBAR CANADA | 4503447536 | Electrical & Instrumentation | Metal Isolation Valves | USD | 386053 | CAD | 258750 | 127303 | Design Optimizations | 2020-08-19 | 2020-08-19 | 2020-08-19 | 2020-08-19 | 2020-08-18 | 2020-10-20 | 2020-08-21 | 2020-08-19 | 2020-12-15 | 2020-12-23 | 2020-12-19 | 4 | 18 | 0
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Permate Pumps | BOERGER, INC | 4503457373 | Rotating Equipment | Centrifugal Pumps | USD | 112543 | USD | 96000 | 16543 | Supplier Competitions / Negotiation | 2020-08-27 | 2020-09-04 | 2020-09-04 | 2020-08-28 | 2020-09-04 | 2020-10-06 | 2020-09-08 | 2020-09-11 | 2020-11-15 | 2020-11-16 | 2020-11-15 | 1 | 30 | 7
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Blower | AERZEN CANADA INC. | 4503457380 | Rotating Equipment | Ele-Control Panels | USD | 99778 | CAD | 100812 | -1034 | Estimate Without Market Reference(No Quote) | 2020-08-27 | 2020-09-03 | 2020-09-03 | 2020-08-28 | 2020-09-03 | 2020-10-12 | 2020-09-03 | 2020-09-11 | 2020-11-15 | 2020-11-27 | 2020-11-21 | 6 | 30 | 8
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Internal Recirculation pumps & Feed Pumps,Anoxic/Anaerobic/Deoxy Mixers | SULZER PUMPS (CANADA) INC. | 4503456864 | Rotating Equipment | Chem. Feed Skids (TurnKey) | USD | 150436 | CAD | 127907 | 22529 | Frame Agreements | 2020-08-27 | 2020-09-03 | 2020-09-03 | 2020-08-28 | 2020-09-03 | 2020-10-14 | 2020-08-31 | 2020-09-10 | 2020-11-15 | 2020-12-01 | 2020-11-23 | 8 | 30 | 7
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503476167 | Electrical & Instrumentation | Ele-Control Panels | USD | 99881 | CAD | 68145 | 31736 | Design Optimizations | 2020-08-27 | 2020-10-12 | 2020-10-19 | 2020-08-28 | 2020-10-18 | 2020-10-21 | 2020-09-10 | 2020-10-20 | 2020-11-15 | 2020-12-15 | 2020-11-30 | 15 | 18 | 8
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Membrane Tank Covers | PRECISIONEERING | 4503467016 | Fabrication | Metal Isolation Valves | USD | 80000 | CAD | 67557 | 12443 | Supplier Competitions / Negotiation | 2020-08-27 | 2020-09-16 | 2020-09-16 | 2020-08-28 | 2020-10-15 | 2020-10-06 | 2020-09-08 | 2020-10-01 | 2020-11-15 | 2020-11-10 | 2020-11-12 | -2 | 12 | 15
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Piping -Stainless Steel (316 & 304 spool fabrication) | NV PIPING SYSTEMS INC. | 4503468359 | Fabrication | Stainless Steel | USD | 76773 | CAD | 30904 | 45869 | Frame Agreements | 2020-08-27 | 2020-09-26 | 2020-09-30 | 2020-08-28 | 2020-10-01 | 2020-10-06 | 2020-09-17 | 2020-10-05 | 2020-11-15 | 2020-11-16 | 2020-11-15 | 1 | 12 | 9
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | DO Probe/PH Meter/ORP | Hach Sales & Service Canada Ltd. | 4503480611 | Electrical & Instrumentation | Carbon Steel | USD | 23233 | CAD | 8185 | 15048 | Design Optimizations | 2020-09-02 | 2020-09-02 | 2020-09-02 | 2020-09-02 | 2020-09-14 | 2020-10-10 | 2020-09-10 | 2020-09-23 | 2020-11-15 | 2020-11-18 | 2020-11-16 | 2 | 18 | 21
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Flow Transmitter /Level Transmitter/Temperature Transmitter | ENDRESS & HAUSER | 4503461817 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 12000 | USD | 19889 | -7889 | Market Impact | 2020-09-02 | 2020-09-16 | 2020-09-16 | 2020-09-02 | 2020-10-20 | 2020-10-09 | 2020-09-10 | 2020-10-21 | 2020-11-15 | 2020-11-09 | 2020-11-12 | -3 | 18 | 35
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Membrane Lifting Module | 3D MECHANICAL | 4503484199 | Fabrication | Platform & Module | USD | 49329 | CAD | 79160 | -29831 | Not included in Proposal / RFQ | 2020-08-27 | 2020-10-18 | 2020-10-21 | 2020-08-28 | 2020-11-02 | 2020-10-25 | 2020-09-15 | 2020-11-04 | 2020-11-15 | 2020-12-23 | 2020-12-04 | 19 | 12 | 17
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | WAS Pumps | SEEPEX | 4503459564 | Rotating Equipment | Centrifugal Pumps | USD | 33340 | USD | 19050 | 14290 | Frame Agreements | 2020-08-27 | 2020-09-03 | 2020-09-03 | 2020-08-28 | 2020-09-03 | 2020-10-08 | 2020-09-04 | 2020-09-16 | 2020-11-15 | 2020-11-19 | 2020-11-17 | 2 | 30 | 13
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Butterfly Valves | BRAY CONTROLS CANADA LTD. | 4503461822 | Flow Control | Metal Isolation Valves | USD | 9608 | USD | 13552 | -3944 | Proposed Supplier Incapable Of Executing | 2020-09-02 | 2020-09-02 | 2020-09-02 | 2020-09-02 | 2020-09-23 | 2020-10-09 | 2020-09-09 | 2020-09-24 | 2020-11-15 | 2020-10-19 | 2020-11-01 | -13 | 12 | 22
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Knife gate valve | WOLSELEY INDUSTRIAL CANADA INC | 4503463475 | Flow Control | Metal Isolation Valves | USD | 14295 | CAD | 6257 | 8038 | Supplier Competitions / Negotiation | 2020-09-02 | 2020-09-18 | 2020-09-18 | 2020-09-02 | 2020-09-18 | 2020-10-09 | 2020-09-09 | 2020-09-24 | 2020-11-15 | 2020-10-19 | 2020-11-01 | -13 | 12 | 6
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Air Compressor | Compressor Science Inc. | 4503472972 | Rotating Equipment | Vapor Compressor | USD | 22815 | USD | 24258 | -1443 | Single Sourced | 2020-08-27 | 2020-09-14 | 2020-09-14 | 2020-08-28 | 2020-10-13 | 2020-10-07 | 2020-09-03 | 2020-10-14 | 2020-11-15 | 2020-11-18 | 2020-11-16 | 2 | 30 | 30
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Diffuser | ENVIRONMENTAL DYNAMICS | 4503457452 | Flow Control | Centrifugal Pumps | USD | 22055 | USD | 21080 | 975 | Frame Agreements | 2020-08-27 | 2020-09-03 | 2020-09-03 | 2020-08-28 | 2020-09-02 | 2020-10-10 | 2020-09-10 | 2020-09-10 | 2020-11-15 | 2020-11-24 | 2020-11-19 | 5 | 12 | 7
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Backpulse Tank | ACO CONTAINER SYSTEMS LTD. | 4503458251 | Flow Control | Metal Isolation Valves | USD | 17841 | CAD | 17250 | 591 | Frame Agreements | 2020-08-27 | 2020-09-03 | 2020-09-03 | 2020-08-28 | 2020-09-03 | 2020-10-06 | 2020-09-08 | 2020-09-15 | 2020-11-15 | 2020-11-09 | 2020-11-12 | -3 | 12 | 12
506489 | Liberty Hill WWTP-OVIVO RETROFIT | Oakville | Chemical dosing system | Prominent Fluid Controls Inc. | 4503468958 | Rotating Equipment | Dosing Pump | USD | 15762 | CAD | 24564 | -8802 | Estimate Without Market Reference(No Quote) | 2020-08-27 | 2020-09-03 | 2020-09-03 | 2020-08-28 | 2020-09-25 | 2020-10-11 | 2020-09-11 | 2020-10-06 | 2020-11-15 | 2020-11-25 | 2020-11-20 | 5 | 30 | 33
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | Pumps | SULZER PUMPS (CANADA) INC. | 4503432819 | Rotating Equipment | Centrifugal Pumps | CAD | 71429 | CAD | 78388 | -6959 | Size/ Weight/ Quantity Underestimated | 2020-04-30 | 2020-08-05 | 2020-06-21 | 2020-05-21 | 2020-06-21 | 2020-08-05 | 2020-05-28 | 2020-07-21 | 2020-09-10 | 2020-11-10 | 2020-10-10 | 31 | 30 | -15
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | Pumps | SULZER PUMPS (CANADA) INC. | 4503440019 | Rotating Equipment | Centrifugal Pumps | CAD | 11927 | CAD | 11927 | 0 | Size/ Weight/ Quantity Underestimated | 2020-04-30 | 2020-08-12 | 2020-08-12 | 2020-05-21 | 2020-08-12 | 2020-08-12 | 2020-05-28 | 2020-08-05 | 2020-09-10 | 2020-11-25 | 2020-10-18 | 38 | 30 | -7
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | Pumps | BOERGER, INC | 4503441744 | Rotating Equipment | Centrifugal Pumps | CAD | 30311 | USD | 30926 | -615 | Estimate Without Market Reference(No Quote) | 2020-04-30 | 2020-07-24 | 2020-07-24 | 2020-05-21 | 2020-07-24 | 2020-07-24 | 2020-05-28 | 2020-08-09 | 2020-09-10 | 2020-10-18 | 2020-09-29 | 19 | 30 | 16
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | Pumps | WATSON MARLOW INC | 4503443983 | Rotating Equipment | Centrifugal Pumps | CAD | 44389 | CAD | 44389 | 0 | Size/ Weight/ Quantity Underestimated | 2020-04-30 | 2020-07-30 | 2020-07-30 | 2020-05-21 | 2020-07-30 | 2020-07-30 | 2020-05-28 | 2020-08-12 | 2020-09-10 | 2020-10-29 | 2020-10-04 | 25 | 30 | 13
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | SCADA (IPC) | SAK Data | 4503453502 | Electrical & Instrumentation | Carbon Steel | CAD | 12725 | CAD | 12725 | 0 | Single Sourced | 2020-06-03 | 2020-08-08 | 2020-08-08 | 2020-06-24 | 2020-08-08 | 2020-08-08 | 2020-07-01 | 2020-09-03 | 2020-10-14 | 2020-10-02 | 2020-10-08 | -6 | 18 | 26
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | HP Servers | CDW CANADA INC. | 4503460203 | Electrical & Instrumentation | Metal Isolation Valves | CAD | 18577 | CAD | 18577 | 0 | Market Impact | 2020-06-03 | 2020-08-08 | 2020-08-08 | 2020-06-24 | 2020-08-08 | 2020-08-08 | 2020-07-01 | 2020-09-17 | 2020-10-14 | 2020-09-28 | 2020-10-06 | -8 | 18 | 40
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | Control Panel, VFD, Electrical Disconnect | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503443691 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 26570 | CAD | 298160 | -271590 | Estimate Without Market Reference(No Quote) | 2020-08-31 | 2020-10-03 | 2020-07-16 | 2020-09-21 | 2020-10-03 | 2020-10-03 | 2020-09-28 | 2020-08-11 | 2020-12-21 | 2020-10-08 | 2020-11-14 | -37 | 18 | -53
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | Instrumentation | ENDRESS + HAUSER CANADA LTD. | 4503454178 | Electrical & Instrumentation | Inst-Instrumentation Others | CAD | 10804 | USD | 11023 | -219 | Not included in Proposal / RFQ | 2020-06-03 | 2020-08-08 | 2020-08-08 | 2020-06-24 | 2020-08-08 | 2020-08-08 | 2020-07-01 | 2020-09-04 | 2020-10-14 | 2020-09-29 | 2020-10-06 | -7 | 18 | 27
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | Blowers | AERZEN CANADA INC. | 4503432934 | Rotating Equipment | Blowers & Fans | CAD | 61740 | CAD | 74910 | -13170 | Proposed Supplier Incapable Of Executing | 2020-07-01 | 2020-08-22 | 2020-08-22 | 2020-07-22 | 2020-08-22 | 2020-08-22 | 2020-07-29 | 2020-07-21 | 2020-10-14 | 2020-10-13 | 2020-10-13 | 0 | 30 | -32
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | Valves | CHAMPION VALVES INC | 4503447041 | Flow Control | Metal Isolation Valves | CAD | 6356 | USD | 8295 | -1939 | Not included in Proposal / RFQ | 2020-06-03 | 2020-08-08 | 2020-08-08 | 2020-06-24 | 2020-08-08 | 2020-08-08 | 2020-07-01 | 2020-08-20 | 2020-10-14 | 2020-09-23 | 2020-10-03 | -10 | 12 | 12
506499 | MISE À NIVEAU DE LA STATION D’ÉPURATION ROCK ISLAND (VILLE DE STANSTEAD) | Oakville | Fabrication (Frame, Beam, Bracket, Hanger) | 3D MECHANICAL | 4503454218 | Fabrication | Metal Isolation Valves | CAD | 7182 | CAD | 5400 | 1782 | Design Optimizations | 2020-06-24 | 2020-08-19 | 2020-08-19 | 2020-07-15 | 2020-08-19 | 2020-08-19 | 2020-07-22 | 2020-09-04 | 2020-10-14 | 2020-10-02 | 2020-10-08 | -6 | 12 | 16
506505 | Babbitt MBR | Oakville | Permeate Pumps | BOERGER, INC | 4503690887 | Rotating Equipment | PD Pumps | USD | 32063 | USD | 31228 | 835 | Supplier Competitions / Negotiation | 2020-12-22 | 2021-10-13 | 2021-10-20 | 2021-01-12 | 2021-11-22 | 2021-11-22 | 2021-01-19 | 2021-11-23 | 2021-04-20 | 2022-06-22 | 2021-11-20 | 214 | 30 | 41
506505 | Babbitt MBR | Oakville | RAS/WAS/Drain Pumps | FLOWSERVE INC. | 4503690859 | Rotating Equipment | Centrifugal Pumps | USD | 36463 | USD | 41784 | -5321 | Market Impact | 2020-11-10 | 2021-10-13 | 2021-10-15 | 2020-12-01 | 2021-11-15 | 2021-11-21 | 2020-12-08 | 2021-11-21 | 2021-04-20 | 2022-06-20 | 2021-11-19 | 213 | 30 | 39
506505 | Babbitt MBR | Oakville | Chemical Panels | PROMINENT FLUID CONTROLS LTD. | 4503691016 | Rotating Equipment | Dosing Pump | USD | 27119 | CAD | 25862 | 1257 | Supplier Competitions / Negotiation | 2021-01-05 | 2021-10-13 | 2021-10-20 | 2021-01-26 | 2021-11-12 | 2021-11-16 | 2021-02-02 | 2021-11-22 | 2021-04-20 | 2022-05-01 | 2021-10-25 | 188 | 30 | 40
506505 | Babbitt MBR | Oakville | Plug Valves | FLOVAL EQUIPMENT LIMITED | 4503690976 | Flow Control | Metal Control Valves | USD | 13389 | CAD | 13389 | 0 | Proposed Supplier Incapable Of Executing | 2021-12-25 | 2021-10-26 | 2021-11-03 | 2021-12-25 | 2021-11-17 | 2021-11-17 | 2021-12-25 | 2021-11-23 | 2021-12-25 | 2022-02-23 | 2022-01-24 | 30 | 12 | 28
506505 | Babbitt MBR | Oakville | Butterfly Valves | BRAY CONTROLS CANADA LTD. | 4503690514 | Flow Control | Metal Control Valves | USD | 8399 | USD | 8399 | 0 | Supplier Competitions / Negotiation | 2021-12-20 | 2021-10-26 | 2021-11-03 | 2021-12-20 | 2021-11-16 | 2021-11-16 | 2021-12-20 | 2021-11-21 | 2021-12-20 | 2022-02-13 | 2022-01-16 | 28 | 12 | 26
506505 | Babbitt MBR | Oakville | Process & Membrane Blower | Great Northern Environment | 4503687535 | Rotating Equipment | Blowers & Fans | USD | 63093 | USD | 77641 | -14548 | Size/ Weight/ Quantity Underestimated | 2020-11-17 | 2021-10-13 | 2021-10-13 | 2020-12-08 | 2021-11-11 | 2021-11-12 | 2020-12-15 | 2021-11-16 | 2021-04-20 | 2022-05-10 | 2021-10-29 | 193 | 30 | 34
506505 | Babbitt MBR | Oakville | Duty & Standby Air Compressor (Gardener Denver) | Compressor Science Inc. | 4503685030 | Rotating Equipment | Compressors | USD | 8525 | USD | 18206 | -9681 | Size/ Weight/ Quantity Underestimated | 2021-02-16 | 2021-10-13 | 2021-10-15 | 2021-03-09 | 2021-11-10 | 2021-11-10 | 2021-03-16 | 2021-11-11 | 2021-04-20 | 2021-11-11 | 2021-07-31 | 103 | 30 | 29
506505 | Babbitt MBR | Oakville | Control Panel + PLC | Machine Control Systems | 4503708623 | Electrical & Instrumentation | Ele-Control Panels | USD | 77844 | CAD | 35838 | 42006 | Supplier Competitions / Negotiation | 2020-12-15 | 2021-11-26 | 2021-12-22 | 2021-01-05 | 2021-12-22 | 2021-12-23 | 2021-01-12 | 2021-12-23 | 2021-04-20 | 2021-12-23 | 2021-08-21 | 124 | 18 | 27
506505 | Babbitt MBR | Oakville | Skids/Beam/Brackets/Supports | 3D MECHANICAL | 4503692923 | Fabrication | Carbon Steel | USD | 13488 | CAD | 21666 | -8178 | Market Impact | 2021-01-12 | 2021-11-18 | 2021-11-25 | 2021-02-02 | 2021-11-25 | 2021-11-26 | 2021-02-09 | 2021-11-26 | 2021-04-20 | 2022-02-04 | 2021-09-12 | 145 | 12 | 8
506505 | Babbitt MBR | Oakville | Anoxic Tank Mixer | SULZER PUMPS (CANADA) INC. | 4503685034 | Rotating Equipment | Mixers | USD | 12350 | CAD | 10504 | 1846 | Supplier Competitions / Negotiation | 2022-01-21 | 2021-10-13 | 2021-10-20 | 2022-01-21 | 2021-11-10 | 2021-11-10 | 2022-01-21 | 2021-11-12 | 2022-01-21 | 2022-05-02 | 2022-03-12 | 51 | 30 | 30
506505 | Babbitt MBR | Oakville | Instruments - Transmitter | ENDRESS & HAUSER | 4503690502 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 14031 | USD | 14031 | 0 | Single Sourced | 2021-12-27 | 2021-10-25 | 2021-11-02 | 2021-12-27 | 2021-11-17 | 2021-11-17 | 2021-12-27 | 2021-11-22 | 2021-12-27 | 2022-02-28 | 2022-01-27 | 32 | 18 | 28
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | FRP TANKS - CITY WATER/TRICKLE/ACT | DIAMOND FIBERGLASS | 4503399826 | Fabrication | Ele-Control Panels | USD | 108751 | USD | 56438 | 52313 | Design Optimizations | 2020-04-24 | 2020-04-24 | 2020-05-01 | 2020-05-01 | 2020-05-01 | 2020-07-06 | 2020-05-04 | 2020-05-03 | 2020-09-18 | 2020-08-09 | 2020-08-29 | -20 | 12 | 9
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | RO PERMEATE TANK | Preferred Stainless Holdings | 4503403701 | Fabrication | Centrifugal Pumps | USD | 72000 | USD | 56252 | 15748 | Supplier Competitions / Negotiation | 2020-05-13 | 2020-05-13 | 2020-04-28 | 2020-06-29 | 2020-04-26 | 2020-06-29 | 2020-06-29 | 2020-05-12 | 2020-06-29 | 2020-09-01 | 2020-08-18 | 14 | 12 | -1
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | CIP Tank | Preferred Stainless Holdings | 4503405087 | Fabrication | Carbon Steel | USD | 34688 | USD | 35778 | -1090 | Estimate Without Market Reference(No Quote) | 2020-05-13 | 2020-05-13 | 2020-05-14 | 2020-05-15 | 2020-05-14 | 2020-06-30 | 2020-05-19 | 2020-05-18 | 2020-08-17 | 2020-08-16 | 2020-08-18 | -2 | 12 | 5
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | AC PRESSURE VESSELS | Arrow Tanks | 4503403546 | Fabrication | Carbon Steel | USD | 134107 | USD | 126096 | 8011 | Frame Agreements | 2020-04-24 | 2020-04-24 | 2020-05-12 | 2020-05-01 | 2020-05-11 | 2020-07-06 | 2020-05-04 | 2020-05-13 | 2020-09-18 | 2020-07-22 | 2020-08-20 | -29 | 12 | 19
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | DEOZONATION UV | ATLANTIUM | 4503397937 | Electrical & Instrumentation | Metal Isolation Valves | USD | 116848 | USD | 78192 | 38656 | Design Optimizations | 2020-04-24 | 2020-04-17 | 2020-04-20 | 2020-05-01 | 2020-04-27 | 2020-07-03 | 2020-05-04 | 2020-04-29 | 2020-09-18 | 2020-07-19 | 2020-08-18 | -30 | 18 | 12
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | BEV RO / CITY WATER / PERMEATE PUMPS | PFC EQUIPMENT | 4503397942 | Flow Control | RO Membrane Housings | USD | 98683 | USD | 98683 | 0 | Estimate Without Market Reference(No Quote) | 2020-05-04 | 2020-04-10 | 2020-05-15 | 2020-05-07 | 2020-04-30 | 2020-06-14 | 2020-05-12 | 2020-05-30 | 2020-08-18 | 2020-07-23 | 2020-08-05 | -13 | 12 | 50
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | BEV RO PROTEC RO HOUSINTS | PROTEC ARISAWA AMERICA, INC. | 4503399845 | Flow Control | RO Membrane Housings | USD | 49950 | USD | 49950 | 0 | Specs / Requirements Misinterpreted in Proposal | 2020-05-23 | 2020-05-23 | 2020-04-30 | 2020-05-23 | 2020-04-29 | 2020-05-23 | 2020-05-23 | 2020-05-05 | 2020-05-23 | 2020-06-16 | 2020-06-04 | 12 | 12 | -18
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | CARTRIDGE FILTRATION HOUSINGS | Duncan Co. | 4503398105 | Flow Control | RO Membrane Housings | USD | 32880 | USD | 32880 | 0 | Market Impact | 2020-06-11 | 2020-06-11 | 2020-04-28 | 2020-06-11 | 2020-04-26 | 2020-06-11 | 2020-06-11 | 2020-04-28 | 2020-06-11 | 2020-07-28 | 2020-07-04 | 24 | 12 | -44
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | Electrical Panels (CIP) | PTS Products | 4503437307 | Electrical & Instrumentation | Ele-Electrical Others | USD | 87604 | USD | 99048 | -11444 | Single Sourced | 2020-07-01 | 2020-08-09 | 2020-07-27 | 2020-07-02 | 2020-07-27 | 2020-08-09 | 2020-07-02 | 2020-07-27 | 2020-09-18 | 2020-09-07 | 2020-09-12 | -5 | 18 | -13
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | Electrical MCE | WERNER ELECTRIC | 4503399748 | Electrical & Instrumentation | Ele-Electrical Others | USD | 115704 | USD | 111601 | 4103 | Frame Agreements | 2020-05-18 | 2020-04-17 | 2020-04-23 | 2020-05-23 | 2020-05-01 | 2020-06-25 | 2020-06-04 | 2020-05-03 | 2020-09-03 | 2020-08-31 | 2020-09-01 | -1 | 18 | 16
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | Electrical MCE | WERNER ELECTRIC | 4503481837 | Electrical & Instrumentation | Ele-Electrical Others | USD | 10846 | USD | 10846 | 0 | Proposed Supplier Incapable Of Executing | 2020-12-20 | 2020-12-20 | 2020-11-02 | 2020-12-20 | 2020-11-01 | 2020-12-20 | 2020-12-20 | 2020-11-01 | 2020-12-20 | 2021-02-08 | 2021-01-14 | 25 | 18 | -49
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | Electrical MCE | WERNER ELECTRIC | 4513481837 | Electrical & Instrumentation | Ele-Electrical Others | USD | 27450 | USD | 27450 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-01-27 | 2021-01-27 | 2021-01-27 | 2021-01-27 | 2021-01-27 | 2021-01-27 | 2021-01-27 | 2021-01-27 | 2021-01-27 | 2021-01-27 | 2021-01-27 | 0 | 18 | 0
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | PRE RO UV | ATLANTIUM | 4513397937 | Electrical & Instrumentation | Metal Isolation Valves | USD | 55000 | USD | 55392 | -392 | Estimate Without Market Reference(No Quote) | 2020-04-24 | 2020-07-25 | 2020-04-20 | 2020-05-01 | 2020-04-30 | 2020-07-25 | 2020-05-04 | 2020-04-30 | 2020-08-24 | 2020-10-30 | 2020-09-26 | 34 | 18 | -86
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | CHEM FEED SKIDS | WASTECH CONTROLS & ENGINEERING, INC | 4503426481 | Flow Control | Carbon Steel | USD | 91800 | USD | 119000 | -27200 | Proposed Supplier Incapable Of Executing | 2020-06-16 | 2020-06-16 | 2020-07-06 | 2020-06-23 | 2020-07-08 | 2020-07-30 | 2020-06-24 | 2020-07-08 | 2020-08-29 | 2020-09-13 | 2020-09-05 | 8 | 12 | 22
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | TEKLEEN | TEKLEEN | 4503395911 | Flow Control | Ele-Control Panels | USD | 92309 | USD | 49875 | 42434 | Supplier Competitions / Negotiation | 2020-04-17 | 2020-05-16 | 2020-04-21 | 2020-04-28 | 2020-04-28 | 2020-05-16 | 2020-04-28 | 2020-04-27 | 2020-06-15 | 2020-06-15 | 2020-06-15 | 0 | 12 | -19
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | LOOSE SHIP VORTEX FLOW METERS | MICRO-MOTION, INC | 4503439801 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 23008 | USD | 23008 | 0 | Design Optimizations | 2020-07-30 | 2020-07-30 | 2020-07-31 | 2020-07-31 | 2020-07-30 | 2020-08-15 | 2020-07-31 | 2020-08-05 | 2020-08-31 | 2020-08-31 | 2020-08-31 | 0 | 18 | 6
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | LOOSE SHIP 24VDC FLOW METERS | ENDRESS & HAUSER | 4503432281 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 6276 | USD | 6276 | 0 | Market Impact | 2020-08-04 | 2020-08-04 | 2020-07-22 | 2020-08-04 | 2020-07-21 | 2020-08-04 | 2020-08-04 | 2020-07-21 | 2020-08-04 | 2020-08-18 | 2020-08-11 | 7 | 18 | -14
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | LOOSE SHIP BTRFLY/CHECK/BALL VALVES | Duncan Co. | 4503429682 | Flow Control | Carbon Steel | USD | 20131 | USD | 20131 | 0 | Design Optimizations | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-07-09 | 2020-07-07 | 2020-07-21 | 2020-07-14 | 2020-07-08 | 2020-08-05 | 2020-08-05 | 2020-08-05 | 0 | 12 | -1
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | LOOSE SHIP CONSERVATION VALVE | Duncan Co. | 4503431027 | Flow Control | Carbon Steel | USD | 5501 | USD | 5501 | 0 | Frame Agreements | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-07-16 | 2020-07-16 | 2020-08-16 | 2020-08-16 | 2020-07-16 | 2020-08-16 | 2020-09-18 | 2020-09-01 | 17 | 12 | 1
506517 | PBS CHEVERLY LTS UPGRADE | Minnetonka | LS - PLATFORM | WOLSELEY INDUSTRIAL GROUP - USA | 4503553433 | Fabrication | Platform & Module | USD | 6909 | USD | 6909 | 0 | Single Sourced | 2021-03-11 | 2021-03-11 | 2021-03-11 | 2021-03-16 | 2021-03-15 | 2021-03-31 | 2021-03-17 | 2021-03-17 | 2021-04-20 | 2021-04-20 | 2021-04-20 | 0 | 12 | 6
506527 | Xcel Cherokee WW | Oakville | CCRO System (SITE) | DESALITECH, INC | 4503413593 | Fabrication | Carbon Steel | USD | 2680180 | USD | 2511918 | 168262 | Supplier Competitions / Negotiation | 2020-05-15 | 2020-06-04 | 2020-06-04 | 2020-06-26 | 2020-06-08 | 2020-10-16 | 2020-07-10 | 2020-06-11 | 2021-03-19 | 2020-06-11 | 2020-10-29 | -140 | 12 | 7
506527 | Xcel Cherokee WW | Oakville | Change Order for PLC Redud and CIP Downcomers | DESALITECH, INC | 4503527183 | Fabrication | Carbon Steel | USD | 82390 | USD | 82390 | 0 | Size/ Weight/ Quantity Underestimated | 2021-01-28 | 2020-11-16 | 2020-12-16 | 2021-01-28 | 2021-01-30 | 2021-01-28 | 2021-01-28 | 2021-02-01 | 2021-01-28 | 2021-04-12 | 2021-03-06 | 37 | 12 | 77
506527 | Xcel Cherokee WW | Oakville | Chem Feed Skids (SITE) | PROMINENT FLUID CONTROLS LTD. | 4503460213 | Rotating Equipment | Chem. Feed Skids (TurnKey) | USD | 62800 | USD | 62682 | 118 | Design Optimizations | 2020-07-01 | 2020-07-24 | 2020-09-15 | 2020-07-29 | 2020-09-10 | 2020-08-12 | 2020-08-12 | 2020-09-16 | 2020-11-04 | 2021-03-04 | 2021-01-03 | 60 | 30 | 54
506527 | Xcel Cherokee WW | Oakville | Chem Feed Skids (SITE) | GRUNDFOS PUMPS CORPORATION | 4503460222 | Rotating Equipment | Chem. Feed Skids (TurnKey) | USD | 127000 | USD | 125644 | 1356 | Design Optimizations | 2020-11-13 | 2020-07-31 | 2020-09-11 | 2020-11-13 | 2020-09-10 | 2020-11-13 | 2020-11-13 | 2020-09-16 | 2020-11-13 | 2021-02-26 | 2021-01-04 | 53 | 30 | 47
506527 | Xcel Cherokee WW | Oakville | Horizontal Centrifugal Pump - Backwash Return Pump (G) | GOULDS PUMPS | 4503441179 | Rotating Equipment | Centrifugal Pumps | USD | 85919 | USD | 90444 | -4525 | Market Impact | 2020-07-01 | 2020-07-10 | 2020-08-06 | 2020-07-29 | 2020-08-06 | 2020-08-07 | 2020-08-12 | 2020-08-08 | 2020-11-04 | 2020-12-19 | 2020-11-26 | 23 | 30 | 29
506527 | Xcel Cherokee WW | Oakville | VFDs + Adder (Rockwell Automation/Allen-Bradley) (SITE) | ENGINEERING ELECTRIC CONTROLS | 4503498828 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 63859 | CAD | 59755 | 4104 | Design Optimizations | 2020-07-15 | 2020-07-08 | 2020-12-04 | 2020-08-12 | 2020-12-03 | 2020-11-21 | 2020-08-26 | 2020-12-07 | 2021-01-27 | 2021-04-07 | 2021-03-03 | 35 | 18 | 152
506527 | Xcel Cherokee WW | Oakville | Tanks - FRP (SITE) | DIAMOND FIBERGLASS | 4503462500 | Fabrication | Ele-Control Panels | USD | 269331 | USD | 263270 | 6061 | Supplier Competitions / Negotiation | 2020-06-01 | 2020-06-10 | 2020-09-16 | 2020-06-29 | 2020-09-06 | 2020-08-19 | 2020-07-13 | 2020-09-15 | 2020-12-28 | 2021-01-26 | 2021-01-11 | 15 | 12 | 97
506527 | Xcel Cherokee WW | Oakville | Soda Ash Silo - Complete Package (SITE) | Sodimate USA | 4503457496 | Fabrication | Ele-Control Panels | USD | 426250 | USD | 446625 | -20375 | Proposed Supplier Incapable Of Executing | 2020-06-01 | 2020-06-18 | 2020-08-21 | 2020-07-13 | 2020-09-08 | 2020-08-14 | 2020-07-27 | 2020-09-10 | 2020-12-14 | 2021-02-23 | 2021-01-18 | 36 | 12 | 84
506527 | Xcel Cherokee WW | Oakville | Instrumentation (G) | LAKESIDE PROCESS CONTROLS LTD. | 4503465775 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 30971 | USD | 113289 | -82318 | Specs / Requirements Misinterpreted in Proposal | 2020-07-01 | 2020-09-21 | 2020-09-29 | 2020-07-29 | 2020-09-23 | 2020-09-16 | 2020-08-12 | 2020-09-26 | 2020-12-02 | 2020-11-09 | 2020-11-20 | -11 | 18 | 5
506527 | Xcel Cherokee WW | Oakville | Instrument Enclosures (G) | LAKESIDE PROCESS CONTROLS LTD. | 4503501741 | Electrical & Instrumentation | Metal Isolation Valves | USD | 7855 | USD | 7878 | -23 | Specs / Requirements Misinterpreted in Proposal | 2021-01-01 | 2020-12-01 | 2020-12-11 | 2021-01-01 | 2020-12-03 | 2021-01-01 | 2021-01-01 | 2020-12-09 | 2021-01-01 | 2021-02-01 | 2021-01-16 | 16 | 18 | 8
506527 | Xcel Cherokee WW | Oakville | Instrumentation Pressure Gauges (G) | CONVAL PROCESS SOLUTIONS INC | 4503464374 | Electrical & Instrumentation | Inst-Instrumentation Accessories | USD | 17600 | USD | 5197 | 12403 | Supplier Competitions / Negotiation | 2020-07-01 | 2020-09-21 | 2020-09-23 | 2020-07-29 | 2020-09-22 | 2020-09-16 | 2020-08-12 | 2020-09-22 | 2020-12-02 | 2020-11-10 | 2020-11-21 | -11 | 18 | 1
506527 | Xcel Cherokee WW | Oakville | Instrumentation Pressure Switches (Guelph) | WAJAX INDUSTRIAL COMPONENTS | 4503476343 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 7043 | CAD | 5212 | 1831 | Supplier Competitions / Negotiation | 2020-09-27 | 2020-07-31 | 2020-10-21 | 2020-09-27 | 2020-10-21 | 2020-09-27 | 2020-09-27 | 2020-10-21 | 2020-09-27 | 2020-11-25 | 2020-10-26 | 30 | 18 | 82
506527 | Xcel Cherokee WW | Oakville | Auto Control valves & Control Components (G) | LAKESIDE PROCESS CONTROLS LTD. | 4503472447 | Flow Control | Ele-Control Panels | USD | 25806 | USD | 61133 | -35327 | Proposed Supplier Incapable Of Executing | 2020-07-01 | 2020-07-28 | 2020-09-29 | 2020-07-29 | 2020-09-25 | 2020-08-31 | 2020-08-12 | 2020-09-25 | 2020-11-04 | 2020-11-28 | 2020-11-16 | 12 | 12 | 59
506527 | Xcel Cherokee WW | Oakville | Manual Plug Valves (G) | SYLVAN AUTOMATION LTD | 4503487427 | Flow Control | Metal Isolation Valves | USD | 20000 | USD | 17398 | 2602 | Supplier Competitions / Negotiation | 2020-10-25 | 2020-07-31 | 2020-11-04 | 2020-10-25 | 2020-11-04 | 2020-10-25 | 2020-10-25 | 2020-11-10 | 2020-10-25 | 2021-01-19 | 2020-12-07 | 43 | 12 | 102
506527 | Xcel Cherokee WW | Oakville | Actuated Valves | BRAY CONTROLS CANADA LTD. | 4503475458 | Flow Control | Metal Isolation Valves | USD | 65096 | USD | 60388 | 4708 | Design Optimizations | 2020-07-01 | 2020-08-07 | 2020-10-16 | 2020-07-29 | 2020-10-11 | 2020-08-31 | 2020-08-12 | 2020-10-17 | 2020-11-04 | 2021-01-24 | 2020-12-14 | 41 | 12 | 71
506527 | Xcel Cherokee WW | Oakville | Fabrication - Skid/Frame CS (G) | 3D MECHANICAL | 4503479330 | Fabrication | Skid Assembly Outsourced | USD | 78848 | USD | 41961 | 36887 | Supplier Competitions / Negotiation | 2020-08-14 | 2020-08-19 | 2020-08-26 | 2020-09-04 | 2020-10-15 | 2020-10-21 | 2020-09-18 | 2020-10-25 | 2020-12-28 | 2020-12-14 | 2020-12-21 | -7 | 12 | 67
506527 | Xcel Cherokee WW | Oakville | Densadeg Fab (SITE) | SOFATEC | 4503500775 | Fabrication | Carbon Steel | USD | 369195 | USD | 253157 | 116038 | Supplier Competitions / Negotiation | 2020-07-01 | 2020-08-28 | 2020-12-01 | 2020-07-29 | 2020-12-08 | 2020-11-15 | 2020-08-12 | 2020-12-08 | 2020-12-02 | 2021-04-01 | 2021-01-31 | 60 | 12 | 102
506527 | Xcel Cherokee WW | Oakville | Densadeg Scraper Drive | DBS MANUFACTURING INC. | 4503514214 | Electrical & Instrumentation | Carbon Steel | USD | 10000 | USD | 10555 | -555 | Single Sourced | 2020-07-07 | 2020-07-23 | 2021-01-12 | 2020-11-25 | 2021-01-07 | 2020-11-25 | 2020-09-09 | 2021-01-11 | 2020-11-25 | 2021-04-16 | 2021-02-04 | 71 | 18 | 172
506527 | Xcel Cherokee WW | Oakville | Densadeg Agitator (SITE) | SPX FLOW INC | 4503500620 | Rotating Equipment | Carbon Steel | USD | 13414 | USD | 16684 | -3270 | Estimate Without Market Reference(No Quote) | 2020-11-22 | 2020-07-28 | 2020-12-01 | 2020-08-25 | 2020-12-09 | 2020-09-02 | 2020-09-09 | 2020-12-09 | 2020-11-22 | 2021-03-20 | 2021-01-20 | 59 | 30 | 134
506527 | Xcel Cherokee WW | Oakville | Pressure Vessel Internals(G) | PANDA PIPING LTD | 4503450594 | Fabrication | Carbon Steel | USD | 53340 | CAD | 65269 | -11929 | Market Impact | 2020-09-19 | 2020-07-31 | 2020-08-07 | 2020-09-19 | 2020-08-19 | 2020-09-19 | 2020-09-19 | 2020-08-29 | 2020-09-19 | 2020-11-08 | 2020-10-14 | 25 | 12 | 29
506527 | Xcel Cherokee WW | Oakville | Coating and Painting (G) | BRANT CORROSION CONTROL, | 4503460142 | Fabrication | Metal Isolation Valves | USD | 22782 | USD | 38094 | -15312 | Not included in Proposal / RFQ | 2020-08-25 | 2020-07-31 | 2020-07-16 | 2020-08-25 | 2020-08-18 | 2020-08-25 | 2020-08-25 | 2020-09-13 | 2020-08-25 | 2020-10-04 | 2020-09-14 | 20 | 12 | 44
506527 | Xcel Cherokee WW | Oakville | MMF Pressure Vessels (G) | LESENA STEEL DIVISION | 4503440676 | Fabrication | Carbon Steel | USD | 98000 | USD | 98541 | -541 | Not included in Proposal / RFQ | 2020-09-04 | 2020-07-31 | 2020-07-31 | 2020-09-04 | 2020-06-30 | 2020-09-04 | 2020-09-04 | 2020-08-04 | 2020-09-04 | 2020-11-10 | 2020-10-07 | 34 | 12 | 4
506527 | Xcel Cherokee WW | Guelph | Progressive Cavity Pumps (G) | SEEPEX | 4503473003 | Rotating Equipment | Centrifugal Pumps | USD | 18835 | USD | 19674 | -839 | Estimate Without Market Reference(No Quote) | 2020-07-01 | 2020-07-23 | 2020-12-01 | 2020-07-29 | 2020-10-02 | 2020-09-15 | 2020-08-12 | 2020-10-14 | 2020-11-04 | 2020-12-01 | 2020-11-17 | 14 | 30 | 83
506527 | Xcel Cherokee WW | Oakville | Blowers & Silencers (SITE) | AERZEN CANADA INC. | 4503450608 | Rotating Equipment | Blowers & Fans | USD | 14596 | CAD | 13882 | 714 | Supplier Competitions / Negotiation | 2020-07-01 | 2020-07-10 | 2020-08-14 | 2020-07-29 | 2020-08-28 | 2020-07-31 | 2020-08-12 | 2020-08-28 | 2020-12-16 | 2021-02-21 | 2021-01-18 | 34 | 30 | 49
506527 | Xcel Cherokee WW | Oakville | Electrical Panels (G) | MACHINE CONTROL SYSTEMS | 4503507704 | Electrical & Instrumentation | Ele-Electrical Others | USD | 27924 | USD | 13435 | 14489 | Supplier Competitions / Negotiation | 2020-07-01 | 2020-10-10 | 2020-12-10 | 2020-07-29 | 2020-12-16 | 2020-09-25 | 2020-08-12 | 2020-12-21 | 2020-10-21 | 2020-12-21 | 2020-11-20 | 31 | 18 | 72
506527 | Xcel Cherokee WW | Oakville | Fabrication - SS Piping (G) | NV PIPING SYSTEMS INC. | 4503486594 | Fabrication | Carbon Steel | USD | 108527 | CAD | 75935 | 32592 | Supplier Competitions / Negotiation | 2020-08-14 | 2020-08-19 | 2020-11-10 | 2020-09-04 | 2020-11-02 | 2020-10-24 | 2020-09-18 | 2020-11-09 | 2020-12-28 | 2021-01-04 | 2020-12-31 | 4 | 12 | 82
506527 | Xcel Cherokee WW | Oakville | RO Pump (G) | GOULDS PUMPS | 4503460546 | Rotating Equipment | Centrifugal Pumps | USD | 26875 | USD | 27618 | -743 | Proposed Supplier Incapable Of Executing | 2020-09-01 | 2020-07-31 | 2020-09-04 | 2020-09-04 | 2020-09-11 | 2020-10-30 | 2020-09-11 | 2020-09-18 | 2021-01-15 | 2021-01-29 | 2021-01-22 | 7 | 30 | 49
506535 | Pooler 6.223 MGD Expansion | Oakville | Permeate PUMP-PD,50HP,480/60/3,FL776,BRG | BOERGER LLC | 4503840445 | Rotating Equipment | PD Pumps | USD | 259908 | USD | 199350 | 60558 | Supplier Competitions / Negotiation | 2022-07-25 | 2022-11-16 | 2022-08-05 | 2022-07-25 | 2022-08-05 | 2022-11-16 | 2022-07-25 | 2022-08-09 | 2023-02-24 | 2023-03-10 | 2023-03-03 | 7 | 30 | -99
506535 | Pooler 6.223 MGD Expansion | Oakville | Membrane air scour and Process blowers,ARZ | AERZEN CANADA INC | 4503840565 | Rotating Equipment | Blowers & Fans | USD | 254409 | CAD | 247315 | 7094 | Design Optimizations | 2022-07-25 | 2022-11-21 | 2022-08-01 | 2022-07-25 | 2022-08-08 | 2022-11-21 | 2022-07-25 | 2022-08-08 | 2023-02-24 | 2023-03-20 | 2023-03-08 | 12 | 30 | -105
506535 | Pooler 6.223 MGD Expansion | Oakville | RAS Pumps, Foam Tank, Anoxic, Anaerobic Pump, GR | GRUNDFOS PUMPS CORPORATION | 4503842438 | Rotating Equipment | Others | USD | 200324 | USD | 171482 | 28842 | Frame Agreements | 2022-07-25 | 2022-11-11 | 2022-08-10 | 2022-08-05 | 2022-08-10 | 2022-11-11 | 2022-08-08 | 2022-08-24 | 2023-02-24 | 2023-02-28 | 2023-02-26 | 2 | 30 | -79
506535 | Pooler 6.223 MGD Expansion | Oakville | DIFFUSER-BUBBLE,FINE,PVC,SANITAIRE | Xylem Water Solutions USA Inc | 4503845233 | Flow Control | Other | USD | 137177 | USD | 137000 | 177 | Supplier Competitions / Negotiation | 2022-07-25 | 2022-12-02 | 2022-08-02 | 2022-08-10 | 2022-12-02 | 2022-12-02 | 2022-08-15 | 2022-08-25 | 2023-02-24 | 2023-04-11 | 2023-03-19 | 23 | 12 | -99
506535 | Pooler 6.223 MGD Expansion | Oakville | MIXER-SUBMERS,5HP,480/60/3,SUL,RW4021, RW4022, LiftingDavit | SULZER PUMPS (CANADA) INC. | 4503848468 | Rotating Equipment | Mixers | USD | 125081 | USD | 139127 | -14046 | Not included in Proposal / RFQ | 2022-07-25 | 2022-11-17 | 2022-07-27 | 2022-08-10 | 2022-11-17 | 2022-11-17 | 2022-08-15 | 2022-08-29 | 2023-02-24 | 2023-03-13 | 2023-03-04 | 9 | 30 | -80
506535 | Pooler 6.223 MGD Expansion | Oakville | ChemDosingSkid -Hypo, Citric Acid, NaOH & Alum | PROMINENT FLUID CONTROLS LTD. | 4503842134 | Electrical & Instrumentation | Ele-Industrial Controls | USD | 42089 | CAD | 31635 | 10454 | Supplier Competitions / Negotiation | 2022-08-01 | 2022-11-19 | 2022-08-09 | 2022-08-15 | 2022-08-10 | 2022-11-19 | 2022-08-22 | 2022-08-11 | 2023-02-24 | 2023-03-10 | 2023-03-03 | 7 | 18 | -100
506535 | Pooler 6.223 MGD Expansion | Oakville | Air Compressor- Dual Receiver Tank + Compressor | COMPRESSOR SCIENCE | 4503841281 | Rotating Equipment | Compressors | USD | 12295 | USD | 19933 | -7638 | Estimate Without Market Reference(No Quote) | 2022-07-25 | 2022-11-09 | 2022-08-02 | 2022-08-05 | 2022-11-09 | 2022-11-09 | 2022-08-08 | 2022-08-10 | 2023-02-24 | 2023-01-30 | 2023-02-11 | -12 | 30 | -91
506554 | SK Hynix DensaDeg+ZLD | Richmond | Densadeg Fabrication | Seoul Machinery Co. Ltd | 4503594898 | Fabrication | Metal Isolation Valves | USD | 263183 | USD | 310000 | -46817 | Single Sourced | 2021-01-26 | 2021-03-03 | 2021-04-14 | 2021-03-02 | 2021-05-18 | 2021-06-09 | 2021-03-16 | 2021-05-18 | 2021-08-31 | 2021-10-21 | 2021-09-25 | 26 | 12 | 76
506554 | SK Hynix DensaDeg+ZLD | Richmond | FRP Troughs (launders) | FIB | 4503573138 | Fabrication | Ele-Control Panels | USD | 48750 | USD | 55650 | -6900 | Single Sourced | 2021-02-23 | 2021-03-03 | 2021-03-25 | 2021-03-30 | 2021-05-15 | 2021-05-28 | 2021-04-13 | 2021-04-27 | 2021-08-31 | 2021-04-27 | 2021-06-29 | -63 | 12 | 55
506554 | SK Hynix DensaDeg+ZLD | Richmond | Reactor Drive | SEW EURODRIVE | 4503587444 | Rotating Equipment | Metal Isolation Valves | USD | 15535 | USD | 13233 | 2302 | Design Optimizations | 2021-04-20 | 2021-02-18 | 2021-04-16 | 2021-05-25 | 2021-05-19 | 2021-05-26 | 2021-06-08 | 2021-05-19 | 2021-08-31 | 2021-07-28 | 2021-08-14 | -17 | 30 | 90
506554 | SK Hynix DensaDeg+ZLD | Richmond | Scraper Drive | DBS MANUFACTURING INC. | 4503569958 | Rotating Equipment | Carbon Steel | USD | 23910 | USD | 29350 | -5440 | Single Sourced | 2021-05-18 | 2021-02-18 | 2021-03-29 | 2021-06-22 | 2021-04-09 | 2021-06-17 | 2021-07-06 | 2021-04-16 | 2021-08-31 | 2021-10-15 | 2021-09-22 | 23 | 30 | 57
506554 | SK Hynix DensaDeg+ZLD | Richmond | Rapid Mixer | Yonwootec co.ltd | 4503589311 | Rotating Equipment | Metal Isolation Valves | USD | 49158 | USD | 37332 | 11826 | Design Optimizations | 2021-03-23 | 2021-02-18 | 2021-05-24 | 2021-04-27 | 2021-05-14 | 2021-06-10 | 2021-05-11 | 2021-05-24 | 2021-08-31 | 2021-09-30 | 2021-09-15 | 15 | 30 | 95
506554 | SK Hynix DensaDeg+ZLD | Richmond | Lamella (Tube settlers) - Clarifier | BRENTWOOD INDUSTRIES | 4503591284 | Fabrication | Metal Isolation Valves | USD | 17088 | USD | 10108 | 6980 | Frame Agreements | 2021-05-18 | 2021-03-03 | 2021-06-01 | 2021-06-22 | 2021-05-26 | 2021-06-01 | 2021-07-06 | 2021-06-01 | 2021-08-31 | 2021-07-06 | 2021-08-03 | -28 | 12 | 90
506608 | Collinsville WTP Expansion | Richmond | SETTLING TUBES | KAL-LITE | 4503516533 | Fabrication | Carbon Steel | USD | 25476 | USD | 8320 | 17156 | Design Optimizations | 2020-08-01 | 2020-11-13 | 2021-01-15 | 2020-08-15 | 2021-01-15 | 2020-11-13 | 2020-08-22 | 2021-01-15 | 2020-10-10 | 2021-02-26 | 2020-12-18 | 70 | 12 | 63
506608 | Collinsville WTP Expansion | Richmond | COMPRESSORS | QUINCY COMPRESSORS | 4503495224 | Rotating Equipment | Compressors | USD | 14688 | USD | 20173 | -5485 | Single Sourced | 2020-07-28 | 2020-11-08 | 2021-01-01 | 2020-08-11 | 2021-01-01 | 2020-11-08 | 2020-08-18 | 2021-01-01 | 2020-10-20 | 2021-02-19 | 2020-12-20 | 61 | 30 | 54
506608 | Collinsville WTP Expansion | Richmond | SUPPORTS & PIPING | JOB SHOP FABRICATORS | 4503516275 | Fabrication | Carbon Steel | USD | 45252 | USD | 34439 | 10813 | Design Optimizations | 2020-08-01 | 2020-11-07 | 2021-01-07 | 2020-08-15 | 2021-01-03 | 2020-11-07 | 2020-08-22 | 2021-01-03 | 2020-10-10 | 2021-02-14 | 2020-12-12 | 64 | 12 | 57
506608 | Collinsville WTP Expansion | Richmond | CONTROL VALVES | AUTOMATIC CONTROLS OF VIRGINIA, INC | 4503495176 | Flow Control | Carbon Steel | USD | 29914 | USD | 37078 | -7164 | Specs / Requirements Misinterpreted in Proposal | 2020-07-07 | 2020-11-10 | 2020-11-14 | 2020-07-21 | 2021-01-20 | 2020-11-10 | 2020-07-28 | 2021-01-20 | 2020-09-15 | 2021-03-17 | 2020-12-15 | 92 | 12 | 71
506629 | Santa Monica | Oakville | Electrical Control (Main Panel) | KELTOUR CONTROLS INC. | 4503543571 | Electrical & Instrumentation | Ele-Electrical Others | USD | 51644 | USD | 40108 | 11536 | Supplier Competitions / Negotiation | 2021-03-23 | 2021-02-06 | 2021-02-16 | 2021-04-10 | 2021-02-22 | 2021-04-04 | 2021-04-18 | 2021-03-02 | 2021-06-01 | 2021-03-02 | 2021-04-16 | -45 | 18 | 24
506629 | Santa Monica | Oakville | 500D Beam, Bracket, Hanger Brace & Arm & Membrane Tank Grating, FRP, Set | 3D MECHANICAL | 4503584752 | Fabrication | Carbon Steel | USD | 32861 | USD | 71313 | -38452 | Market Impact | 2021-03-21 | 2021-04-10 | 2021-04-22 | 2021-04-04 | 2021-04-30 | 2021-04-24 | 2021-04-12 | 2021-05-08 | 2021-05-28 | 2021-05-08 | 2021-05-18 | -10 | 12 | 28
506629 | Santa Monica | Oakville | Permeate Header(s), Aeration Header(s) & Permeate Isolation Valves - Long Shaft - SS 316, SS Pipe, Fab Labor | NV PIPING SYSTEMS INC. | 4503583935 | Fabrication | Metal Isolation Valves | USD | 13921 | USD | 16093 | -2172 | Not included in Proposal / RFQ | 2021-03-19 | 2021-04-09 | 2021-04-21 | 2021-04-02 | 2021-05-03 | 2021-04-22 | 2021-04-10 | 2021-05-11 | 2021-05-26 | 2021-05-11 | 2021-05-18 | -7 | 12 | 32
506629 | Santa Monica | Oakville | Turbidity Meter | Hach Sales & Service Canada Ltd. | 4503547424 | Electrical & Instrumentation | Carbon Steel | USD | 8519 | USD | 12286 | -3767 | Single Sourced | 2021-03-23 | 2021-02-06 | 2021-02-16 | 2021-04-10 | 2021-02-25 | 2021-04-04 | 2021-04-18 | 2021-03-07 | 2021-06-01 | 2021-03-07 | 2021-04-19 | -43 | 18 | 29
506629 | Santa Monica | Oakville | Mag Flow Meter, Tank Level & Temp Trans, Press Indicator, Flow Switch Low Level, Backpulse Pres Switch High | ENDRESS + HAUSER CANADA LTD. | 4503549667 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 11562 | USD | 11494 | 68 | Supplier Competitions / Negotiation | 2021-03-21 | 2021-02-14 | 2021-02-23 | 2021-04-08 | 2021-03-02 | 2021-04-07 | 2021-04-16 | 2021-03-09 | 2021-05-30 | 2021-03-09 | 2021-04-19 | -41 | 18 | 23
506629 | Santa Monica | Oakville | Grundfos - Chemical Dosing Sysems for Both Hypo and Citric (Non-Classified) | GRUNDFOS CANADA INC. | 4503568963 | Fabrication | Non-Metal Equipment | USD | 43074 | USD | 17568 | 25506 | Supplier Competitions / Negotiation | 2021-03-22 | 2021-03-03 | 2021-03-18 | 2021-04-05 | 2021-03-24 | 2021-04-15 | 2021-04-13 | 2021-04-12 | 2021-05-29 | 2021-04-12 | 2021-05-05 | -23 | 12 | 40
506629 | Santa Monica | Oakville | Process Pump | BOERGER LLC | 4503547045 | Rotating Equipment | Centrifugal Pumps | USD | 26538 | USD | 27714 | -1176 | Market Impact | 2021-02-06 | 2021-02-13 | 2021-02-23 | 2021-02-20 | 2021-02-28 | 2021-04-02 | 2021-02-28 | 2021-03-07 | 2021-05-27 | 2021-03-07 | 2021-04-16 | -40 | 30 | 22
506629 | Santa Monica | Oakville | Blower Rotary Lobe | AERZEN CANADA INC. | 4503547023 | Rotating Equipment | Ele-Control Panels | USD | 17020 | USD | 17251 | -231 | Single Sourced | 2021-02-12 | 2021-02-07 | 2021-02-19 | 2021-02-26 | 2021-02-25 | 2021-04-02 | 2021-03-06 | 2021-03-07 | 2021-05-26 | 2021-03-07 | 2021-04-16 | -40 | 30 | 28
506641 | BRUNSWICK COUNTY, NC | Richmond | Control Center (Greenleaf) - Center Core | JOB SHOP FABRICATORS | 4503561223 | Fabrication | Ele-Control Panels | USD | 78564 | USD | 78564 | 0 | Frame Agreements | 2021-03-15 | 2021-05-07 | 2021-03-23 | 2021-03-20 | 2021-03-23 | 2021-05-07 | 2021-03-27 | 2021-03-27 | 2021-06-30 | 2021-05-15 | 2021-06-07 | -23 | 12 | -41
506641 | BRUNSWICK COUNTY, NC | Richmond | Influent Slide Gates (Greenleaf) | AUTOMATIC CONTROLS OF VIRGINIA, INC | 4503477792 | Fabrication | Ele-Control Panels | USD | 44944 | USD | 62424 | -17480 | Size/ Weight/ Quantity Underestimated | 2021-03-15 | 2021-02-23 | 2021-01-04 | 2021-03-20 | 2020-10-20 | 2021-02-23 | 2021-03-27 | 2021-01-18 | 2021-06-30 | 2021-03-29 | 2021-05-14 | -46 | 12 | -36
506641 | BRUNSWICK COUNTY, NC | Richmond | Platforms & Walkways | L&W FAB | 4503567697 | Fabrication | Metal Isolation Valves | USD | 71900 | USD | 67640 | 4260 | Frame Agreements | 2021-03-15 | 2021-04-03 | 2021-01-06 | 2021-03-20 | 2021-01-10 | 2021-04-03 | 2021-03-27 | 2021-01-17 | 2021-06-30 | 2021-04-11 | 2021-05-21 | -40 | 12 | -76
506641 | BRUNSWICK COUNTY, NC | Richmond | Vacuum Pumps & Hot Box (Greenleaf) | SWITZER INDUSTRIES | 4203537493 | Rotating Equipment | Gear Box | USD | 53802 | USD | 71708 | -17906 | Specs / Requirements Misinterpreted in Proposal | 2021-03-25 | 2021-04-19 | 2021-02-02 | 2021-04-01 | 2021-02-04 | 2021-04-19 | 2021-04-08 | 2021-02-15 | 2021-06-17 | 2021-07-05 | 2021-06-26 | 9 | 30 | -63
506641 | BRUNSWICK COUNTY, NC | Richmond | Filter Valves (Greenleaf) | DEZURIK | 4503568455 | Flow Control | Metal Isolation Valves | USD | 138397 | USD | 161235 | -22838 | Not included in Proposal / RFQ | 2021-03-25 | 2021-04-23 | 2021-03-02 | 2021-04-01 | 2021-02-28 | 2021-04-23 | 2021-04-08 | 2021-04-09 | 2021-06-17 | 2021-05-21 | 2021-06-03 | -13 | 12 | -14
506641 | BRUNSWICK COUNTY, NC | Richmond | VALVES/INSTR - GL | TRIAD | 4503580075 | Flow Control | Metal Control Valves | USD | 44670 | USD | 36000 | 8670 | Supplier Competitions / Negotiation | 2021-03-15 | 2021-05-07 | 2021-04-01 | 2021-03-20 | 2021-04-01 | 2021-05-07 | 2021-03-27 | 2021-04-05 | 2021-06-30 | 2021-05-17 | 2021-06-08 | -22 | 12 | -32
506641 | BRUNSWICK COUNTY, NC | Richmond | Rapid Mixer (SuperPulsator) | Philadelphia Mixing Solutions | 4503505092 | Rotating Equipment | Carbon Steel | USD | 91963 | USD | 91963 | 0 | Estimate Without Market Reference(No Quote) | 2020-01-26 | 2020-09-27 | 2021-04-06 | 2020-03-08 | 2021-04-06 | 2020-09-27 | 2021-03-11 | 2021-04-12 | 2021-05-06 | 2021-05-31 | 2021-05-18 | 13 | 30 | 197
506641 | BRUNSWICK COUNTY, NC | Richmond | Collectors/Distributors PVC | JOB SHOP FABRICATORS | 4503503047 | Fabrication | Centrifugal Pumps | USD | 127440 | USD | 62183 | 65257 | Supplier Competitions / Negotiation | 2020-01-26 | 2020-10-20 | 2021-02-02 | 2020-03-08 | 2021-02-04 | 2020-10-20 | 2021-05-20 | 2021-02-11 | 2021-07-15 | 2021-04-08 | 2021-05-27 | -49 | 12 | 114
506641 | BRUNSWICK COUNTY, NC | Richmond | Settling Plates | KAL-LITE | 4503490147 | Fabrication | Non-Metal Equipment | USD | 120775 | USD | 120775 | 0 | Single Sourced | 2020-01-26 | 2020-10-20 | 2020-11-18 | 2020-03-08 | 2020-11-16 | 2020-10-20 | 2021-05-20 | 2020-11-16 | 2021-07-15 | 2021-01-11 | 2021-04-13 | -92 | 12 | 27
506641 | BRUNSWICK COUNTY, NC | Richmond | Support Hangers,Brackets | Burke's Mechanical, Inc. | 4103490085 | Fabrication | Ele-Control Panels | USD | 215068 | USD | 292658 | -77590 | Proposed Supplier Incapable Of Executing | 2021-05-01 | 2021-04-24 | 2021-02-02 | 2021-05-15 | 2021-02-09 | 2021-04-24 | 2021-05-20 | 2021-02-16 | 2021-07-15 | 2021-04-13 | 2021-05-29 | -46 | 12 | -67
506641 | BRUNSWICK COUNTY, NC | Richmond | Sludge Bl Dwn Pipe | JOB SHOP FABRICATORS | 4503545733 | Fabrication | Centrifugal Pumps | USD | 8774 | USD | 67016 | -58242 | Size/ Weight/ Quantity Underestimated | 2021-05-01 | 2021-04-24 | 2021-02-02 | 2021-05-15 | 2021-02-08 | 2021-04-24 | 2021-05-20 | 2021-02-15 | 2021-07-15 | 2021-03-15 | 2021-05-15 | -61 | 12 | -68
506641 | BRUNSWICK COUNTY, NC | Richmond | Valves (SuperPulsator) | DEZURIK | 4503470312 | Flow Control | Metal Isolation Valves | USD | 179714 | USD | 167948 | 11766 | Design Optimizations | 2021-04-01 | 2021-02-08 | 2020-10-08 | 2021-04-15 | 2020-10-04 | 2021-02-08 | 2021-04-20 | 2020-10-04 | 2021-06-15 | 2020-12-13 | 2021-03-15 | -92 | 12 | -127
506641 | BRUNSWICK COUNTY, NC | Richmond | Collection System (SuperPulsator) | JOB SHOP FABRICATORS | 4503489958 | Fabrication | Carbon Steel | USD | 33501 | USD | 55673 | -22172 | Specs / Requirements Misinterpreted in Proposal | 2021-02-06 | 2021-02-06 | 2021-01-21 | 2021-02-06 | 2021-01-16 | 2021-02-06 | 2021-02-06 | 2021-01-16 | 2021-02-06 | 2021-02-27 | 2021-02-16 | 11 | 12 | -21
506641 | BRUNSWICK COUNTY, NC | Richmond | Extrusions | EASTERN METAL | 4503562127 | Fabrication | Ele-Control Panels | USD | 177243 | USD | 254432 | -77189 | Not included in Proposal / RFQ | 2021-03-08 | 2021-03-08 | 2021-02-02 | 2021-03-08 | 2021-02-08 | 2021-03-08 | 2021-03-08 | 2021-02-15 | 2021-03-08 | 2021-04-12 | 2021-03-25 | 18 | 12 | -21
506641 | BRUNSWICK COUNTY, NC | Richmond | Aluminum Supports | L&W FAB | 4203490138 | Fabrication | Centrifugal Pumps | USD | 73000 | USD | 193240 | -120240 | Estimate Without Market Reference(No Quote) | 2021-03-29 | 2021-03-29 | 2021-02-19 | 2021-03-29 | 2021-03-01 | 2021-03-29 | 2021-03-29 | 2021-03-11 | 2021-03-29 | 2021-05-06 | 2021-04-17 | 19 | 12 | -18
506641 | BRUNSWICK COUNTY, NC | Richmond | SS&AL Fabrication | BURKES MECHANICAL | 4503606895 | Fabrication | Carbon Steel | USD | 286526 | USD | 286526 | 0 | Frame Agreements | 2021-07-28 | 2021-07-28 | 2021-06-23 | 2021-07-28 | 2021-06-23 | 2021-07-28 | 2021-07-28 | 2021-06-23 | 2021-07-28 | 2021-09-01 | 2021-08-14 | 18 | 12 | -35
506641 | BRUNSWICK COUNTY, NC | Richmond | Vaccum Pump skid | GARDNER DENVER NASH LLC | 4503577542 | Rotating Equipment | Compressors | USD | 62934 | USD | 62934 | 0 | Frame Agreements | 2021-06-25 | 2021-06-25 | 2021-04-30 | 2021-06-25 | 2021-04-30 | 2021-06-25 | 2021-06-25 | 2021-04-30 | 2021-06-25 | 2021-08-20 | 2021-07-23 | 28 | 30 | -56
506641 | BRUNSWICK COUNTY, NC | Richmond | PVC Fabrication | JOB SHOP FABRICATORS | 4503558824 | Fabrication | Carbon Steel | USD | 29330 | USD | 71298 | -41968 | Estimate Without Market Reference(No Quote) | 2021-04-16 | 2021-04-16 | 2021-03-26 | 2021-04-16 | 2021-03-26 | 2021-04-16 | 2021-04-16 | 2021-03-26 | 2021-04-16 | 2021-05-07 | 2021-04-26 | 11 | 12 | -21
506649 | Global Foundries F9 EJ IX | Guelph | Pressure Vessels with Internals and painted skid | LESENA STEEL DIVISION | 4503424570 | Fabrication | Skid Assembly Outsourced | USD | 75256 | CAD | 67805 | 7451 | Design Optimizations | 2020-05-14 | 2020-06-22 | 2020-07-02 | 2020-05-29 | 2020-07-01 | 2020-07-05 | 2020-06-04 | 2020-07-03 | 2020-08-27 | 2020-08-21 | 2020-08-24 | -3 | 12 | 11
506649 | Global Foundries F9 EJ IX | Guelph | ETFE Lining for Vessels | Fisher Utah | 4503453664 | Fabrication | Carbon Steel | USD | 43400 | USD | 39950 | 3450 | Supplier Competitions / Negotiation | 2020-05-14 | 2020-07-08 | 2020-07-16 | 2020-05-29 | 2020-08-06 | 2020-07-30 | 2020-06-04 | 2020-09-04 | 2020-10-15 | 2020-09-30 | 2020-10-07 | -7 | 12 | 58
506649 | Global Foundries F9 EJ IX | Guelph | PVDF Internals for PV | PLASCO WELDING AND FABRICATION INC | 4503443283 | Flow Control | Centrifugal Pumps | USD | 24690 | CAD | 13967 | 10723 | Design Optimizations | 2020-05-28 | 2020-07-24 | 2020-07-22 | 2020-06-12 | 2020-08-07 | 2020-07-24 | 2020-06-19 | 2020-08-09 | 2020-07-31 | 2020-09-20 | 2020-08-25 | 26 | 12 | 16
506696 | Intel RA4 CO2 Skid System | Oakville | Electrical Panels | KELTOUR CONTROLS INC. | 4503467615 | Electrical & Instrumentation | Ele-Electrical Others | USD | 43394 | USD | 26970 | 16424 | Frame Agreements | 2020-08-14 | 2020-09-14 | 2020-09-30 | 2020-09-04 | 2020-09-29 | 2020-10-04 | 2020-09-18 | 2020-09-30 | 2020-11-20 | 2020-11-25 | 2020-11-22 | 3 | 18 | 16
506696 | Intel RA4 CO2 Skid System | Oakville | Storage Tank (HDPE) | TERRACON CORP | 4503465270 | Fabrication | Centrifugal Pumps | USD | 5285 | USD | 7045 | -1760 | Estimate Without Market Reference(No Quote) | 2020-07-24 | 2020-09-07 | 2020-09-21 | 2020-08-14 | 2020-09-21 | 2020-09-22 | 2020-08-28 | 2020-09-27 | 2020-11-20 | 2020-11-22 | 2020-11-21 | 1 | 12 | 20
506696 | Intel RA4 CO2 Skid System | Oakville | Jordan Valves | Jenkinson an Company | 4503466536 | Flow Control | Metal Isolation Valves | USD | 12794 | CAD | 9761 | 3033 | Supplier Competitions / Negotiation | 2020-08-21 | 2020-09-17 | 2020-09-04 | 2020-09-11 | 2020-09-28 | 2020-10-05 | 2020-09-25 | 2020-09-28 | 2020-11-20 | 2020-11-16 | 2020-11-18 | -2 | 12 | 11
506696 | Intel RA4 CO2 Skid System | Oakville | Valves (Fisher) | LAKESIDE PROCESS CONTROLS LTD. | 4503463891 | Flow Control | Metal Isolation Valves | USD | 5285 | USD | 5285 | 0 | Specs / Requirements Misinterpreted in Proposal | 2020-10-13 | 2020-09-01 | 2020-09-10 | 2020-10-13 | 2020-09-23 | 2020-10-13 | 2020-10-13 | 2020-09-24 | 2020-10-13 | 2020-11-25 | 2020-11-03 | 22 | 12 | 23
506699 | Niagara Kenosha | Minnetonka | AC VESSEL | Arrow Tanks | 4503415156 | Fabrication | Carbon Steel | USD | 70720 | USD | 64000 | 6720 | Supplier Competitions / Negotiation | 2020-06-08 | 2020-06-08 | 2020-06-08 | 2020-06-12 | 2020-06-07 | 2020-07-26 | 2020-06-12 | 2020-06-07 | 2020-08-07 | 2020-08-30 | 2020-09-14 | -15 | 12 | -1
506699 | Niagara Kenosha | Minnetonka | RO Electric Panels 506699A-EE-01/B-EE-01 | BW Systems | 4503421415 | Electrical & Instrumentation | Ele-Control Panels | USD | 27830 | USD | 27830 | 0 | Proposed Supplier Incapable Of Executing | 2020-06-08 | 2020-06-08 | 2020-06-12 | 2020-07-17 | 2020-06-25 | 2020-07-17 | 2020-07-17 | 2020-06-25 | 2020-07-17 | 2020-08-19 | 2020-08-25 | -6 | 18 | 17
506699 | Niagara Kenosha | Minnetonka | RO Machine 506699A-MA-02 | PROTEC ARISAWA AMERICA, INC. | 4503418175 | Fabrication | Carbon Steel | USD | 13556 | USD | 13556 | 0 | Supplier Competitions / Negotiation | 2020-07-08 | 2020-07-08 | 2020-05-29 | 2020-07-08 | 2020-06-16 | 2020-07-08 | 2020-07-08 | 2020-06-17 | 2020-07-08 | 2020-08-12 | 2020-08-17 | -5 | 12 | -21
506699 | Niagara Kenosha | Minnetonka | RO Machine | WERNER ELECTRIC | 4503417826 | Electrical & Instrumentation | Ele-Control Panels | USD | 24673 | USD | 24673 | 0 | Single Sourced | 2020-07-17 | 2020-07-17 | 2020-06-17 | 2020-07-17 | 2020-06-17 | 2020-07-17 | 2020-07-17 | 2020-06-17 | 2020-07-17 | 2020-08-17 | 2020-08-11 | 6 | 18 | -30
506699 | Niagara Kenosha | Minnetonka | RO BEV FRAME 506699A-SA-01 | R&R Metalworks | 4503453311 | Fabrication | Carbon Steel | USD | 5833 | USD | 30700 | -24867 | Proposed Supplier Incapable Of Executing | 2020-07-27 | 2020-07-27 | 2020-09-03 | 2020-07-30 | 2020-09-03 | 2020-08-19 | 2020-07-30 | 2020-09-03 | 2020-08-26 | 2020-09-10 | 2020-09-11 | -1 | 12 | 38
506704 | Provo | Oakville | Valve - Bray | BRAY CONTROLS CANADA LTD | 4503750859 | Flow Control | Metal Control Valves | USD | 279491 | USD | 126362 | 153129 | Design Optimizations | 2022-04-29 | 2022-05-26 | 2022-01-19 | 2022-04-29 | 2022-05-26 | 2022-05-26 | 2022-05-13 | 2022-03-06 | 2022-09-30 | 2022-08-07 | 2022-09-03 | -27 | 12 | -81
506704 | Provo | Oakville | Spools S.S | Cambridge Pro Fab Inc. | 4503777396 | Fabrication | Stainless Steel | USD | 242179 | USD | 254933 | -12754 | Specs / Requirements Misinterpreted in Proposal | 2022-04-29 | 2022-07-10 | 2022-04-21 | 2022-04-29 | 2022-07-10 | 2022-07-10 | 2022-05-13 | 2022-04-20 | 2022-09-30 | 2022-07-13 | 2022-08-21 | -39 | 12 | -81
506704 | Provo | Oakville | Process Pumps+Spare | SULZER PUMPS (CANADA) IN | 4503763756 | Rotating Equipment | Centrifugal Pumps | USD | 285081 | USD | 327836 | -42755 | Not included in Proposal / RFQ | 2022-04-29 | 2022-08-28 | 2022-03-16 | 2022-04-29 | 2022-08-28 | 2022-08-28 | 2022-05-13 | 2022-03-25 | 2022-09-30 | 2023-02-10 | 2022-12-05 | 67 | 30 | -156
506704 | Provo | Oakville | Control Panel | Machine Control Systems | 4503833197 | Electrical & Instrumentation | Ele-Control Panels | USD | 173773 | USD | 200659 | -26886 | Estimate Without Market Reference(No Quote) | 2022-04-29 | 2022-08-21 | 2022-07-11 | 2022-04-29 | 2022-08-21 | 2022-08-21 | 2022-05-13 | 2022-07-26 | 2022-09-30 | 2022-12-14 | 2022-11-06 | 38 | 18 | -26
506704 | Provo | Oakville | Inst - E&H | ENDRESS + HAUSER CANADA LTD. | 4503786890 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 57096 | USD | 31491 | 25605 | Supplier Competitions / Negotiation | 2022-04-29 | 2022-05-19 | 2022-01-06 | 2022-04-29 | 2022-05-19 | 2022-05-19 | 2022-05-13 | 2022-05-11 | 2022-09-30 | 2022-08-03 | 2022-09-01 | -29 | 18 | -8
506704 | Provo | Oakville | Inst - Ashcroft | CONVAL PROCESS SOLUTIONS INC | 4503789289 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 7660 | USD | 5717 | 1943 | Supplier Competitions / Negotiation | 2022-04-29 | 2022-07-15 | 2022-05-11 | 2022-04-29 | 2022-07-15 | 2022-07-15 | 2022-05-13 | 2022-05-10 | 2022-09-30 | 2022-08-02 | 2022-08-31 | -29 | 18 | -66
506704 | Provo | Oakville | Comppressor | Compressor Science | 4503705096 | Rotating Equipment | Compressors | USD | 20000 | USD | 34524 | -14524 | Size/ Weight/ Quantity Underestimated | 2022-04-29 | 2022-05-08 | 2021-12-15 | 2022-04-29 | 2022-05-08 | 2022-05-08 | 2022-05-13 | 2021-12-15 | 2022-09-30 | 2022-06-01 | 2022-07-31 | -60 | 30 | -144
506704 | Provo | Oakville | Dosing Pump | WATSON MARLOW INC | 4503787043 | Rotating Equipment | Dosing Pump | USD | 68940 | USD | 68900 | 40 | Supplier Competitions / Negotiation | 2022-04-29 | 2022-06-25 | 2022-03-21 | 2022-04-29 | 2022-06-25 | 2022-06-25 | 2022-05-13 | 2022-05-06 | 2022-09-30 | 2022-09-23 | 2022-09-26 | -3 | 30 | -50
506704 | Provo | Oakville | Liffting Module | 3D MECHANICAL | 4503770352 | Fabrication | Stainless Steel | USD | 87081 | USD | 273028 | -185947 | Not included in Proposal / RFQ | 2022-04-29 | 2022-07-03 | 2022-04-07 | 2022-04-29 | 2022-07-03 | 2022-07-03 | 2022-05-13 | 2022-04-05 | 2022-09-30 | 2022-06-28 | 2022-08-14 | -47 | 12 | -89
506704 | Provo | Oakville | Blower+Spare | LONE STAR BLOWER, INC. | 4503777226 | Rotating Equipment | Blowers & Fans | USD | 778900 | USD | 777924 | 976 | Design Optimizations | 2022-04-29 | 2022-06-17 | 2021-12-17 | 2022-04-29 | 2022-06-17 | 2022-06-17 | 2022-05-13 | 2022-04-16 | 2022-09-30 | 2022-12-16 | 2022-11-07 | 39 | 30 | -62
506704 | Provo | Oakville | Blower+Spare | LONE STAR BLOWER, INC. | 4503574491 | Rotating Equipment | Blowers & Fans | USD | 22500 | USD | 22500 | 0 | Not included in Proposal / RFQ | 2022-01-05 | 2022-01-05 | 2021-11-24 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2022-01-05 | 2021-11-24 | 2022-01-05 | 2022-02-16 | 2022-01-26 | 21 | 30 | -42
506716 | Weston WTP | Richmond | PULSAPAK TANK | POSEIDON, INC | 4503452845 | Fabrication | Metal Isolation Valves | USD | 817514 | USD | 675800 | 141714 | Frame Agreements | 2020-09-02 | 2020-08-10 | 2020-08-20 | 2019-09-09 | 2020-08-05 | 2020-05-29 | 2019-09-12 | 2020-09-15 | 2020-01-02 | 2021-02-16 | 2020-07-25 | 206 | 12 | 36
506716 | Weston WTP | Richmond | VALVES | BRAY CONTROLS CANADA LTD. | 4503437484 | Flow Control | Ele-Control Panels | USD | 92212 | USD | 76836 | 15376 | Frame Agreements | 2020-10-17 | 2020-07-13 | 2020-07-13 | 2019-10-31 | 2020-07-13 | 2020-05-03 | 2019-11-14 | 2020-07-15 | 2020-01-02 | 2020-11-04 | 2020-06-03 | 154 | 12 | 2
506722 | Exyte Cree Mohawk | Oakville | Electrical Equipment - MCC & VFD | GERRIE ELECTRIC LIMITED | 4503448539 | Electrical & Instrumentation | Ele-Electrical Others | USD | 400000 | USD | 289013 | 110987 | Supplier Competitions / Negotiation | 2020-08-10 | 2020-07-28 | 2020-08-11 | 2020-09-07 | 2020-08-18 | 2020-10-30 | 2020-09-14 | 2020-08-25 | 2021-02-01 | 2020-08-25 | 2020-11-13 | -80 | 18 | 28
506722 | Exyte Cree Mohawk | Oakville | Electrical Equipment - PLC | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503481348 | Electrical & Instrumentation | Ele-Electrical Others | USD | 331599 | USD | 77035 | 254564 | Supplier Competitions / Negotiation | 2020-07-24 | 2020-10-14 | 2020-10-21 | 2020-08-21 | 2020-10-26 | 2020-10-19 | 2020-08-28 | 2020-11-02 | 2021-01-15 | 2020-11-02 | 2020-12-09 | -37 | 18 | 19
506722 | Exyte Cree Mohawk | Oakville | Electrical Equipment - RIO (RO, ACF) | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503463819 | Electrical & Instrumentation | Ele-Electrical Others | USD | 98576 | USD | 71769 | 26807 | Design Optimizations | 2020-09-16 | 2020-09-09 | 2020-09-16 | 2020-09-16 | 2020-09-22 | 2020-09-16 | 2020-09-16 | 2020-09-24 | 2020-09-16 | 2020-09-24 | 2020-09-20 | 4 | 18 | 15
506722 | Exyte Cree Mohawk | Oakville | Electrical Equipment - RIO (E-cell) | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503463821 | Electrical & Instrumentation | Ele-Electrical Others | USD | 23538 | USD | 35433 | -11895 | Specs / Requirements Misinterpreted in Proposal | 2020-09-16 | 2020-09-09 | 2020-09-16 | 2020-09-16 | 2020-09-22 | 2020-09-16 | 2020-09-16 | 2020-09-24 | 2020-09-16 | 2020-09-24 | 2020-09-20 | 4 | 18 | 15
506722 | Exyte Cree Mohawk | Oakville | Electrical Equipment - PLC | GERRIE ELECTRIC LIMITED | 4503573663 | Electrical & Instrumentation | Ele-Electrical Others | USD | 30000 | USD | 28687 | 1313 | Design Optimizations | 2021-04-11 | 2021-03-31 | 2021-04-09 | 2021-04-11 | 2021-04-16 | 2021-04-11 | 2021-04-11 | 2021-04-23 | 2021-04-11 | 2021-04-23 | 2021-04-17 | 6 | 18 | 23
506722 | Exyte Cree Mohawk | Oakville | Membrane Element - Liqui-Cel | 3M Company | 4503428154 | Flow Control | RO Membrane Housings | USD | 144105 | USD | 141646 | 2459 | Design Optimizations | 2020-06-23 | 2020-06-19 | 2020-06-26 | 2020-07-07 | 2020-07-02 | 2020-09-09 | 2020-07-14 | 2020-07-10 | 2020-12-01 | 2020-11-20 | 2020-11-25 | -5 | 12 | 21
506722 | Exyte Cree Mohawk | Oakville | Filter - Cartridge Filter Housing | FIL-TREK CORPORATION | 4503467641 | Flow Control | Filters And Strainers (Incl Housings) | USD | 24969 | USD | 15450 | 9519 | Frame Agreements | 2020-08-18 | 2020-09-14 | 2020-09-21 | 2020-09-01 | 2020-09-28 | 2020-10-09 | 2020-09-08 | 2020-10-05 | 2020-12-01 | 2020-11-16 | 2020-11-23 | -7 | 12 | 21
506722 | Exyte Cree Mohawk | Oakville | Filter - Filter Cartridge | Pall | 4503469122 | Flow Control | Filters And Strainers (Incl Housings) | USD | 47520 | USD | 46077 | 1443 | Frame Agreements | 2020-10-13 | 2020-07-10 | 2020-07-17 | 2020-10-27 | 2020-07-23 | 2020-09-20 | 2020-11-03 | 2020-10-05 | 2020-12-01 | 2020-10-05 | 2020-11-02 | -28 | 12 | 87
506722 | Exyte Cree Mohawk | Oakville | Pump - Centrifugal (UPW to Guelph) | GRUNDFOS PUMPS CORPORATION | 4503467640 | Rotating Equipment | Centrifugal Pumps | USD | 30000 | USD | 22714 | 7286 | Supplier Competitions / Negotiation | 2020-07-07 | 2020-07-22 | 2020-07-29 | 2020-07-21 | 2020-08-05 | 2020-09-26 | 2020-07-28 | 2020-08-18 | 2020-12-01 | 2020-12-16 | 2020-12-08 | 8 | 30 | 27
506722 | Exyte Cree Mohawk | Oakville | Pump - Centrifugal (Others to Trivaco) | GRUNDFOS PUMPS CORPORATION | 4503442593 | Rotating Equipment | Centrifugal Pumps | USD | 44145 | USD | 40349 | 3796 | Frame Agreements | 2020-08-01 | 2020-07-22 | 2020-07-29 | 2020-08-01 | 2020-08-04 | 2020-08-01 | 2020-08-01 | 2020-08-11 | 2020-08-01 | 2020-08-11 | 2020-08-06 | 5 | 30 | 20
506722 | Exyte Cree Mohawk | Oakville | Pump Skids (RW ROP SW ROW) | TRIVACO | 4503465195 | Fabrication | Centrifugal Pumps | USD | 75000 | USD | 80215 | -5215 | Proposed Supplier Incapable Of Executing | 2020-09-17 | 2020-09-07 | 2020-09-14 | 2020-09-17 | 2020-09-20 | 2020-09-17 | 2020-09-17 | 2020-09-27 | 2020-09-17 | 2020-09-27 | 2020-09-22 | 5 | 12 | 20
506722 | Exyte Cree Mohawk | Oakville | Pump Skids (UPW) | TRIVACO | 4503465200 | Fabrication | Centrifugal Pumps | USD | 60000 | USD | 61317 | -1317 | Not included in Proposal / RFQ | 2020-11-11 | 2020-09-07 | 2020-09-14 | 2020-11-11 | 2020-09-21 | 2020-11-11 | 2020-11-11 | 2020-09-28 | 2020-11-11 | 2021-01-15 | 2020-12-13 | 33 | 12 | 21
506722 | Exyte Cree Mohawk | Oakville | Filter Skid | TRIVACO | 4503493707 | Fabrication | Skid Assembly Outsourced | USD | 152161 | USD | 53757 | 98404 | Supplier Competitions / Negotiation | 2020-11-21 | 2020-10-01 | 2020-10-07 | 2020-11-21 | 2020-10-13 | 2020-11-21 | 2020-11-21 | 2020-10-20 | 2020-11-21 | 2021-01-12 | 2020-12-17 | 26 | 12 | 19
506722 | Exyte Cree Mohawk | Oakville | HX Skids | TITAN PIPING SYSTEMS INC. | 4503477899 | Fabrication | Carbon Steel | USD | 56400 | USD | 77131 | -20731 | Estimate Without Market Reference(No Quote) | 2020-10-15 | 2020-10-05 | 2020-10-12 | 2020-10-15 | 2020-10-18 | 2020-10-15 | 2020-10-15 | 2020-10-25 | 2020-10-15 | 2020-10-25 | 2020-10-20 | 5 | 12 | 20
506722 | Exyte Cree Mohawk | Oakville | IX Skid | TRIVACO | 4503506541 | Fabrication | Skid Assembly Outsourced | USD | 80000 | USD | 82881 | -2881 | Specs / Requirements Misinterpreted in Proposal | 2020-12-11 | 2020-12-02 | 2020-12-07 | 2020-12-11 | 2020-12-14 | 2020-12-11 | 2020-12-11 | 2020-12-21 | 2020-12-11 | 2020-12-21 | 2020-12-16 | 5 | 12 | 19
506722 | Exyte Cree Mohawk | Oakville | GTM Vacuum Pump Skid | Flowserve US Inc. | 4503436348 | Rotating Equipment | Centrifugal Pumps | USD | 53683 | USD | 48000 | 5683 | Design Optimizations | 2020-08-04 | 2020-07-09 | 2020-07-16 | 2020-08-18 | 2020-07-21 | 2020-09-26 | 2020-08-25 | 2020-07-27 | 2020-12-15 | 2020-12-02 | 2020-12-08 | -6 | 30 | 18
506722 | Exyte Cree Mohawk | Oakville | Dosing Skid | Prominent Fluid Controls Inc. | 4503442698 | Rotating Equipment | Dosing Pump | USD | 37956 | USD | 30203 | 7753 | Design Optimizations | 2020-08-18 | 2020-07-22 | 2020-07-29 | 2020-09-01 | 2020-08-04 | 2020-10-03 | 2020-09-08 | 2020-08-11 | 2020-12-15 | 2020-08-11 | 2020-10-13 | -63 | 30 | 20
506722 | Exyte Cree Mohawk | Oakville | Dosing Skid | PROMINENT FLUID CONTROLS LTD. | 4503577516 | Rotating Equipment | Dosing Pump | USD | 33000 | USD | 7692 | 25308 | Design Optimizations | 2021-04-19 | 2021-04-09 | 2021-04-16 | 2021-04-19 | 2021-04-23 | 2021-04-19 | 2021-04-19 | 2021-04-30 | 2021-04-19 | 2021-04-30 | 2021-04-24 | 6 | 30 | 21
506722 | Exyte Cree Mohawk | Oakville | Tank | Augusta Fiberglass | 4503443891 | Fabrication | Non-Metal Equipment | USD | 176794 | USD | 152295 | 24499 | Supplier Competitions / Negotiation | 2020-07-07 | 2020-08-03 | 2020-08-10 | 2020-07-21 | 2020-08-17 | 2020-10-02 | 2020-07-28 | 2020-08-24 | 2020-12-15 | 2020-12-28 | 2020-12-21 | 7 | 12 | 21
506722 | Exyte Cree Mohawk | Oakville | Heat Exchanger | ALFA LAVAL | 4503436119 | Fabrication | Ele-Control Panels | USD | 82466 | USD | 75224 | 7242 | Supplier Competitions / Negotiation | 2020-07-07 | 2020-07-09 | 2020-07-16 | 2020-07-21 | 2020-07-23 | 2020-09-18 | 2020-07-28 | 2020-07-28 | 2020-12-01 | 2020-11-18 | 2020-11-24 | -6 | 12 | 19
506722 | Exyte Cree Mohawk | Oakville | Frame (E-cell) | Plasfab Inc | 4503471075 | Fabrication | Ele-Control Panels | USD | 24782 | USD | 29916 | -5134 | Size/ Weight/ Quantity Underestimated | 2020-10-06 | 2020-10-01 | 2020-10-06 | 2020-10-06 | 2020-10-04 | 2020-10-06 | 2020-10-06 | 2020-10-11 | 2020-10-06 | 2020-10-11 | 2020-10-08 | 3 | 12 | 10
506722 | Exyte Cree Mohawk | Oakville | Valve - Control (FCV/PCV/LCV) | LAKESIDE PROCESS CONTROLS LTD. | 4503463808 | Flow Control | Ele-Control Panels | USD | 40122 | USD | 50277 | -10155 | Estimate Without Market Reference(No Quote) | 2020-08-07 | 2020-09-04 | 2020-09-11 | 2020-09-04 | 2020-09-17 | 2020-10-26 | 2020-09-11 | 2020-09-24 | 2021-01-15 | 2020-09-24 | 2020-11-19 | -56 | 12 | 20
506722 | Exyte Cree Mohawk | Oakville | Valve - Control (TCV) | LAKESIDE PROCESS CONTROLS LTD. | 4503465272 | Flow Control | Ele-Control Panels | USD | 20300 | USD | 25035 | -4735 | Single Sourced | 2020-06-23 | 2020-09-04 | 2020-09-11 | 2020-07-21 | 2020-09-18 | 2020-09-11 | 2020-07-28 | 2020-09-29 | 2020-12-01 | 2020-11-20 | 2020-11-25 | -5 | 12 | 25
506722 | Exyte Cree Mohawk | Oakville | Valve - Butterfly (Bray - Guelph) | BRAY CONTROLS CANADA LTD. | 4503468440 | Flow Control | Metal Isolation Valves | USD | 105000 | USD | 8297 | 96703 | Supplier Competitions / Negotiation | 2020-09-25 | 2020-09-15 | 2020-09-22 | 2020-09-25 | 2020-09-28 | 2020-09-25 | 2020-09-25 | 2020-10-05 | 2020-09-25 | 2020-10-05 | 2020-09-30 | 5 | 12 | 20
506722 | Exyte Cree Mohawk | Oakville | Valve - Butterfly (Bray - Aquafine) | BRAY CONTROLS CANADA LTD. | 4503468442 | Flow Control | Metal Isolation Valves | USD | 5000 | USD | 5022 | -22 | Not included in Proposal / RFQ | 2020-10-15 | 2020-10-01 | 2020-10-05 | 2020-10-15 | 2020-10-12 | 2020-10-15 | 2020-10-15 | 2020-10-19 | 2020-10-15 | 2020-10-30 | 2020-10-22 | 8 | 12 | 18
506722 | Exyte Cree Mohawk | Oakville | Valve - Butterfly (Bray - Trivaco - AMRI) | BRAY CONTROLS CANADA LTD. | 4503469649 | Flow Control | Metal Isolation Valves | USD | 12000 | USD | 11748 | 252 | Frame Agreements | 2020-10-08 | 2020-09-16 | 2020-09-23 | 2020-10-08 | 2020-09-30 | 2020-10-08 | 2020-10-08 | 2020-10-07 | 2020-10-08 | 2020-10-30 | 2020-10-19 | 11 | 12 | 21
506722 | Exyte Cree Mohawk | Oakville | Valve - Butterfly (Bray - Titan) | BRAY CONTROLS CANADA LTD. | 4503487500 | Flow Control | Metal Isolation Valves | USD | 6000 | USD | 6349 | -349 | Estimate Without Market Reference(No Quote) | 2020-10-27 | 2020-09-16 | 2020-09-23 | 2020-10-27 | 2020-09-30 | 2020-10-27 | 2020-10-27 | 2020-10-07 | 2020-10-27 | 2020-12-07 | 2020-11-16 | 21 | 12 | 21
506722 | Exyte Cree Mohawk | Oakville | Valve - Butterfly (Bray - Trivaco) | BRAY CONTROLS CANADA LTD. | 4503487503 | Flow Control | Metal Isolation Valves | USD | 12000 | USD | 11621 | 379 | Frame Agreements | 2020-10-27 | 2020-09-16 | 2020-09-23 | 2020-10-27 | 2020-09-30 | 2020-10-27 | 2020-10-27 | 2020-10-07 | 2020-10-27 | 2020-12-07 | 2020-11-16 | 21 | 12 | 21
506722 | Exyte Cree Mohawk | Oakville | Valve - Butterfly (Bray - Trivaco) | BRAY CONTROLS CANADA LTD. | 4503510392 | Flow Control | Metal Isolation Valves | USD | 14718 | USD | 11070 | 3648 | Supplier Competitions / Negotiation | 2020-12-24 | 2020-12-14 | 2020-12-21 | 2020-12-24 | 2020-12-28 | 2020-12-24 | 2020-12-24 | 2021-01-04 | 2020-12-24 | 2021-01-04 | 2020-12-29 | 6 | 12 | 21
506722 | Exyte Cree Mohawk | Oakville | Valve - PSV/PRV | Duncan Co. | 4503484805 | Flow Control | Metal Isolation Valves | USD | 14822 | USD | 19560 | -4738 | Market Impact | 2020-08-04 | 2020-09-30 | 2020-10-07 | 2020-09-01 | 2020-10-09 | 2020-10-23 | 2020-09-08 | 2020-10-13 | 2020-12-01 | 2021-01-11 | 2020-12-21 | 21 | 12 | 13
506722 | Exyte Cree Mohawk | Oakville | Valve - PSV/PRV | Great Lakes Industrial Controls | 4503514744 | Flow Control | Metal Isolation Valves | USD | 27039 | USD | 11511 | 15528 | Supplier Competitions / Negotiation | 2020-12-28 | 2020-12-15 | 2020-12-29 | 2020-12-28 | 2021-01-03 | 2020-12-28 | 2020-12-28 | 2021-01-10 | 2020-12-28 | 2021-01-10 | 2021-01-03 | 7 | 12 | 26
506722 | Exyte Cree Mohawk | Oakville | Valve - Others (DFT - Trivaco) | DFT | 4503470250 | Flow Control | Metal Isolation Valves | USD | 7000 | USD | 7560 | -560 | Not included in Proposal / RFQ | 2020-10-31 | 2020-10-02 | 2020-10-12 | 2020-10-31 | 2020-10-19 | 2020-10-31 | 2020-10-31 | 2020-10-26 | 2020-10-31 | 2020-11-30 | 2020-11-15 | 15 | 12 | 24
506722 | Exyte Cree Mohawk | Oakville | Instrument - Analyzer (Particle Counter) | PMS CO. LTD. | 4503472322 | Electrical & Instrumentation | Ele-Control Panels | USD | 85721 | USD | 93148 | -7427 | Not included in Proposal / RFQ | 2020-08-04 | 2020-09-02 | 2020-09-09 | 2020-09-01 | 2020-09-15 | 2020-10-02 | 2020-09-08 | 2020-10-13 | 2020-12-01 | 2020-10-13 | 2020-11-06 | -24 | 18 | 41
506722 | Exyte Cree Mohawk | Oakville | Instrument - Analyzer (Silica) | SWAN ANALYTICAL INSTRUMENTS | 4503486852 | Electrical & Instrumentation | Centrifugal Pumps | USD | 12000 | USD | 11820 | 180 | Frame Agreements | 2020-10-18 | 2020-09-02 | 2020-09-09 | 2020-10-18 | 2020-09-16 | 2020-10-18 | 2020-10-18 | 2020-10-14 | 2020-10-18 | 2020-12-03 | 2020-11-10 | 23 | 18 | 42
506722 | Exyte Cree Mohawk | Oakville | Instrument - Analyzer (DO) | SWAN ANALYTICAL INSTRUMENTS | 4503485616 | Electrical & Instrumentation | Centrifugal Pumps | USD | 8000 | USD | 7850 | 150 | Frame Agreements | 2020-10-17 | 2020-09-02 | 2020-09-09 | 2020-10-17 | 2020-09-16 | 2020-10-17 | 2020-10-17 | 2020-10-14 | 2020-10-17 | 2020-12-01 | 2020-11-08 | 23 | 18 | 42
506722 | Exyte Cree Mohawk | Oakville | Instrument - Flow/Level/Press/Temp | ENDRESS + HAUSER CANADA LTD. | 4503498364 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 40000 | USD | 26706 | 13294 | Frame Agreements | 2020-12-02 | 2020-11-13 | 2020-11-20 | 2020-12-02 | 2020-11-27 | 2020-12-02 | 2020-12-02 | 2020-12-04 | 2020-12-02 | 2020-12-21 | 2020-12-11 | 10 | 18 | 21
506725 | Leprino | Minnetonka | TANK-WELL WATER,FRP,30K,506725E | DIAMOND FIBERGLASS | 4503420787 | Fabrication | Ele-Control Panels | USD | 97000 | USD | 98010 | -1010 | Specs / Requirements Misinterpreted in Proposal | 2020-04-17 | 2020-07-23 | 2020-04-23 | 2020-04-21 | 2020-06-21 | 2020-07-23 | 2020-06-23 | 2020-06-23 | 2020-09-21 | 2020-10-13 | 2020-10-29 | -16 | 12 | -30
506725 | Leprino | Minnetonka | Booster Pump Skid - MCE | WERNER ELECTRIC | 4503430335 | Electrical & Instrumentation | Centrifugal Pumps | USD | 22500 | USD | 22440 | 60 | Frame Agreements | 2020-06-25 | 2020-07-30 | 2020-07-15 | 2020-07-09 | 2020-07-15 | 2020-07-30 | 2020-07-09 | 2020-07-15 | 2020-08-27 | 2020-09-02 | 2020-09-03 | -1 | 18 | -15
506725 | Leprino | Minnetonka | Booster Pump Skid -PUMPS | PFC EQUIPMENT | 4503429123 | Rotating Equipment | Centrifugal Pumps | USD | 22000 | USD | 22020 | -20 | Proposed Supplier Incapable Of Executing | 2020-04-17 | 2020-07-11 | 2020-06-25 | 2020-04-21 | 2020-07-09 | 2020-07-11 | 2020-07-16 | 2020-07-12 | 2020-08-27 | 2020-10-04 | 2020-08-17 | 48 | 30 | 1
506725 | Leprino | Minnetonka | RO Membrane Skid - FRAME | R&R Metalworks | 4503453451 | Fabrication | Skid Assembly Outsourced | USD | 32372 | USD | 38800 | -6428 | Not included in Proposal / RFQ | 2020-10-01 | 2020-09-24 | 2020-09-03 | 2020-10-01 | 2020-09-02 | 2020-09-24 | 2020-10-01 | 2020-09-02 | 2020-10-16 | 2020-09-16 | 2020-09-17 | -1 | 12 | -22
506725 | Leprino | Minnetonka | RO Membrane Skid - MCE | WERNER ELECTRIC | 4503430391 | Electrical & Instrumentation | Carbon Steel | USD | 40000 | USD | 39484 | 516 | Design Optimizations | 2020-08-07 | 2020-08-19 | 2020-07-15 | 2020-08-12 | 2020-07-14 | 2020-08-19 | 2020-08-14 | 2020-07-14 | 2020-09-24 | 2020-09-08 | 2020-09-18 | -10 | 18 | -36
506725 | Leprino | Minnetonka | RO Membrane Skid - Housings | PROTEC ARISAWA AMERICA, INC. | 4503427806 | Flow Control | RO Membrane Housings | USD | 47000 | USD | 45514 | 1486 | Frame Agreements | 2020-04-17 | 2020-07-03 | 2020-06-25 | 2020-04-21 | 2020-07-09 | 2020-07-03 | 2020-07-16 | 2020-08-06 | 2020-08-27 | 2020-09-14 | 2020-09-18 | -4 | 12 | 34
506725 | Leprino | Minnetonka | Tekleen Strainer Skid - FRAME 506725B-SA-01/C-SA-01 | ARC SERVICES | 4503446900 | Fabrication | Skid Assembly Outsourced | USD | 21065 | USD | 12514 | 8551 | Frame Agreements | 2020-06-16 | 2020-08-16 | 2020-08-17 | 2020-06-24 | 2020-08-19 | 2020-08-16 | 2020-06-30 | 2020-08-19 | 2020-10-16 | 2020-09-09 | 2020-09-15 | -6 | 12 | 3
506725 | Leprino | Minnetonka | Tekleen Strainer Skid - SCREEN, 506725C-MA-01 | TEKLEEN | 4503426259 | Flow Control | Ele-Control Panels | USD | 63450 | USD | 63450 | 0 | Size/ Weight/ Quantity Underestimated | 2020-04-20 | 2020-07-17 | 2020-07-02 | 2020-04-29 | 2020-07-02 | 2020-07-17 | 2020-07-02 | 2020-07-07 | 2020-09-29 | 2020-10-13 | 2020-10-06 | 7 | 12 | -10
506725 | Leprino | Minnetonka | Electrical Panels (MAIN/REMOTE/TEKLEEN) | PTS Products | 4503450183 | Electrical & Instrumentation | Ele-Electrical Others | USD | 56608 | USD | 56608 | 0 | Not included in Proposal / RFQ | 2020-08-24 | 2020-08-24 | 2020-08-27 | 2020-08-27 | 2020-08-26 | 2020-09-08 | 2020-08-27 | 2020-08-27 | 2020-09-11 | 2020-09-24 | 2020-09-17 | 7 | 18 | 3
506725 | Leprino | Minnetonka | TEKLEEN NSF VALVES | Duncan Co. | 4503448688 | Flow Control | Carbon Steel | USD | 15444 | USD | 15505 | -61 | Not included in Proposal / RFQ | 2020-07-14 | 2020-07-14 | 2020-07-14 | 2020-07-21 | 2020-08-23 | 2020-08-17 | 2020-07-22 | 2020-08-24 | 2020-09-18 | 2020-09-21 | 2020-09-19 | 2 | 12 | 41
506725 | Leprino | Minnetonka | BOOSTER PUMP SKID NSF VALVES | BRAY SALES MINNEAPOLIS | 4503448655 | Flow Control | Ele-Control Panels | USD | 5596 | USD | 5596 | 0 | Not included in Proposal / RFQ | 2020-08-10 | 2020-08-10 | 2020-07-06 | 2020-08-10 | 2020-08-25 | 2020-08-10 | 2020-08-10 | 2020-08-25 | 2020-08-10 | 2020-09-15 | 2020-09-14 | 1 | 12 | 15
506725 | Leprino | Minnetonka | RO MEMBRANE SKID NSF VALVES | BRAY SALES MINNEAPOLIS | 4503445700 | Flow Control | RO Membrane Housings | USD | 5839 | USD | 5839 | 0 | Not included in Proposal / RFQ | 2020-09-05 | 2020-09-05 | 2020-08-18 | 2020-09-05 | 2020-08-17 | 2020-09-05 | 2020-09-05 | 2020-08-27 | 2020-09-05 | 2020-09-24 | 2020-09-09 | 15 | 12 | -9
506725 | Leprino | Minnetonka | RO MEMBRANE NSF INSTRUMENTS | ENDRESS & HAUSER | 4503448588 | Electrical & Instrumentation | Carbon Steel | USD | 6242 | USD | 6242 | 0 | Single Sourced | 2020-08-15 | 2020-08-15 | 2020-07-15 | 2020-08-15 | 2020-08-25 | 2020-08-15 | 2020-08-15 | 2020-08-25 | 2020-08-15 | 2020-09-15 | 2020-09-16 | -1 | 18 | 10
506725 | Leprino | Minnetonka | CIP/PERMEATE FLUSH SYSTEM | Chromalox Inc. | 4503472831 | Electrical & Instrumentation | Carbon Steel | USD | 31762 | USD | 16816 | 14946 | Frame Agreements | 2020-09-28 | 2020-09-28 | 2020-07-15 | 2020-10-13 | 2020-10-12 | 2020-09-13 | 2020-10-14 | 2020-10-14 | 2020-11-13 | 2020-11-13 | 2020-11-13 | 0 | 18 | 16
506750 | Cape Girardeau | Minnetonka | Densadeg Fabrication Package and Reactor Impeller inc. balancing | SOFATEC | 4503503261 | Fabrication | Carbon Steel | USD | 280173 | USD | 197444 | 82729 | Supplier Competitions / Negotiation | 2020-08-27 | 2020-10-19 | 2020-11-09 | 2020-10-01 | 2020-12-25 | 2020-12-06 | 2020-10-15 | 2020-12-15 | 2021-03-18 | 2021-03-05 | 2021-02-23 | 10 | 36 | 57
506750 | Cape Girardeau | Minnetonka | Progressive Cavity Pumps (Drop Ship) | SEEPEX - USA | 4503483325 | Rotating Equipment | Centrifugal Pumps | USD | 41536 | USD | 17612 | 23924 | Frame Agreements | 2020-10-08 | 2020-09-11 | 2020-09-21 | 2020-11-05 | 2020-11-14 | 2020-12-14 | 2020-11-12 | 2020-11-04 | 2021-03-18 | 2021-01-06 | 2021-03-11 | -64 | 30 | 54
506750 | Cape Girardeau | Minnetonka | Progressive Cavity Pumps (Ship Loose) | SEEPEX - USA | 4503483338 | Rotating Equipment | Centrifugal Pumps | USD | 21283 | USD | 17084 | 4199 | Supplier Competitions / Negotiation | 2020-10-08 | 2020-09-11 | 2020-09-21 | 2020-11-05 | 2020-10-12 | 2020-12-10 | 2020-11-12 | 2020-11-02 | 2020-12-10 | 2020-12-28 | 2021-03-11 | -73 | 30 | 52
506750 | Cape Girardeau | Minnetonka | Densadeg Walkway and Platform | METELMEX | 4503518265 | Fabrication | Platform & Module | USD | 55269 | USD | 27857 | 27412 | Supplier Competitions / Negotiation | 2020-11-19 | 2020-11-22 | 2020-12-10 | 2020-12-17 | 2020-12-16 | 2021-01-21 | 2020-12-24 | 2021-01-19 | 2021-03-18 | 2021-03-09 | 2021-03-26 | -17 | 30 | 58
506750 | Cape Girardeau | Minnetonka | Lamella | BRENTWOOD INDUSTRIES | 4503524780 | Fabrication | Ele-Control Panels | USD | 17738 | USD | 12959 | 4779 | Design Optimizations | 2020-11-26 | 2020-11-02 | 2020-11-24 | 2020-12-17 | 2020-12-10 | 2021-01-09 | 2020-12-24 | 2021-01-23 | 2021-03-18 | 2021-02-27 | 2021-03-16 | -17 | 30 | 82
506750 | Cape Girardeau | Minnetonka | Chem Feed Skid | JOHN BROOKS COMPANY LTD. | 4503538062 | Fabrication | Skid Assembly Outsourced | USD | 15844 | CAD | 37948 | -22104 | Proposed Supplier Incapable Of Executing | 2020-10-22 | 2020-10-14 | 2021-01-29 | 2020-11-19 | 2021-01-29 | 2021-01-26 | 2020-11-26 | 2021-02-12 | 2021-03-18 | 2021-04-23 | 2021-05-10 | -17 | 12 | 121
506750 | Cape Girardeau | Minnetonka | Instrumentation (Shipped to Skids Assembler) | CLEARWATER INC. | 4503504238 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 15713 | USD | 15713 | 0 | Frame Agreements | 2020-11-26 | 2020-10-20 | 2020-11-09 | 2020-12-31 | 2020-12-03 | 2021-01-04 | 2021-01-07 | 2020-12-14 | 2021-03-18 | 2021-02-01 | 2021-03-22 | -49 | 30 | 55
506750 | Cape Girardeau | Minnetonka | Control Panel / HOA Panel | ICSE | 4503505041 | Electrical & Instrumentation | Ele-Control Panels | USD | 46108 | USD | 27457 | 18651 | Frame Agreements | 2020-10-15 | 2020-10-20 | 2020-11-10 | 2020-11-12 | 2020-12-13 | 2021-01-23 | 2020-11-26 | 2020-12-15 | 2021-03-18 | 2021-01-26 | 2021-05-04 | -98 | 12 | 56
506750 | Cape Girardeau | Minnetonka | Plug Valves Manual (Shipped To Site) | DEZURIK | 4503515608 | Flow Control | Metal Isolation Valves | USD | 13026 | USD | 15594 | -2568 | Market Impact | 2020-11-26 | 2020-10-23 | 2020-12-29 | 2020-12-31 | 2020-12-04 | 2021-01-04 | 2021-01-07 | 2021-01-09 | 2021-03-18 | 2021-02-13 | 2021-02-17 | -4 | 30 | 78
506750 | Cape Girardeau | Minnetonka | Plug Valves Automatic | PROCONEX | 4503508737 | Flow Control | Metal Isolation Valves | USD | 9528 | USD | 30392 | -20864 | Specs / Requirements Misinterpreted in Proposal | 2020-12-31 | 2020-10-23 | 2020-11-23 | 2020-12-31 | 2020-12-27 | 2020-12-31 | 2020-12-31 | 2020-12-28 | 2020-12-31 | 2021-02-08 | 2021-03-10 | -30 | 18 | 66
506750 | Cape Girardeau | Minnetonka | Plug Valves Manual (Shipped To Skids Assembler) | DEZURIK | 4503515602 | Flow Control | Metal Isolation Valves | USD | 5803 | USD | 5803 | 0 | Design Optimizations | 2021-01-11 | 2021-01-11 | 2020-12-29 | 2021-01-11 | 2020-12-06 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-01-11 | 2021-02-15 | 2021-02-17 | -2 | 30 | 0
506750 | Cape Girardeau | Minnetonka | Filter Press | EVOQUA WATER TECHNOLOGIES, LLC | 4503483952 | Rotating Equipment | Filter Press | USD | 443890 | USD | 440020 | 3870 | Supplier Competitions / Negotiation | 2020-09-30 | 2020-08-31 | 2020-09-30 | 2020-11-04 | 2020-11-12 | 2021-01-19 | 2020-11-18 | 2020-10-23 | 2021-04-21 | 2021-04-23 | 2021-06-09 | -47 | 30 | 53
506750 | Cape Girardeau | Minnetonka | Pumping Skid - Filter Press | TRIVACO | 4503503398 | Fabrication | Skid Assembly Outsourced | USD | 101781 | USD | 73649 | 28132 | Frame Agreements | 2020-09-24 | 2020-11-05 | 2020-11-17 | 2020-10-29 | 2020-11-28 | 2021-01-02 | 2020-11-12 | 2020-12-12 | 2021-03-18 | 2021-03-26 | 2021-04-12 | -17 | 30 | 37
506750 | Cape Girardeau | Minnetonka | Sludge Storage Tank | Burke's Mechanical, Inc. | 4503478575 | Fabrication | Ele-Control Panels | USD | 82727 | USD | 90013 | -7286 | Size/ Weight/ Quantity Underestimated | 2020-09-24 | 2020-09-18 | 2020-10-19 | 2020-10-29 | 2020-10-18 | 2021-01-03 | 2020-11-12 | 2020-10-25 | 2021-03-18 | 2021-01-24 | 2021-04-20 | -86 | 30 | 37
506750 | Cape Girardeau | Minnetonka | Control Valve | PROCONEX | 4503495151 | Flow Control | Metal Isolation Valves | USD | 24236 | USD | 24758 | -522 | Specs / Requirements Misinterpreted in Proposal | 2020-09-17 | 2020-09-21 | 2020-10-09 | 2020-10-22 | 2020-11-03 | 2020-12-17 | 2020-10-29 | 2020-11-30 | 2021-03-18 | 2021-01-26 | 2020-12-21 | 36 | 18 | 70
506750 | Cape Girardeau | Minnetonka | Filter Press Feed Pump Enclosure | Ferguson Enterprise | 4503542067 | Electrical & Instrumentation | Ele-Control Panels | USD | 28899 | USD | 28899 | 0 | Single Sourced | 2021-02-24 | 2021-02-24 | 2020-12-14 | 2021-02-24 | 2020-12-14 | 2021-02-24 | 2021-02-24 | 2021-02-26 | 2021-02-24 | 2021-05-07 | 2021-04-29 | 8 | 12 | 2
506751 | PECO FOODS | Oakville | DTI3 MEDIA | PEXCO | 4503456180 | Flow Control | Metal Isolation Valves | USD | 217750 | USD | 216045 | 1705 | Design Optimizations | 2020-07-09 | 2020-08-02 | 2020-08-23 | 2020-07-30 | 2020-09-03 | 2020-09-16 | 2020-08-10 | 2020-09-08 | 2020-10-02 | 2020-11-24 | 2020-10-28 | 27 | 12 | 37
506751 | PECO FOODS | Oakville | AERATION GRID | XYLEM | 4503452501 | Flow Control | Metal Isolation Valves | USD | 70300 | USD | 64725 | 5575 | Design Optimizations | 2020-06-18 | 2020-06-24 | 2020-08-06 | 2020-07-30 | 2020-08-31 | 2020-09-06 | 2020-08-10 | 2020-09-02 | 2020-10-02 | 2020-11-25 | 2020-10-29 | 27 | 12 | 70
506752 | English River Property Management Wastewater Treatment Facility | Oakville | Fine Screens | JWC Environmental Canada | 4503569241 | Rotating Equipment | Others | CAD | 155875 | CAD | 147116 | 8759 | Supplier Competitions / Negotiation | 2020-12-03 | 2020-08-24 | 2020-09-09 | 2020-12-17 | 2021-04-06 | 2021-02-23 | 2020-12-24 | 2021-04-15 | 2021-05-18 | 2021-08-25 | 2021-07-06 | 50 | 30 | 234
506752 | English River Property Management Wastewater Treatment Facility | Oakville | Electrical Panel | KELTOUR CONTROLS INC. | 4503590567 | Electrical & Instrumentation | Ele-Control Panels | CAD | 55831 | CAD | 56626 | -795 | Proposed Supplier Incapable Of Executing | 2020-12-03 | 2021-05-05 | 2021-05-19 | 2020-12-17 | 2021-05-20 | 2021-03-27 | 2020-12-24 | 2021-05-24 | 2021-03-25 | 2021-07-19 | 2021-05-22 | 58 | 18 | 19
506752 | English River Property Management Wastewater Treatment Facility | Oakville | Dosing Pump | PROMINENT FLUID CONTROLS LTD. | 4503576691 | Rotating Equipment | Dosing Pump | CAD | 32740 | CAD | 25840 | 6900 | Frame Agreements | 2020-12-03 | 2020-08-07 | 2020-10-10 | 2020-12-17 | 2021-04-29 | 2021-02-08 | 2020-12-24 | 2021-04-29 | 2021-03-25 | 2021-08-13 | 2021-06-03 | 71 | 30 | 265
506752 | English River Property Management Wastewater Treatment Facility | Oakville | Blowers | AERZEN CANADA INC. | 4503569230 | Rotating Equipment | Blowers & Fans | CAD | 41200 | CAD | 40680 | 520 | Frame Agreements | 2020-12-07 | 2020-07-15 | 2020-09-02 | 2020-12-10 | 2021-04-06 | 2021-01-24 | 2020-12-17 | 2021-04-15 | 2021-05-18 | 2021-08-05 | 2021-06-26 | 40 | 30 | 274
506752 | English River Property Management Wastewater Treatment Facility | Oakville | Flow Transmitter | ENDRESS + HAUSER CANADA LTD. | 4503584070 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | CAD | 18250 | USD | 10931 | 7319 | Supplier Competitions / Negotiation | 2020-12-31 | 2021-05-05 | 2021-05-07 | 2021-01-14 | 2021-05-09 | 2021-04-03 | 2021-01-21 | 2021-05-11 | 2021-03-25 | 2021-07-06 | 2021-05-15 | 52 | 18 | 6
506752 | English River Property Management Wastewater Treatment Facility | Oakville | RAS Pumps | SULZER PUMPS (CANADA) INC. | 4503564497 | Rotating Equipment | Centrifugal Pumps | CAD | 24979 | CAD | 14110 | 10869 | Frame Agreements | 2020-12-03 | 2020-07-15 | 2020-07-16 | 2020-12-17 | 2021-04-06 | 2021-02-02 | 2020-12-24 | 2021-04-07 | 2021-03-25 | 2021-08-24 | 2021-06-09 | 76 | 30 | 266
506752 | English River Property Management Wastewater Treatment Facility | Oakville | Fabrication- Frames (Part 4) | 3D MECHANICAL | 4503586866 | Fabrication | Stainless Steel | CAD | 8875 | CAD | 8875 | 0 | Market Impact | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 2021-05-18 | 0 | 12 | 0
506752 | English River Property Management Wastewater Treatment Facility | Oakville | Compressor | Compressor Science Inc. | 4503583441 | Rotating Equipment | Compressors | CAD | 14007 | USD | 15903 | -1896 | Size/ Weight/ Quantity Underestimated | 2020-12-17 | 2021-05-03 | 2021-05-03 | 2020-12-31 | 2021-05-03 | 2021-03-20 | 2021-01-07 | 2021-05-10 | 2021-03-25 | 2021-06-21 | 2021-05-08 | 44 | 30 | 7
506752 | English River Property Management Wastewater Treatment Facility | Oakville | Knife Gate Valves | WOLSELEY INDUSTRIAL CANADA INC | 4503577023 | Flow Control | Metal Control Valves | CAD | 6802 | CAD | 10795 | -3993 | Specs / Requirements Misinterpreted in Proposal | 2021-04-05 | 2021-10-04 | 2020-10-06 | 2021-04-05 | 2021-04-29 | 2021-04-05 | 2021-04-05 | 2021-04-29 | 2021-04-05 | 2021-07-19 | 2021-05-27 | 53 | 12 | -158
506752 | English River Property Management Wastewater Treatment Facility | Oakville | Diffuser | ENVIRONMENTAL DYNAMICS | 4503571618 | Flow Control | Injection Quills, Ejectors, Diffusers | CAD | 20905 | USD | 17290 | 3615 | Supplier Competitions / Negotiation | 2020-12-03 | 2020-07-28 | 2020-09-22 | 2020-12-17 | 2021-04-06 | 2021-02-11 | 2020-12-24 | 2021-04-20 | 2021-05-18 | 2021-08-28 | 2021-07-08 | 51 | 12 | 266
506752 | English River Property Management Wastewater Treatment Facility | Oakville | Anoxic Mixers | XYLEM CANADA COMPANY | 4503574642 | Rotating Equipment | Mixers | CAD | 34218 | CAD | 7810 | 26408 | Design Optimizations | 2020-12-03 | 2020-08-14 | 2020-08-20 | 2020-12-17 | 2021-04-06 | 2021-01-11 | 2020-12-24 | 2021-04-26 | 2021-03-25 | 2021-06-10 | 2021-05-02 | 39 | 30 | 255
506782 | Enterprise PDH II | Richmond | Accelator | AZ INDUSTRIES | 4503570027 | Fabrication | Metal Isolation Valves | USD | 302940 | USD | 232020 | 70920 | Frame Agreements | 2021-02-05 | 2020-09-09 | 2021-04-15 | 2021-03-12 | 2021-04-14 | 2021-03-21 | 2021-04-23 | 2021-04-14 | 2021-10-01 | 2021-04-14 | 2021-07-08 | -85 | 12 | 217
506782 | Enterprise PDH II | Richmond | Filter Press | EVOQUA WATER TECHNOLOGIES, LLC | 4503451319 | Rotating Equipment | Filter Press | USD | 105319 | USD | 120360 | -15041 | Proposed Supplier Incapable Of Executing | 2021-02-05 | 2020-07-02 | 2020-07-30 | 2021-03-05 | 2020-07-30 | 2021-02-15 | 2021-04-23 | 2020-08-25 | 2021-10-01 | 2021-08-29 | 2021-09-14 | -16 | 30 | 54
506782 | Enterprise PDH II | Richmond | Sludge Thickener | SPS ENGINEERING INC | 4503438951 | Fabrication | Ele-Control Panels | USD | 156876 | USD | 147958 | 8918 | Design Optimizations | 2020-12-25 | 2020-06-26 | 2020-08-07 | 2021-01-22 | 2020-08-20 | 2021-02-12 | 2021-03-05 | 2020-08-19 | 2021-10-01 | 2021-08-30 | 2021-09-15 | -16 | 12 | 54
506782 | Enterprise PDH II | Richmond | Instrumentation (Magnetrol Level Switch) | EW PROCESS | 4503640203 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 13813 | USD | 5408 | 8405 | Design Optimizations | 2021-04-30 | 2021-07-07 | 2021-06-24 | 2021-05-28 | 2021-08-23 | 2021-07-17 | 2021-07-09 | 2021-08-23 | 2021-10-01 | 2021-10-04 | 2021-10-02 | 2 | 18 | 47
506782 | Enterprise PDH II | Richmond | Sludge Forwarding Pumps/ Sump Pump (Sulzer) | SULZER PUMP SOLUTIONS - USA | 4503584986 | Rotating Equipment | Centrifugal Pumps | USD | 46583 | USD | 51828 | -5245 | Specs / Requirements Misinterpreted in Proposal | 2021-03-05 | 2020-08-05 | 2020-08-18 | 2021-04-02 | 2021-05-10 | 2021-03-04 | 2021-05-14 | 2021-05-18 | 2021-10-01 | 2021-09-30 | 2021-09-30 | 0 | 30 | 286
506782 | Enterprise PDH II | Richmond | Sump Mixer | R.E. MASON | 4503580438 | Rotating Equipment | Centrifugal Pumps | USD | 17187 | USD | 19030 | -1843 | Single Sourced | 2021-03-05 | 2020-08-05 | 2020-08-24 | 2021-04-02 | 2021-04-29 | 2021-03-04 | 2021-05-14 | 2021-05-07 | 2021-10-01 | 2021-08-15 | 2021-09-07 | -23 | 30 | 275
506785 | Ocean State Power Seed Recycle System | Oakville | HYDROCYCLONE | FLSmidth Krebs | 4503466432 | Rotating Equipment | Ele-Control Panels | USD | 58625 | USD | 58475 | 150 | Supplier Competitions / Negotiation | 2020-09-01 | 2020-12-30 | 2020-09-25 | 2020-09-15 | 2020-09-27 | 2020-12-30 | 2020-09-30 | 2020-09-27 | 2021-04-30 | 2021-02-14 | 2021-03-23 | -37 | 30 | -94
506785 | Ocean State Power Seed Recycle System | Oakville | HYDROCYCLONE PUMP | Flowserve US Inc. | 4503467121 | Rotating Equipment | Centrifugal Pumps | USD | 11166 | USD | 12046 | -880 | Specs / Requirements Misinterpreted in Proposal | 2020-09-01 | 2020-11-11 | 2020-09-30 | 2020-09-15 | 2020-10-01 | 2020-11-11 | 2020-10-01 | 2020-10-01 | 2021-01-20 | 2021-01-21 | 2021-01-20 | 1 | 30 | -41
506799 | Hyperion | Oakville | Vendor Control Panel (MCP + MCC) | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503538009 | Electrical & Instrumentation | Ele-Control Panels | USD | 95000 | USD | 39699 | 55301 | Design Optimizations | 2020-10-25 | 2021-01-16 | 2021-01-29 | 2020-11-10 | 2021-02-09 | 2020-12-21 | 2020-11-22 | 2021-02-17 | 2021-01-13 | 2021-02-17 | 2021-01-30 | 18 | 18 | 32
506799 | Hyperion | Oakville | 500D Lifting Module, Beam, Hanger-Arm, Hanger Brace & Beam Bracket | 3D MECHANICAL | 4503501856 | Fabrication | Platform & Module | USD | 7177 | USD | 10339 | -3162 | Single Sourced | 2020-10-01 | 2020-10-28 | 2020-11-17 | 2020-10-15 | 2020-11-26 | 2020-12-15 | 2020-11-01 | 2020-12-10 | 2021-03-01 | 2020-12-10 | 2021-01-19 | -40 | 12 | 43
506799 | Hyperion | Oakville | Mag Flow Meter, RAS Mag Meter, Temperature & Air Pressure Transmitter | ENDRESS + HAUSER CANADA LTD. | 4503507665 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 5034 | USD | 15184 | -10150 | Specs / Requirements Misinterpreted in Proposal | 2020-10-20 | 2020-11-19 | 2020-12-05 | 2020-11-05 | 2020-12-15 | 2021-01-06 | 2020-11-15 | 2020-12-23 | 2021-02-15 | 2021-03-25 | 2021-03-06 | 19 | 18 | 34
506799 | Hyperion | Oakville | RAS Pump system | SULZER PUMPS (CANADA) INC. | 4503511324 | Rotating Equipment | Centrifugal Pumps | USD | 15200 | USD | 17546 | -2346 | Size/ Weight/ Quantity Underestimated | 2020-10-01 | 2020-11-28 | 2020-12-15 | 2020-10-15 | 2020-12-25 | 2021-01-02 | 2020-11-01 | 2021-01-06 | 2021-03-01 | 2021-04-05 | 2021-03-18 | 18 | 30 | 39
506799 | Hyperion | Oakville | Citric Acid - Peristaltic & Sodium Hypo - Peristaltic Pump & Process Skid Fab | PROMINENT FLUID CONTROLS LTD. | 4503512754 | Rotating Equipment | Centrifugal Pumps | USD | 32204 | USD | 56346 | -24142 | Not included in Proposal / RFQ | 2020-11-15 | 2020-11-30 | 2020-12-12 | 2020-11-30 | 2020-12-22 | 2021-01-17 | 2020-12-15 | 2021-01-07 | 2021-03-15 | 2021-03-21 | 2021-03-18 | 3 | 30 | 38
506799 | Hyperion | Oakville | Process Pump | BOERGER LLC | 4503507336 | Rotating Equipment | Centrifugal Pumps | USD | 11347 | USD | 27524 | -16177 | Specs / Requirements Misinterpreted in Proposal | 2020-11-15 | 2020-11-06 | 2020-11-28 | 2020-11-30 | 2020-12-11 | 2021-01-09 | 2020-12-15 | 2020-12-22 | 2021-03-15 | 2020-12-22 | 2021-02-01 | -41 | 30 | 46
506799 | Hyperion | Oakville | Aerzen Blower GM10S DN 80; 15 HP @ 1800 RPM with sound enclosure | AERZEN CANADA INC. | 4503499156 | Rotating Equipment | Carbon Steel | USD | 7495 | USD | 10827 | -3332 | Estimate Without Market Reference(No Quote) | 2020-10-01 | 2020-10-26 | 2020-11-12 | 2020-10-10 | 2020-11-20 | 2021-01-02 | 2020-10-20 | 2020-12-06 | 2021-03-07 | 2021-04-06 | 2021-03-22 | 15 | 30 | 41
506799 | Hyperion | Oakville | SS Tank 1 x 52M w Rail & Memb Deflector Plate & Tank Drain/RAS Solenoid Valve For Steel Tank | D&R CUSTOM STEEL | 4503505149 | Fabrication | Alloy Steel | USD | 33260 | USD | 42263 | -9003 | Single Sourced | 2020-10-01 | 2020-11-06 | 2020-11-25 | 2020-10-10 | 2020-12-08 | 2020-12-23 | 2020-10-20 | 2020-12-17 | 2021-03-07 | 2021-03-17 | 2021-03-12 | 5 | 12 | 41
506799 | Hyperion | Oakville | Seismic Design, Cals and Considerations | The Leffler Group | 4503470943 | Fabrication | Metal Isolation Valves | USD | 8600 | USD | 10400 | -1800 | Size/ Weight/ Quantity Underestimated | 2020-09-15 | 2020-08-24 | 2020-09-15 | 2020-09-15 | 2020-09-23 | 2020-09-15 | 2020-09-15 | 2020-10-08 | 2020-09-15 | 2020-10-08 | 2020-09-26 | 12 | 12 | 45
506879 | Niagara Mesa | Minnetonka | RO & ACF PANELS | BW Systems | 4503462961 | Electrical & Instrumentation | Carbon Steel | USD | 28020 | USD | 28020 | 0 | Specs / Requirements Misinterpreted in Proposal | 2020-09-16 | 2020-09-16 | 2020-09-22 | 2020-09-23 | 2020-09-22 | 2020-10-04 | 2020-09-23 | 2020-09-23 | 2020-10-23 | 2020-10-21 | 2020-10-22 | -1 | 18 | 7
506879 | Niagara Mesa | Minnetonka | AC TOWER 96X168 | Arrow Tanks | 4503451401 | Fabrication | Carbon Steel | USD | 76000 | USD | 76000 | 0 | Not included in Proposal / RFQ | 2020-08-12 | 2020-08-12 | 2020-08-13 | 2020-08-18 | 2020-08-14 | 2020-10-05 | 2020-08-18 | 2020-08-14 | 2020-11-20 | 2020-11-28 | 2020-11-24 | 4 | 12 | 2
506879 | Niagara Mesa | Minnetonka | TEKLEEN | TEKLEEN | 4503453501 | Fabrication | Ele-Control Panels | USD | 20175 | USD | 23700 | -3525 | Market Impact | 2020-08-31 | 2020-08-31 | 2020-09-02 | 2020-09-02 | 2020-09-02 | 2020-10-27 | 2020-09-03 | 2020-09-10 | 2020-12-23 | 2020-12-24 | 2020-12-23 | 1 | 12 | 10
506879 | Niagara Mesa | Minnetonka | TEKLEEN - CONTROLLER | TEKLEEN | 4503469532 | Fabrication | Ele-Control Panels | USD | 7200 | USD | 7200 | 0 | Single Sourced | 2020-09-23 | 2020-09-23 | 2020-09-25 | 2020-10-06 | 2020-10-04 | 2020-10-21 | 2020-10-07 | 2020-10-06 | 2020-11-18 | 2020-11-17 | 2020-11-17 | 0 | 12 | 13
506880 | Niagara Kansas City | Minnetonka | AC TOWER 96X168 | Arrow Tanks | 4503451913 | Fabrication | Carbon Steel | USD | 64000 | USD | 64000 | 0 | Frame Agreements | 2020-08-12 | 2020-10-01 | 2020-09-18 | 2020-08-18 | 2020-08-29 | 2020-10-01 | 2020-08-18 | 2020-08-30 | 2020-11-20 | 2020-11-09 | 2020-11-14 | -5 | 12 | -32
506880 | Niagara Kansas City | Minnetonka | Electrical Panels | BW Systems | 4503462963 | Electrical & Instrumentation | Ele-Electrical Others | USD | 43795 | USD | 43795 | 0 | Estimate Without Market Reference(No Quote) | 2020-09-16 | 2020-09-16 | 2020-09-22 | 2020-09-22 | 2020-09-22 | 2020-10-07 | 2020-09-23 | 2020-09-23 | 2020-10-21 | 2020-10-28 | 2020-10-24 | 4 | 18 | 7
506908 | South Collier County | Richmond | Rotor Impeller Drive | Tampa Tank | 4503550640 | Rotating Equipment | Metal Isolation Valves | USD | 15235 | USD | 29324 | -14089 | Single Sourced | 2020-01-25 | 2020-08-31 | 2021-03-02 | 2020-03-07 | 2021-03-02 | 2020-08-31 | 2020-03-10 | 2021-03-10 | 2020-05-12 | 2021-04-07 | 2020-10-24 | 165 | 30 | 191
506908 | South Collier County | Richmond | Rotor Impeller Drive | SEW EURODRIVE | 4503549840 | Rotating Equipment | Metal Isolation Valves | USD | 25089 | USD | 25089 | 0 | Single Sourced | 2021-04-25 | 2021-04-25 | 2021-03-19 | 2021-04-25 | 2021-03-18 | 2021-04-25 | 2021-04-25 | 2021-03-18 | 2021-04-25 | 2021-06-03 | 2021-05-14 | 20 | 30 | -38
506908 | South Collier County | Richmond | Accelator Tank (#22) Internals | Tampa Tank | 4503550638 | Fabrication | Centrifugal Pumps | USD | 184590 | USD | 196059 | -11469 | Specs / Requirements Misinterpreted in Proposal | 2020-01-25 | 2020-08-31 | 2021-03-02 | 2020-03-07 | 2021-03-11 | 2020-08-31 | 2020-03-10 | 2021-03-11 | 2020-04-14 | 2021-04-08 | 2020-10-10 | 180 | 12 | 192
506908 | South Collier County | Richmond | Bottom Flushing System | Tampa Tank | 4503550632 | Fabrication | Carbon Steel | USD | 44549 | USD | 63957 | -19408 | Single Sourced | 2020-01-15 | 2020-08-26 | 2021-03-02 | 2020-02-26 | 2021-03-03 | 2020-08-26 | 2020-02-29 | 2021-03-11 | 2020-04-04 | 2021-04-08 | 2020-10-05 | 185 | 12 | 197
506908 | South Collier County | Richmond | Launders | Tampa Tank | 4503550643 | Fabrication | Ele-Control Panels | USD | 67837 | USD | 166456 | -98619 | Not included in Proposal / RFQ | 2020-01-29 | 2020-09-25 | 2021-03-02 | 2020-03-11 | 2021-02-01 | 2020-09-25 | 2020-03-14 | 2021-04-25 | 2020-04-18 | 2021-05-23 | 2020-11-04 | 200 | 12 | 212
506908 | South Collier County | Richmond | Platforms & Walkways | Tampa Tank | 4503555789 | Fabrication | Metal Isolation Valves | USD | 64975 | USD | 68530 | -3555 | Single Sourced | 2020-01-26 | 2020-08-20 | 2020-08-20 | 2020-03-08 | 2021-03-16 | 2020-08-20 | 2020-03-11 | 2020-08-20 | 2020-04-15 | 2020-08-20 | 2020-06-17 | 64 | 12 | 0
506908 | South Collier County | Richmond | Valves | AUTOMATIC CONTROLS OF VIRGINIA, INC | 4503572769 | Flow Control | Metal Isolation Valves | USD | 20039 | USD | 9600 | 10439 | Frame Agreements | 2020-01-26 | 2020-09-20 | 2021-03-02 | 2020-03-08 | 2021-03-04 | 2020-09-20 | 2020-03-11 | 2021-03-08 | 2020-05-06 | 2021-05-17 | 2020-11-10 | 188 | 12 | 169
506908 | South Collier County | Richmond | Control Panel | ELECTRICAL EQUIPMENT COMP | 4503529774 | Electrical & Instrumentation | Ele-Control Panels | USD | 24920 | USD | 28313 | -3393 | Single Sourced | 2020-01-26 | 2020-09-04 | 2021-01-19 | 2020-03-08 | 2021-02-08 | 2020-09-04 | 2020-03-11 | 2021-02-03 | 2020-05-06 | 2021-04-14 | 2020-10-24 | 172 | 18 | 152
506937 | PEPSICO GUATEMALA | Minnetonka | ELECTRICAL | PTS Products | 4503553382 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 60809 | USD | 35514 | 25295 | Design Optimizations | 2021-04-01 | 2021-04-01 | 2021-03-17 | 2021-04-01 | 2021-03-17 | 2021-04-01 | 2021-04-01 | 2021-03-17 | 2021-04-01 | 2021-04-16 | 2021-04-08 | 8 | 18 | -15
506937 | PEPSICO GUATEMALA | Minnetonka | UF CLEANING CHEM SKIDS | PROMINENT FLUID CONTROLS LTD. | 4503510340 | Electrical & Instrumentation | Carbon Steel | CAD | 27688 | CAD | 20712 | 6976 | Frame Agreements | 2021-02-01 | 2021-03-04 | 2021-01-04 | 2021-02-10 | 2021-01-03 | 2021-03-04 | 2021-02-15 | 2021-01-03 | 2021-05-01 | 2021-05-04 | 2021-05-02 | 2 | 18 | -60
506937 | PEPSICO GUATEMALA | Minnetonka | RAS PUMPS UF | FLOWSERVE INC. | 4503495432 | Rotating Equipment | Metal Isolation Valves | CAD | 47369 | USD | 37845 | 9524 | Supplier Competitions / Negotiation | 2020-10-19 | 2021-01-09 | 2020-10-20 | 2020-10-30 | 2020-11-30 | 2021-01-09 | 2020-11-01 | 2020-11-30 | 2021-04-01 | 2021-04-01 | 2021-04-01 | 0 | 30 | -40
506937 | PEPSICO GUATEMALA | Minnetonka | MBR TANKS | D & R FABRICATION INC - BELDING TANKS | 4503479325 | Fabrication | Metal Isolation Valves | CAD | 227208 | CAD | 203192 | 24016 | Frame Agreements | 2020-10-19 | 2021-01-16 | 2020-10-27 | 2020-10-27 | 2020-10-24 | 2021-01-16 | 2020-10-27 | 2020-10-25 | 2021-04-15 | 2021-02-28 | 2021-03-23 | -23 | 12 | -83
506945 | Winona WTP, Peabody MA | Richmond | Control Panel w/ Spares | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503625577 | Electrical & Instrumentation | Ele-Control Panels | USD | 134155 | CAD | 67144 | 67011 | Supplier Competitions / Negotiation | 2021-03-13 | 2021-03-05 | 2021-03-16 | 2021-04-10 | 2021-07-20 | 2021-06-06 | 2021-05-08 | 2021-07-27 | 2021-07-31 | 2021-09-07 | 2021-08-19 | 19 | 18 | 144
506945 | Winona WTP, Peabody MA | Richmond | Laterals (EMBEDMENT ITEMS) - Anchors | 3D MECHANICAL | 4503625909 | Fabrication | Centrifugal Pumps | USD | 11137 | USD | 27178 | -16041 | Not included in Proposal / RFQ | 2021-03-13 | 2021-04-12 | 2021-07-23 | 2021-04-10 | 2021-07-22 | 2021-06-24 | 2021-05-08 | 2021-07-27 | 2021-07-31 | 2021-10-05 | 2021-09-02 | 33 | 12 | 106
506945 | Winona WTP, Peabody MA | Richmond | Level Transmitters w/ Spares-Siemens | LAKESIDE PROCESS CONTROLS LTD. | 4503613115 | Electrical & Instrumentation | Inst-Multiparam Transmitters, Controllers | USD | 21938 | USD | 20046 | 1892 | Design Optimizations | 2021-03-13 | 2021-06-29 | 2021-06-29 | 2021-04-10 | 2021-07-01 | 2021-05-30 | 2021-05-08 | 2021-07-05 | 2021-07-31 | 2021-08-16 | 2021-08-08 | 8 | 18 | 6
506945 | Winona WTP, Peabody MA | Richmond | Weir Actuator | DUFF NORTON | 4503602249 | Electrical & Instrumentation | Metal Isolation Valves | USD | 17727 | USD | 15925 | 1802 | Frame Agreements | 2021-03-13 | 2020-10-04 | 2020-10-08 | 2021-04-10 | 2021-06-04 | 2021-03-16 | 2021-05-08 | 2021-06-15 | 2021-07-31 | 2021-08-27 | 2021-08-13 | 14 | 18 | 254
506945 | Winona WTP, Peabody MA | Richmond | Air Compressor | ATLAS COPCO COMPRESSORS | 4503585230 | Rotating Equipment | Vapor Compressor | USD | 8629 | USD | 9691 | -1062 | Specs / Requirements Misinterpreted in Proposal | 2021-03-13 | 2020-10-14 | 2020-10-21 | 2021-04-10 | 2021-05-07 | 2021-03-08 | 2021-05-08 | 2021-05-14 | 2021-07-31 | 2021-07-23 | 2021-07-27 | -4 | 30 | 212
506945 | Winona WTP, Peabody MA | Richmond | Mixers | SPX FLOW INC | 4503606787 | Rotating Equipment | Mixers | USD | 38783 | USD | 37000 | 1783 | Frame Agreements | 2021-03-13 | 2021-02-09 | 2021-02-19 | 2021-04-10 | 2021-06-04 | 2021-05-19 | 2021-05-08 | 2021-06-23 | 2021-07-31 | 2021-08-27 | 2021-08-13 | 14 | 30 | 134
506945 | Winona WTP, Peabody MA | Richmond | Recycle Pumps & Baffle | FLOWSERVE | 4503506373 | Rotating Equipment | Centrifugal Pumps | USD | 84159 | USD | 81000 | 3159 | Supplier Competitions / Negotiation | 2021-03-13 | 2020-10-13 | 2020-10-19 | 2021-04-10 | 2020-12-07 | 2021-03-07 | 2021-05-08 | 2020-12-21 | 2021-07-31 | 2021-06-28 | 2021-07-14 | -16 | 30 | 69
506945 | Winona WTP, Peabody MA | Richmond | Manual Valves | HAJOCA CORP | 4503614721 | Flow Control | Metal Isolation Valves | USD | 19146 | USD | 17243 | 1903 | Supplier Competitions / Negotiation | 2021-03-13 | 2020-12-11 | 2020-12-11 | 2021-04-10 | 2021-07-04 | 2021-04-11 | 2021-05-08 | 2021-07-05 | 2021-07-31 | 2021-08-10 | 2021-08-05 | 5 | 12 | 206
506945 | Winona WTP, Peabody MA | Richmond | Air Saturation Tank w/ Packing (AIR SATURATION SYSTEM FABRICATIONS) | BE PETERSON | 4503606633 | Fabrication | Metal Isolation Valves | USD | 48696 | USD | 70092 | -21396 | Estimate Without Market Reference(No Quote) | 2021-03-13 | 2021-04-12 | 2021-04-27 | 2021-04-10 | 2021-06-01 | 2021-06-19 | 2021-05-08 | 2021-06-20 | 2021-07-31 | 2021-09-26 | 2021-08-28 | 29 | 12 | 69
506954 | City of Leoni MBR retrofit | Oakville | Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503658246 | Electrical & Instrumentation | Ele-Control Panels | USD | 53000 | CAD | 38720 | 14280 | Design Optimizations | 2020-12-22 | 2021-09-17 | 2021-09-23 | 2020-12-30 | 2021-09-26 | 2021-06-03 | 2020-12-31 | 2021-09-27 | 2021-02-01 | 2021-11-14 | 2021-06-24 | 143 | 18 | 10
506954 | City of Leoni MBR retrofit | Oakville | Diffuser | ENVIRONMENTAL DYNAMICS | 4503600568 | Flow Control | Centrifugal Pumps | USD | 60000 | USD | 51320 | 8680 | Design Optimizations | 2021-03-01 | 2020-10-28 | 2020-11-05 | 2021-03-29 | 2021-06-04 | 2021-04-01 | 2021-04-05 | 2021-06-11 | 2021-06-28 | 2021-09-03 | 2021-07-31 | 34 | 12 | 226
506954 | City of Leoni MBR retrofit | Oakville | Fabrication-500D Lifting Module,Side & Middle Bracket,500D Hanger/Arm | 3D MECHANICAL | 4503657395 | Fabrication | Platform & Module | USD | 56255 | CAD | 111314 | -55059 | Specs / Requirements Misinterpreted in Proposal | 2020-12-23 | 2020-11-27 | 2021-01-22 | 2020-12-30 | 2021-09-26 | 2021-05-29 | 2021-01-04 | 2021-09-27 | 2021-02-01 | 2021-11-29 | 2021-07-01 | 151 | 12 | 304
506954 | City of Leoni MBR retrofit | Oakville | Flow Transmitter | ENDRESS & HAUSER | 4503664516 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 10434 | USD | 8126 | 2308 | Supplier Competitions / Negotiation | 2021-04-20 | 2021-08-07 | 2021-10-06 | 2021-04-26 | 2021-10-07 | 2021-08-07 | 2021-05-03 | 2021-10-07 | 2021-06-28 | 2021-11-24 | 2021-09-10 | 75 | 18 | 61
506954 | City of Leoni MBR retrofit | Oakville | Piping-Stainless steel | NV PIPING SYSTEMS INC. | 4503606167 | Fabrication | Stainless Steel | USD | 42888 | CAD | 44958 | -2070 | Estimate Without Market Reference(No Quote) | 2021-05-06 | 2021-06-08 | 2021-06-15 | 2021-05-10 | 2021-06-13 | 2021-06-14 | 2021-05-17 | 2021-07-20 | 2021-06-28 | 2021-07-24 | 2021-07-11 | 13 | 12 | 42
506954 | City of Leoni MBR retrofit | Oakville | Air Compressor & Dryer-Interim | Compressor Science Inc. | 4503509409 | Rotating Equipment | Vapor Compressor | USD | 10743 | USD | 10743 | 0 | Proposed Supplier Incapable Of Executing | 2020-12-23 | 2020-12-21 | 2020-12-24 | 2020-12-30 | 2020-12-28 | 2021-01-14 | 2021-01-04 | 2020-12-30 | 2021-02-01 | 2021-02-08 | 2021-02-04 | 4 | 30 | 9
506954 | City of Leoni MBR retrofit | Oakville | Air Blower | AERZEN CANADA INC. | 4503602766 | Rotating Equipment | Metal Isolation Valves | USD | 125260 | CAD | 179244 | -53984 | Estimate Without Market Reference(No Quote) | 2020-12-23 | 2020-12-07 | 2020-12-14 | 2020-12-30 | 2021-06-07 | 2021-05-10 | 2021-01-04 | 2021-06-14 | 2021-02-01 | 2021-10-12 | 2021-06-07 | 127 | 30 | 189
506954 | City of Leoni MBR retrofit | Oakville | Air Blower-Interim | AERZEN CANADA INC. | 4503509408 | Rotating Equipment | Centrifugal Pumps | USD | 10925 | CAD | 17655 | -6730 | Single Sourced | 2020-12-23 | 2020-12-20 | 2020-12-24 | 2020-12-30 | 2020-12-24 | 2021-01-11 | 2021-01-04 | 2020-12-30 | 2021-02-02 | 2021-01-22 | 2021-01-27 | -5 | 30 | 10
506954 | City of Leoni MBR retrofit | Oakville | Dosing Pumps-Mag driven | JOHN BROOKS COMPANY LTD. | 4503649511 | Rotating Equipment | Dosing Pump | USD | 28000 | CAD | 7216 | 20784 | Design Optimizations | 2021-03-10 | 2021-01-22 | 2021-01-26 | 2021-03-15 | 2021-06-02 | 2021-06-02 | 2021-03-22 | 2021-09-09 | 2021-06-28 | 2021-10-11 | 2021-08-19 | 53 | 30 | 230
506954 | City of Leoni MBR retrofit | Oakville | Process Pumps | BOERGER, INC | 4503643649 | Rotating Equipment | Centrifugal Pumps | USD | 78000 | USD | 68322 | 9678 | Design Optimizations | 2021-02-25 | 2020-10-16 | 2020-10-30 | 2021-03-01 | 2021-08-28 | 2021-05-01 | 2021-03-08 | 2021-08-31 | 2021-06-28 | 2021-11-15 | 2021-09-06 | 70 | 30 | 319
506954 | City of Leoni MBR retrofit | Oakville | Valves-Actuator | BRAY CONTROLS CANADA LTD. | 4503654949 | Flow Control | Metal Isolation Valves | USD | 25240 | USD | 24864 | 376 | Supplier Competitions / Negotiation | 2021-02-01 | 2021-08-06 | 2021-09-08 | 2021-02-15 | 2021-09-20 | 2021-08-06 | 2021-02-22 | 2021-09-21 | 2021-06-28 | 2022-02-08 | 2021-10-18 | 113 | 12 | 46
506973 | MP Materials | Oakville | XLZR Heater Tubes | NEOTISS, INC. | 4503463723 | Fabrication | Alloy Steel | USD | 305298 | USD | 319005 | -13707 | Proposed Supplier Incapable Of Executing | 2020-09-11 | 2020-09-14 | 2020-09-22 | 2020-09-26 | 2020-09-17 | 2020-11-16 | 2020-10-01 | 2020-09-23 | 2021-01-21 | 2020-12-04 | 2020-12-19 | -15 | 12 | 9
506973 | MP Materials | Oakville | Recirculation Pump - axial flow | WEIR MINERALS | 4503469861 | Rotating Equipment | Centrifugal Pumps | USD | 347829 | USD | 392898 | -45069 | Estimate Without Market Reference(No Quote) | 2020-09-18 | 2020-09-21 | 2020-10-07 | 2020-10-02 | 2020-09-29 | 2020-12-26 | 2020-10-05 | 2020-10-03 | 2021-04-05 | 2021-03-21 | 2021-03-28 | -7 | 30 | 12
506973 | MP Materials | Oakville | Centrifuge | FERRUM PROCESS SYSTEMS | 4503476531 | Rotating Equipment | Centrifuge | USD | 380395 | USD | 318800 | 61595 | Frame Agreements | 2020-09-17 | 2020-09-21 | 2020-10-12 | 2020-10-02 | 2020-10-17 | 2021-01-13 | 2020-10-07 | 2020-10-19 | 2021-04-07 | 2021-03-15 | 2021-05-11 | -57 | 30 | 28
506973 | MP Materials | Oakville | Crystallizer Vapor Body | Harris Thermal Transfer Products | 4503471065 | Fabrication | Process Equipment | USD | 1292225 | USD | 1393882 | -101657 | Estimate Without Market Reference(No Quote) | 2020-09-25 | 2020-08-31 | 2020-09-30 | 2020-10-10 | 2020-10-06 | 2021-01-08 | 2020-10-15 | 2020-10-08 | 2021-03-11 | 2021-04-22 | 2021-05-18 | -26 | 12 | 38
506973 | MP Materials | Oakville | Crystallizer Heater | Harris Thermal Transfer Products | 450347106 | Fabrication | Process Equipment | USD | 832420 | USD | 718500 | 113920 | Frame Agreements | 2020-09-25 | 2020-08-31 | 2020-09-30 | 2020-10-10 | 2020-10-08 | 2020-12-28 | 2020-10-15 | 2020-10-09 | 2021-04-01 | 2021-03-19 | 2021-04-26 | -38 | 12 | 39
506973 | MP Materials | Oakville | Duct Work | NORTHWEST COPPER WORKS | 4503498375 | Fabrication | Stainless Steel | USD | 567495 | USD | 941462 | -373967 | Estimate Without Market Reference(No Quote) | 2020-10-18 | 2020-11-05 | 2020-11-19 | 2020-10-31 | 2020-11-29 | 2021-01-18 | 2020-11-03 | 2020-12-02 | 2021-04-20 | 2021-04-07 | 2021-04-13 | -6 | 12 | 27
506973 | MP Materials | Oakville | Centrate Tank/Condensate Tank | Harris Thermal Transfer Products | 4503477224 | Fabrication | Stainless Steel | USD | 88000 | USD | 114623 | -26623 | Single Sourced | 2020-10-06 | 2020-10-06 | 2020-10-14 | 2020-10-21 | 2020-10-20 | 2021-01-11 | 2020-10-26 | 2020-10-21 | 2021-04-12 | 2021-02-03 | 2021-04-19 | -75 | 12 | 15
506973 | MP Materials | Oakville | Vaccum Pump | Flowserve Canada Corp. | 4503472946 | Rotating Equipment | PD Pumps | USD | 48330 | USD | 121695 | -73365 | Specs / Requirements Misinterpreted in Proposal | 2020-09-28 | 2020-08-31 | 2020-10-05 | 2020-10-12 | 2020-10-06 | 2021-01-22 | 2020-10-15 | 2020-10-09 | 2021-03-04 | 2021-04-13 | 2021-06-16 | -64 | 30 | 39
506973 | MP Materials | Oakville | Hydrocyclone | FLSmidth Krebs | 4503477889 | Fabrication | Process Equipment | USD | 54905 | USD | 83250 | -28345 | Estimate Without Market Reference(No Quote) | 2020-10-02 | 2020-10-02 | 2020-10-06 | 2020-10-17 | 2020-10-19 | 2021-01-23 | 2020-10-22 | 2020-10-21 | 2021-02-11 | 2021-04-09 | 2021-05-17 | -38 | 12 | 19
506973 | MP Materials | Oakville | Process Pump - Centrifugal | Flowserve US Inc. | 4503488002 | Rotating Equipment | Centrifugal Pumps | USD | 152535 | USD | 85958 | 66577 | Design Optimizations | 2020-10-07 | 2020-10-09 | 2020-11-04 | 2020-10-21 | 2020-11-06 | 2021-01-17 | 2020-10-24 | 2020-11-10 | 2021-03-27 | 2021-01-13 | 2021-04-29 | -106 | 30 | 32
506973 | MP Materials | Oakville | Centrate Tank Mixer | SHARPE MIXERS | 4503484738 | Rotating Equipment | Electric Motors | USD | 20500 | USD | 12287 | 8213 | Frame Agreements | 2020-11-04 | 2020-10-20 | 2020-10-28 | 2020-11-19 | 2020-11-05 | 2021-02-05 | 2020-11-24 | 2020-11-09 | 2021-03-30 | 2021-01-18 | 2021-05-24 | -126 | 30 | 20
506973 | MP Materials | Oakville | Metering Pump | Prominent Fluid Controls Inc. | 4503511304 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 37835 | CAD | 19448 | 18387 | Supplier Competitions / Negotiation | 2020-10-28 | 2020-10-29 | 2020-12-23 | 2020-11-11 | 2021-01-03 | 2021-01-14 | 2020-11-14 | 2021-01-04 | 2021-04-03 | 2021-02-01 | 2021-03-02 | -29 | 30 | 67
506973 | MP Materials | Oakville | Thermocompressor | Croll Reynolds | 450347613 | Fabrication | Process Equipment | USD | 50000 | USD | 48420 | 1580 | Supplier Competitions / Negotiation | 2020-10-02 | 2020-10-02 | 2020-10-07 | 2020-10-16 | 2020-10-16 | 2021-01-25 | 2020-10-21 | 2020-10-21 | 2021-02-10 | 2021-01-27 | 2021-05-20 | -113 | 12 | 19
506973 | MP Materials | Oakville | Vapor Body Mist Eliminator-Chevron | COSTACURTA SPA - VICO | 4503527092 | Fabrication | Process Equipment | USD | 24242 | USD | 41750 | -17508 | Specs / Requirements Misinterpreted in Proposal | 2020-12-15 | 2020-12-23 | 2021-01-13 | 2020-12-28 | 2021-01-24 | 2021-02-23 | 2020-12-31 | 2021-02-15 | 2021-04-08 | 2021-04-27 | 2021-05-05 | -8 | 12 | 54
506973 | MP Materials | Oakville | Duct Supports | GULF STATE HANGERS & SUPPORTS MFG | 4503551399 | Fabrication | Stainless Steel | USD | 6000 | USD | 50211 | -44211 | Proposed Supplier Incapable Of Executing | 2020-12-15 | 2021-02-18 | 2021-03-02 | 2020-12-28 | 2021-03-13 | 2021-02-27 | 2020-12-31 | 2021-03-14 | 2021-02-25 | 2021-05-09 | 2021-05-13 | -4 | 12 | 24
506973 | MP Materials | Oakville | Condenser -Heat Exchanger | Croll Reynolds | 4503476136 | Fabrication | Process Equipment | USD | 138720 | USD | 244800 | -106080 | Market Impact | 2020-10-02 | 2020-09-30 | 2020-10-09 | 2020-10-17 | 2020-10-14 | 2021-01-24 | 2020-10-22 | 2020-10-19 | 2021-03-11 | 2021-03-15 | 2021-05-20 | -66 | 12 | 19
506973 | MP Materials | Oakville | Flow Meters | LAKESIDE PROCESS CONTROLS LTD. | 4503499623 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 22971 | USD | 30119 | -7148 | Estimate Without Market Reference(No Quote) | 2020-11-24 | 2020-12-04 | 2020-12-04 | 2020-12-08 | 2020-12-03 | 2021-01-20 | 2020-12-11 | 2020-12-08 | 2021-03-19 | 2021-02-02 | 2021-03-01 | -27 | 18 | 4
506973 | MP Materials | Oakville | On-Off Control Valves - TSP | LAKESIDE PROCESS CONTROLS LTD. | 4503497969 | Flow Control | Metal Control Valves | USD | 190784 | USD | 230577 | -39793 | Estimate Without Market Reference(No Quote) | 2020-11-07 | 2020-11-29 | 2020-12-01 | 2020-11-24 | 2020-11-30 | 2021-02-24 | 2020-11-27 | 2020-12-02 | 2021-04-16 | 2021-06-02 | 2021-06-14 | -12 | 12 | 3
506973 | MP Materials | Oakville | FlowMeter/PresGau/Level Switch/CCTV | AVENSYS SOLUTION | 4503521102 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 38623 | USD | 127603 | -88980 | Size/ Weight/ Quantity Underestimated | 2020-11-24 | 2020-01-24 | 2021-01-15 | 2020-12-08 | 2021-01-18 | 2020-09-27 | 2020-12-11 | 2021-01-20 | 2021-03-19 | 2021-04-24 | 2021-06-02 | -39 | 18 | 362
506973 | MP Materials | Oakville | Pressure Transmitter | LAKESIDE PROCESS CONTROLS LTD. | 4503504958 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 31599 | USD | 31599 | 0 | Single Sourced | 2021-01-24 | 2020-12-02 | 2020-12-14 | 2021-01-24 | 2020-12-13 | 2021-01-24 | 2021-01-24 | 2020-12-15 | 2021-01-24 | 2021-02-02 | 2021-03-18 | -44 | 18 | 13
506973 | MP Materials | Oakville | Temp Transmitter | LAKESIDE PROCESS CONTROLS LTD. | 4503505043 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 40933 | USD | 40933 | 0 | Single Sourced | 2021-02-11 | 2020-12-10 | 2020-12-11 | 2021-02-11 | 2020-12-12 | 2021-02-11 | 2021-02-11 | 2020-12-14 | 2021-02-11 | 2020-12-14 | 2021-04-15 | -122 | 18 | 4
506973 | MP Materials | Oakville | Level Transmitter | LAKESIDE PROCESS CONTROLS LTD. | 4503505057 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 45684 | USD | 45684 | 0 | Not included in Proposal / RFQ | 2021-01-24 | 2020-12-02 | 2020-12-04 | 2021-01-24 | 2021-01-17 | 2021-01-24 | 2021-01-24 | 2020-12-17 | 2021-01-24 | 2021-01-28 | 2021-03-18 | -49 | 18 | 15
506973 | MP Materials | Oakville | Relief Valve | LAKESIDE PROCESS CONTROLS LTD. | 4503505533 | Flow Control | Metal Safety(relief) Valves | USD | 19913 | USD | 19913 | 0 | Frame Agreements | 2021-02-11 | 2020-12-05 | 2020-12-17 | 2021-02-11 | 2020-12-18 | 2021-02-11 | 2021-02-11 | 2020-12-18 | 2021-02-11 | 2021-02-01 | 2021-04-21 | -79 | 12 | 13
507022 | Greenville (TA-Loving) | Richmond | Pumps -Other | Tencarva Machinery Co. | 4503357390 | Rotating Equipment | Centrifugal Pumps | USD | 49341 | USD | 43818 | 5523 | Supplier Competitions / Negotiation | 2021-10-25 | 2021-09-03 | 2021-04-15 | 2021-11-09 | 2021-09-03 | 2021-09-03 | 2021-11-23 | 2021-03-23 | 2022-02-15 | 2021-06-15 | 2021-10-15 | -122 | 30 | -164
507022 | Greenville (TA-Loving) | Richmond | Control Panel | BW Systems | 4503568424 | Electrical & Instrumentation | Ele-Control Panels | USD | 34231 | USD | 14920 | 19311 | Design Optimizations | 2021-11-08 | 2021-09-10 | 2021-04-06 | 2021-11-23 | 2021-09-10 | 2021-09-10 | 2021-12-07 | 2021-04-13 | 2022-02-15 | 2021-05-25 | 2021-10-05 | -133 | 18 | -150
507022 | Greenville (TA-Loving) | Richmond | Settling Plates | KAL-LITE | 4503574591 | Fabrication | Metal Isolation Valves | USD | 25122 | USD | 24050 | 1072 | Supplier Competitions / Negotiation | 2021-08-23 | 2021-08-22 | 2021-04-23 | 2021-09-07 | 2021-08-22 | 2021-08-22 | 2021-09-21 | 2021-04-26 | 2021-12-21 | 2021-06-21 | 2021-09-20 | -91 | 12 | -118
507022 | Greenville (TA-Loving) | Richmond | Extrusions Pipes | EASTERN METAL | 4503595509 | Fabrication | Ele-Control Panels | USD | 32472 | USD | 37627 | -5155 | Specs / Requirements Misinterpreted in Proposal | 2021-07-05 | 2021-09-10 | 2021-06-01 | 2021-07-20 | 2021-09-10 | 2021-09-10 | 2021-08-03 | 2021-06-01 | 2021-12-21 | 2021-06-29 | 2021-09-24 | -87 | 12 | -101
507022 | Greenville (TA-Loving) | Richmond | Extrusion Fab | JOB SHOP FABRICATORS | 4503595519 | Fabrication | Metal Isolation Valves | USD | 27292 | USD | 24882 | 2410 | Design Optimizations | 2021-08-23 | 2021-09-07 | 2021-06-07 | 2021-09-07 | 2021-09-07 | 2021-09-07 | 2021-09-21 | 2021-06-01 | 2021-12-14 | 2021-08-24 | 2021-10-19 | -56 | 12 | -98
507022 | Greenville (TA-Loving) | Richmond | Control valves & Control Components | HENRY PRATT | 4503575282 | Flow Control | Metal Control Valves | USD | 39284 | USD | 40470 | -1186 | Single Sourced | 2021-07-08 | 2021-07-21 | 2021-04-26 | 2021-07-23 | 2021-07-21 | 2021-07-21 | 2021-08-06 | 2021-04-27 | 2021-10-15 | 2021-06-08 | 2021-08-11 | -64 | 12 | -85
507022 | Greenville (TA-Loving) | Richmond | Piping: Supports, Spools, Protection, Fittings | JOB SHOP FABRICATORS | 4503586927 | Fabrication | Non-Metal Equipment | USD | 56466 | USD | 55878 | 588 | Frame Agreements | 2021-08-23 | 2021-08-23 | 2021-05-17 | 2021-09-07 | 2021-08-23 | 2021-08-23 | 2021-09-21 | 2021-05-17 | 2021-11-30 | 2021-06-21 | 2021-09-10 | -81 | 12 | -98
507046 | Vail Pass Rest Area Water Treatment System | Oakville | Control Panel & ISB Junction Box | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503482668 | Electrical & Instrumentation | Ele-Control Panels | USD | 35372 | CAD | 44288 | -8916 | Market Impact | 2020-10-22 | 2020-10-28 | 2020-11-02 | 2020-10-29 | 2020-10-29 | 2020-11-26 | 2020-10-30 | 2020-11-02 | 2020-12-31 | 2020-12-14 | 2020-12-22 | -8 | 18 | 5
507046 | Vail Pass Rest Area Water Treatment System | Oakville | Mixers | XYLEM CANADA COMPANY | 4503483436 | Rotating Equipment | Mixers | USD | 21440 | CAD | 10774 | 10666 | Design Optimizations | 2020-10-08 | 2020-10-06 | 2020-10-08 | 2020-10-19 | 2020-10-26 | 2020-11-18 | 2020-10-20 | 2020-11-04 | 2020-12-31 | 2020-12-10 | 2020-12-20 | -10 | 30 | 29
507046 | Vail Pass Rest Area Water Treatment System | Oakville | Dosing Pump & Reuse pump | GRUNDFOS PUMPS CORPORATION | 4503481213 | Rotating Equipment | Dosing Pump | USD | 10868 | USD | 7855 | 3013 | Design Optimizations | 2020-10-23 | 2020-10-14 | 2020-10-21 | 2020-10-26 | 2020-11-25 | 2020-11-22 | 2020-10-28 | 2020-10-29 | 2020-12-31 | 2020-12-03 | 2020-12-17 | -14 | 30 | 15
507046 | Vail Pass Rest Area Water Treatment System | Oakville | Submersible Pump (EQ feed pump) | SULZER PUMPS (CANADA) INC. | 4503477800 | Rotating Equipment | Chem. Feed Skids (TurnKey) | USD | 5179 | CAD | 6657 | -1478 | Single Sourced | 2020-10-08 | 2020-10-07 | 2020-10-14 | 2020-10-21 | 2020-10-21 | 2020-11-18 | 2020-10-22 | 2020-10-23 | 2020-12-31 | 2020-12-02 | 2020-12-16 | -14 | 30 | 16
507082 | PANHANDLE PURE(PLAINS DIARY) | Minnetonka | TWO PASS BEV RO UV | Aquafine | 4503477182 | Fabrication | Carbon Steel | USD | 7979 | USD | 7979 | 0 | Not included in Proposal / RFQ | 2020-10-22 | 2020-10-19 | 2020-10-20 | 2020-10-22 | 2020-10-20 | 2020-11-19 | 2020-10-23 | 2020-10-20 | 2020-12-21 | 2020-12-21 | 2020-12-21 | 0 | 12 | 1
507082 | PANHANDLE PURE(PLAINS DIARY) | Minnetonka | TWO PASS BEV RO ELEC PANELS | PTS Products | 4503499719 | Electrical & Instrumentation | Carbon Steel | USD | 24555 | USD | 26898 | -2343 | Specs / Requirements Misinterpreted in Proposal | 2020-12-03 | 2020-12-03 | 2020-12-07 | 2020-12-22 | 2020-12-07 | 2020-12-22 | 2020-12-22 | 2020-12-07 | 2020-12-22 | 2021-01-11 | 2021-01-01 | 10 | 18 | 4
507082 | PANHANDLE PURE(PLAINS DIARY) | Minnetonka | TANK 500 GALLON SS CIP | Preferred Stainless Holdings | 4513478124 | Fabrication | Carbon Steel | USD | 14857 | USD | 14587 | 270 | Frame Agreements | 2020-10-12 | 2020-10-14 | 2020-10-15 | 2020-10-25 | 2020-10-26 | 2020-12-01 | 2020-10-25 | 2020-10-26 | 2021-01-21 | 2021-01-21 | 2021-01-21 | 0 | 12 | 12
507082 | PANHANDLE PURE(PLAINS DIARY) | Minnetonka | BAG FILTER HOUSING ASSEMBLY | Duncan Co. | 4503477921 | Flow Control | Carbon Steel | USD | 7000 | USD | 7814 | -814 | Single Sourced | 2020-10-20 | 2020-10-21 | 2020-10-22 | 2020-10-23 | 2020-10-23 | 2020-07-16 | 2020-10-27 | 2020-10-24 | 2020-01-15 | 2021-01-15 | 2020-07-16 | 183 | 12 | 3
507082 | PANHANDLE PURE(PLAINS DIARY) | Minnetonka | ACTIVATED CARBON TOWER | Arrow Tanks | 4503486799 | Fabrication | Carbon Steel | USD | 31542 | USD | 29688 | 1854 | Supplier Competitions / Negotiation | 2020-10-15 | 2020-10-08 | 2020-10-12 | 2020-10-15 | 2020-10-19 | 2020-11-25 | 2020-10-15 | 2020-11-11 | 2020-12-31 | 2021-01-12 | 2021-01-06 | 6 | 12 | 34
507082 | PANHANDLE PURE(PLAINS DIARY) | Minnetonka | OZONE GENERATOR | OZONE INTERNATIONAL LLC | 4503475684 | Fabrication | Ele-Control Panels | USD | 54000 | USD | 52350 | 1650 | Frame Agreements | 2020-10-19 | 2020-10-12 | 2020-10-19 | 2020-10-20 | 2020-10-19 | 2020-11-30 | 2020-10-21 | 2020-10-20 | 2021-01-15 | 2021-01-19 | 2021-01-17 | 2 | 12 | 8
507082 | PANHANDLE PURE(PLAINS DIARY) | Minnetonka | LOOSE OZONE EQUIPMENT | OZONE WATER SYSTEMS | 4503490795 | Electrical & Instrumentation | Ele-Control Panels | USD | 13600 | USD | 6350 | 7250 | Frame Agreements | 2020-11-02 | 2020-12-21 | 2020-10-27 | 2020-11-05 | 2020-11-19 | 2020-12-21 | 2020-11-10 | 2020-11-19 | 2021-02-15 | 2020-12-13 | 2021-01-14 | -32 | 18 | -32
507082 | PANHANDLE PURE(PLAINS DIARY) | Minnetonka | LOOSE VFD'S | WERNER ELECTRIC | 4503475691 | Electrical & Instrumentation | Metal Isolation Valves | USD | 13000 | USD | 11985 | 1015 | Frame Agreements | 2020-10-19 | 2020-11-15 | 2020-11-19 | 2020-10-20 | 2020-11-19 | 2020-11-15 | 2020-10-20 | 2020-11-19 | 2020-12-07 | 2020-12-13 | 2020-12-10 | 3 | 18 | 4
507082 | PANHANDLE PURE(PLAINS DIARY) | Minnetonka | TANK 5000 GALLON FRP CITY WATER | DIAMOND FIBERGLASS | 4503476320 | Fabrication | Centrifugal Pumps | USD | 18000 | USD | 16735 | 1265 | Frame Agreements | 2020-10-15 | 2020-10-14 | 2020-10-15 | 2020-10-15 | 2020-10-20 | 2020-12-06 | 2020-10-21 | 2020-10-21 | 2021-01-21 | 2021-01-29 | 2021-01-25 | 4 | 12 | 7
507082 | PANHANDLE PURE(PLAINS DIARY) | Minnetonka | TANK 5000 GALLON SS OZONATED PERMEATE TANK | Preferred Stainless Holdings | 4503478124 | Fabrication | Carbon Steel | USD | 44000 | USD | 42198 | 1802 | Frame Agreements | 2020-10-12 | 2020-10-14 | 2020-10-15 | 2020-10-25 | 2020-10-22 | 2020-12-01 | 2020-10-25 | 2020-10-26 | 2021-01-21 | 2021-01-21 | 2021-01-21 | 0 | 12 | 12
507103 | Coke Nashville Treated Water System | Minnetonka | PUMPS, SANI , TRICK;E | ALFA LAVAL | 4503481900 | Rotating Equipment | Metal Isolation Valves | USD | 13661 | USD | 13661 | 0 | Frame Agreements | 2020-10-20 | 2020-10-21 | 2020-10-21 | 2020-11-23 | 2020-11-02 | 2020-11-23 | 2020-11-23 | 2020-11-02 | 2020-11-23 | 2020-12-28 | 2020-12-10 | 18 | 30 | 12
507103 | Coke Nashville Treated Water System | Minnetonka | PUMPS GOULDS, CITY WATER | PFC EQUIPMENT | 4503482350 | Rotating Equipment | Carbon Steel | USD | 26376 | USD | 26376 | 0 | Proposed Supplier Incapable Of Executing | 2020-10-29 | 2020-10-29 | 2020-10-29 | 2020-12-01 | 2020-10-31 | 2020-12-01 | 2020-12-01 | 2020-11-01 | 2020-12-01 | 2021-01-03 | 2020-12-17 | 17 | 30 | 3
507103 | Coke Nashville Treated Water System | Minnetonka | VESSEL - AC TOWER | Arrow Tanks | 4503480748 | Fabrication | Ele-Control Panels | USD | 56000 | USD | 55000 | 1000 | Supplier Competitions / Negotiation | 2020-10-22 | 2020-10-21 | 2020-10-21 | 2020-10-22 | 2020-10-22 | 2020-12-06 | 2020-11-05 | 2020-10-28 | 2021-01-14 | 2021-01-21 | 2021-01-17 | 4 | 12 | 7
507103 | Coke Nashville Treated Water System | Minnetonka | TEKLEEN FILTER | TEKLEEN | 4503481835 | Flow Control | Metal Isolation Valves | USD | 18344 | USD | 16800 | 1544 | Design Optimizations | 2020-10-23 | 2020-10-20 | 2020-10-22 | 2020-10-30 | 2020-11-02 | 2020-12-02 | 2020-11-05 | 2020-11-02 | 2021-01-14 | 2021-01-11 | 2021-01-12 | -1 | 12 | 13
507103 | Coke Nashville Treated Water System | Minnetonka | CAUSTIC PANEL MOUNTED Grundfos | GRUNDFOS PUMPS CORPORATION | 4503489274 | Flow Control | Carbon Steel | USD | 6000 | USD | 5018 | 982 | Design Optimizations | 2020-11-16 | 2020-10-20 | 2020-10-22 | 2020-11-20 | 2020-11-16 | 2020-12-23 | 2020-11-23 | 2020-11-17 | 2021-02-26 | 2021-02-22 | 2021-02-24 | -2 | 12 | 28
507103 | Coke Nashville Treated Water System | Minnetonka | PRE RO UV STERILIZER | AQUIONICS, INC. | 4503482371 | Flow Control | RO Membrane Housings | USD | 47000 | USD | 47000 | 0 | Proposed Supplier Incapable Of Executing | 2020-10-26 | 2020-10-26 | 2020-10-26 | 2020-11-30 | 2020-11-02 | 2020-11-30 | 2020-11-30 | 2020-11-02 | 2020-11-30 | 2021-01-04 | 2020-12-17 | 18 | 12 | 7
507103 | Coke Nashville Treated Water System | Minnetonka | HACH SODIUM ANALYZER | Hach Company | 4503497962 | Electrical & Instrumentation | Carbon Steel | USD | 17500 | USD | 13486 | 4014 | Frame Agreements | 2020-10-26 | 2020-10-22 | 2020-11-29 | 2020-10-29 | 2020-12-04 | 2020-12-06 | 2020-11-04 | 2020-12-03 | 2021-01-13 | 2021-01-21 | 2021-01-17 | 4 | 18 | 42
507103 | Coke Nashville Treated Water System | Minnetonka | HACH ANALYZERS | Hach Company | 4503499142 | Electrical & Instrumentation | Carbon Steel | USD | 9844 | USD | 9844 | 0 | Size/ Weight/ Quantity Underestimated | 2021-01-08 | 2020-12-07 | 2020-12-07 | 2021-01-08 | 2020-12-06 | 2021-01-08 | 2021-01-08 | 2020-12-06 | 2021-01-08 | 2021-02-11 | 2021-01-25 | 17 | 18 | -1
507103 | Coke Nashville Treated Water System | Minnetonka | MCE W/ VFDS | BW Systems | 4503491896 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 86716 | USD | 77970 | 8746 | Frame Agreements | 2020-10-26 | 2020-11-02 | 2020-11-03 | 2020-10-29 | 2020-11-23 | 2020-12-18 | 2020-11-04 | 2020-11-23 | 2021-01-13 | 2021-02-10 | 2021-01-27 | 14 | 18 | 21
507103 | Coke Nashville Treated Water System | Minnetonka | ELECTRICAL PANELS | BW Systems | 4503503133 | Electrical & Instrumentation | Ele-Electrical Others | USD | 54910 | USD | 58875 | -3965 | Size/ Weight/ Quantity Underestimated | 2021-01-05 | 2020-12-14 | 2020-12-14 | 2021-01-05 | 2020-12-15 | 2021-01-05 | 2021-01-05 | 2020-12-15 | 2021-01-05 | 2021-01-28 | 2021-01-16 | 12 | 18 | 1
507103 | Coke Nashville Treated Water System | Minnetonka | TANKS, RO PERM - SS | Preferred Stainless Holdings | 4503487896 | Fabrication | Carbon Steel | USD | 131575 | USD | 93158 | 38417 | Design Optimizations | 2020-10-23 | 2020-10-29 | 2020-10-30 | 2020-10-30 | 2020-11-12 | 2020-12-24 | 2020-11-05 | 2020-11-11 | 2021-02-11 | 2021-02-24 | 2021-02-17 | 7 | 12 | 13
507103 | Coke Nashville Treated Water System | Minnetonka | TANK, TRICKLE - FRP | DIAMOND FIBERGLASS | 4503481255 | Fabrication | Ele-Control Panels | USD | 64630 | USD | 43190 | 21440 | Design Optimizations | 2020-10-23 | 2020-10-20 | 2020-10-30 | 2020-10-30 | 2020-10-29 | 2020-12-16 | 2020-11-05 | 2020-10-29 | 2021-02-11 | 2021-01-21 | 2021-01-31 | -10 | 12 | 9
507103 | Coke Nashville Treated Water System | Minnetonka | TANK, CIP - SS | Preferred Stainless Holdings | 4513487896 | Fabrication | Carbon Steel | USD | 29905 | USD | 29905 | 0 | Single Sourced | 2020-10-23 | 2020-10-29 | 2020-11-30 | 2020-10-30 | 2020-11-12 | 2020-12-21 | 2020-11-05 | 2020-11-13 | 2021-02-11 | 2021-02-19 | 2021-02-15 | 4 | 12 | 15
507103 | Coke Nashville Treated Water System | Minnetonka | INSTRUMENTS - GRISWOLD | Duncan Co. | 4503505052 | Electrical & Instrumentation | Carbon Steel | USD | 20180 | USD | 5147 | 15033 | Design Optimizations | 2020-12-31 | 2020-12-19 | 2020-12-19 | 2020-12-31 | 2020-12-19 | 2020-12-31 | 2020-12-31 | 2020-12-19 | 2020-12-31 | 2021-01-13 | 2021-01-06 | 7 | 18 | 0
507103 | Coke Nashville Treated Water System | Minnetonka | SOLENOID PANELS | BW Systems | 4503552206 | Electrical & Instrumentation | Ele-Control Panels | USD | 10106 | USD | 5611 | 4495 | Supplier Competitions / Negotiation | 2021-03-15 | 2021-03-15 | 2021-03-16 | 2021-03-16 | 2021-03-14 | 2021-03-22 | 2021-03-16 | 2021-03-15 | 2021-03-31 | 2021-03-29 | 2021-03-30 | -1 | 18 | 0
507133 | Lucketts Elementary School WWTP | Oakville | Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503583907 | Electrical & Instrumentation | Ele-Control Panels | USD | 53594 | CAD | 39889 | 13705 | Design Optimizations | 2021-03-25 | 2021-05-13 | 2021-05-11 | 2021-03-22 | 2021-05-11 | 2021-05-07 | 2021-04-20 | 2021-05-11 | 2021-05-28 | 2021-06-23 | 2021-06-10 | 13 | 18 | -2
507133 | Lucketts Elementary School WWTP | Oakville | Frames | 3D MECHANICAL | 4503568702 | Fabrication | Metal Isolation Valves | USD | 10500 | CAD | 20008 | -9508 | Specs / Requirements Misinterpreted in Proposal | 2021-03-22 | 2021-03-22 | 2021-04-14 | 2021-03-22 | 2021-04-13 | 2021-04-26 | 2021-04-05 | 2021-04-13 | 2021-05-28 | 2021-05-31 | 2021-05-29 | 2 | 12 | 22
507133 | Lucketts Elementary School WWTP | Oakville | Diffuser | ENVIRONMENTAL DYNAMICS | 4503569807 | Fabrication | Centrifugal Pumps | USD | 7867 | USD | 6777 | 1090 | Design Optimizations | 2020-10-30 | 2020-10-30 | 2021-04-14 | 2021-03-22 | 2021-04-15 | 2021-03-01 | 2021-04-20 | 2021-04-16 | 2021-05-28 | 2021-07-02 | 2021-06-14 | 18 | 12 | 168
507133 | Lucketts Elementary School WWTP | Oakville | Do Probes | ENDRESS + HAUSER CANADA LTD. | 4503565105 | Electrical & Instrumentation | Ele-Control Panels | USD | 10925 | USD | 10870 | 55 | Frame Agreements | 2020-11-05 | 2020-11-05 | 2020-11-09 | 2021-03-22 | 2021-03-19 | 2021-02-15 | 2021-04-13 | 2021-04-08 | 2021-05-28 | 2021-05-05 | 2021-05-16 | -11 | 18 | 154
507133 | Lucketts Elementary School WWTP | Oakville | Effulent sampler | AVENSYS SOLUTION | 4503566753 | Electrical & Instrumentation | Ele-Control Panels | USD | 11081 | CAD | 9435 | 1646 | Frame Agreements | 2020-11-09 | 2020-11-09 | 2020-11-19 | 2021-03-22 | 2021-03-19 | 2021-02-17 | 2021-04-13 | 2021-04-12 | 2021-05-28 | 2021-05-25 | 2021-05-26 | -1 | 18 | 154
507133 | Lucketts Elementary School WWTP | Oakville | Fine screens | NRW ANLAGENTECHNIK GMBH | 4503569862 | Rotating Equipment | Metal Isolation Valves | USD | 32002 | EUR | 36580 | -4578 | Size/ Weight/ Quantity Underestimated | 2020-07-30 | 2020-07-30 | 2021-04-15 | 2021-03-22 | 2021-04-15 | 2021-02-04 | 2021-04-08 | 2021-04-16 | 2021-05-28 | 2021-08-13 | 2021-07-05 | 39 | 30 | 260
507133 | Lucketts Elementary School WWTP | Oakville | Dosing Panels | PROMINENT FLUID CONTROLS LTD. | 4503563734 | Rotating Equipment | Dosing Pump | USD | 18285 | CAD | 12512 | 5773 | Frame Agreements | 2020-11-16 | 2020-11-16 | 2020-11-25 | 2021-03-22 | 2021-03-16 | 2021-02-20 | 2021-04-07 | 2021-04-03 | 2021-05-28 | 2021-05-01 | 2021-05-14 | -13 | 30 | 138
507133 | Lucketts Elementary School WWTP | Oakville | Blower | AERZEN CANADA INC. | 4503563361 | Rotating Equipment | Ele-Control Panels | USD | 22085 | CAD | 23446 | -1361 | Proposed Supplier Incapable Of Executing | 2020-11-04 | 2020-11-04 | 2021-02-02 | 2021-03-22 | 2021-03-19 | 2021-02-16 | 2021-04-08 | 2021-04-06 | 2021-05-28 | 2021-05-31 | 2021-05-29 | 2 | 30 | 153
507133 | Lucketts Elementary School WWTP | Oakville | Mixers | XYLEM CANADA COMPANY | 4503563219 | Rotating Equipment | Mixers | USD | 10789 | CAD | 10487 | 302 | Design Optimizations | 2020-10-29 | 2020-10-29 | 2020-08-04 | 2021-03-22 | 2021-03-19 | 2021-01-01 | 2021-04-20 | 2021-04-06 | 2021-05-28 | 2021-05-31 | 2021-05-29 | 2 | 30 | 159
507133 | Lucketts Elementary School WWTP | Oakville | Telescope decant valve | AUTOMATIC CONTROLS OF VIRGINIA, INC | 4503570703 | Flow Control | Metal Isolation Valves | USD | 5000 | USD | 6125 | -1125 | Size/ Weight/ Quantity Underestimated | 2021-03-22 | 2021-03-22 | 2021-04-16 | 2021-03-22 | 2021-04-16 | 2021-05-02 | 2021-04-20 | 2021-04-18 | 2021-05-28 | 2021-06-13 | 2021-06-05 | 8 | 12 | 27
507135 | Conestoga Meat Packers RO Expansion | Minnetonka | Greensand Filter | Arrow Tanks | 4503495093 | Fabrication | Metal Isolation Valves | CAD | 29914 | USD | 28956 | 958 | Market Impact | 2021-01-15 | 2020-11-19 | 2020-11-19 | 2021-01-15 | 2020-11-28 | 2021-01-15 | 2021-01-15 | 2020-11-28 | 2021-01-15 | 2021-03-13 | 2021-02-12 | 29 | 12 | 9
507135 | Conestoga Meat Packers RO Expansion | Minnetonka | RO PRO SERIES - Elec Panels | KELTOUR CONTROLS INC. | 4503504245 | Electrical & Instrumentation | Ele-Control Panels | CAD | 25474 | USD | 24658 | 816 | Frame Agreements | 2020-12-31 | 2020-12-01 | 2020-12-01 | 2020-12-31 | 2020-12-13 | 2020-12-31 | 2020-12-31 | 2020-12-13 | 2020-12-31 | 2021-01-31 | 2021-01-15 | 16 | 18 | 12
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | PROCESS PUMP RIO PANEL | MACHINE CONTROL SYSTEMS | 4503518201 | Fabrication | Process Equipment | CAD | 17149 | CAD | 17149 | 0 | Not included in Proposal / RFQ | 2021-01-05 | 2021-01-05 | 2021-01-13 | 2021-01-07 | 2021-01-18 | 2021-02-02 | 2021-01-07 | 2021-01-18 | 2021-02-22 | 2021-03-03 | 2021-02-26 | 5 | 12 | 13
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | PROCESS SKID | BOERGER, INC | 4503517065 | Rotating Equipment | Carbon Steel | CAD | 18650 | USD | 17420 | 1230 | Frame Agreements | 2021-02-04 | 2021-01-07 | 2021-01-07 | 2021-02-04 | 2021-01-10 | 2021-02-04 | 2021-02-04 | 2021-01-14 | 2021-02-04 | 2021-03-04 | 2021-02-18 | 14 | 30 | 7
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | BIOLOGICAL EQUIPMENT - DIFFUSER GRID AND DISKS | EDI | 4503511782 | Rotating Equipment | Carbon Steel | CAD | 33624 | CAD | 24157 | 9467 | Frame Agreements | 2020-12-01 | 2020-10-09 | 2020-11-11 | 2020-12-07 | 2020-12-29 | 2020-09-06 | 2020-12-07 | 2020-12-30 | 2020-02-15 | 2021-03-29 | 2020-09-06 | 204 | 30 | 82
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | BIOLOGICAL EQUIPMENT / RAS PUMP | FLOWSERVE INC. | 4503511795 | Rotating Equipment | Carbon Steel | CAD | 13604 | CAD | 11063 | 2541 | Frame Agreements | 2020-11-04 | 2020-11-04 | 2020-12-17 | 2020-11-12 | 2020-12-31 | 2021-01-16 | 2020-11-16 | 2021-01-01 | 2021-03-12 | 2021-03-31 | 2021-03-21 | 10 | 30 | 58
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | BIOLOGICAL EQUIPMENT / DIFFUSER GRID AND DISKS - REPLACEMENTS | PRO AQUA INC | 4503511785 | Rotating Equipment | Carbon Steel | CAD | 8281 | CAD | 8781 | -500 | Size/ Weight/ Quantity Underestimated | 2021-01-19 | 2020-11-06 | 2020-11-06 | 2021-01-19 | 2021-01-04 | 2021-01-19 | 2021-01-19 | 2021-01-05 | 2021-01-19 | 2021-04-04 | 2021-02-25 | 38 | 30 | 60
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | MEMBRANE & BIO BLOWERS | AERZEN CANADA INC. | 4503511805 | Rotating Equipment | Blowers & Fans | CAD | 72250 | CAD | 62220 | 10030 | Supplier Competitions / Negotiation | 2020-12-01 | 2020-11-09 | 2020-11-09 | 2020-12-07 | 2021-01-04 | 2020-09-09 | 2020-12-07 | 2021-01-05 | 2020-02-15 | 2021-04-04 | 2020-09-09 | 207 | 30 | 57
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | CHEMICAL FEED SYS | PROMINENT FLUID CONTROLS LTD. | 4503511771 | Fabrication | Carbon Steel | CAD | 15157 | CAD | 18800 | -3643 | Specs / Requirements Misinterpreted in Proposal | 2020-12-01 | 2020-12-15 | 2020-12-17 | 2020-12-07 | 2021-01-05 | 2021-02-05 | 2020-12-10 | 2021-01-06 | 2021-04-08 | 2021-04-12 | 2021-04-10 | 2 | 12 | 22
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | MEMBRANE TANK | D&R CUSTOM STEEL | 4503514259 | Fabrication | Metal Isolation Valves | CAD | 121073 | CAD | 108350 | 12723 | Supplier Competitions / Negotiation | 2020-11-05 | 2020-12-15 | 2020-12-08 | 2020-11-11 | 2021-01-06 | 2021-01-25 | 2020-11-12 | 2021-01-09 | 2021-04-08 | 2021-04-17 | 2021-04-12 | 5 | 12 | 25
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | AEROBIC TANK | TANK CONNECTION | 4503494664 | Fabrication | Ele-Control Panels | CAD | 127122 | USD | 123466 | 3656 | Supplier Competitions / Negotiation | 2020-11-05 | 2020-10-28 | 2020-08-12 | 2020-11-11 | 2020-11-17 | 2020-12-09 | 2020-11-12 | 2020-11-19 | 2021-04-08 | 2021-02-18 | 2021-03-14 | -24 | 12 | 22
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | AEROBIC TANK - CO1 LADDER | TANK CONNECTION | 4506494664 | Fabrication | Ele-Control Panels | CAD | 24224 | USD | 22626 | 1598 | Supplier Competitions / Negotiation | 2021-02-16 | 2021-01-05 | 2021-01-05 | 2021-02-16 | 2021-01-17 | 2021-02-16 | 2021-02-16 | 2021-01-20 | 2021-02-16 | 2021-03-30 | 2021-03-09 | 21 | 12 | 15
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | ANOXIC TANK | TANK CONNECTION | 4513494664 | Fabrication | Carbon Steel | CAD | 44765 | USD | 41812 | 2953 | Design Optimizations | 2020-11-05 | 2020-10-28 | 2020-08-12 | 2020-11-11 | 2020-11-18 | 2020-12-09 | 2020-11-12 | 2020-11-21 | 2021-04-08 | 2021-02-20 | 2021-03-15 | -23 | 12 | 24
507141 | HYLIFE EXPANSION 3RD MBR TRAIN | Guelph | ANOXIC TANK CO 1 LADDER | TANK CONNECTION | 4507494664 | Fabrication | Carbon Steel | CAD | 14765 | USD | 13791 | 974 | Frame Agreements | 2021-02-16 | 2021-01-05 | 2021-01-05 | 2021-02-16 | 2021-01-17 | 2021-02-16 | 2021-02-16 | 2021-01-20 | 2021-02-16 | 2021-03-30 | 2021-03-09 | 21 | 12 | 15
507145 | Formosa Plastics - Baton Rouge | Oakville | Lined Piping | BAUM AMERICA CORP | 4503672526 | Fabrication | Stainless Steel | USD | 281794 | USD | 229878 | 51916 | Supplier Competitions / Negotiation | 2021-01-30 | 2021-08-17 | 2021-08-27 | 2021-02-13 | 2021-10-08 | 2021-08-03 | 2021-02-20 | 2021-10-21 | 2021-05-15 | 2022-02-04 | 2021-09-24 | 133 | 12 | 65
507145 | Formosa Plastics - Baton Rouge | Oakville | Lined Piping - Lot 2 | BAUM AMERICA CORP | 4503790766 | Fabrication | Stainless Steel | USD | 90000 | USD | 88762 | 1238 | Estimate Without Market Reference(No Quote) | 2022-04-22 | 2022-02-20 | 2022-02-25 | 2022-04-22 | 2022-05-11 | 2022-04-22 | 2022-04-22 | 2022-05-12 | 2022-04-22 | 2022-06-23 | 2022-05-23 | 31 | 12 | 81
507145 | Formosa Plastics - Baton Rouge | Oakville | Vessel Internals | PANDA PIPING LTD | 4503584042 | Fabrication | Stainless Steel | USD | 315501 | CAD | 480308 | -164807 | Specs / Requirements Misinterpreted in Proposal | 2020-12-15 | 2021-02-18 | 2021-03-20 | 2021-01-05 | 2021-03-31 | 2021-03-10 | 2021-01-12 | 2021-04-07 | 2021-04-06 | 2021-06-03 | 2021-05-05 | 29 | 12 | 48
507145 | Formosa Plastics - Baton Rouge | Oakville | Valves - On/Off Butterfly - Amri | BRAY CONTROLS CANADA LTD. | 4503554302 | Flow Control | Metal Control Valves | USD | 320945 | USD | 435060 | -114115 | Size/ Weight/ Quantity Underestimated | 2020-12-07 | 2020-12-03 | 2021-01-05 | 2021-01-11 | 2021-02-19 | 2021-04-08 | 2021-01-18 | 2021-02-26 | 2021-05-10 | 2021-08-13 | 2021-06-26 | 48 | 12 | 85
507145 | Formosa Plastics - Baton Rouge | Oakville | Electrical PLC | KELTOUR CONTROLS INC. | 4503823089 | Electrical & Instrumentation | Ele-PLCs, HMIs | USD | 136350 | CAD | 148946 | -12596 | Specs / Requirements Misinterpreted in Proposal | 2021-02-15 | 2021-08-04 | 2021-11-04 | 2021-03-22 | 2022-07-02 | 2022-02-24 | 2021-04-05 | 2022-07-11 | 2021-06-28 | 2023-03-06 | 2022-05-02 | 308 | 18 | 341
507145 | Formosa Plastics - Baton Rouge | Oakville | Spools - SS | NV PIPING SYSTEMS INC. | 4503652607 | Fabrication | Stainless Steel | USD | 243487 | CAD | 199401 | 44086 | Size/ Weight/ Quantity Underestimated | 2021-01-30 | 2021-04-12 | 2021-04-29 | 2021-02-20 | 2021-05-03 | 2021-07-08 | 2021-02-27 | 2021-09-21 | 2021-05-22 | 2021-12-14 | 2021-09-02 | 103 | 12 | 162
507145 | Formosa Plastics - Baton Rouge | Oakville | Instrumentation - Silica Analyzer | HACH SALES & SERVICE CANADA LTD-REM | 4503565289 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 47080 | USD | 38151 | 8929 | Specs / Requirements Misinterpreted in Proposal | 2021-02-19 | 2021-02-10 | 2021-03-22 | 2021-03-12 | 2021-03-24 | 2021-04-06 | 2021-03-19 | 2021-04-07 | 2021-04-30 | 2021-05-31 | 2021-05-15 | 16 | 18 | 56
507145 | Formosa Plastics - Baton Rouge | Oakville | Instrumentation - Sodium Analyzer | Fisher Scientific | 4503577384 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 39745 | USD | 40927 | -1182 | Specs / Requirements Misinterpreted in Proposal | 2021-02-19 | 2021-03-03 | 2021-03-18 | 2021-03-12 | 2021-03-11 | 2021-04-15 | 2021-03-19 | 2021-04-29 | 2021-04-30 | 2021-06-10 | 2021-05-20 | 21 | 18 | 57
507145 | Formosa Plastics - Baton Rouge | Oakville | Chem Pump - Others - Changed to Centrifugal Pumps, lined pumps | Magnatex | 4503553805 | Rotating Equipment | Centrifugal Pumps | USD | 51701 | USD | 49408 | 2293 | Single Sourced | 2020-11-26 | 2020-12-18 | 2021-01-12 | 2021-01-07 | 2021-02-19 | 2021-02-13 | 2021-01-14 | 2021-03-16 | 2021-03-25 | 2021-05-03 | 2021-04-13 | 20 | 30 | 88
507145 | Formosa Plastics - Baton Rouge | Oakville | Instrumentation - PIT | LAKESIDE PROCESS CONTROLS LTD. | 4503582513 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 129864 | USD | 190364 | -60500 | Specs / Requirements Misinterpreted in Proposal | 2021-01-07 | 2020-12-07 | 2020-12-22 | 2021-01-28 | 2021-05-05 | 2021-03-11 | 2021-02-04 | 2021-05-08 | 2021-04-29 | 2021-06-13 | 2021-05-21 | 23 | 18 | 152
507145 | Formosa Plastics - Baton Rouge | Oakville | Instrumentation - FIT | ENDRESS + HAUSER CANADA LTD. | 4503572048 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 24493 | USD | 27939 | -3446 | Specs / Requirements Misinterpreted in Proposal | 2021-01-15 | 2020-12-07 | 2021-04-08 | 2021-02-05 | 2021-04-16 | 2021-03-28 | 2021-02-12 | 2021-04-21 | 2021-06-04 | 2021-07-17 | 2021-06-25 | 22 | 18 | 135
507145 | Formosa Plastics - Baton Rouge | Oakville | Valves - Control | LAKESIDE INDUSTRIAL SERVI | 4503536536 | Flow Control | Metal Control Valves | USD | 18591 | USD | 14751 | 3840 | Estimate Without Market Reference(No Quote) | 2020-12-07 | 2020-12-03 | 2020-12-14 | 2021-01-11 | 2021-01-14 | 2021-03-03 | 2021-01-18 | 2021-02-17 | 2021-05-10 | 2021-06-01 | 2021-05-21 | 11 | 12 | 76
507145 | Formosa Plastics - Baton Rouge | Oakville | Electrical - Junction Boxes | KELTOUR CONTROLS INC. | 4503806544 | Electrical & Instrumentation | Ele-Control Panels | USD | 21936 | CAD | 37758 | -15822 | Specs / Requirements Misinterpreted in Proposal | 2021-01-15 | 2021-08-11 | 2022-05-09 | 2021-02-12 | 2022-05-31 | 2021-11-12 | 2021-02-19 | 2022-06-01 | 2021-04-16 | 2022-09-09 | 2021-12-27 | 256 | 18 | 294
507145 | Formosa Plastics - Baton Rouge | Oakville | Heat Exchanger | PROCESS & STEAM SPECIALTIES | 4503610988 | Fabrication | Stainless Steel | USD | 8131 | USD | 34897 | -26766 | Not included in Proposal / RFQ | 2020-12-15 | 2020-12-18 | 2021-06-16 | 2021-01-12 | 2021-07-01 | 2021-06-02 | 2021-01-19 | 2021-07-06 | 2021-04-13 | 2021-11-19 | 2021-08-01 | 110 | 12 | 200
507145 | Formosa Plastics - Baton Rouge | Oakville | Valves - Check | WOLSELEY INDUSTRIAL CANADA INC | 4503537127 | Flow Control | Metal Isolation Valves | USD | 11581 | CAD | 18491 | -6910 | Size/ Weight/ Quantity Underestimated | 2020-11-26 | 2020-12-03 | 2021-01-15 | 2021-01-07 | 2021-01-14 | 2021-03-11 | 2021-01-14 | 2021-02-18 | 2021-03-25 | 2021-06-24 | 2021-05-09 | 46 | 12 | 77
507145 | Formosa Plastics - Baton Rouge | Oakville | FRP Ball Valve | Fibreglass Solutions | 4503541310 | Flow Control | Plastic Valves (All) | USD | 12217 | USD | 53110 | -40893 | Size/ Weight/ Quantity Underestimated | 2020-11-26 | 2020-12-03 | 2021-01-18 | 2021-01-07 | 2021-02-08 | 2021-03-04 | 2021-01-14 | 2021-02-24 | 2021-04-08 | 2021-06-10 | 2021-05-09 | 32 | 12 | 83
507189 | UNIX PACKAGING | Minnetonka | BEV RO SKID & ASSEMBLY | A & B PROCESS SYSTEMS CORP. | 4503493673 | Fabrication | Skid Assembly Outsourced | USD | 216184 | USD | 193476 | 22708 | Design Optimizations | 2020-11-16 | 2020-08-08 | 2020-11-24 | 2020-01-19 | 2020-11-19 | 2020-08-08 | 2020-11-20 | 2020-11-19 | 2021-02-26 | 2021-01-14 | 2021-02-04 | -21 | 12 | 103
507189 | UNIX PACKAGING | Minnetonka | BEV RO SKID - ELEC PANELS | BW Systems | 4503495433 | Electrical & Instrumentation | Carbon Steel | USD | 41607 | USD | 41740 | -133 | Proposed Supplier Incapable Of Executing | 2020-11-16 | 2020-11-16 | 2020-11-23 | 2020-12-14 | 2020-11-23 | 2020-12-14 | 2020-12-14 | 2020-11-30 | 2020-12-14 | 2021-01-11 | 2021-01-11 | 0 | 18 | 14
507189 | UNIX PACKAGING | Minnetonka | AC TOWERS | Arrow Tanks | 4503493311 | Fabrication | Carbon Steel | USD | 119982 | USD | 119982 | 0 | Estimate Without Market Reference(No Quote) | 2020-11-09 | 2020-12-03 | 2020-11-09 | 2020-11-09 | 2020-11-15 | 2020-12-03 | 2020-11-09 | 2020-11-16 | 2020-12-28 | 2020-12-27 | 2020-12-27 | 0 | 12 | -17
507189 | UNIX PACKAGING | Minnetonka | CIP TANK & ASSEMBLY | Preferred Stainless Holdings | 4503496834 | Fabrication | Carbon Steel | USD | 30057 | USD | 29869 | 188 | Design Optimizations | 2020-11-12 | 2020-11-17 | 2020-11-24 | 2020-11-13 | 2020-12-01 | 2021-01-02 | 2020-11-13 | 2020-12-01 | 2021-02-15 | 2021-02-23 | 2021-02-19 | 4 | 12 | 14
507189 | UNIX PACKAGING | Minnetonka | AQUAFINE | Aquafine | 4503490796 | Fabrication | Ele-Control Panels | USD | 22365 | USD | 22365 | 0 | Proposed Supplier Incapable Of Executing | 2020-11-09 | 2020-12-13 | 2020-10-27 | 2020-11-09 | 2020-11-18 | 2020-12-13 | 2020-11-09 | 2020-11-19 | 2021-01-29 | 2021-01-25 | 2021-01-27 | -2 | 12 | -24
507189 | UNIX PACKAGING | Minnetonka | TEKLEEN SKID & ASSEMBLY | TEKLEEN | 4503493768 | Fabrication | Skid Assembly Outsourced | USD | 61731 | USD | 64950 | -3219 | Estimate Without Market Reference(No Quote) | 2020-11-09 | 2020-12-26 | 2020-10-26 | 2020-11-09 | 2020-11-16 | 2020-12-26 | 2020-11-09 | 2020-11-25 | 2021-01-26 | 2021-02-26 | 2021-02-10 | 16 | 12 | -31
507189 | UNIX PACKAGING | Minnetonka | FINAL POLISHING FILTERS | Duncan Co. | 4503497272 | Flow Control | Filters And Strainers (Incl Housings) | USD | 24750 | USD | 13345 | 11405 | Design Optimizations | 2020-11-17 | 2020-11-17 | 2020-11-17 | 2020-12-03 | 2020-11-29 | 2020-12-22 | 2020-12-03 | 2020-11-30 | 2021-01-26 | 2021-01-23 | 2021-01-24 | -1 | 12 | 13
507189 | UNIX PACKAGING | Minnetonka | DISTRIBUTION PUMP SKID | R&R Metalworks | 4503533451 | Rotating Equipment | Carbon Steel | USD | 6135 | USD | 6135 | 0 | Single Sourced | 2021-02-05 | 2021-03-14 | 2021-02-09 | 2021-02-09 | 2021-02-08 | 2021-03-14 | 2021-02-09 | 2021-02-08 | 2021-04-20 | 2021-03-08 | 2021-03-29 | -21 | 30 | -34
507192 | Olymel Saint-Esprit UF-RO Expansion 2019 | Guelph | LS OXIDATION TANK/HDPE | ACO CONTAINER SYSTEMS LTD. | 4503511685 | Fabrication | Metal Isolation Valves | CAD | 12431 | CAD | 9212 | 3219 | Design Optimizations | 2020-11-23 | 2020-11-23 | 2020-11-25 | 2020-11-30 | 2021-01-05 | 2020-08-31 | 2020-12-01 | 2021-01-05 | 2020-03-01 | 2021-03-02 | 2020-08-31 | 183 | 12 | 43
507192 | Olymel Saint-Esprit UF-RO Expansion 2019 | Guelph | PRO RO PUMPS (CHEM/RO) & VALVES | FLUID EQUIPMENT DEVELOPMENT | 4503514888 | Rotating Equipment | Chem. Feed Skids (TurnKey) | CAD | 14001 | USD | 14001 | 0 | Design Optimizations | 2020-11-23 | 2020-11-23 | 2020-11-23 | 2020-11-30 | 2020-12-06 | 2020-08-31 | 2020-12-01 | 2021-01-11 | 2020-03-01 | 2021-03-02 | 2020-08-31 | 183 | 30 | 49
507192 | Olymel Saint-Esprit UF-RO Expansion 2019 | Guelph | PRO RO SKID - FRAME | 3D MECHANICAL | 4503511694 | Fabrication | Skid Assembly Outsourced | CAD | 11494 | CAD | 9995 | 1499 | Supplier Competitions / Negotiation | 2021-01-20 | 2020-12-02 | 2020-12-02 | 2021-01-20 | 2021-01-06 | 2021-01-20 | 2021-01-20 | 2021-01-06 | 2021-01-20 | 2021-03-10 | 2021-02-13 | 25 | 12 | 35
507192 | Olymel Saint-Esprit UF-RO Expansion 2019 | Guelph | PRO RO HOUSINGS | CODELINE | 4503490800 | Fabrication | Metal Isolation Valves | CAD | 7079 | USD | 7079 | 0 | Single Sourced | 2021-01-11 | 2020-11-19 | 2020-11-17 | 2021-01-11 | 2020-12-08 | 2021-01-11 | 2021-01-11 | 2020-12-08 | 2021-01-11 | 2021-03-08 | 2021-02-08 | 28 | 12 | 19
507192 | Olymel Saint-Esprit UF-RO Expansion 2019 | Guelph | LS TANK MIXER | DYNAMIX | 4503511683 | Rotating Equipment | Metal Isolation Valves | CAD | 5774 | CAD | 5774 | 0 | Frame Agreements | 2020-11-23 | 2020-11-23 | 2020-12-02 | 2020-11-30 | 2021-01-06 | 2020-09-27 | 2020-12-01 | 2021-01-06 | 2020-03-01 | 2021-04-26 | 2020-09-27 | 211 | 30 | 44
507192 | Olymel Saint-Esprit UF-RO Expansion 2019 | Guelph | ZBOX Electrical Panels | KELTOUR CONTROLS INC. | 4503509413 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 28195 | CAD | 28195 | 0 | Design Optimizations | 2020-11-17 | 2020-11-17 | 2020-11-24 | 2020-11-23 | 2020-12-29 | 2020-12-29 | 2020-11-24 | 2020-12-30 | 2021-01-12 | 2021-02-10 | 2021-01-26 | 15 | 18 | 43
507201 | Exyte Cree UPW Install | Oakville | Valve - Control | LAKESIDE PROCESS CONTROLS LTD. | 4503510280 | Flow Control | Ele-Control Panels | USD | 45000 | USD | 8491 | 36509 | Frame Agreements | 2020-12-14 | 2020-12-14 | 2020-12-21 | 2020-12-28 | 2020-12-27 | 2020-12-24 | 2021-01-04 | 2021-01-03 | 2021-01-04 | 2021-01-03 | 2021-01-03 | 0 | 12 | 20
507201 | Exyte Cree UPW Install | Oakville | Valve - Butterfly | BRAY CONTROLS CANADA LTD. | 4503504303 | Flow Control | Metal Isolation Valves | USD | 52172 | USD | 43874 | 8298 | Supplier Competitions / Negotiation | 2020-12-01 | 2020-11-25 | 2020-12-02 | 2020-12-08 | 2020-12-06 | 2020-12-05 | 2020-12-15 | 2020-12-13 | 2020-12-15 | 2020-12-13 | 2020-12-14 | -1 | 12 | 18
507201 | Exyte Cree UPW Install | Oakville | Valve - Others | RYAN HERCO FLOW SOLUTIONS | 4503507158 | Flow Control | Metal Isolation Valves | USD | 30591 | USD | 19608 | 10983 | Supplier Competitions / Negotiation | 2020-12-01 | 2020-12-01 | 2020-12-08 | 2020-12-14 | 2020-12-13 | 2020-12-11 | 2020-12-21 | 2020-12-20 | 2020-12-21 | 2020-12-20 | 2020-12-20 | 0 | 12 | 19
507220 | PepsiCo Medellin | Guelph | PROCESS PUMP SPOOLS | NV PIPING SYSTEMS INC. | 4503542155 | Fabrication | Process Equipment | CAD | 15655 | CAD | 15655 | 0 | Frame Agreements | 2021-02-24 | 2021-02-24 | 2021-03-01 | 2021-02-26 | 2021-02-23 | 2021-03-23 | 2021-02-26 | 2021-02-24 | 2021-04-21 | 2021-04-19 | 2021-04-20 | -1 | 12 | 0
507220 | PepsiCo Medellin | Guelph | PROCESS PUMP FRAMES | PLASFAB LIMITED | 4503544908 | Fabrication | Process Equipment | CAD | 12338 | CAD | 12338 | 0 | Single Sourced | 2021-03-18 | 2021-03-18 | 2021-03-05 | 2021-03-18 | 2021-03-04 | 2021-03-18 | 2021-03-18 | 2021-03-04 | 2021-03-18 | 2021-04-01 | 2021-03-25 | 7 | 12 | -14
507220 | PepsiCo Medellin | Guelph | ELECTRICAL & CONTROL (PLC, HMI | KELTOUR CONTROLS INC. | 4503553390 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 42736 | CAD | 42736 | 0 | Supplier Competitions / Negotiation | 2021-03-15 | 2021-04-06 | 2021-03-17 | 2021-03-17 | 2021-03-16 | 2021-04-06 | 2021-03-17 | 2021-03-16 | 2021-04-29 | 2021-04-27 | 2021-04-28 | -1 | 18 | -21
507220 | PepsiCo Medellin | Guelph | AIR (BLOWERS, EJECTORS) | AERZEN CANADA INC. | 4503536578 | Rotating Equipment | Blowers & Fans | CAD | 37547 | CAD | 32370 | 5177 | Estimate Without Market Reference(No Quote) | 2021-02-17 | 2021-04-09 | 2021-02-17 | 2021-02-17 | 2021-02-16 | 2021-04-09 | 2021-02-17 | 2021-02-16 | 2021-05-31 | 2021-04-13 | 2021-05-07 | -24 | 30 | -52
507220 | PepsiCo Medellin | Guelph | RAS PUMPS UF | FLOWSERVE INC. | 4503538113 | Rotating Equipment | Metal Isolation Valves | CAD | 44807 | CAD | 20455 | 24352 | Estimate Without Market Reference(No Quote) | 2021-02-19 | 2021-04-10 | 2021-02-19 | 2021-02-19 | 2021-02-18 | 2021-04-10 | 2021-02-19 | 2021-02-18 | 2021-05-31 | 2021-05-13 | 2021-05-22 | -9 | 30 | -51
507220 | PepsiCo Medellin | Guelph | UF CLEANING | PROMINENT FLUID CONTROLS LTD. | 4503549077 | Flow Control | Metal Isolation Valves | CAD | 27507 | CAD | 27507 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-02-19 | 2021-04-01 | 2021-03-10 | 2021-02-19 | 2021-03-10 | 2021-04-01 | 2021-02-19 | 2021-03-10 | 2021-04-28 | 2021-05-12 | 2021-05-05 | 7 | 12 | -22
507235 | South Davis WWTP MBBR | Oakville | Screen | Aqseptance | 4503579352 | Fabrication | Stainless Steel | USD | 9842 | USD | 8750 | 1092 | Design Optimizations | 2021-04-13 | 2021-05-09 | 2021-02-17 | 2021-04-27 | 2021-05-09 | 2021-05-09 | 2021-05-04 | 2021-05-04 | 2021-07-29 | 2021-07-29 | 2021-07-29 | 0 | 12 | -5
507242 | COKE DENVER 350 GPM H20 | Minnetonka | LS - TEKLEEN | TEKLEEN | 4503506551 | Electrical & Instrumentation | Carbon Steel | USD | 15150 | USD | 15150 | 0 | Frame Agreements | 2021-11-12 | 2020-12-11 | 2020-11-18 | 2021-12-20 | 2020-11-18 | 2021-06-05 | 2021-12-21 | 2020-12-21 | 2021-03-11 | 2021-03-11 | 2021-01-08 | 62 | 18 | 10
507242 | COKE DENVER 350 GPM H20 | Minnetonka | LS - UV | AQUIONICS, INC. | 4503506548 | Electrical & Instrumentation | Carbon Steel | USD | 49174 | USD | 59880 | -10706 | Size/ Weight/ Quantity Underestimated | 2021-11-12 | 2020-12-07 | 2020-12-07 | 2021-12-20 | 2020-12-21 | 2021-06-14 | 2021-12-21 | 2020-12-21 | 2021-04-29 | 2021-03-01 | 2021-03-30 | -29 | 18 | 14
507242 | COKE DENVER 350 GPM H20 | Minnetonka | TANKS FRP: TRICKLE/CITY/REC RO | DIAMOND FIBERGLASS | 4503506542 | Fabrication | Ele-Control Panels | USD | 73950 | USD | 65325 | 8625 | Design Optimizations | 2021-11-12 | 2020-11-03 | 2020-11-03 | 2021-12-20 | 2020-12-19 | 2021-05-28 | 2021-12-21 | 2020-12-19 | 2021-05-05 | 2021-05-03 | 2021-05-04 | -1 | 12 | 46
507242 | COKE DENVER 350 GPM H20 | Minnetonka | TANKS SS: CIP / RO PERMEATE | Preferred Stainless Holdings | 4503506537 | Fabrication | Centrifugal Pumps | USD | 77505 | USD | 77660 | -155 | Estimate Without Market Reference(No Quote) | 2021-11-12 | 2020-11-11 | 2020-11-11 | 2021-12-20 | 2020-12-20 | 2021-06-01 | 2021-12-21 | 2020-12-20 | 2021-05-05 | 2021-05-05 | 2021-05-05 | 0 | 12 | 39
507242 | COKE DENVER 350 GPM H20 | Minnetonka | CITY WATER PUMPS | PFC EQUIPMENT | 4503506556 | Rotating Equipment | Carbon Steel | USD | 16278 | USD | 16278 | 0 | Proposed Supplier Incapable Of Executing | 2021-12-21 | 2020-12-10 | 2020-12-10 | 2021-12-21 | 2020-12-20 | 2021-06-16 | 2021-12-21 | 2020-12-20 | 2021-05-05 | 2021-03-08 | 2021-04-06 | -29 | 30 | 10
507242 | COKE DENVER 350 GPM H20 | Minnetonka | AC TOWERS - GRISWOLD | Duncan Co. | 4503527298 | Electrical & Instrumentation | Carbon Steel | USD | 6646 | USD | 6646 | 0 | Single Sourced | 2021-02-15 | 2021-02-01 | 2021-02-01 | 2021-02-15 | 2021-02-01 | 2021-02-15 | 2021-02-15 | 2021-02-01 | 2021-02-15 | 2021-03-01 | 2021-02-22 | 7 | 18 | 0
507242 | COKE DENVER 350 GPM H20 | Minnetonka | AC TOWERS / SPOOLS 507242B-PS-01 | Liquid Flow | 4503537444 | Fabrication | Carbon Steel | USD | 12987 | USD | 12987 | 0 | Single Sourced | 2021-03-07 | 2021-02-11 | 2021-02-19 | 2021-03-07 | 2021-02-18 | 2021-03-07 | 2021-03-07 | 2021-02-18 | 2021-03-07 | 2021-04-01 | 2021-03-19 | 13 | 12 | 7
507242 | COKE DENVER 350 GPM H20 | Minnetonka | VESSEL: AC TOWER / 507242B | Arrow Tanks | 4503504823 | Fabrication | Carbon Steel | USD | 122200 | USD | 122200 | 0 | Frame Agreements | 2021-11-12 | 2020-11-18 | 2020-11-18 | 2021-12-17 | 2020-12-17 | 2021-06-03 | 2021-12-17 | 2020-12-17 | 2021-03-30 | 2021-03-30 | 2021-03-30 | 0 | 12 | 29
507242 | COKE DENVER 350 GPM H20 | Minnetonka | RO Electrical Panels | Wunderlich-Malec Systems Inc | 4503537942 | Electrical & Instrumentation | Ele-Electrical Others | USD | 64130 | USD | 64130 | 0 | Market Impact | 2021-02-09 | 2021-02-09 | 2021-02-15 | 2021-02-15 | 2021-02-19 | 2021-03-10 | 2021-02-15 | 2021-02-22 | 2021-04-08 | 2021-03-29 | 2021-04-03 | -5 | 18 | 13
507242 | COKE DENVER 350 GPM H20 | Minnetonka | LS - MCE | WERNER ELECTRIC | 4503524756 | Electrical & Instrumentation | Ele-Control Panels | USD | 85000 | USD | 84395 | 605 | Design Optimizations | 2021-12-19 | 2021-01-19 | 2021-01-19 | 2021-01-18 | 2021-01-26 | 2021-07-04 | 2021-01-18 | 2021-01-26 | 2021-03-03 | 2021-04-06 | 2021-03-20 | 17 | 18 | 7
507242 | COKE DENVER 350 GPM H20 | Minnetonka | REC RO SKID - PUMPS | ALFA LAVAL | 4503506558 | Rotating Equipment | Carbon Steel | USD | 24643 | USD | 24643 | 0 | Not included in Proposal / RFQ | 2021-11-12 | 2020-11-04 | 2020-11-04 | 2021-12-20 | 2020-12-21 | 2021-05-29 | 2021-12-21 | 2020-12-21 | 2021-03-08 | 2021-03-01 | 2021-03-04 | -3 | 30 | 47
507242 | COKE DENVER 350 GPM H20 | Minnetonka | REC RO HOUSINGS | PROTEC ARISAWA AMERICA, INC. | 4503507202 | Flow Control | RO Membrane Housings | USD | 28738 | USD | 30303 | -1565 | Market Impact | 2021-11-12 | 2020-12-18 | 2020-12-18 | 2021-12-20 | 2020-12-22 | 2021-06-20 | 2021-12-21 | 2020-12-22 | 2021-03-01 | 2021-03-16 | 2021-03-08 | 8 | 12 | 4
507242 | COKE DENVER 350 GPM H20 | Minnetonka | LS - LOOSE SHIP | MICRO-MOTION, INC | 4503532456 | Electrical & Instrumentation | Ele-Control Panels | USD | 39731 | USD | 16461 | 23270 | Design Optimizations | 2021-01-29 | 2020-12-23 | 2020-12-23 | 2021-02-01 | 2021-02-09 | 2021-02-27 | 2021-02-02 | 2021-02-09 | 2021-05-05 | 2021-04-06 | 2021-04-20 | -14 | 18 | 48
507242 | COKE DENVER 350 GPM H20 | Minnetonka | LS - LOOSE SHIP | Duncan Co. | 4503518958 | Flow Control | Ele-Control Panels | USD | 12825 | USD | 12825 | 0 | Estimate Without Market Reference(No Quote) | 2021-02-21 | 2020-12-24 | 2020-12-24 | 2021-02-21 | 2021-01-19 | 2021-02-21 | 2021-02-21 | 2021-01-20 | 2021-02-21 | 2021-04-21 | 2021-03-22 | 30 | 12 | 27
507292 | St Paul | Oakville | Accelator Pack | Astro Metal Craft | 4503564208 | Fabrication | Metal Isolation Valves | USD | 73670 | USD | 71500 | 2170 | Design Optimizations | 2021-01-27 | 2021-03-07 | 2021-01-27 | 2021-02-08 | 2021-02-08 | 2021-03-07 | 2021-02-23 | 2021-02-21 | 2021-04-15 | 2021-04-14 | 2021-04-14 | 0 | 12 | -14
507299 | Global Foundries Fab 10 | Guelph | Pressure Vessel MB DI 36" OD x 63" Straight Side | LESENA STEEL DIVISION | 4503570829 | Fabrication | Carbon Steel | USD | 20150 | CAD | 13914 | 6236 | Design Optimizations | 2021-03-02 | 2021-02-16 | 2021-03-16 | 2021-03-12 | 2021-03-30 | 2021-04-01 | 2021-03-19 | 2021-04-04 | 2021-05-14 | 2021-05-16 | 2021-05-15 | 1 | 12 | 47
507299 | Global Foundries Fab 10 | Guelph | ETFE Lining for Vessels | Fisher Utah | 4503570832 | Fabrication | Carbon Steel | USD | 14935 | USD | 15350 | -415 | Market Impact | 2021-03-02 | 2021-02-16 | 2021-03-09 | 2021-03-12 | 2021-03-30 | 2021-04-11 | 2021-03-19 | 2021-04-19 | 2021-06-04 | 2021-05-10 | 2021-05-22 | -12 | 12 | 62
507299 | Global Foundries Fab 10 | Guelph | Vessel Internals (Inlet distributors and underdrain laterals) | NV PIPING SYSTEMS INC. | 4503586080 | Fabrication | Carbon Steel | USD | 5916 | CAD | 14896 | -8980 | Market Impact | 2021-03-02 | 2021-02-16 | 2021-03-31 | 2021-03-12 | 2021-04-16 | 2021-04-19 | 2021-03-19 | 2021-05-17 | 2021-05-14 | 2021-06-21 | 2021-06-02 | 19 | 12 | 90
507299 | Global Foundries Fab 10 | Guelph | Resin | DDP SPECIALITY PRODUCTS 102 PRIVA | 4503586110 | Fabrication | Metal Isolation Valves | USD | 6754 | USD | 7587 | -833 | Estimate Without Market Reference(No Quote) | 2021-05-05 | 2021-05-05 | 2021-03-20 | 2021-05-05 | 2021-05-14 | 2021-05-05 | 2021-05-05 | 2021-05-17 | 2021-05-05 | 2021-06-21 | 2021-05-28 | 24 | 12 | 12
507300 | Coke Londonderry | Minnetonka | AC TOWER | Arrow Tanks | 4503512731 | Fabrication | Carbon Steel | USD | 55000 | USD | 56059 | -1059 | Proposed Supplier Incapable Of Executing | 2021-01-07 | 2021-02-03 | 2021-01-07 | 2021-01-07 | 2021-01-06 | 2021-02-03 | 2021-01-07 | 2021-01-06 | 2021-03-03 | 2021-03-02 | 2021-03-02 | 0 | 12 | -28
507300 | Coke Londonderry | Minnetonka | CARTRIDGE FILTERS | Duncan Co. | 4503506559 | Flow Control | Filters And Strainers (Incl Housings) | USD | 13680 | USD | 13680 | 0 | Estimate Without Market Reference(No Quote) | 2020-12-08 | 2021-01-18 | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2021-01-18 | 2020-12-08 | 2020-12-08 | 2021-03-01 | 2021-03-01 | 2021-03-01 | 0 | 12 | -41
507311 | Nor-Cal Beverages | Minnetonka | (2) CARBON TOWER VESSEL | Arrow Tanks | 4503511914 | Fabrication | Carbon Steel | USD | 119982 | USD | 119982 | 0 | Estimate Without Market Reference(No Quote) | 2021-01-04 | 2020-12-17 | 2020-12-17 | 2021-01-05 | 2021-01-06 | 2021-01-13 | 2021-01-06 | 2021-01-06 | 2021-02-10 | 2021-02-10 | 2021-02-10 | 0 | 12 | 20
507311 | Nor-Cal Beverages | Minnetonka | POLISHING FILTERS | Duncan Co. | 4503519245 | Flow Control | Filters And Strainers (Incl Housings) | USD | 15750 | USD | 10000 | 5750 | Frame Agreements | 2021-02-01 | 2021-01-20 | 2021-01-20 | 2021-02-03 | 2021-01-19 | 2021-02-26 | 2021-02-04 | 2021-01-19 | 2021-04-05 | 2021-03-14 | 2021-03-25 | -11 | 12 | -1
507311 | Nor-Cal Beverages | Minnetonka | HMI/PLC ENCLOSURE | BW Systems | 4513528054 | Electrical & Instrumentation | Ele-Control Panels | USD | 37998 | USD | 38053 | -55 | Market Impact | 2021-02-01 | 2021-02-03 | 2021-02-03 | 2021-02-03 | 2021-02-01 | 2021-03-04 | 2021-02-04 | 2021-03-05 | 2021-04-05 | 2021-03-08 | 2021-03-22 | -14 | 18 | 30
507610 | Georges Creek | Oakville | Control Panel | ICSE | 4503588574 | Electrical & Instrumentation | Ele-Control Panels | USD | 9849 | USD | 9849 | 0 | Size/ Weight/ Quantity Underestimated | 2021-03-24 | 2021-03-25 | 2021-04-13 | 2021-04-08 | 2021-05-27 | 2021-05-27 | 2021-04-15 | 2021-05-20 | 2021-07-31 | 2021-06-28 | 2021-07-14 | -16 | 18 | 56
507610 | Georges Creek | Oakville | Climber Screen - Fabricator | RICHLAND LLC | 4503570010 | Fabrication | Stainless Steel | USD | 61034 | USD | 82561 | -21527 | Specs / Requirements Misinterpreted in Proposal | 2021-03-23 | 2021-03-25 | 2021-04-05 | 2021-04-01 | 2021-05-30 | 2021-05-30 | 2021-04-08 | 2021-04-16 | 2021-07-31 | 2021-08-06 | 2021-08-03 | 3 | 12 | 22
507610 | Georges Creek | Oakville | Climber Screen - Machined Parts | HALL INDUSTRIES INC. | 4503572439 | Fabrication | Stainless Steel | USD | 9694 | USD | 18159 | -8465 | Not included in Proposal / RFQ | 2021-03-23 | 2021-05-27 | 2021-04-04 | 2021-04-02 | 2021-05-27 | 2021-05-27 | 2021-04-09 | 2021-04-21 | 2021-07-31 | 2021-05-17 | 2021-06-23 | -37 | 12 | -36
507616 | ABBOTT HOT WATER SANI | Minnetonka | Instrumentation - Rosemount SENSORS | ROSEMOUNT INC | 4503548008 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 10685 | USD | 6010 | 4675 | Design Optimizations | 2021-03-12 | 2021-02-26 | 2021-02-26 | 2021-03-15 | 2021-03-09 | 2021-03-30 | 2021-03-15 | 2021-03-09 | 2021-05-01 | 2021-04-16 | 2021-04-23 | -7 | 18 | 11
507616 | ABBOTT HOT WATER SANI | Minnetonka | Valves - Jamesbury | Duncan Co. | 4503546618 | Flow Control | Metal Isolation Valves | USD | 10277 | USD | 61352 | -51075 | Not included in Proposal / RFQ | 2021-03-01 | 2021-03-04 | 2021-03-04 | 2021-03-03 | 2021-03-06 | 2021-03-31 | 2021-03-04 | 2021-03-06 | 2021-05-01 | 2021-05-01 | 2021-05-01 | 0 | 12 | 2
507616 | ABBOTT HOT WATER SANI | Minnetonka | Control Panel | BW Systems | 4503544428 | Electrical & Instrumentation | Ele-Control Panels | USD | 44820 | USD | 31405 | 13415 | Design Optimizations | 2021-03-12 | 2021-02-24 | 2021-03-01 | 2021-03-15 | 2021-03-01 | 2021-03-29 | 2021-03-15 | 2021-03-01 | 2021-05-01 | 2021-04-05 | 2021-04-18 | -13 | 18 | 5
507620 | ALMEX | Minnetonka | PROflex 18-2S-MOD | Duncan Co. | 4503555039 | Flow Control | Ele-Control Panels | USD | 9278 | USD | 9278 | 0 | Supplier Competitions / Negotiation | 2021-03-13 | 2021-03-13 | 2021-01-22 | 2021-03-13 | 2021-03-19 | 2021-03-13 | 2021-03-13 | 2021-03-19 | 2021-03-13 | 2021-05-03 | 2021-04-07 | 26 | 12 | 6
507620 | ALMEX | Minnetonka | PROflex 18-2S-MOD | Duncan Co. | 4503553503 | Electrical & Instrumentation | Ele-Control Panels | USD | 23446 | USD | 23446 | 0 | Not included in Proposal / RFQ | 2021-03-15 | 2021-04-05 | 2021-02-08 | 2021-03-18 | 2021-03-17 | 2021-04-05 | 2021-03-21 | 2021-03-17 | 2021-06-01 | 2021-05-18 | 2021-05-25 | -7 | 18 | -19
507669 | Ponce Nueva | Richmond | Air Compressor | ATLAS COPCO COMPRESSORS | 4503772293 | Rotating Equipment | Compressors | USD | 15110 | CAD | 19648 | -4538 | Specs / Requirements Misinterpreted in Proposal | 2021-12-21 | 2021-05-15 | 2021-05-19 | 2021-12-29 | 2022-02-03 | 2021-12-15 | 2022-01-03 | 2022-04-10 | 2022-03-25 | 2022-07-17 | 2022-05-21 | 57 | 30 | 330
507669 | Ponce Nueva | Richmond | SS304 Brackets | BURKES MECHANICAL | 4503717639 | Fabrication | Stainless Steel | USD | 74195 | USD | 76003 | -1808 | Size/ Weight/ Quantity Underestimated | 2021-12-21 | 2022-01-05 | 2022-01-12 | 2021-12-29 | 2022-01-06 | 2022-02-12 | 2022-01-03 | 2022-01-12 | 2022-03-25 | 2022-04-06 | 2022-03-31 | 6 | 12 | 7
507669 | Ponce Nueva | Richmond | Control Panel | KELTOUR CONTROLS INC. | 4503699762 | Electrical & Instrumentation | Ele-Control Panels | USD | 40412 | CAD | 34446 | 5966 | Frame Agreements | 2021-12-21 | 2021-10-29 | 2021-11-03 | 2021-12-29 | 2021-10-18 | 2022-01-06 | 2022-01-03 | 2021-12-05 | 2022-03-25 | 2022-03-27 | 2022-03-26 | 1 | 18 | 37
507669 | Ponce Nueva | Richmond | Slide Gates | JOB SHOP FABRICATORS | 4503753408 | Fabrication | Non-Metal Equipment | USD | 10820 | USD | 28009 | -17189 | Estimate Without Market Reference(No Quote) | 2021-12-21 | 2022-03-08 | 2022-03-10 | 2021-12-29 | 2022-03-09 | 2022-03-22 | 2022-01-03 | 2022-03-09 | 2022-03-25 | 2022-06-21 | 2022-05-08 | 44 | 12 | 1
507669 | Ponce Nueva | Richmond | Aluminium Fabrication | SHARP IRON GROUP | 4503730713 | Fabrication | Alloy Steel | USD | 55811 | USD | 323852 | -268041 | Specs / Requirements Misinterpreted in Proposal | 2021-12-21 | 2022-01-04 | 2022-01-06 | 2021-12-29 | 2022-01-30 | 2022-03-25 | 2022-01-03 | 2022-01-31 | 2022-03-25 | 2022-06-27 | 2022-05-11 | 47 | 12 | 27
507669 | Ponce Nueva | Richmond | Cross Member support - Job shop | EASTERN METAL | 4503646000 | Fabrication | Alloy Steel | USD | 6860 | USD | 6479 | 381 | Supplier Competitions / Negotiation | 2021-11-11 | 2021-08-29 | 2021-09-03 | 2021-11-11 | 2021-09-03 | 2021-11-11 | 2021-11-11 | 2021-09-03 | 2021-11-11 | 2022-01-25 | 2021-12-18 | 38 | 12 | 5
507669 | Ponce Nueva | Richmond | Cross member support - Site | EASTERN METAL | 4503645932 | Fabrication | Alloy Steel | USD | 94140 | USD | 94140 | 0 | Estimate Without Market Reference(No Quote) | 2022-03-03 | 2022-09-01 | 2021-09-03 | 2022-03-03 | 2021-09-03 | 2022-03-03 | 2022-03-03 | 2021-09-03 | 2022-03-03 | 2022-02-25 | 2022-02-28 | -3 | 12 | -363
507669 | Ponce Nueva | Richmond | Mixers | Philadelphia Mixing Solutions | 4503699756 | Rotating Equipment | Mixers | USD | 82102 | USD | 66996 | 15106 | Frame Agreements | 2021-12-21 | 2021-10-25 | 2021-10-27 | 2021-12-29 | 2021-12-07 | 2022-01-08 | 2022-01-03 | 2021-12-07 | 2022-03-25 | 2022-03-21 | 2022-03-23 | -2 | 30 | 43
507669 | Ponce Nueva | Richmond | Settling Plates | KAL-LITE | 4503725746 | Fabrication | Non-Metal Equipment | USD | 52272 | USD | 58545 | -6273 | Not included in Proposal / RFQ | 2021-12-21 | 2022-01-05 | 2022-01-13 | 2021-12-29 | 2022-01-12 | 2022-02-18 | 2022-01-03 | 2022-01-24 | 2022-03-25 | 2022-04-18 | 2022-04-06 | 12 | 12 | 19
507669 | Ponce Nueva | Richmond | Settling tubes | BRENTWOOD INDUSTRIES | 4503729240 | Fabrication | Non-Metal Equipment | USD | 92390 | USD | 116103 | -23713 | Single Sourced | 2021-12-21 | 2022-01-05 | 2022-01-14 | 2021-12-29 | 2022-01-13 | 2022-03-16 | 2022-01-03 | 2022-01-31 | 2022-03-25 | 2022-06-10 | 2022-05-02 | 39 | 12 | 26
507669 | Ponce Nueva | Richmond | PVC Piping Part 1 | Indelco Plastics | 4503708268 | Flow Control | Plastic Pipe and Fittings | USD | 106476 | USD | 96059 | 10417 | Supplier Competitions / Negotiation | 2021-12-21 | 2021-11-29 | 2021-12-02 | 2021-12-29 | 2021-12-21 | 2022-01-26 | 2022-01-03 | 2021-12-23 | 2022-03-25 | 2022-03-22 | 2022-03-23 | -1 | 12 | 24
507669 | Ponce Nueva | Richmond | Buy outs | BURKES MECHANICAL | 4503735741 | Fabrication | Non-Metal Equipment | USD | 11278 | USD | 15386 | -4108 | Specs / Requirements Misinterpreted in Proposal | 2021-12-21 | 2022-02-08 | 2022-02-10 | 2021-12-29 | 2022-02-09 | 2022-03-12 | 2022-01-03 | 2022-02-09 | 2022-03-25 | 2022-06-02 | 2022-04-28 | 35 | 12 | 1
507669 | Ponce Nueva | Richmond | Plug valves | DEZURIK | 4503710090 | Flow Control | Metal Control Valves | USD | 60167 | USD | 58604 | 1563 | Design Optimizations | 2021-12-21 | 2021-12-25 | 2021-12-30 | 2021-12-29 | 2021-12-22 | 2022-02-06 | 2022-01-03 | 2021-12-30 | 2022-03-25 | 2022-03-10 | 2022-03-17 | -7 | 12 | 5
507669 | Ponce Nueva | Richmond | Vaccum Pumps | Tencarva Machinery Co. | 4503729248 | Rotating Equipment | Others | USD | 22611 | USD | 37112 | -14501 | Market Impact | 2021-12-21 | 2021-12-25 | 2021-12-30 | 2021-12-29 | 2022-02-08 | 2022-03-16 | 2022-01-03 | 2022-01-30 | 2022-03-25 | 2022-06-09 | 2022-05-02 | 38 | 30 | 36
507670 | Midnite Mine via Stantec Denver | Richmond | Clarifier Tank + Mechanism | AZ INDUSTRIES | 4503758176 | Fabrication | Carbon Steel | USD | 242736 | USD | 159024 | 83712 | Frame Agreements | 2021-12-02 | 2022-02-08 | 2022-03-02 | 2021-12-15 | 2022-03-09 | 2022-03-22 | 2022-02-28 | 2022-03-16 | 2022-07-11 | 2022-07-07 | 2022-07-09 | -2 | 12 | 36
507670 | Midnite Mine via Stantec Denver | Richmond | Reactor Drive | SEW EURODRIVE | 4503768975 | Electrical & Instrumentation | Ele-Electrical Others | USD | 8885 | USD | 8860 | 25 | Supplier Competitions / Negotiation | 2022-02-26 | 2021-09-05 | 2021-09-09 | 2022-04-14 | 2022-03-30 | 2022-02-25 | 2022-04-26 | 2022-04-05 | 2022-08-16 | 2022-08-17 | 2022-08-16 | 1 | 18 | 212
507670 | Midnite Mine via Stantec Denver | Richmond | Rapid mixers | DYNAMIX | 4503769300 | Rotating Equipment | Mixers | USD | 10017 | CAD | 27307 | -17290 | Market Impact | 2022-02-26 | 2021-12-21 | 2022-01-06 | 2022-04-14 | 2022-04-01 | 2022-04-19 | 2022-04-26 | 2022-04-06 | 2022-08-16 | 2022-08-17 | 2022-08-16 | 1 | 30 | 106
507670 | Midnite Mine via Stantec Denver | Richmond | Clarifier Drive | DBS MANUFACTURING INC. | 4503766313 | Electrical & Instrumentation | Ele-Electrical Others | USD | 11430 | USD | 16681 | -5251 | Specs / Requirements Misinterpreted in Proposal | 2022-05-17 | 2022-02-15 | 2022-02-25 | 2022-05-17 | 2022-03-23 | 2022-05-17 | 2022-05-17 | 2022-03-31 | 2022-05-17 | 2022-08-17 | 2022-07-02 | 46 | 18 | 44
507670 | Midnite Mine via Stantec Denver | Richmond | Sludge Recycle/Blowdown pumps | MILTON ROY MIXING *** USE 241730 ** | 4503777578 | Rotating Equipment | PD Pumps | USD | 18473 | USD | 30215 | -11742 | Estimate Without Market Reference(No Quote) | 2022-02-26 | 2021-01-31 | 2022-02-17 | 2022-04-14 | 2022-04-15 | 2021-11-08 | 2022-04-26 | 2022-04-20 | 2022-08-16 | 2022-06-08 | 2022-07-12 | -34 | 30 | 444
507670 | Midnite Mine via Stantec Denver | Richmond | Control Panel | ICSE | 4503782321 | Electrical & Instrumentation | Ele-Control Panels | USD | 48410 | USD | 18950 | 29460 | Design Optimizations | 2022-03-23 | 2022-04-07 | 2022-04-13 | 2022-04-12 | 2022-04-28 | 2022-06-04 | 2022-04-26 | 2022-04-28 | 2022-08-16 | 2022-08-07 | 2022-08-11 | -4 | 18 | 21
507670 | Midnite Mine via Stantec Denver | Richmond | Plug Valves | DEZURIK | 4503766316 | Flow Control | Metal Control Valves | USD | 12191 | USD | 9438 | 2753 | Supplier Competitions / Negotiation | 2022-04-26 | 2022-02-01 | 2022-02-03 | 2022-05-10 | 2022-03-28 | 2022-05-10 | 2022-05-24 | 2022-03-30 | 2022-08-16 | 2022-06-01 | 2022-07-09 | -38 | 12 | 57
507681 | Shamattawa | Oakville | UV | Trojan Technologies INC. | 4503681716 | Flow Control | Other | CAD | 124750 | CAD | 129750 | -5000 | Market Impact | 2021-06-09 | 2021-07-20 | 2021-07-22 | 2021-08-03 | 2021-10-27 | 2021-10-16 | 2021-08-25 | 2021-11-06 | 2021-11-10 | 2022-02-23 | 2022-01-01 | 53 | 12 | 109
507681 | Shamattawa | Oakville | Control Panel | MACHINE CONTROL SYSTEMS | 4503668241 | Electrical & Instrumentation | Ele-Control Panels | CAD | 109200 | CAD | 75183 | 34017 | Design Optimizations | 2021-06-09 | 2021-09-08 | 2021-09-16 | 2021-08-03 | 2021-10-12 | 2021-08-28 | 2021-08-25 | 2021-10-13 | 2021-11-10 | 2021-11-17 | 2021-11-13 | 4 | 18 | 35
507681 | Shamattawa | Oakville | Strainer components | BOLL FILTER CORPORATION | 4503647642 | Flow Control | Other | CAD | 55127 | USD | 41872 | 13255 | Frame Agreements | 2021-06-09 | 2021-07-20 | 2021-07-22 | 2021-08-03 | 2021-09-07 | 2021-09-09 | 2021-08-25 | 2021-09-08 | 2021-11-10 | 2021-12-10 | 2021-11-25 | 15 | 12 | 50
507681 | Shamattawa | Oakville | Butterfly Valve | BRAY CONTROLS CANADA LTD. | 4503663814 | Flow Control | Metal Control Valves | CAD | 36219 | USD | 26626 | 9593 | Design Optimizations | 2021-06-09 | 2021-09-16 | 2021-09-17 | 2021-08-03 | 2021-10-04 | 2021-09-11 | 2021-08-25 | 2021-10-05 | 2021-11-10 | 2021-12-14 | 2021-11-27 | 17 | 12 | 19
507681 | Shamattawa | Oakville | Permeate Pump | FLOWSERVE | 4503647585 | Rotating Equipment | Centrifugal Pumps | CAD | 52960 | USD | 52249 | 711 | Design Optimizations | 2021-06-09 | 2021-05-20 | 2021-05-25 | 2021-08-03 | 2021-05-25 | 2021-08-22 | 2021-08-25 | 2021-09-07 | 2021-11-10 | 2021-11-25 | 2021-11-17 | 8 | 30 | 110
507681 | Shamattawa | Oakville | Chemical Dosing system | PROMINENT FLUID CONTROLS LTD. | 4503706799 | Rotating Equipment | Chem. Feed Skids (Turnkey) | CAD | 31748 | CAD | 12442 | 19306 | Supplier Competitions / Negotiation | 2021-06-09 | 2021-12-09 | 2021-12-09 | 2021-08-03 | 2021-12-14 | 2021-10-26 | 2021-08-25 | 2021-12-20 | 2021-11-10 | 2022-03-14 | 2022-01-11 | 62 | 30 | 11
507681 | Shamattawa | Oakville | Tanks | ACO CONTAINER SYSTEMS LTD. | 4503643979 | Flow Control | Plastic Tanks | CAD | 25308 | CAD | 34414 | -9106 | Proposed Supplier Incapable Of Executing | 2021-06-09 | 2021-07-22 | 2021-07-27 | 2021-08-03 | 2021-09-01 | 2021-08-25 | 2021-08-25 | 2021-09-01 | 2021-11-10 | 2021-11-01 | 2021-11-05 | -4 | 12 | 41
507681 | Shamattawa | Oakville | Air Compressor | Compressor Science Inc. | 4503643987 | Rotating Equipment | Compressors | CAD | 15500 | USD | 24834 | -9334 | Proposed Supplier Incapable Of Executing | 2021-06-09 | 2021-07-13 | 2021-07-19 | 2021-08-03 | 2021-08-29 | 2021-08-25 | 2021-08-25 | 2021-08-30 | 2021-11-10 | 2021-10-25 | 2021-11-02 | -8 | 30 | 48
507681 | Shamattawa | Oakville | Level Transmitter | ENDRESS & HAUSER | 4503662825 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | CAD | 28545 | USD | 34134 | -5589 | Not included in Proposal / RFQ | 2021-06-09 | 2021-10-02 | 2021-10-04 | 2021-08-03 | 2021-10-03 | 2021-09-10 | 2021-08-25 | 2021-10-04 | 2021-11-10 | 2021-12-13 | 2021-11-26 | 17 | 18 | 2
507681 | Shamattawa | Oakville | Membrane Accessories | 3D MECHANICAL | 4503704838 | Fabrication | Stainless Steel | CAD | 23976 | CAD | 29364 | -5388 | Size/ Weight/ Quantity Underestimated | 2021-06-09 | 2021-11-28 | 2021-12-16 | 2021-08-03 | 2021-12-16 | 2021-10-10 | 2021-08-25 | 2021-12-16 | 2021-11-10 | 2022-02-10 | 2021-12-26 | 46 | 12 | 18
507681 | Shamattawa | Oakville | Blower | FPZ INC | 4503650351 | Rotating Equipment | Blowers & Fans | CAD | 7154 | USD | 7816 | -662 | Estimate Without Market Reference(No Quote) | 2021-06-09 | 2020-12-16 | 2020-12-17 | 2021-08-03 | 2021-09-09 | 2021-05-29 | 2021-08-25 | 2021-09-12 | 2021-11-10 | 2021-11-07 | 2021-11-08 | -1 | 30 | 270
507767 | Danone | Oakville | Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503565707 | Electrical & Instrumentation | Ele-Control Panels | USD | 44226 | USD | 17923 | 26303 | Frame Agreements | 2021-02-12 | 2021-03-19 | 2021-03-26 | 2021-02-26 | 2021-04-02 | 2021-03-19 | 2021-03-12 | 2021-04-09 | 2021-04-23 | 2021-04-09 | 2021-04-16 | -7 | 18 | 21
507811 | Wis-Pak | Minnetonka | AC VESSEL 84X144 | Arrow Tanks | 4503541149 | Fabrication | Carbon Steel | USD | 51800 | USD | 51800 | 0 | Design Optimizations | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-03-27 | 2021-02-17 | 2021-02-25 | 2021-05-04 | 2021-05-04 | 2021-05-04 | 0 | 12 | 8
507811 | Wis-Pak | Minnetonka | LS-03 DESTRUCT AND PRE UV | Trojan Technologies INC. | 4503547080 | Electrical & Instrumentation | Carbon Steel | USD | 44899 | USD | 45270 | -371 | Specs / Requirements Misinterpreted in Proposal | 2021-02-17 | 2021-02-17 | 2021-03-03 | 2021-03-04 | 2021-03-05 | 2021-03-30 | 2021-03-05 | 2021-03-08 | 2021-05-10 | 2021-05-03 | 2021-05-06 | -3 | 18 | 19
507811 | Wis-Pak | Minnetonka | FORSTA FILTERS | FORSTA FILTERS | 4503540318 | Flow Control | Filters And Strainers (Incl Housings) | USD | 72395 | USD | 72395 | 0 | Market Impact | 2021-02-18 | 2021-02-18 | 2021-02-18 | 2021-02-19 | 2021-02-23 | 2021-03-22 | 2021-02-24 | 2021-02-24 | 2021-04-23 | 2021-04-21 | 2021-04-22 | -1 | 12 | 6
507811 | Wis-Pak | Minnetonka | LS PDE | BW Systems | 4503550031 | Electrical & Instrumentation | Ele-Control Panels | USD | 43985 | USD | 43985 | 0 | Estimate Without Market Reference(No Quote) | 2021-03-02 | 2021-03-03 | 2021-03-11 | 2021-03-08 | 2021-03-09 | 2021-03-21 | 2021-03-08 | 2021-03-09 | 2021-04-10 | 2021-04-06 | 2021-04-08 | -2 | 18 | 6
507811 | Wis-Pak | Minnetonka | MCE | WERNER ELECTRIC | 4503550045 | Electrical & Instrumentation | Ele-Control Panels | USD | 39289 | USD | 39289 | 0 | Single Sourced | 2021-03-02 | 2021-03-03 | 2021-03-08 | 2021-03-08 | 2021-03-11 | 2021-03-24 | 2021-03-08 | 2021-03-11 | 2021-04-10 | 2021-04-15 | 2021-04-12 | 3 | 18 | 8
507825 | CLIFFSTAR REFRESCO | Minnetonka | AC FILTER | Arrow Tanks | 4503542257 | Fabrication | Metal Isolation Valves | USD | 46750 | USD | 46750 | 0 | Size/ Weight/ Quantity Underestimated | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-02-17 | 2021-03-24 | 2021-02-17 | 2021-02-27 | 2021-04-28 | 2021-04-28 | 2021-04-28 | 0 | 12 | 10
507882 | CHEVRON BELLE CHASSE | Oakville | Control Panel | KELTOUR CONTROLS INC. | 4503660745 | Electrical & Instrumentation | Ele-Control Panels | USD | 59940 | USD | 67314 | -7374 | Market Impact | 2021-04-01 | 2021-09-09 | 2021-09-16 | 2021-04-15 | 2021-09-21 | 2021-06-30 | 2021-04-29 | 2021-09-28 | 2021-08-13 | 2021-09-28 | 2021-09-05 | 23 | 18 | 19
507882 | CHEVRON BELLE CHASSE | Oakville | Piping Spool | R&R Metalworks | 4503676427 | Fabrication | Alloy Steel | USD | 10000 | USD | 29200 | -19200 | Not included in Proposal / RFQ | 2021-10-16 | 2021-10-06 | 2021-10-13 | 2021-10-16 | 2021-10-20 | 2021-10-16 | 2021-10-16 | 2021-10-27 | 2021-10-16 | 2021-10-27 | 2021-10-21 | 6 | 12 | 21
507882 | CHEVRON BELLE CHASSE | Oakville | Heater | Chromalox Inc. | 4503653369 | Electrical & Instrumentation | Ele-Electrical Others | USD | 10151 | USD | 9050 | 1101 | Design Optimizations | 2021-09-06 | 2021-08-27 | 2021-09-03 | 2021-09-06 | 2021-09-10 | 2021-09-06 | 2021-09-06 | 2021-09-17 | 2021-09-06 | 2021-09-17 | 2021-09-11 | 6 | 18 | 21
507882 | CHEVRON BELLE CHASSE | Oakville | Instrument - Transmitters | LAKESIDE PROCESS CONTROLS LTD. | 4503660984 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 8735 | USD | 22965 | -14230 | Size/ Weight/ Quantity Underestimated | 2021-09-20 | 2021-09-10 | 2021-09-17 | 2021-09-20 | 2021-09-24 | 2021-09-20 | 2021-09-20 | 2021-10-01 | 2021-09-20 | 2021-10-01 | 2021-09-25 | 6 | 18 | 21
507882 | CHEVRON BELLE CHASSE | Oakville | Change Order - Dosing Skid | PROMINENT FLUID CONTROLS LTD. | 4503655697 | Fabrication | Skid Assembly Outsourced | USD | 92928 | USD | 75240 | 17688 | Design Optimizations | 2021-09-11 | 2021-09-01 | 2021-09-08 | 2021-09-11 | 2021-09-15 | 2021-09-11 | 2021-09-11 | 2021-09-22 | 2021-09-11 | 2021-09-22 | 2021-09-16 | 6 | 12 | 21
507894 | Coke Montgomery | Minnetonka | Pre RO UV | AQUIONICS, INC. | 4503555694 | Electrical & Instrumentation | Metal Isolation Valves | USD | 28000 | USD | 22692 | 5308 | Supplier Competitions / Negotiation | 2021-03-03 | 2021-03-21 | 2021-03-22 | 2021-03-22 | 2021-03-22 | 2021-04-08 | 2021-03-22 | 2021-03-22 | 2021-04-28 | 2021-05-14 | 2021-05-06 | 8 | 18 | 1
507894 | Coke Montgomery | Minnetonka | RIO Panel | BW Systems | 4503558584 | Electrical & Instrumentation | Ele-Control Panels | USD | 15000 | USD | 9625 | 5375 | Design Optimizations | 2021-03-22 | 2021-03-22 | 2021-03-26 | 2021-03-24 | 2021-03-26 | 2021-04-09 | 2021-03-25 | 2021-03-26 | 2021-04-28 | 2021-04-23 | 2021-04-25 | -2 | 18 | 4
507936 | Lloydminster MBR | Oakville | Primary Clarifier | EVOQUA WATER TECHNOLOGIES, LLC | 4503597887 | Fabrication | Alloy Steel | CAD | 407431 | CAD | 614866 | -207435 | Supplier Competitions / Negotiation | 2021-05-25 | 2021-05-03 | 2021-06-07 | 2021-06-15 | 2022-06-07 | 2021-06-07 | 2021-06-22 | 2022-06-07 | 2021-06-22 | 2022-06-07 | 2021-12-14 | 175 | 12 | 400
507936 | Lloydminster MBR | Oakville | Butterfly & Check Valves (Bray) | CHICAGO TUBE AND IRON COMPANY | 4503744635 | Flow Control | Metal Control Valves | CAD | 19922 | USD | 19922 | 0 | Estimate Without Market Reference(No Quote) | 2021-11-12 | 2022-02-21 | 2022-02-24 | 2021-12-03 | 2022-02-24 | 2022-02-24 | 2021-12-10 | 2022-02-24 | 2021-12-10 | 2022-03-21 | 2022-01-29 | 51 | 12 | 3
507936 | Lloydminster MBR | Oakville | Ball Valves (Pinnacle) | Sylvan Automation Ltd. | 4503752887 | Flow Control | Metal Control Valves | CAD | 7400 | CAD | 7400 | 0 | Size/ Weight/ Quantity Underestimated | 2022-03-05 | 2022-02-01 | 2022-02-08 | 2022-03-05 | 2022-02-16 | 2022-03-08 | 2022-03-05 | 2022-03-09 | 2022-03-05 | 2022-04-06 | 2022-03-21 | 16 | 12 | 36
507936 | Lloydminster MBR | Oakville | Knife Gate (Bray) | BRAY CONTROLS CANADA LTD. | 4503752884 | Flow Control | Metal Control Valves | CAD | 11046 | USD | 11046 | 0 | Market Impact | 2022-03-17 | 2022-01-21 | 2022-01-25 | 2022-03-17 | 2022-02-23 | 2022-02-23 | 2022-03-17 | 2022-03-09 | 2022-03-17 | 2022-05-12 | 2022-04-14 | 28 | 12 | 47
507936 | Lloydminster MBR | Oakville | Kinife Gate Valves (Bray) | BRAY CONTROLS CANADA LTD. | 4503676971 | Flow Control | Metal Control Valves | CAD | 21837 | USD | 21837 | 0 | Single Sourced | 2021-12-12 | 2021-10-06 | 2021-10-22 | 2021-12-12 | 2021-10-28 | 2021-10-28 | 2021-12-12 | 2021-10-28 | 2021-12-12 | 2022-02-17 | 2022-01-14 | 34 | 12 | 22
507936 | Lloydminster MBR | Oakville | Air Relief Valves (ARI) | Pelmar Engineering Ltd | 4503767079 | Flow Control | Metal Control Valves | CAD | 15868 | USD | 24069 | -8201 | Size/ Weight/ Quantity Underestimated | 2022-04-11 | 2022-03-21 | 2022-03-28 | 2022-04-11 | 2022-03-29 | 2022-03-29 | 2022-04-11 | 2022-04-01 | 2022-04-11 | 2022-05-02 | 2022-04-21 | 11 | 12 | 11
507936 | Lloydminster MBR | Oakville | Butterfly Valves (Bray) | BRAY CONTROLS CANADA LTD. | 4503751969 | Flow Control | Metal Control Valves | CAD | 115719 | USD | 115719 | 0 | Size/ Weight/ Quantity Underestimated | 2022-03-18 | 2022-02-02 | 2022-02-11 | 2022-03-18 | 2022-03-03 | 2022-03-03 | 2022-03-18 | 2022-03-08 | 2022-03-18 | 2022-05-02 | 2022-04-09 | 23 | 12 | 34
507936 | Lloydminster MBR | Oakville | Kinife Gate Valves (Bray) | BRAY CONTROLS CANADA LTD. | 4503689972 | Flow Control | Metal Control Valves | CAD | 181062 | USD | 181062 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-10-28 | 2021-10-06 | 2021-11-10 | 2021-10-28 | 2021-11-17 | 2021-11-19 | 2021-10-28 | 2021-11-19 | 2021-10-28 | 2021-11-19 | 2021-11-08 | 11 | 12 | 44
507936 | Lloydminster MBR | Oakville | Ball Valves (Pinacle) | Sylvan Automation Ltd. | 4503766971 | Electrical & Instrumentation | Inst-Instrumentation Others | CAD | 8460 | CAD | 8460 | 0 | Specs / Requirements Misinterpreted in Proposal | 2022-04-02 | 2022-03-07 | 2022-03-28 | 2022-04-02 | 2022-03-28 | 2022-03-28 | 2022-04-02 | 2022-03-31 | 2022-04-02 | 2022-04-28 | 2022-04-15 | 13 | 18 | 24
507936 | Lloydminster MBR | Oakville | Air Relief Valve (APCO) | FLOVAL EQUIPMENT LIMITED | 4503767047 | Flow Control | Metal Control Valves | CAD | 7584 | CAD | 7584 | 0 | Single Sourced | 2022-03-23 | 2022-02-16 | 2022-02-23 | 2022-03-23 | 2022-03-17 | 2022-03-17 | 2022-03-23 | 2022-04-01 | 2022-03-23 | 2022-04-28 | 2022-04-10 | 18 | 12 | 44
507936 | Lloydminster MBR | Oakville | Instruments (Ashcroft) | CONVAL EQUIPMENT LIMITED | 4503751957 | Electrical & Instrumentation | Inst-Instrumentation Others | CAD | 8299 | USD | 8299 | 0 | Size/ Weight/ Quantity Underestimated | 2022-03-08 | 2022-02-09 | 2022-02-16 | 2022-03-08 | 2022-03-03 | 2022-03-04 | 2022-03-08 | 2022-03-08 | 2022-03-08 | 2022-04-04 | 2022-03-21 | 14 | 18 | 27
507936 | Lloydminster MBR | Oakville | Instruments (E&H) | ENDRESS & HAUSER | 4503751961 | Electrical & Instrumentation | Inst-Instrumentation Others | CAD | 48558 | USD | 48558 | 0 | Estimate Without Market Reference(No Quote) | 2022-02-25 | 2022-02-16 | 2022-03-02 | 2022-02-25 | 2022-03-03 | 2022-03-04 | 2022-02-25 | 2022-03-07 | 2022-02-25 | 2022-03-07 | 2022-03-02 | 5 | 18 | 19
507936 | Lloydminster MBR | Oakville | Instruments (Hach) | HACH SALES & SERVICE CANADA LTD-REM | 4503751974 | Electrical & Instrumentation | Inst-Instrumentation Others | CAD | 18831 | USD | 18831 | 0 | Frame Agreements | 2022-03-09 | 2022-01-04 | 2022-02-16 | 2022-03-09 | 2022-03-04 | 2022-03-08 | 2022-03-09 | 2022-03-08 | 2022-03-09 | 2022-05-13 | 2022-04-10 | 33 | 18 | 63
507936 | Lloydminster MBR | Oakville | Pressure Transmitter (UE) | AC CONTROLS INC. | 4503727797 | Electrical & Instrumentation | Inst-Instrumentation Others | CAD | 8459 | USD | 8459 | 0 | Not included in Proposal / RFQ | 2022-02-09 | 2022-01-18 | 2022-01-24 | 2022-02-09 | 2022-01-25 | 2022-01-26 | 2022-02-09 | 2022-01-28 | 2022-02-09 | 2022-03-03 | 2022-02-20 | 11 | 18 | 10
507936 | Lloydminster MBR | Oakville | Beams, Hangers, Lifting Modules and Baffle Plates | 3D MECHANICAL | 4503633393 | Fabrication | Carbon Steel | CAD | 135345 | CAD | 127060 | 8285 | Supplier Competitions / Negotiation | 2021-06-25 | 2021-07-12 | 2021-08-06 | 2021-07-16 | 2021-08-10 | 2021-08-10 | 2021-07-23 | 2021-08-10 | 2021-07-23 | 2021-09-28 | 2021-08-25 | 34 | 12 | 29
507936 | Lloydminster MBR | Oakville | Fine bubble Diffuser Grid | ENVIRONMENTAL DYNAMICS | 4503602196 | Fabrication | Process Equipment | CAD | 132456 | USD | 117662 | 14794 | Supplier Competitions / Negotiation | 2022-01-28 | 2021-02-24 | 2021-03-02 | 2022-02-18 | 2021-05-26 | 2021-05-28 | 2022-02-25 | 2021-06-16 | 2022-02-25 | 2022-05-02 | 2022-03-30 | 33 | 12 | 112
507936 | Lloydminster MBR | Oakville | Chemical Pumps | PROMINENT FLUID CONTROLS LTD. | 4503705749 | Rotating Equipment | Dosing Pump | CAD | 36364 | CAD | 37557 | -1193 | Size/ Weight/ Quantity Underestimated | 2021-12-10 | 2021-10-21 | 2021-11-01 | 2021-12-31 | 2021-11-29 | 2021-12-01 | 2022-01-07 | 2021-12-17 | 2022-01-07 | 2022-04-04 | 2022-02-19 | 44 | 30 | 57
507936 | Lloydminster MBR | Oakville | Blower | AERZEN CANADA INC. | 4503667840 | Rotating Equipment | Blowers & Fans | CAD | 322800 | CAD | 342080 | -19280 | Specs / Requirements Misinterpreted in Proposal | 2021-12-03 | 2021-09-24 | 2021-10-08 | 2021-12-24 | 2021-10-08 | 2021-10-08 | 2021-12-31 | 2021-10-13 | 2021-12-31 | 2022-04-02 | 2022-02-15 | 46 | 30 | 19
507936 | Lloydminster MBR | Oakville | Fine Screens with Main Control Panel | Hydro-Dyne Engineering | 4503586763 | Fabrication | Alloy Steel | CAD | 377498 | USD | 438615 | -61117 | Size/ Weight/ Quantity Underestimated | 2021-03-27 | 2021-03-27 | 2021-05-14 | 2021-04-17 | 2021-05-14 | 2021-05-14 | 2021-04-24 | 2021-05-17 | 2021-04-24 | 2022-06-30 | 2021-11-26 | 216 | 12 | 51
507936 | Lloydminster MBR | Oakville | HDPE Tanks | ACO CONTAINER SYSTEMS LTD. | 4503677236 | Fabrication | Non-Metal Equipment | CAD | 75404 | CAD | 71464 | 3940 | Frame Agreements | 2021-11-26 | 2021-10-21 | 2021-10-22 | 2021-12-17 | 2021-10-26 | 2021-10-26 | 2021-12-24 | 2021-10-27 | 2021-12-24 | 2022-02-03 | 2022-01-13 | 21 | 12 | 6
507936 | Lloydminster MBR | Oakville | Mixers | SULZER PUMPS (CANADA) INC. | 4503677244 | Rotating Equipment | Mixers | CAD | 64153 | CAD | 57130 | 7023 | Design Optimizations | 2022-02-25 | 2021-10-21 | 2021-10-28 | 2022-03-18 | 2021-10-28 | 2021-10-28 | 2022-03-25 | 2021-10-28 | 2022-03-25 | 2022-04-29 | 2022-04-11 | 18 | 30 | 7
507936 | Lloydminster MBR | Oakville | Process Pumps (RAS Pumps) | SULZER PUMPS (CANADA) INC. | 4503731269 | Rotating Equipment | Centrifugal Pumps | CAD | 271722 | CAD | 274300 | -2578 | Supplier Competitions / Negotiation | 2021-09-03 | 2021-10-01 | 2021-10-07 | 2021-09-24 | 2021-10-09 | 2021-10-10 | 2021-10-01 | 2021-10-10 | 2021-10-01 | 2021-10-10 | 2021-10-05 | 5 | 30 | 9
507936 | Lloydminster MBR | Oakville | Process Pumps (Permeate, WAS Sludge, Primary Sludge, Grinder Pumps) | BOERGER, INC | 4503660648 | Rotating Equipment | Others | CAD | 272317 | USD | 245011 | 27306 | Supplier Competitions / Negotiation | 2021-11-18 | 2021-09-17 | 2021-09-20 | 2021-11-18 | 2021-09-29 | 2021-09-29 | 2021-11-18 | 2021-09-29 | 2021-11-18 | 2022-01-20 | 2021-12-19 | 32 | 30 | 12
507936 | Lloydminster MBR | Oakville | Air Compressors + Dryers | Compressor Science Inc. | 4503695311 | Rotating Equipment | Compressors | CAD | 26810 | USD | 25741 | 1069 | Frame Agreements | 2021-11-26 | 2021-10-29 | 2021-11-15 | 2021-12-17 | 2021-11-23 | 2021-11-26 | 2021-12-24 | 2021-11-26 | 2021-12-24 | 2022-01-21 | 2022-01-07 | 14 | 30 | 28
507953 | Molson Coors | Minnetonka | RO UV AQUIONICS | AQUIONICS, INC. | 4503576134 | Electrical & Instrumentation | Ele-Electrical Others | USD | 20003 | USD | 20003 | 0 | Market Impact | 2021-04-12 | 2021-04-05 | 2021-04-05 | 2021-04-16 | 2021-04-28 | 2021-04-28 | 2021-04-16 | 2021-04-28 | 2021-06-25 | 2021-06-23 | 2021-06-24 | -1 | 18 | 23
507953 | Molson Coors | Minnetonka | MAIN & CIP PANELS | BW Systems | 4503587387 | Electrical & Instrumentation | Ele-Control Panels | USD | 34750 | USD | 34750 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-05-13 | 2021-05-13 | 2021-05-19 | 2021-05-17 | 2021-05-15 | 2021-05-30 | 2021-05-17 | 2021-05-18 | 2021-06-17 | 2021-06-15 | 2021-06-16 | -1 | 18 | 5
507953 | Molson Coors | Minnetonka | RO INSTRUMENTS | ENDRESS & HAUSER | 4503595329 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 6650 | USD | 6650 | 0 | Proposed Supplier Incapable Of Executing | 2021-06-06 | 2021-05-19 | 2021-05-19 | 2021-06-06 | 2021-06-01 | 2021-06-06 | 2021-06-06 | 2021-06-02 | 2021-06-06 | 2021-06-24 | 2021-06-15 | 9 | 18 | 14
507953 | Molson Coors | Minnetonka | FILTER/FORSTA FILTERS | FORSTA FILTERS | 4503578709 | Flow Control | Filters And Strainers (Incl Housings) | USD | 11216 | USD | 11216 | 0 | Market Impact | 2021-04-12 | 2021-04-12 | 2021-04-21 | 2021-04-14 | 2021-05-03 | 2021-04-14 | 2021-04-14 | 2021-05-03 | 2021-07-15 | 2021-07-23 | 2021-07-19 | 4 | 12 | 21
507953 | Molson Coors | Minnetonka | GRUNDFOS CHEM SKIDS | GRUNDFOS PUMPS CORPORATION | 4503600287 | Rotating Equipment | Centrifugal Pumps | USD | 5000 | USD | 5000 | 0 | Not included in Proposal / RFQ | 2021-05-10 | 2021-05-10 | 2021-05-20 | 2021-05-17 | 2021-06-10 | 2021-06-12 | 2021-05-18 | 2021-06-11 | 2021-06-15 | 2021-07-16 | 2021-06-30 | 16 | 30 | 32
507953 | Molson Coors | Minnetonka | GRUNDFOS CHEM SKIDS | GRUNDFOS PUMPS CORPORATION | 4503600405 | Rotating Equipment | Centrifugal Pumps | USD | 54249 | USD | 47936 | 6313 | Estimate Without Market Reference(No Quote) | 2021-06-16 | 2021-05-18 | 2021-05-20 | 2021-06-16 | 2021-06-10 | 2021-06-16 | 2021-06-16 | 2021-06-11 | 2021-06-16 | 2021-07-16 | 2021-07-01 | 15 | 30 | 24
507953 | Molson Coors | Minnetonka | LS SHIP KIT | KOFLO CORPORATION | 4503578711 | Rotating Equipment | Mixers | USD | 9439 | USD | 5550 | 3889 | Frame Agreements | 2021-04-20 | 2021-04-29 | 2021-04-29 | 2021-04-21 | 2021-05-02 | 2021-05-18 | 2021-04-21 | 2021-05-02 | 2021-06-15 | 2021-06-16 | 2021-06-15 | 1 | 30 | 3
507966 | Grifols NC WWTP | Oakville | Centrifuge - D5L + Dosing Pump + Conveyor + spirac convy | Andritz Separation Technologies Inc. | 4503643704 | Rotating Equipment | Centrifuge | USD | 531550 | USD | 515300 | 16250 | Frame Agreements | 2021-07-28 | 2021-07-20 | 2021-08-31 | 2021-08-11 | 2021-09-04 | 2021-12-29 | 2021-08-25 | 2021-09-04 | 2022-06-10 | 2022-04-02 | 2022-05-06 | -34 | 30 | 46
507966 | Grifols NC WWTP | Oakville | Rotary Sludge Drum Thckener - PDR 600L | Andritz Separation Technologies Inc. | 4503643740 | Rotating Equipment | Centrifuge | USD | 169200 | USD | 120000 | 49200 | Design Optimizations | 2021-07-28 | 2021-07-20 | 2021-09-02 | 2021-08-11 | 2021-09-07 | 2021-12-29 | 2021-08-25 | 2021-09-07 | 2022-06-10 | 2022-04-20 | 2022-05-15 | -25 | 30 | 49
507966 | Grifols NC WWTP | Oakville | Media Replacement - MBBR (672 m3) | CHRISTIAN STOEHR GmbH & Co. | 4503690051 | Flow Control | Extruded Plastics | USD | 293873 | EUR | 279756 | 14117 | Design Optimizations | 2021-09-15 | 2021-10-04 | 2021-10-13 | 2021-10-06 | 2021-11-16 | 2022-04-28 | 2021-10-29 | 2021-11-21 | 2022-12-09 | 2022-01-30 | 2022-07-05 | -156 | 12 | 48
507966 | Grifols NC WWTP | Oakville | Blower (incl 2 year maint kit V Belt Oil change, Air Filter) | AERZEN CANADA INC. | 4503653289 | Rotating Equipment | Blowers & Fans | USD | 368331 | CAD | 301748 | 66583 | Supplier Competitions / Negotiation | 2021-07-13 | 2021-07-14 | 2021-09-08 | 2021-07-21 | 2021-09-07 | 2021-12-26 | 2021-10-22 | 2021-09-16 | 2022-06-10 | 2022-05-25 | 2022-06-02 | -8 | 30 | 64
507966 | Grifols NC WWTP | Oakville | RAS Pump - Goulds (3+1) | GOULDS PUMPS | 4503656540 | Rotating Equipment | Centrifugal Pumps | USD | 150980 | USD | 146952 | 4028 | Frame Agreements | 2021-05-10 | 2021-05-26 | 2021-09-02 | 2021-05-27 | 2021-09-12 | 2021-11-24 | 2021-09-09 | 2021-09-22 | 2022-06-10 | 2022-02-16 | 2022-04-14 | -57 | 30 | 119
507966 | Grifols NC WWTP | Oakville | Mixers (Incl Jib Crane)*6 | SULZER PUMPS (CANADA) INC. | 4503653280 | Rotating Equipment | Mixers | USD | 92711 | CAD | 52183 | 40528 | Frame Agreements | 2021-08-10 | 2021-08-12 | 2021-08-19 | 2021-08-24 | 2021-09-13 | 2021-12-08 | 2021-09-21 | 2021-09-17 | 2022-04-08 | 2022-01-07 | 2022-02-21 | -45 | 30 | 36
507966 | Grifols NC WWTP | Oakville | Chemical Dosing Skids + Inj Quill - Prominent | PROMINENT FLUID CONTROLS LTD. | 4503686728 | Rotating Equipment | Dosing Pump | USD | 42249 | CAD | 29988 | 12261 | Frame Agreements | 2021-09-15 | 2021-09-17 | 2021-09-17 | 2021-10-06 | 2021-11-09 | 2022-01-27 | 2021-10-29 | 2021-11-15 | 2022-06-10 | 2022-05-24 | 2022-06-01 | -8 | 30 | 59
507966 | Grifols NC WWTP | Oakville | Process Pump - Boerger (3+1) - Rotary Lobe | BOERGER LLC | 4503653361 | Rotating Equipment | PD Pumps | USD | 90296 | USD | 58959 | 31337 | Design Optimizations | 2021-06-11 | 2021-06-23 | 2021-08-04 | 2021-06-25 | 2021-09-13 | 2021-12-10 | 2021-10-08 | 2021-09-19 | 2022-06-10 | 2021-12-12 | 2022-03-12 | -90 | 30 | 88
507966 | Grifols NC WWTP | Oakville | Fabrication - Pump(s) Skid Frames, 500d BRAKCETS, COUPLING | Plasfab Inc | 4503693285 | Fabrication | Carbon Steel | USD | 102036 | CAD | 89500 | 12536 | Supplier Competitions / Negotiation | 2021-08-30 | 2021-10-22 | 2021-11-24 | 2021-09-14 | 2021-11-26 | 2021-12-18 | 2021-09-27 | 2021-11-29 | 2022-04-08 | 2022-02-25 | 2022-03-18 | -21 | 12 | 38
507966 | Grifols NC WWTP | Oakville | Fabrication - SS316 Spools | NV PIPING SYSTEMS INC. | 4503690175 | Fabrication | Stainless Steel | USD | 68119 | CAD | 53823 | 14296 | Supplier Competitions / Negotiation | 2021-09-06 | 2021-10-22 | 2021-11-22 | 2021-09-20 | 2021-11-21 | 2021-12-22 | 2021-10-04 | 2021-12-03 | 2022-04-08 | 2022-02-15 | 2022-03-13 | -26 | 12 | 42
507966 | Grifols NC WWTP | Oakville | Fabrication - HDPE Tanks ACO | ACO CONTAINER SYSTEMS LTD. | 4503692120 | Fabrication | Non-Metal Equipment | USD | 61071 | CAD | 37721 | 23350 | Supplier Competitions / Negotiation | 2021-07-27 | 2021-08-05 | 2021-11-02 | 2021-07-29 | 2021-11-22 | 2022-01-02 | 2021-10-19 | 2021-11-25 | 2022-06-10 | 2022-03-07 | 2022-04-23 | -47 | 12 | 112
507966 | Grifols NC WWTP | Oakville | Fabrication - MBBR Screen Replacement / Influent Screen | AQSEPTENCE GROUP INC | 4503715606 | Fabrication | Platform & Module | USD | 50750 | USD | 8878 | 41872 | Design Optimizations | 2021-09-15 | 2021-10-20 | 2022-01-06 | 2021-10-06 | 2022-01-07 | 2021-12-31 | 2021-10-29 | 2022-01-10 | 2022-04-08 | 2022-04-18 | 2022-04-13 | 5 | 12 | 82
507966 | Grifols NC WWTP | Oakville | Flow - Diffuser Grid | ENVIRONMENTAL DYNAMICS INTERNATIONAL | 4503656651 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 127872 | USD | 76630 | 51242 | Design Optimizations | 2021-08-09 | 2021-08-10 | 2021-08-20 | 2021-08-20 | 2021-09-13 | 2021-12-08 | 2021-09-17 | 2021-09-23 | 2022-04-08 | 2022-02-10 | 2022-03-10 | -28 | 12 | 44
507966 | Grifols NC WWTP | Oakville | Flow - Basket Strainer 2mm 316SS | JOHN BROOKS COMPANY LTD. | 4503686171 | Flow Control | Filters And Strainers (Incl Housings) | USD | 20000 | CAD | 16433 | 3567 | Frame Agreements | 2021-09-15 | 2021-10-12 | 2021-10-15 | 2021-09-29 | 2021-11-10 | 2021-12-26 | 2021-10-13 | 2021-11-15 | 2022-04-08 | 2022-01-17 | 2022-02-26 | -40 | 12 | 34
507966 | Grifols NC WWTP | Oakville | Valves - Dezurik Control & Manual + Topworx Positioners | FLOVAL EQUIPMENT LIMITED | 4503683790 | Flow Control | Metal Isolation Valves | USD | 151437 | CAD | 47401 | 104036 | Frame Agreements | 2021-08-10 | 2021-08-16 | 2021-11-08 | 2021-08-24 | 2021-11-08 | 2021-12-08 | 2021-09-07 | 2021-11-10 | 2022-04-08 | 2022-02-23 | 2022-03-17 | -22 | 12 | 86
507966 | Grifols NC WWTP | Oakville | Valves - Fisher Lakeside | LAKESIDE PROCESS CONTROLS LTD. | 4503683693 | Flow Control | Metal Control Valves | USD | 63616 | USD | 18613 | 45003 | Frame Agreements | 2021-08-11 | 2021-08-12 | 2021-11-09 | 2021-08-25 | 2021-11-10 | 2021-12-09 | 2021-09-08 | 2021-11-10 | 2022-04-08 | 2022-02-02 | 2022-03-06 | -32 | 12 | 90
507966 | Grifols NC WWTP | Oakville | Instruments - E&H | ENDRESS + HAUSER CANADA LTD. | 4503686225 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 40069 | USD | 27960 | 12109 | Supplier Competitions / Negotiation | 2021-09-15 | 2021-11-15 | 2021-11-15 | 2021-10-06 | 2021-11-15 | 2021-12-26 | 2021-10-27 | 2021-11-15 | 2022-04-08 | 2022-01-17 | 2022-02-26 | -40 | 18 | 0
507966 | Grifols NC WWTP | Oakville | Instruments - HACH pH & Turbid | Hach Sales & Service Canada Ltd. | 4503702030 | Electrical & Instrumentation | Inst-Multiparam Transmitters, Controllers | USD | 15004 | CAD | 8698 | 6306 | Supplier Competitions / Negotiation | 2021-09-15 | 2021-11-12 | 2021-12-14 | 2021-10-06 | 2021-12-14 | 2021-12-26 | 2021-10-27 | 2021-12-14 | 2022-04-08 | 2022-01-25 | 2022-03-02 | -36 | 18 | 32
507966 | Grifols NC WWTP | Oakville | Electrical - Control Panel (RIO, SCADA Intg) | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503683684 | Electrical & Instrumentation | Ele-Control Panels | USD | 139419 | CAD | 78036 | 61383 | Design Optimizations | 2021-08-23 | 2021-09-08 | 2021-11-10 | 2021-09-13 | 2021-10-26 | 2022-01-15 | 2021-10-04 | 2021-11-08 | 2022-06-10 | 2022-03-18 | 2022-04-29 | -42 | 18 | 61
507966 | Grifols NC WWTP | Oakville | Bray Valves | Bray Controls Canada Ltd. | 4503693467 | Flow Control | Metal Control Valves | USD | 100000 | USD | 27613 | 72387 | Design Optimizations | 2021-09-10 | 2021-08-11 | 2021-11-29 | 2021-10-15 | 2021-11-28 | 2021-12-13 | 2021-11-30 | 2021-11-28 | 2022-03-31 | 2022-04-17 | 2022-04-08 | 9 | 12 | 109
507966 | Grifols NC WWTP | Oakville | Prominent Chem Dosing Skid | PROMINENT FLUID CONTROLS LTD. | 4503697202 | Rotating Equipment | Dosing Pump | USD | 25000 | CAD | 28480 | -3480 | Not included in Proposal / RFQ | 2021-12-03 | 2021-10-11 | 2021-12-03 | 2021-12-10 | 2021-12-02 | 2022-02-02 | 2021-12-17 | 2021-12-04 | 2022-05-27 | 2022-05-14 | 2022-05-20 | -6 | 30 | 54
507966 | Grifols NC WWTP | Oakville | SWTS Tempest System | EQUIPSOLUTIONS | 4503693588 | Rotating Equipment | Dosing Pump | USD | 15000 | USD | 21496 | -6496 | Single Sourced | 2021-12-03 | 2021-09-07 | 2021-10-13 | 2021-12-10 | 2021-11-24 | 2022-01-16 | 2021-12-17 | 2021-11-28 | 2022-05-27 | 2022-05-19 | 2022-05-23 | -4 | 30 | 82
507969 | Lockwood, MT - SuperP | Richmond | Piping Plastic- Vacuum chamber,Collection system,sludge removal -Part -2 | JOB SHOP FABRICATORS | 4503649687 | Flow Control | Plastic Pipe and Fittings | USD | 25628 | USD | 26889 | -1261 | Estimate Without Market Reference(No Quote) | 2021-08-09 | 2021-08-14 | 2021-08-16 | 2021-08-25 | 2021-08-21 | 2021-10-06 | 2021-08-31 | 2021-09-11 | 2021-12-03 | 2021-11-20 | 2021-11-26 | -6 | 12 | 28
507969 | Lockwood, MT - SuperP | Richmond | Metal work- Settling plate & Vaccum Chamber | EASTERN METAL | 4503643667 | Fabrication | Carbon Steel | USD | 10263 | USD | 11235 | -972 | Specs / Requirements Misinterpreted in Proposal | 2021-08-09 | 2021-08-14 | 2021-08-19 | 2021-08-25 | 2021-08-26 | 2021-10-07 | 2021-08-31 | 2021-08-30 | 2021-12-03 | 2021-12-06 | 2021-12-04 | 2 | 12 | 16
507969 | Lockwood, MT - SuperP | Richmond | FRP work for Settling plate | KAL-LITE | 4503650258 | Flow Control | Other | USD | 12386 | USD | 5674 | 6712 | Design Optimizations | 2021-08-09 | 2021-09-08 | 2021-09-10 | 2021-08-25 | 2021-09-09 | 2021-10-06 | 2021-08-31 | 2021-09-12 | 2021-12-03 | 2021-11-07 | 2021-11-20 | -13 | 12 | 4
507969 | Lockwood, MT - SuperP | Richmond | Vacuum Pumps | Tencarva Machinery Co. | 4503637902 | Rotating Equipment | Others | USD | 7478 | USD | 6332 | 1146 | Frame Agreements | 2021-08-09 | 2021-08-06 | 2021-08-06 | 2021-08-25 | 2021-08-15 | 2021-10-04 | 2021-08-31 | 2021-08-18 | 2021-12-03 | 2021-11-03 | 2021-11-18 | -15 | 30 | 12
507969 | Lockwood, MT - SuperP | Richmond | Plug Valves | COMMONWEALTH CONTROLS CORPORATION | 4503637872 | Flow Control | Metal Isolation Valves | USD | 10071 | USD | 8484 | 1587 | Frame Agreements | 2021-08-09 | 2021-08-06 | 2021-08-06 | 2021-08-25 | 2021-08-10 | 2021-10-04 | 2021-08-31 | 2021-08-20 | 2021-12-03 | 2021-10-09 | 2021-11-05 | -27 | 12 | 14
507987 | Johnstown WWTP | Oakville | Process Pump | BOERGER LLC | 4503779890 | Rotating Equipment | Centrifugal Pumps | USD | 26578 | USD | 30420 | -3842 | Single Sourced | 2022-02-14 | 2022-05-23 | 2022-02-16 | 2022-02-28 | 2022-05-23 | 2022-05-23 | 2022-03-14 | 2022-04-25 | 2022-08-01 | 2022-08-29 | 2022-08-15 | 14 | 30 | -28
507987 | Johnstown WWTP | Oakville | Air Compressor | Compressor Science | 4503789256 | Rotating Equipment | Compressors | USD | 21642 | USD | 24786 | -3144 | Proposed Supplier Incapable Of Executing | 2022-02-14 | 2022-06-07 | 2022-05-11 | 2022-02-28 | 2022-06-07 | 2022-06-07 | 2022-03-14 | 2022-05-11 | 2022-08-01 | 2022-09-28 | 2022-08-30 | 29 | 30 | -27
507987 | Johnstown WWTP | Oakville | Fabrication- Fram | 3D MECHANICAL | 4503798895 | Fabrication | Stainless Steel | USD | 46314 | USD | 53158 | -6844 | Estimate Without Market Reference(No Quote) | 2022-01-10 | 2022-04-25 | 2022-05-24 | 2022-01-24 | 2022-04-25 | 2022-04-25 | 2022-02-07 | 2022-05-24 | 2022-08-01 | 2022-08-09 | 2022-08-05 | 4 | 12 | 29
507987 | Johnstown WWTP | Oakville | Fabrication- Spools | Cambridge Pro Fab Inc. | 4503799503 | Fabrication | Stainless Steel | USD | 40281 | CAD | 37042 | 3239 | Supplier Competitions / Negotiation | 2022-01-10 | 2022-04-27 | 2022-05-20 | 2022-01-24 | 2022-04-27 | 2022-04-27 | 2022-02-07 | 2022-05-28 | 2022-08-01 | 2022-08-13 | 2022-08-07 | 6 | 12 | 31
508039 | North Toronto MABR | Oakville | Compressor and dryer | COMPRESSOR SCIENCE | 4503783006 | Rotating Equipment | Compressors | CAD | 17100 | USD | 14458 | 2642 | Design Optimizations | 2022-03-16 | 2022-09-07 | 2022-04-29 | 2022-03-22 | 2022-09-07 | 2022-09-07 | 2022-03-30 | 2022-05-05 | 2023-03-01 | 2022-09-05 | 2022-12-02 | -88 | 30 | -125
508039 | North Toronto MABR | Oakville | Blowers | ATLAS COPCO COMPRESSORS | 4503783024 | Rotating Equipment | Blowers & Fans | CAD | 35000 | CAD | 38530 | -3530 | Market Impact | 2022-03-16 | 2022-09-07 | 2022-04-05 | 2022-03-22 | 2022-05-03 | 2022-09-07 | 2022-03-30 | 2022-05-03 | 2023-03-01 | 2022-05-03 | 2022-10-01 | -151 | 30 | -127
508039 | North Toronto MABR | Oakville | Metal Fab | BENNETT MECHANICAL INSTALLATIONS | 4503760743 | Fabrication | Stainless Steel | CAD | 76155 | CAD | 72855 | 3300 | Supplier Competitions / Negotiation | 2022-03-16 | 2022-12-06 | 2022-03-22 | 2022-03-22 | 2022-12-06 | 2022-12-06 | 2022-03-30 | 2022-03-21 | 2022-07-15 | 2023-08-29 | 2023-02-05 | 205 | 12 | -260
508039 | North Toronto MABR | Oakville | Valves -Solenoid | ASCO NUMATICS | 4503785138 | Electrical & Instrumentation | Inst-Instrumentation Accessories | CAD | 21075 | USD | 5738 | 15337 | Frame Agreements | 2022-03-16 | 2022-09-07 | 2022-05-03 | 2022-03-22 | 2022-05-03 | 2022-09-07 | 2022-03-30 | 2022-05-05 | 2023-03-01 | 2022-05-05 | 2022-10-02 | -150 | 18 | -125
508039 | North Toronto MABR | Oakville | Oxygen sensor | VERONICS INSTRUMENTS INC. | 4503787663 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | CAD | 6090 | CAD | 6515 | -425 | Market Impact | 2022-03-16 | 2022-09-07 | 2022-05-03 | 2022-03-22 | 2022-05-04 | 2022-09-07 | 2022-03-30 | 2022-05-05 | 2023-03-01 | 2022-05-05 | 2022-10-02 | -150 | 18 | -125
508039 | North Toronto MABR | Oakville | Stainless steel manifold insulation covers | ProInsul | 4503768628 | Fabrication | Stainless Steel | CAD | 15000 | CAD | 34304 | -19304 | Market Impact | 2022-03-01 | 2022-03-08 | 2022-03-31 | 2022-04-19 | 2022-08-19 | 2022-08-19 | 2022-04-23 | 2022-04-04 | 2023-02-06 | 2022-10-15 | 2022-12-11 | -57 | 12 | 27
508060 | 3M - Cordova, IL | Oakville | Pump-Booster | SULZER PUMPS (CANADA) INC. | 4503630412 | Rotating Equipment | Centrifugal Pumps | USD | 163693 | USD | 184158 | -20465 | Design Optimizations | 2021-07-02 | 2021-06-18 | 2021-07-08 | 2021-07-23 | 2021-08-02 | 2021-09-13 | 2021-07-30 | 2021-08-04 | 2021-12-10 | 2021-11-24 | 2021-12-02 | -8 | 30 | 47
508060 | 3M - Cordova, IL | Oakville | Chem Feed Skids + Injection Quill (Buy Out) | PROMINENT FLUID CONTROLS LTD. | 4503660421 | Rotating Equipment | Dosing Pump | USD | 146136 | CAD | 151542 | -5406 | Single Sourced | 2021-07-02 | 2021-06-18 | 2021-06-25 | 2021-07-30 | 2021-07-04 | 2021-09-18 | 2021-08-13 | 2021-09-12 | 2021-12-10 | 2021-12-19 | 2021-12-14 | 5 | 30 | 86
508060 | 3M - Cordova, IL | Oakville | Sulphuric Acid System | PROMINENT FLUID CONTROLS LTD. | 4503747070 | Rotating Equipment | Dosing Pump | USD | 11583 | CAD | 10569 | 1014 | Single Sourced | 2022-06-28 | 2022-12-28 | 2021-12-28 | 2022-06-28 | 2022-03-18 | 2022-06-28 | 2022-06-28 | 2022-03-01 | 2022-06-28 | 2022-04-04 | 2022-05-16 | -42 | 30 | -302
508060 | 3M - Cordova, IL | Oakville | Blowers (Guelph) | AERZEN CANADA INC. | 4503669331 | Rotating Equipment | Blowers & Fans | USD | 46563 | CAD | 25171 | 21392 | Frame Agreements | 2021-09-13 | 2021-09-13 | 2021-06-08 | 2021-10-11 | 2021-10-03 | 2021-09-27 | 2021-10-25 | 2021-10-14 | 2022-01-17 | 2022-01-05 | 2022-01-11 | -6 | 30 | 31
508060 | 3M - Cordova, IL | Oakville | Blower | FPZ INC | 4503680914 | Rotating Equipment | Blowers & Fans | USD | 6665 | USD | 10524 | -3859 | Estimate Without Market Reference(No Quote) | 2021-10-04 | 2021-09-13 | 2021-07-27 | 2021-10-04 | 2021-10-08 | 2021-10-04 | 2021-10-04 | 2021-11-04 | 2021-10-04 | 2021-12-12 | 2021-11-07 | 35 | 30 | 52
508060 | 3M - Cordova, IL | Oakville | Blowers (Minnetonka) | AERZEN CANADA INC | 4503731074 | Rotating Equipment | Blowers & Fans | USD | 14828 | CAD | 14828 | 0 | Market Impact | 2021-09-22 | 2021-06-08 | 2021-06-08 | 2021-09-22 | 2021-10-04 | 2021-09-22 | 2021-09-22 | 2021-10-15 | 2021-09-22 | 2022-01-07 | 2021-11-14 | 54 | 30 | 129
508060 | 3M - Cordova, IL | Oakville | Pump - Process (Centrifugal) | SULZER PUMPS (CANADA) INC. | 4503630397 | Rotating Equipment | Centrifugal Pumps | USD | 209392 | USD | 197962 | 11430 | Design Optimizations | 2021-07-02 | 2021-06-18 | 2021-07-06 | 2021-07-23 | 2021-07-31 | 2021-09-06 | 2021-07-30 | 2021-08-02 | 2021-11-26 | 2021-10-25 | 2021-11-10 | -16 | 30 | 45
508060 | 3M - Cordova, IL | Oakville | Floc Tank Mixers (Guelph) | DYNAMIX | 4503682614 | Rotating Equipment | Mixers | USD | 5469 | CAD | 5469 | 0 | Design Optimizations | 2021-11-17 | 2021-09-17 | 2021-09-17 | 2021-11-17 | 2021-10-12 | 2021-11-17 | 2021-11-17 | 2021-11-08 | 2021-11-17 | 2022-01-17 | 2021-12-17 | 31 | 30 | 52
508060 | 3M - Cordova, IL | Oakville | RO Housings - FRP | CODELINE | 4503611717 | Flow Control | RO membrane housings | USD | 302736 | USD | 298479 | 4257 | Single Sourced | 2021-06-25 | 2021-06-14 | 2021-06-08 | 2021-07-09 | 2021-06-23 | 2021-09-01 | 2021-07-09 | 2021-06-25 | 2021-11-26 | 2021-09-29 | 2021-10-28 | -29 | 12 | 11
508060 | 3M - Cordova, IL | Oakville | Butterfly & Check Valves (System A & C) | Bray Controls Canada Ltd. | 4503649576 | Flow Control | Metal Control Valves | USD | 149969 | USD | 211493 | -61524 | Size/ Weight/ Quantity Underestimated | 2021-07-27 | 2021-08-11 | 2021-08-26 | 2021-08-10 | 2021-09-01 | 2021-09-24 | 2021-08-17 | 2021-08-31 | 2021-11-23 | 2021-08-31 | 2021-10-12 | -42 | 12 | 20
508060 | 3M - Cordova, IL | Oakville | Cartridge Filter System A & C | JOHN BROOKS COMPANY LTD. | 4503657425 | Flow Control | Filters And Strainers (Incl Housings) | USD | 64104 | CAD | 121978 | -57874 | Size/ Weight/ Quantity Underestimated | 2021-08-24 | 2021-07-23 | 2021-07-29 | 2021-09-07 | 2021-09-02 | 2021-11-09 | 2021-09-14 | 2021-09-12 | 2021-11-23 | 2022-02-27 | 2022-01-10 | 48 | 12 | 51
508060 | 3M - Cordova, IL | Oakville | Cartridge Filter System B | JOHN BROOKS COMPANY LTD. | 4503657426 | Flow Control | Filters And Strainers (Incl Housings) | USD | 32053 | CAD | 35971 | -3918 | Size/ Weight/ Quantity Underestimated | 2021-10-04 | 2021-07-23 | 2021-07-29 | 2021-10-04 | 2021-09-06 | 2021-10-04 | 2021-10-04 | 2021-09-25 | 2021-10-04 | 2021-12-17 | 2021-11-10 | 37 | 12 | 64
508060 | 3M - Cordova, IL | Oakville | Strainer A - Automaic Backwash +Self cleaning - Boll | BOLL FILTER CORPORATION | 4503636809 | Flow Control | Filters And Strainers (Incl Housings) | USD | 34170 | USD | 34170 | 0 | Supplier Competitions / Negotiation | 2021-07-06 | 2021-07-23 | 2021-07-23 | 2021-08-03 | 2021-08-10 | 2021-09-21 | 2021-08-10 | 2021-08-12 | 2021-12-07 | 2021-08-12 | 2021-10-09 | -58 | 12 | 20
508060 | 3M - Cordova, IL | Oakville | Strainer C - Automaic Backwash +Self cleaning + Basket - Boll | BOLL FILTER CORPORATION | 4503636784 | Flow Control | Filters And Strainers (Incl Housings) | USD | 61830 | USD | 61830 | 0 | Not included in Proposal / RFQ | 2021-07-06 | 2021-07-23 | 2021-07-22 | 2021-07-20 | 2021-08-14 | 2021-09-14 | 2021-07-27 | 2021-08-16 | 2021-11-23 | 2021-11-01 | 2021-11-12 | -11 | 12 | 24
508060 | 3M - Cordova, IL | Oakville | Control Valve -RO (Globe) | LAKESIDE PROCESS CONTROLS LTD. | 4503655607 | Flow Control | Metal Control Valves | USD | 149662 | USD | 137540 | 12122 | Supplier Competitions / Negotiation | 2021-07-02 | 2021-08-04 | 2021-08-10 | 2021-07-16 | 2021-09-15 | 2021-09-19 | 2021-07-16 | 2021-09-22 | 2021-11-26 | 2021-12-08 | 2021-12-02 | 6 | 12 | 49
508060 | 3M - Cordova, IL | Oakville | Heaters - UF/CIP/RO | ASB HEATING ELEMENTS LIMITED | 4503680911 | Electrical & Instrumentation | Ele-Electrical Others | USD | 34772 | CAD | 17242 | 17530 | Supplier Competitions / Negotiation | 2021-08-13 | 2021-09-15 | 2021-09-23 | 2021-08-27 | 2021-10-18 | 2021-10-29 | 2021-09-03 | 2021-11-03 | 2021-12-03 | 2022-01-14 | 2021-12-24 | 21 | 18 | 49
508060 | 3M - Cordova, IL | Oakville | Pressure Relief Valve (Guelph) | Great Lakes Industrial Controls | 4503636063 | Flow Control | Metal Isolation Valves | USD | 32564 | CAD | 25795 | 6769 | Size/ Weight/ Quantity Underestimated | 2021-10-26 | 2021-07-27 | 2021-08-10 | 2021-10-26 | 2021-08-13 | 2021-10-26 | 2021-10-26 | 2021-11-16 | 2021-10-26 | 2022-01-25 | 2021-12-10 | 46 | 12 | 112
508060 | 3M - Cordova, IL | Oakville | Spools (System A) | NV PIPING SYSTEMS INC. | 4503661905 | Fabrication | Stainless Steel | USD | 393885 | CAD | 511999 | -118114 | Size/ Weight/ Quantity Underestimated | 2021-08-06 | 2021-08-28 | 2021-09-09 | 2021-09-03 | 2021-09-05 | 2021-10-22 | 2021-09-17 | 2021-09-18 | 2022-01-07 | 2022-01-01 | 2022-01-04 | -3 | 12 | 21
508060 | 3M - Cordova, IL | Oakville | Spools (System B) | PANDA PIPING LTD | 4503665524 | Fabrication | Stainless Steel | USD | 123304 | CAD | 90719 | 32585 | Size/ Weight/ Quantity Underestimated | 2021-08-06 | 2021-08-28 | 2021-09-09 | 2021-07-30 | 2021-09-01 | 2021-10-18 | 2021-09-17 | 2021-09-14 | 2022-01-07 | 2021-12-21 | 2021-12-29 | -8 | 12 | 17
508060 | 3M - Cordova, IL | Oakville | Frames (System A) | 3D MECHANICAL | 4503661120 | Fabrication | Carbon Steel | USD | 216220 | CAD | 352255 | -136035 | Size/ Weight/ Quantity Underestimated | 2021-08-06 | 2021-08-28 | 2021-09-08 | 2021-09-03 | 2021-09-05 | 2021-10-23 | 2021-09-17 | 2021-09-19 | 2022-01-07 | 2022-01-09 | 2022-01-08 | 1 | 12 | 22
508060 | 3M - Cordova, IL | Oakville | Frames (System B) | PLASFAB LIMITED | 4503664855 | Fabrication | Carbon Steel | USD | 108111 | CAD | 117501 | -9390 | Size/ Weight/ Quantity Underestimated | 2021-11-01 | 2021-08-28 | 2021-09-08 | 2021-11-01 | 2021-09-02 | 2021-11-01 | 2021-11-01 | 2021-09-15 | 2021-11-01 | 2022-01-05 | 2021-12-03 | 33 | 12 | 18
508060 | 3M - Cordova, IL | Oakville | TANK - FRP | PRECISIONEERING | 4503673673 | Fabrication | Non-Metal Equipment | USD | 47288 | CAD | 43554 | 3734 | Supplier Competitions / Negotiation | 2021-09-13 | 2021-09-13 | 2021-09-21 | 2021-10-11 | 2021-09-25 | 2021-12-02 | 2021-10-25 | 2021-10-21 | 2022-02-21 | 2022-01-27 | 2022-02-08 | -12 | 12 | 38
508060 | 3M - Cordova, IL | Oakville | TANK - HDPE (Site) | ACO CONTAINER SYSTEMS LTD. | 4503663809 | Fabrication | Non-Metal Equipment | USD | 64119 | CAD | 97446 | -33327 | Size/ Weight/ Quantity Underestimated | 2021-11-09 | 2021-09-14 | 2021-08-18 | 2021-11-23 | 2021-09-30 | 2021-11-20 | 2021-11-30 | 2021-10-01 | 2022-02-22 | 2021-12-17 | 2022-01-19 | -33 | 12 | 17
508060 | 3M - Cordova, IL | Oakville | Control Panels (Guelph)) | KELTOUR CONTROLS INC. | 4503665539 | Electrical & Instrumentation | Ele-Control Panels | USD | 274152 | CAD | 267795 | 6357 | Supplier Competitions / Negotiation | 2021-08-13 | 2021-08-25 | 2021-09-07 | 2021-09-03 | 2021-09-05 | 2021-10-26 | 2021-09-10 | 2021-10-03 | 2021-12-31 | 2022-01-09 | 2022-01-04 | 5 | 18 | 39
508060 | 3M - Cordova, IL | Oakville | Flow Transmitter (System A) | ENDRESS + HAUSER CANADA LTD. | 4503669352 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 86536 | USD | 16104 | 70432 | Frame Agreements | 2021-08-13 | 2021-10-04 | 2021-09-10 | 2021-08-27 | 2021-10-04 | 2021-10-11 | 2021-09-03 | 2021-10-14 | 2021-11-26 | 2021-12-09 | 2021-12-02 | 7 | 18 | 10
508060 | 3M - Cordova, IL | Oakville | Chlorine & pH Panel (System B) | ENDRESS + HAUSER CANADA LTD. | 4503684187 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 7066 | USD | 8366 | -1300 | Estimate Without Market Reference(No Quote) | 2021-08-24 | 2021-08-24 | 2021-10-04 | 2021-09-07 | 2021-10-20 | 2021-11-06 | 2021-09-14 | 2021-11-10 | 2021-11-23 | 2022-01-19 | 2021-12-21 | 29 | 18 | 78
508085 | COKE CHARLOTTE CA TO PA RRO CONVERSION | Minnetonka | DS_CRRO FEED UV | AQUIONICS, INC. | 4503582458 | Electrical & Instrumentation | Metal Isolation Valves | USD | 18600 | USD | 10266 | 8334 | Design Optimizations | 2021-05-03 | 2021-05-03 | 2021-02-12 | 2021-05-07 | 2021-05-10 | 2021-04-30 | 2021-07-16 | 2021-05-10 | 2021-07-16 | 2021-06-07 | 2021-06-26 | -19 | 18 | 7
508085 | COKE CHARLOTTE CA TO PA RRO CONVERSION | Minnetonka | LS_RI/O ENCLOSURE | PTS Products | 4503589625 | Electrical & Instrumentation | Carbon Steel | USD | 13000 | USD | 9585 | 3415 | Supplier Competitions / Negotiation | 2021-05-20 | 2021-05-21 | 2021-05-24 | 2021-05-21 | 2021-05-24 | 2021-06-19 | 2021-05-22 | 2021-05-24 | 2021-07-20 | 2021-06-21 | 2021-07-05 | -14 | 18 | 3
508093 | PEPSICO FRITOLAY | Minnetonka | DS_BLOWERS (BIO & MEMBRANE) | AERZEN CANADA INC. | 4503675570 | Rotating Equipment | Blowers & Fans | USD | 91872 | CAD | 101488 | -9616 | Estimate Without Market Reference(No Quote) | 2021-08-02 | 2021-06-19 | 2021-07-05 | 2021-08-09 | 2021-10-19 | 2021-09-23 | 2021-08-09 | 2021-10-26 | 2021-09-25 | 2021-12-28 | 2021-11-11 | 47 | 30 | 129
508093 | PEPSICO FRITOLAY | Minnetonka | DS_DIFFUSER | ENVIRONMENTAL DYNAMICS INTERNATIONAL | 4503672788 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 38000 | USD | 26940 | 11060 | Supplier Competitions / Negotiation | 2021-08-02 | 2021-10-07 | 2021-06-10 | 2021-08-09 | 2021-10-20 | 2021-10-07 | 2021-08-09 | 2021-10-21 | 2021-09-15 | 2022-02-03 | 2021-11-24 | 71 | 12 | 14
508093 | PEPSICO FRITOLAY | Minnetonka | DS_MEMBRANE TANK, LADDER, HANDRAIL, FRP | POSEIDON, INC | 4503659963 | Fabrication | Skid Assembly Outsourced | USD | 104821 | USD | 171600 | -66779 | Proposed Supplier Incapable Of Executing | 2021-06-10 | 2021-07-02 | 2021-09-28 | 2021-06-25 | 2021-09-28 | 2021-09-09 | 2021-08-02 | 2021-09-29 | 2021-12-10 | 2021-12-10 | 2021-12-10 | 0 | 12 | 89
508093 | PEPSICO FRITOLAY | Minnetonka | DS_ZMOD SKID | ARC SERVICES | 4503660356 | Fabrication | Skid Assembly Outsourced | USD | 83529 | USD | 50125 | 33404 | Proposed Supplier Incapable Of Executing | 2021-06-10 | 2021-07-10 | 2021-09-25 | 2021-06-25 | 2021-09-27 | 2021-09-14 | 2021-08-02 | 2021-09-29 | 2021-12-10 | 2021-12-20 | 2021-12-15 | 5 | 12 | 81
508093 | PEPSICO FRITOLAY | Minnetonka | DS_TANKS - BP/UFPERM/RO FEED | PRECISIONEERING | 4503672759 | Fabrication | Stainless Steel | USD | 18762 | CAD | 26082 | -7320 | Estimate Without Market Reference(No Quote) | 2021-07-01 | 2021-06-21 | 2021-07-07 | 2021-07-08 | 2021-10-20 | 2021-10-09 | 2021-07-08 | 2021-10-21 | 2021-09-08 | 2022-01-27 | 2021-11-17 | 71 | 12 | 122
508093 | PEPSICO FRITOLAY | Minnetonka | DS_RAS PUMP | GOULDS PUMPS | 4503670179 | Rotating Equipment | Centrifugal Pumps | USD | 27000 | USD | 18066 | 8934 | Frame Agreements | 2021-08-02 | 2021-06-19 | 2021-06-16 | 2021-08-09 | 2021-10-18 | 2021-09-17 | 2021-08-09 | 2021-10-18 | 2021-09-25 | 2021-12-10 | 2021-12-20 | -10 | 30 | 121
508093 | PEPSICO FRITOLAY | Minnetonka | DS_HYPO, CITRIC, H2SO4, CAUSTIC, ANTISCA | GRUNDFOS CANADA INC. | 4503672814 | Fabrication | Skid Assembly Outsourced | USD | 50548 | USD | 50548 | 0 | Estimate Without Market Reference(No Quote) | 2021-06-10 | 2021-06-30 | 2021-10-15 | 2021-06-25 | 2021-10-20 | 2021-09-18 | 2021-08-02 | 2021-10-21 | 2021-12-10 | 2021-12-28 | 2021-12-19 | 9 | 12 | 113
508093 | PEPSICO FRITOLAY | Minnetonka | DS_COMPRESSOR, FILTER, DRYER | ATLAS COPCO COMPRESSORS | 4503680189 | Rotating Equipment | Compressors | USD | 11794 | CAD | 7192 | 4602 | Estimate Without Market Reference(No Quote) | 2021-08-02 | 2021-06-16 | 2021-11-02 | 2021-08-09 | 2021-11-03 | 2021-09-29 | 2021-08-09 | 2021-11-03 | 2021-09-25 | 2022-01-12 | 2021-11-18 | 55 | 12 | 140
508093 | PEPSICO FRITOLAY | Minnetonka | DS_ACF FEED/BW PUMP | PFC EQUIPMENT | 4503670181 | Rotating Equipment | PD Pumps | USD | 5481 | USD | 10710 | -5229 | Not included in Proposal / RFQ | 2021-08-02 | 2021-06-22 | 2021-10-18 | 2021-08-09 | 2021-10-17 | 2021-09-15 | 2021-08-09 | 2021-10-17 | 2021-09-25 | 2021-12-09 | 2021-11-01 | 38 | 30 | 117
508093 | PEPSICO FRITOLAY | Minnetonka | DS_ACF-01&02 (INCLUDING LS VALVES) | Arrow Tanks | 4503662304 | Fabrication | Stainless Steel | USD | 59000 | USD | 59600 | -600 | Market Impact | 2021-07-01 | 2021-09-15 | 2021-07-09 | 2021-07-08 | 2021-10-04 | 2021-09-15 | 2021-07-08 | 2021-10-04 | 2021-09-08 | 2021-11-30 | 2021-10-19 | 42 | 12 | 19
508093 | PEPSICO FRITOLAY | Minnetonka | DS_PRE-RO UV | Trojan Technologies INC. | 4503672831 | Rotating Equipment | Others | USD | 119188 | USD | 41400 | 77788 | Estimate Without Market Reference(No Quote) | 2021-07-01 | 2021-09-19 | 2021-08-04 | 2021-07-08 | 2021-10-20 | 2021-09-19 | 2021-07-08 | 2021-10-21 | 2021-09-25 | 2021-12-08 | 2021-11-01 | 37 | 30 | 32
508093 | PEPSICO FRITOLAY | Minnetonka | DS_LP RO FEED PUMP | PFC EQUIPMENT | 4513670181 | Rotating Equipment | Centrifugal Pumps | USD | 5177 | USD | 10710 | -5533 | Proposed Supplier Incapable Of Executing | 2021-08-02 | 2021-10-06 | 2021-09-03 | 2021-08-09 | 2021-10-18 | 2021-10-06 | 2021-08-09 | 2021-10-18 | 2021-09-25 | 2021-12-10 | 2021-11-02 | 38 | 30 | 12
508093 | PEPSICO FRITOLAY | Minnetonka | DS_RO CIP SKID | ARC SERVICES | 4513660356 | Fabrication | Skid Assembly Outsourced | USD | 44957 | USD | 20185 | 24772 | Proposed Supplier Incapable Of Executing | 2021-06-10 | 2021-07-10 | 2021-09-25 | 2021-06-25 | 2021-09-27 | 2021-09-15 | 2021-08-02 | 2021-09-29 | 2021-12-10 | 2021-12-22 | 2021-12-16 | 6 | 12 | 81
508093 | PEPSICO FRITOLAY | Minnetonka | DS_RO MEMBRANE SYSTEM | ARC SERVICES | 4533660356 | Fabrication | Skid Assembly Outsourced | USD | 37169 | USD | 61342 | -24173 | Proposed Supplier Incapable Of Executing | 2021-06-10 | 2021-07-10 | 2021-09-25 | 2021-06-25 | 2021-09-27 | 2021-09-14 | 2021-08-02 | 2021-09-29 | 2021-12-10 | 2021-12-20 | 2021-12-15 | 5 | 12 | 81
508093 | PEPSICO FRITOLAY | Minnetonka | DS_CONTROL PANEL (MCP, RIOS) | BW Systems | 4503678276 | Electrical & Instrumentation | Ele-Control Panels | USD | 112533 | USD | 66325 | 46208 | Supplier Competitions / Negotiation | 2021-08-02 | 2021-10-16 | 2021-11-03 | 2021-08-09 | 2021-11-01 | 2021-10-12 | 2021-08-09 | 2021-11-01 | 2021-09-15 | 2021-12-23 | 2021-11-03 | 50 | 18 | 16
508093 | PEPSICO FRITOLAY | Minnetonka | DS_AC TOWER) | ARC SERVICES | 4523660356 | Fabrication | Skid Assembly Outsourced | USD | 59065 | USD | 76078 | -17013 | Proposed Supplier Incapable Of Executing | 2021-07-10 | 2021-07-10 | 2021-09-09 | 2021-07-30 | 2021-09-26 | 2021-09-29 | 2021-08-13 | 2021-09-28 | 2021-12-10 | 2021-12-19 | 2021-12-14 | 5 | 12 | 80
508093 | PEPSICO FRITOLAY | Minnetonka | DS_RO MEMBRANE SYSTEM | Duncan Co. | 4503666921 | Flow Control | Filters And Strainers (Incl Housings) | USD | 20236 | USD | 20236 | 0 | Size/ Weight/ Quantity Underestimated | 2021-06-17 | 2021-06-17 | 2021-10-12 | 2021-06-21 | 2021-10-10 | 2021-09-13 | 2021-06-22 | 2021-10-12 | 2021-12-10 | 2021-12-07 | 2021-12-08 | -1 | 12 | 117
508093 | PEPSICO FRITOLAY | Minnetonka | DS_ZMOD SKID | BOERGER LLC | 4503665173 | Rotating Equipment | Dosing Pump | USD | 17690 | USD | 24718 | -7028 | Proposed Supplier Incapable Of Executing | 2021-06-22 | 2021-06-22 | 2021-06-22 | 2021-06-29 | 2021-10-07 | 2021-09-12 | 2021-06-30 | 2021-10-08 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 0 | 30 | 108
508093 | PEPSICO FRITOLAY | Minnetonka | DS_MEMBRANE TANK, LADDER, HANDRAIL, FRP | PRECISIONENG | 4503672754 | Fabrication | Skid Assembly Outsourced | USD | 23098 | CAD | 23098 | 0 | Frame Agreements | 2021-11-06 | 2021-11-06 | 2021-09-28 | 2021-11-06 | 2021-10-18 | 2021-11-06 | 2021-11-06 | 2021-10-21 | 2021-11-06 | 2021-12-16 | 2021-11-26 | 20 | 12 | -16
508093 | PEPSICO FRITOLAY | Minnetonka | DS_MEMBRANE TANK, LADDER, HANDRAIL, FRP | R&R Metalworks | 4503672828 | Fabrication | Skid Assembly Outsourced | USD | 19960 | USD | 16960 | 3000 | Estimate Without Market Reference(No Quote) | 2021-11-17 | 2021-11-17 | 2021-10-21 | 2021-11-17 | 2021-10-20 | 2021-11-17 | 2021-11-17 | 2021-10-20 | 2021-11-17 | 2021-12-15 | 2021-12-01 | 14 | 12 | -28
508113 | Alabama Power | Oakville | Pressure Vessel: Fabrication | LESENA STEEL DIVISION | 4503633917 | Fabrication | Carbon Steel | USD | 187029 | CAD | 181708 | 5321 | Frame Agreements | 2021-06-06 | 2021-06-02 | 2021-06-18 | 2021-06-20 | 2021-06-15 | 2021-08-05 | 2021-07-04 | 2021-06-18 | 2021-08-30 | 2021-10-08 | 2021-09-23 | 15 | 30 | 16
508113 | Alabama Power | Oakville | Pressure Vessel: External Painting & Internal Rubber Lining | BRANT CORROSION CONTROL, | 4503611028 | Fabrication | Carbon Steel | USD | 85756 | CAD | 71816 | 13940 | Supplier Competitions / Negotiation | 2021-06-06 | 2021-06-02 | 2021-06-18 | 2021-06-20 | 2021-06-16 | 2021-08-13 | 2021-08-01 | 2021-06-22 | 2021-09-26 | 2021-10-19 | 2021-10-25 | -6 | 30 | 20
508113 | Alabama Power | Oakville | Pressure Vessel: Internals - Piping Fabrication | NV PIPING SYSTEMS INC. | 4503633929 | Fabrication | Stainless Steel | USD | 90223 | CAD | 93822 | -3599 | Market Impact | 2021-06-18 | 2021-06-16 | 2021-06-28 | 2021-07-02 | 2021-07-17 | 2021-08-10 | 2021-07-16 | 2021-07-22 | 2021-09-10 | 2021-09-02 | 2021-10-05 | -33 | 24 | 36
508145 | NIAGARA HAZLETON | Minnetonka | AC Towers 96x168 | Arrow Tanks | 4503606822 | Fabrication | Stainless Steel | USD | 64000 | USD | 64000 | 0 | Supplier Competitions / Negotiation | 2021-05-11 | 2021-05-05 | 2021-06-29 | 2021-05-12 | 2021-06-29 | 2021-08-03 | 2021-05-12 | 2021-06-29 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 0 | 12 | 55
508145 | NIAGARA HAZLETON | Minnetonka | AC Towers 108x168 | Arrow Tanks | 4513606822 | Fabrication | Stainless Steel | USD | 69850 | USD | 69850 | 0 | Design Optimizations | 2021-05-11 | 2021-05-05 | 2021-06-29 | 2021-05-12 | 2021-06-29 | 2021-08-03 | 2021-05-12 | 2021-06-29 | 2021-11-02 | 2021-11-02 | 2021-11-02 | 0 | 12 | 55
508145 | NIAGARA HAZLETON | Minnetonka | AC Towers 108x168 | Arrow Tanks | 4523606822 | Fabrication | Stainless Steel | USD | 69850 | USD | 69850 | 0 | Supplier Competitions / Negotiation | 2021-05-11 | 2021-05-05 | 2021-06-29 | 2021-05-12 | 2021-06-28 | 2021-08-07 | 2021-05-12 | 2021-06-28 | 2021-11-09 | 2021-11-09 | 2021-11-09 | 0 | 12 | 54
508145 | NIAGARA HAZLETON | Minnetonka | AC Towers 108x168 | Arrow Tanks | 4533606822 | Fabrication | Stainless Steel | USD | 69850 | USD | 69850 | 0 | Estimate Without Market Reference(No Quote) | 2021-05-11 | 2021-05-05 | 2021-06-29 | 2021-05-12 | 2021-06-29 | 2021-08-10 | 2021-05-12 | 2021-06-29 | 2021-11-15 | 2021-11-15 | 2021-11-15 | 0 | 12 | 55
508145 | NIAGARA HAZLETON | Minnetonka | AC Towers 108x168 | Arrow Tanks | 4543606822 | Fabrication | Stainless Steel | USD | 69850 | USD | 69850 | 0 | Single Sourced | 2021-05-11 | 2021-05-05 | 2021-05-11 | 2021-05-12 | 2021-06-29 | 2021-08-12 | 2021-05-12 | 2021-06-29 | 2021-11-19 | 2021-11-19 | 2021-11-19 | 0 | 12 | 55
508145 | NIAGARA HAZLETON | Minnetonka | AC Towers ELEC PANELS | BW Systems | 4503617228 | Electrical & Instrumentation | Ele-Control Panels | USD | 11450 | USD | 11450 | 0 | Frame Agreements | 2021-05-11 | 2021-06-21 | 2021-06-21 | 2021-05-12 | 2021-07-12 | 2021-08-13 | 2021-05-12 | 2021-07-12 | 2021-11-16 | 2021-11-05 | 2021-11-10 | -5 | 18 | 21
508145 | NIAGARA HAZLETON | Minnetonka | RO HOUSINGS - PROTEC | PROTEC ARISAWA AMERICA, INC. | 4503603480 | Flow Control | RO membrane housings | USD | 32256 | USD | 32256 | 0 | Design Optimizations | 2021-05-11 | 2021-05-05 | 2021-05-11 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-17 | 2021-06-17 | 2021-08-02 | 2021-08-02 | 2021-08-02 | 0 | 12 | 43
508145 | NIAGARA HAZLETON | Minnetonka | RO ELEC Panels | BW Systems | 4503629393 | Electrical & Instrumentation | Ele-Control Panels | USD | 87445 | USD | 77555 | 9890 | Supplier Competitions / Negotiation | 2021-08-12 | 2021-07-12 | 2021-08-03 | 2021-08-19 | 2021-07-31 | 2021-09-06 | 2021-08-20 | 2021-08-01 | 2021-11-02 | 2021-09-26 | 2021-10-14 | -18 | 18 | 20
508145 | NIAGARA HAZLETON | Minnetonka | CIP TANK | Preferred Stainless Holdings | 4503610223 | Fabrication | Stainless Steel | USD | 17628 | USD | 27975 | -10347 | Estimate Without Market Reference(No Quote) | 2021-06-29 | 2021-05-21 | 2021-05-24 | 2021-07-01 | 2021-06-29 | 2021-08-01 | 2021-07-01 | 2021-06-29 | 2021-10-12 | 2021-10-12 | 2021-10-12 | 0 | 12 | 39
508145 | NIAGARA HAZLETON | Minnetonka | RO HOUSINGS - PROTEC | PROTEC ARISAWA AMERICA, INC. | 4503603483 | Flow Control | RO membrane housings | USD | 9116 | USD | 9116 | 0 | Frame Agreements | 2021-07-21 | 2021-05-11 | 2021-05-11 | 2021-07-21 | 2021-06-16 | 2021-07-21 | 2021-07-21 | 2021-06-16 | 2021-07-21 | 2021-09-30 | 2021-08-25 | 36 | 12 | 36
508145 | NIAGARA HAZLETON | Minnetonka | RRO Skid_ASSY PUMPS | PFC EQUIPMENT | 4503623619 | Rotating Equipment | Centrifugal Pumps | USD | 7075 | USD | 7075 | 0 | Estimate Without Market Reference(No Quote) | 2021-07-05 | 2021-07-05 | 2021-07-06 | 2021-07-14 | 2021-07-13 | 2021-08-25 | 2021-07-23 | 2021-07-24 | 2021-10-15 | 2021-10-15 | 2021-10-15 | 0 | 30 | 19
508145 | NIAGARA HAZLETON | Minnetonka | RO FRAMES | 3D MECHANICAL | 4503628005 | Fabrication | Stainless Steel | USD | 44333 | USD | 72414 | -28081 | Proposed Supplier Incapable Of Executing | 2021-07-14 | 2021-07-14 | 2021-07-30 | 2021-07-16 | 2021-07-28 | 2021-08-17 | 2021-07-20 | 2021-07-31 | 2021-09-21 | 2021-09-04 | 2021-09-12 | -8 | 12 | 17
508145 | NIAGARA HAZLETON | Minnetonka | RO SPOOLS | R&R Metalworks | 4503628892 | Fabrication | Stainless Steel | USD | 24169 | USD | 33870 | -9701 | Size/ Weight/ Quantity Underestimated | 2021-07-22 | 2021-07-22 | 2021-07-21 | 2021-07-27 | 2021-08-02 | 2021-08-17 | 2021-07-27 | 2021-08-02 | 2021-08-09 | 2021-09-13 | 2021-08-26 | 18 | 12 | 11
508145 | NIAGARA HAZLETON | Minnetonka | RRO O ELEC Panels | BW Systems | 4523629393 | Electrical & Instrumentation | Ele-Control Panels | USD | 16940 | USD | 20920 | -3980 | Single Sourced | 2021-08-30 | 2021-08-30 | 2021-08-02 | 2021-08-30 | 2021-08-03 | 2021-08-30 | 2021-08-30 | 2021-08-03 | 2021-08-30 | 2021-09-28 | 2021-09-13 | 15 | 18 | -27
508146 | NIAGARA JACKSONVILLE | Minnetonka | ACF TANKS 96x168 | Arrow Tanks | 4503596658 | Fabrication | Stainless Steel | USD | 63989 | USD | 64000 | -11 | Proposed Supplier Incapable Of Executing | 2021-05-10 | 2021-05-11 | 2021-05-11 | 2021-05-10 | 2021-05-11 | 2021-06-25 | 2021-06-03 | 2021-06-07 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 0 | 12 | 27
508146 | NIAGARA JACKSONVILLE | Minnetonka | ACF TANKS 108x168 | Arrow Tanks | 4513596658 | Fabrication | Stainless Steel | USD | 140000 | USD | 141300 | -1300 | Size/ Weight/ Quantity Underestimated | 2021-05-10 | 2021-05-11 | 2021-06-07 | 2021-05-10 | 2021-05-10 | 2021-07-01 | 2021-06-03 | 2021-06-06 | 2021-08-23 | 2021-08-22 | 2021-08-22 | 0 | 12 | 26
508146 | NIAGARA JACKSONVILLE | Minnetonka | ACF_SPOOLS | R&R Metalworks | 4503617562 | Fabrication | Stainless Steel | USD | 27404 | USD | 30000 | -2596 | Proposed Supplier Incapable Of Executing | 2021-07-02 | 2021-06-30 | 2021-07-12 | 2021-07-06 | 2021-07-06 | 2021-08-01 | 2021-07-09 | 2021-07-13 | 2021-08-10 | 2021-09-02 | 2021-08-21 | 12 | 12 | 13
508146 | NIAGARA JACKSONVILLE | Minnetonka | RO HOUSINGS | PROTEC ARISAWA AMERICA, INC. | 4503599723 | Flow Control | Filters And Strainers (Incl Housings) | USD | 11970 | USD | 13824 | -1854 | Specs / Requirements Misinterpreted in Proposal | 2021-05-10 | 2021-06-10 | 2021-06-10 | 2021-06-03 | 2021-06-10 | 2021-06-21 | 2021-06-04 | 2021-06-10 | 2021-07-29 | 2021-08-02 | 2021-07-31 | 2 | 12 | 0
508146 | NIAGARA JACKSONVILLE | Minnetonka | CIP TANK | Preferred Stainless Holdings | 4503596677 | Fabrication | Stainless Steel | USD | 21992 | USD | 27975 | -5983 | Estimate Without Market Reference(No Quote) | 2021-05-25 | 2021-05-24 | 2021-05-24 | 2021-05-26 | 2021-05-26 | 2021-07-13 | 2021-06-03 | 2021-06-07 | 2021-09-01 | 2021-09-01 | 2021-09-01 | 0 | 12 | 14
508146 | NIAGARA JACKSONVILLE | Minnetonka | CIP PUMP | ALFA LAVAL | 4503599698 | Rotating Equipment | Dosing Pump | USD | 7593 | USD | 7593 | 0 | Size/ Weight/ Quantity Underestimated | 2021-06-14 | 2021-05-20 | 2021-05-20 | 2021-06-15 | 2021-06-09 | 2021-06-30 | 2021-06-16 | 2021-06-09 | 2021-07-29 | 2021-08-11 | 2021-08-04 | 7 | 12 | 20
508146 | NIAGARA JACKSONVILLE | Minnetonka | RO MAIN PANEL | PTS Products | 4513606157 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 47952 | USD | 21979 | 25973 | Supplier Competitions / Negotiation | 2021-07-13 | 2021-07-13 | 2021-06-22 | 2021-07-13 | 2021-06-22 | 2021-07-13 | 2021-07-13 | 2021-06-22 | 2021-07-13 | 2021-08-03 | 2021-07-23 | 11 | 12 | -21
508146 | NIAGARA JACKSONVILLE | Minnetonka | LS_VALVES | BRAY SALES MINNEAPOLIS | 4503609117 | Flow Control | Metal Safety(relief) Valves | USD | 6942 | USD | 5884 | 1058 | Design Optimizations | 2021-06-22 | 2021-06-21 | 2021-06-21 | 2021-06-23 | 2021-06-25 | 2021-07-10 | 2021-06-24 | 2021-06-25 | 2021-07-29 | 2021-07-17 | 2021-07-23 | -6 | 12 | 4
508150 | Marathon Martinez | Oakville | Cylindrical Screens | AQSEPTENCE GROUP (102) PRIVATE LI | 4503662228 | Fabrication | Stainless Steel | USD | 64908 | USD | 54008 | 10900 | Supplier Competitions / Negotiation | 2021-11-26 | 2021-07-19 | 2021-09-01 | 2021-12-17 | 2021-09-28 | 2022-01-22 | 2022-01-14 | 2021-09-27 | 2022-07-29 | 2022-01-31 | 2022-04-30 | -89 | 18 | 70
508150 | Marathon Martinez | Oakville | Aeration Grid & Air Knife | ENVIRONMENTAL DYNAMICS | 4503620758 | Fabrication | Stainless Steel | USD | 451901 | USD | 469576 | -17675 | Size/ Weight/ Quantity Underestimated | 2021-06-11 | 2021-05-19 | 2021-07-15 | 2021-06-25 | 2021-07-19 | 2021-12-23 | 2021-06-30 | 2021-07-19 | 2022-07-29 | 2022-01-07 | 2022-04-18 | -101 | 18 | 61
508150 | Marathon Martinez | Oakville | Outlet Manifold Screen Pipe & Supports | BURKES MECHANICAL | 4503675504 | Fabrication | Carbon Steel | USD | 41456 | USD | 100558 | -59102 | Not included in Proposal / RFQ | 2021-11-26 | 2021-09-15 | 2021-10-24 | 2021-12-17 | 2021-10-16 | 2022-02-20 | 2022-01-14 | 2021-10-23 | 2022-07-29 | 2022-05-03 | 2022-06-15 | -43 | 12 | 38
508194 | Cleveland WTP - SuperP | Richmond | Plug Valves | AUTOMATIC CONTROLS OF VIRGINIA, INC | 4503679924 | Flow Control | Metal Isolation Valves | USD | 23767 | USD | 22648 | 1119 | Supplier Competitions / Negotiation | 2021-08-30 | 2021-08-17 | 2021-08-18 | 2021-10-04 | 2021-10-21 | 2021-11-26 | 2021-10-11 | 2021-11-02 | 2022-03-07 | 2022-02-22 | 2022-02-28 | -6 | 12 | 77
508194 | Cleveland WTP - SuperP | Richmond | Extrusions- TO PROJECT SITE | EASTERN METAL | 4503645921 | Fabrication | Alloy Steel | USD | 9000 | USD | 7442 | 1558 | Supplier Competitions / Negotiation | 2021-08-30 | 2021-08-24 | 2021-09-02 | 2021-10-04 | 2021-09-01 | 2021-11-29 | 2021-09-02 | 2021-09-02 | 2022-03-07 | 2022-02-24 | 2022-03-01 | -5 | 12 | 9
508194 | Cleveland WTP - SuperP | Richmond | Settling Plates | KAL-LITE | 4503668169 | Fabrication | Alloy Steel | USD | 10000 | USD | 5434 | 4566 | Design Optimizations | 2021-12-14 | 2021-09-08 | 2021-09-09 | 2021-12-14 | 2021-10-12 | 2021-12-14 | 2021-12-14 | 2021-10-14 | 2021-12-14 | 2022-03-22 | 2022-02-01 | 49 | 12 | 36
508194 | Cleveland WTP - SuperP | Richmond | Control panel | KELTOUR CONTROLS INC. | 4503699511 | Electrical & Instrumentation | Ele-Control Panels | USD | 15003 | CAD | 12500 | 2503 | Supplier Competitions / Negotiation | 2021-08-30 | 2021-09-10 | 2021-10-29 | 2021-10-04 | 2021-12-06 | 2021-12-04 | 2021-10-11 | 2021-12-07 | 2022-03-07 | 2022-03-11 | 2022-03-09 | 2 | 18 | 88
508194 | Cleveland WTP - SuperP | Richmond | Embedment Items (SuperPulsator) | JOB SHOP FABRICATORS | 4503667492 | Fabrication | Alloy Steel | USD | 63926 | USD | 56978 | 6948 | Design Optimizations | 2021-08-30 | 2021-09-07 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-12-02 | 2021-10-11 | 2021-10-12 | 2022-03-07 | 2022-02-26 | 2022-03-02 | -4 | 12 | 35
508194 | Cleveland WTP - SuperP | Richmond | Tube Settlers- Setteling tubes | BRENTWOOD INDUSTRIES | 4503679089 | Fabrication | Process Equipment | USD | 12985 | USD | 11253 | 1732 | Frame Agreements | 2021-08-30 | 2021-09-08 | 2021-09-14 | 2021-10-04 | 2021-10-26 | 2021-12-02 | 2021-10-11 | 2021-11-01 | 2022-03-07 | 2021-12-24 | 2022-01-29 | -36 | 12 | 54
508194 | Cleveland WTP - SuperP | Richmond | Air Compressor | Compressor Science Inc. | 4503686182 | Rotating Equipment | Compressors | USD | 9370 | USD | 12408 | -3038 | Market Impact | 2021-08-30 | 2021-08-16 | 2021-08-18 | 2021-10-04 | 2021-11-10 | 2021-11-25 | 2021-10-11 | 2021-11-14 | 2022-03-07 | 2022-02-07 | 2022-02-21 | -14 | 30 | 90
508194 | Cleveland WTP - SuperP | Richmond | Stop log gates | GOLDEN HARVEST INC. | 4503672404 | Flow Control | Other | USD | 7713 | USD | 10235 | -2522 | Estimate Without Market Reference(No Quote) | 2021-08-30 | 2021-09-13 | 2021-09-20 | 2021-10-04 | 2021-10-20 | 2021-12-02 | 2021-10-11 | 2021-10-19 | 2022-03-07 | 2022-02-10 | 2022-02-22 | -12 | 12 | 36
508199 | City of Shawnee WTP | Richmond | Removable Baffle Supports | SHARP IRON GROUP | 4503685392 | Fabrication | Stainless Steel | USD | 38974 | USD | 18672 | 20302 | Supplier Competitions / Negotiation | 2021-11-16 | 2021-09-02 | 2021-10-14 | 2021-11-16 | 2021-11-12 | 2021-11-16 | 2021-11-16 | 2021-11-14 | 2021-11-16 | 2022-01-30 | 2021-12-23 | 38 | 12 | 73
508199 | City of Shawnee WTP | Richmond | Crossmembers Settling Plate System (Aluminum) | EASTERN METAL | 4503645990 | Fabrication | Non-Metal Equipment | USD | 62362 | USD | 108182 | -45820 | Size/ Weight/ Quantity Underestimated | 2021-10-18 | 2021-08-20 | 2021-08-28 | 2021-11-15 | 2021-09-02 | 2021-11-27 | 2021-11-29 | 2021-09-06 | 2022-03-07 | 2022-02-27 | 2022-03-03 | -4 | 12 | 17
508199 | City of Shawnee WTP | Richmond | FRP Settling Plate System | KAL-LITE | 4503683153 | Fabrication | Non-Metal Equipment | USD | 41732 | USD | 40247 | 1485 | Frame Agreements | 2021-11-15 | 2021-08-20 | 2021-08-23 | 2021-12-13 | 2021-11-09 | 2021-11-27 | 2021-12-27 | 2021-11-09 | 2022-03-07 | 2022-01-30 | 2022-02-17 | -18 | 12 | 81
508199 | City of Shawnee WTP | Richmond | Settling Tubes | BRENTWOOD INDUSTRIES | 4503686234 | Fabrication | Non-Metal Equipment | USD | 102326 | USD | 99025 | 3301 | Supplier Competitions / Negotiation | 2021-10-04 | 2021-08-20 | 2021-08-23 | 2021-11-01 | 2021-11-15 | 2021-11-27 | 2021-11-15 | 2021-11-15 | 2022-03-07 | 2022-01-31 | 2022-02-17 | -17 | 12 | 87
508199 | City of Shawnee WTP | Richmond | Control Panels | ICSE | 4503683053 | Electrical & Instrumentation | Ele-Control Panels | USD | 20400 | USD | 26880 | -6480 | Single Sourced | 2021-11-01 | 2021-08-10 | 2021-08-18 | 2021-11-29 | 2021-11-08 | 2021-11-22 | 2021-12-13 | 2021-11-08 | 2022-03-07 | 2022-01-19 | 2022-02-11 | -23 | 18 | 90
508199 | City of Shawnee WTP | Richmond | Vaccum Pumps | Tencarva Machinery Co. | 4503681710 | Rotating Equipment | Others | USD | 44493 | USD | 10591 | 33902 | Frame Agreements | 2021-08-09 | 2021-07-07 | 2021-07-27 | 2021-09-06 | 2021-11-03 | 2021-11-05 | 2021-09-20 | 2021-11-05 | 2022-03-07 | 2022-01-17 | 2022-02-10 | -24 | 30 | 121
508199 | City of Shawnee WTP | Richmond | Air Compressor | NCA Ltd. | 4503705917 | Rotating Equipment | Compressors | USD | 50447 | USD | 24448 | 25999 | Supplier Competitions / Negotiation | 2021-11-01 | 2021-07-07 | 2021-12-15 | 2021-11-29 | 2021-11-02 | 2021-11-05 | 2021-12-13 | 2021-12-19 | 2022-03-07 | 2022-03-06 | 2022-03-06 | 0 | 30 | 165
508199 | City of Shawnee WTP | Richmond | Manual Valves | AUTOMATIC CONTROLS OF VIRGINIA, INC | 4503694673 | Flow Control | Metal Isolation Valves | USD | 43475 | USD | 10000 | 33475 | Frame Agreements | 2021-07-20 | 2021-07-07 | 2021-07-15 | 2021-09-18 | 2021-11-30 | 2021-11-05 | 2021-11-01 | 2021-11-29 | 2022-03-07 | 2022-02-21 | 2022-02-28 | -7 | 12 | 145
508199 | City of Shawnee WTP | Richmond | Automated and Manual Valmatic Plug Valves | BRAY CONTROLS CANADA LTD. | 4503680853 | Flow Control | Metal Isolation Valves | USD | 68136 | USD | 101308 | -33172 | Size/ Weight/ Quantity Underestimated | 2021-12-25 | 2021-10-26 | 2021-11-04 | 2021-12-25 | 2021-11-04 | 2021-12-25 | 2021-12-25 | 2021-11-04 | 2021-12-25 | 2022-02-24 | 2022-01-24 | 31 | 12 | 9
508199 | City of Shawnee WTP | Richmond | Stop Gates | GOLDEN HARVEST INC. | 4503669305 | Fabrication | Carbon Steel | USD | 24480 | USD | 33500 | -9020 | Proposed Supplier Incapable Of Executing | 2021-10-04 | 2021-07-16 | 2021-07-27 | 2021-11-01 | 2021-10-15 | 2021-11-10 | 2021-11-15 | 2021-10-15 | 2022-03-07 | 2022-01-31 | 2022-02-17 | -17 | 12 | 91
508199 | City of Shawnee WTP | Richmond | Embedments | JOB SHOP FABRICATORS | 4503664739 | Fabrication | Carbon Steel | USD | 27518 | USD | 19296 | 8222 | Design Optimizations | 2021-10-22 | 2021-09-02 | 2021-09-12 | 2021-10-22 | 2021-10-07 | 2021-10-22 | 2021-10-22 | 2021-10-07 | 2021-10-22 | 2021-12-12 | 2021-11-16 | 26 | 12 | 35
508199 | City of Shawnee WTP | Richmond | Job Shop Item Distribution System | JOB SHOP FABRICATORS | 4503666356 | Fabrication | Carbon Steel | USD | 16000 | USD | 62732 | -46732 | Single Sourced | 2021-11-16 | 2021-09-02 | 2021-09-12 | 2021-11-16 | 2021-10-07 | 2021-11-16 | 2021-11-16 | 2021-10-12 | 2021-11-16 | 2022-01-31 | 2021-12-24 | 38 | 12 | 40
508199 | City of Shawnee WTP | Richmond | Job Shop Item Settling Plate System | JOB SHOP FABRICATORS | 4503667143 | Fabrication | Carbon Steel | USD | 37000 | USD | 38719 | -1719 | Proposed Supplier Incapable Of Executing | 2021-11-10 | 2021-09-02 | 2021-09-12 | 2021-11-10 | 2021-10-07 | 2021-11-10 | 2021-11-10 | 2021-10-12 | 2021-11-10 | 2022-01-18 | 2021-12-14 | 35 | 12 | 40
508199 | City of Shawnee WTP | Richmond | Job Shop Item Vacuum System | JOB SHOP FABRICATORS | 4503667890 | Fabrication | Carbon Steel | USD | 13000 | USD | 13184 | -184 | Specs / Requirements Misinterpreted in Proposal | 2021-11-16 | 2021-09-02 | 2021-09-12 | 2021-11-16 | 2021-10-06 | 2021-11-16 | 2021-11-16 | 2021-10-12 | 2021-11-16 | 2022-01-30 | 2021-12-23 | 38 | 12 | 40
508199 | City of Shawnee WTP | Richmond | Job Shop Item SAMPLE SYSTEM and COLLECTION & EFFLUENT WEIR SYSTEM | JOB SHOP FABRICATORS | 4503668654 | Fabrication | Carbon Steel | USD | 41000 | USD | 41545 | -545 | Estimate Without Market Reference(No Quote) | 2021-11-15 | 2021-09-02 | 2021-09-12 | 2021-11-15 | 2021-10-06 | 2021-11-15 | 2021-11-15 | 2021-10-12 | 2021-11-15 | 2022-01-29 | 2021-12-22 | 38 | 12 | 40
508199 | City of Shawnee WTP | Richmond | Metal Embeds | Ferguson Enterprise | 4503691027 | Fabrication | Non-Metal Equipment | USD | 28000 | USD | 28309 | -309 | Single Sourced | 2021-11-03 | 2021-09-02 | 2021-11-20 | 2021-11-03 | 2021-11-20 | 2021-11-03 | 2021-11-03 | 2021-11-23 | 2021-11-03 | 2022-01-04 | 2021-12-04 | 31 | 12 | 82
508200 | Owatonna | Oakville | Premeat,BP,RAS | SULZER PUMPS (CANADA) IN | 4503828493 | Rotating Equipment | Centrifugal Pumps | USD | 212186 | CAD | 390607 | -178421 | Single Sourced | 2022-06-16 | 2022-09-08 | 2022-07-01 | 2022-06-30 | 2022-09-08 | 2022-09-08 | 2022-07-14 | 2022-07-19 | 2022-12-01 | 2022-11-16 | 2022-11-23 | -7 | 30 | -51
508200 | Owatonna | Oakville | Air Compressor+Labor | Compressor Science | 4503848383 | Rotating Equipment | Compressors | USD | 19534 | USD | 19792 | -258 | Proposed Supplier Incapable Of Executing | 2022-06-16 | 2022-09-17 | 2022-08-24 | 2022-06-30 | 2022-09-17 | 2022-09-17 | 2022-07-14 | 2022-08-25 | 2022-12-01 | 2022-12-20 | 2022-12-10 | 10 | 30 | -23
508200 | Owatonna | Oakville | Blower | AERZEN CANADA INC | 4503848369 | Rotating Equipment | Blowers & Fans | USD | 98376 | CAD | 87656 | 10720 | Design Optimizations | 2022-06-16 | 2022-09-17 | 2022-08-24 | 2022-06-30 | 2022-09-17 | 2022-09-17 | 2022-07-14 | 2022-08-24 | 2022-12-01 | 2022-12-20 | 2022-12-10 | 10 | 30 | -24
508200 | Owatonna | Oakville | Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503837987 | Electrical & Instrumentation | Ele-Control Panels | USD | 154685 | CAD | 141047 | 13638 | Supplier Competitions / Negotiation | 2022-06-16 | 2022-09-18 | 2022-07-01 | 2022-06-30 | 2022-09-18 | 2022-09-18 | 2022-07-14 | 2022-08-04 | 2022-12-01 | 2022-12-22 | 2022-12-11 | 11 | 18 | -45
508201 | COKE HARAHAN CA TO PA TREATED WATER | Minnetonka | BEV RO _ CONTROL PANELS | PTS Products | 4503619263 | Electrical & Instrumentation | Ele-Control Panels | USD | 27770 | USD | 27770 | 0 | Frame Agreements | 2021-07-08 | 2021-07-08 | 2021-07-12 | 2021-07-12 | 2021-07-15 | 2021-08-04 | 2021-07-14 | 2021-07-15 | 2021-09-01 | 2021-08-11 | 2021-09-01 | -21 | 12 | 7
508201 | COKE HARAHAN CA TO PA TREATED WATER | Minnetonka | ASSY_CITY WATER BOOSTER PUMP | ALFA LAVAL | 4503606158 | Fabrication | Stainless Steel | USD | 11500 | USD | 7872 | 3628 | Frame Agreements | 2021-06-28 | 2021-06-09 | 2021-06-10 | 2021-06-29 | 2021-06-16 | 2021-07-25 | 2021-06-29 | 2021-06-20 | 2021-08-10 | 2021-08-01 | 2021-09-10 | -40 | 12 | 11
508201 | COKE HARAHAN CA TO PA TREATED WATER | Minnetonka | LS_TEKLEEN FILTERS | TEKLEEN | 4503604506 | Flow Control | Filters And Strainers (Incl Housings) | USD | 27000 | USD | 26700 | 300 | Frame Agreements | 2021-06-10 | 2021-05-18 | 2021-05-18 | 2021-06-11 | 2021-06-19 | 2021-07-01 | 2021-06-11 | 2021-06-19 | 2021-08-03 | 2021-08-14 | 2021-07-01 | 44 | 12 | 32
508201 | COKE HARAHAN CA TO PA TREATED WATER | Minnetonka | LS_SODIUM BISULFITE FEED SYSTEM | GRUNDFOS PUMPS CORPORATION | 4503616719 | Rotating Equipment | Dosing Pump | USD | 16844 | USD | 5756 | 11088 | Supplier Competitions / Negotiation | 2021-06-28 | 2021-06-21 | 2021-06-22 | 2021-06-29 | 2021-07-12 | 2021-08-30 | 2021-06-29 | 2021-07-12 | 2021-08-10 | 2021-09-06 | 2021-11-08 | -63 | 12 | 21
508201 | COKE HARAHAN CA TO PA TREATED WATER | Minnetonka | LS_NEAT ANTISCALANT FEED | GRUNDFOS PUMPS CORPORATION | 4513616719 | Rotating Equipment | Dosing Pump | USD | 13344 | USD | 7390 | 5954 | Frame Agreements | 2021-06-28 | 2021-06-21 | 2021-06-22 | 2021-06-29 | 2021-07-12 | 2021-08-30 | 2021-06-29 | 2021-07-12 | 2021-08-10 | 2021-09-06 | 2021-11-08 | -63 | 12 | 21
508201 | COKE HARAHAN CA TO PA TREATED WATER | Minnetonka | LS_MCE | WERNER ELECTRIC | 4503618087 | Electrical & Instrumentation | Ele-Control Panels | USD | 52260 | USD | 56437 | -4177 | Market Impact | 2021-07-01 | 2021-06-27 | 2021-06-27 | 2021-07-01 | 2021-07-07 | 2021-09-09 | 2021-07-01 | 2021-07-12 | 2021-08-10 | 2021-09-05 | 2021-11-22 | -78 | 12 | 15
508203 | Dry Creek | Oakville | Control Panel | Keltour Controls Inc. | 4503684149 | Electrical & Instrumentation | Ele-Control Panels | USD | 62666 | CAD | 53097 | 9569 | Supplier Competitions / Negotiation | 2021-09-22 | 2021-11-02 | 2021-11-04 | 2021-10-01 | 2021-11-03 | 2021-12-04 | 2021-10-15 | 2021-11-08 | 2022-02-15 | 2022-01-29 | 2022-02-06 | -8 | 18 | 6
508203 | Dry Creek | Oakville | Blower | FPZ INC | 4503670173 | Rotating Equipment | Blowers & Fans | USD | 18957 | USD | 7236 | 11721 | Frame Agreements | 2021-09-22 | 2021-10-12 | 2021-10-15 | 2021-10-01 | 2021-10-15 | 2021-12-04 | 2021-10-15 | 2021-10-18 | 2022-02-15 | 2022-01-10 | 2022-01-28 | -18 | 30 | 6
508203 | Dry Creek | Oakville | Air Compressor | Compressor Science Inc. | 4503680244 | Rotating Equipment | Compressors | USD | 18465 | USD | 17536 | 929 | Supplier Competitions / Negotiation | 2021-09-22 | 2021-06-22 | 2021-06-24 | 2021-10-01 | 2021-10-14 | 2021-10-19 | 2021-10-15 | 2021-11-04 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 0 | 30 | 135
508203 | Dry Creek | Oakville | Chemical dosing skid | PROMINENT FLUID CONTROLS LTD. | 4503663897 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 17304 | CAD | 16844 | 460 | Frame Agreements | 2021-09-22 | 2021-10-02 | 2021-10-05 | 2021-10-01 | 2021-10-05 | 2021-12-04 | 2021-10-15 | 2021-10-06 | 2022-02-15 | 2022-01-10 | 2022-01-28 | -18 | 30 | 4
508203 | Dry Creek | Oakville | Process Pump | BOERGER, INC | 4503669122 | Rotating Equipment | Centrifugal Pumps | USD | 15708 | USD | 13432 | 2276 | Frame Agreements | 2021-09-22 | 2021-10-12 | 2021-10-14 | 2021-10-01 | 2021-10-14 | 2021-12-04 | 2021-10-15 | 2021-10-15 | 2022-02-15 | 2021-12-21 | 2022-01-18 | -28 | 30 | 3
508203 | Dry Creek | Oakville | FRP Cover | D&R CUSTOM STEEL | 4503670178 | Fabrication | Non-Metal Equipment | USD | 12717 | CAD | 12640 | 77 | Design Optimizations | 2021-09-22 | 2021-10-18 | 2021-10-20 | 2021-10-01 | 2021-10-20 | 2021-12-04 | 2021-10-15 | 2021-10-18 | 2022-02-15 | 2022-01-10 | 2022-01-28 | -18 | 12 | 0
508203 | Dry Creek | Oakville | Frames | 3D MECHANICAL | 4503690479 | Fabrication | Stainless Steel | USD | 6631 | CAD | 6156 | 475 | Frame Agreements | 2021-09-22 | 2021-11-06 | 2021-11-12 | 2021-10-01 | 2021-10-22 | 2021-12-04 | 2021-10-15 | 2021-11-22 | 2022-02-15 | 2022-01-06 | 2022-01-26 | -20 | 12 | 16
508203 | Dry Creek | Oakville | Backpulse tank | ACO CONTAINER SYSTEMS LTD. | 4503680249 | Fabrication | Non-Metal Equipment | USD | 6537 | CAD | 6537 | 0 | Single Sourced | 2021-09-22 | 2021-09-22 | 2021-09-24 | 2021-10-01 | 2021-09-25 | 2021-12-04 | 2021-10-15 | 2021-11-04 | 2022-02-15 | 2022-02-15 | 2022-02-15 | 0 | 12 | 43
508246 | Diageo Gimli RO | Minnetonka | RO ASSY | ARC SERVICES | 4503628915 | Fabrication | Process Equipment | CAD | 135099 | USD | 139529 | -4430 | Market Impact | 2021-06-30 | 2021-07-21 | 2021-07-21 | 2021-07-13 | 2021-07-31 | 2021-08-25 | 2021-07-14 | 2021-07-31 | 2021-10-20 | 2021-10-17 | 2021-10-18 | -1 | 12 | 10
508246 | Diageo Gimli RO | Minnetonka | GREENSAND FILTERS | ARC SERVICES | 4513628915 | Fabrication | Process Equipment | CAD | 92712 | USD | 81078 | 11634 | Frame Agreements | 2021-06-28 | 2021-08-03 | 2021-08-03 | 2021-07-13 | 2021-07-31 | 2021-08-24 | 2021-07-14 | 2021-07-31 | 2021-10-20 | 2021-10-17 | 2021-10-18 | -1 | 12 | -3
508246 | Diageo Gimli RO | Minnetonka | CIP ASSY | ARC SERVICES | 4523628915 | Fabrication | Process Equipment | CAD | 20666 | USD | 22762 | -2096 | Size/ Weight/ Quantity Underestimated | 2021-06-30 | 2021-07-21 | 2021-07-21 | 2021-07-13 | 2021-07-31 | 2021-08-25 | 2021-07-14 | 2021-07-31 | 2021-10-20 | 2021-10-09 | 2021-10-14 | -5 | 12 | 10
508246 | Diageo Gimli RO | Guelph | RO HOUSINGS - FRP | PROTEC ARISAWA AMERICA, INC. | 4503629629 | Fabrication | Process Equipment | CAD | 19784 | USD | 20081 | -297 | Market Impact | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2021-08-04 | 2021-08-02 | 2021-08-16 | 2021-08-04 | 2021-08-03 | 2021-08-31 | 2021-08-30 | 2021-08-30 | 0 | 12 | -1
508246 | Diageo Gimli RO | Minnetonka | RO ELEC PANELS | BW Systems | 4503642861 | Electrical & Instrumentation | Ele-Control Panels | CAD | 54046 | USD | 72267 | -18221 | Proposed Supplier Incapable Of Executing | 2021-08-20 | 2021-08-20 | 2021-08-28 | 2021-08-27 | 2021-08-28 | 2021-09-15 | 2021-08-28 | 2021-08-28 | 2021-10-06 | 2021-10-11 | 2021-10-08 | 3 | 18 | 8
508246 | Diageo Gimli RO | Minnetonka | GREENSAND FILTERS | Arrow Tanks | 4503625978 | Fabrication | Carbon Steel | CAD | 49776 | USD | 51408 | -1632 | Estimate Without Market Reference(No Quote) | 2021-06-10 | 2021-07-16 | 2021-06-30 | 2021-07-06 | 2021-07-24 | 2021-08-10 | 2021-07-08 | 2021-07-24 | 2021-10-10 | 2021-10-02 | 2021-10-06 | -4 | 12 | 8
508246 | Diageo Gimli RO | Minnetonka | DS_UV | AQUIONICS, INC. | 4503618590 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 18582 | USD | 19191 | -609 | Estimate Without Market Reference(No Quote) | 2021-07-02 | 2021-06-15 | 2021-06-16 | 2021-07-02 | 2021-07-09 | 2021-08-12 | 2021-07-02 | 2021-07-09 | 2021-10-10 | 2021-09-05 | 2021-09-22 | -17 | 18 | 24
508246 | Diageo Gimli RO | Minnetonka | LS_GS BLOWER / CHEM SYSTEMS / STRAINER / FWDING PUMPS / FLOWMETERS / GTM / UV / POST-CARBON | AERZEN CANADA INC | 4503651922 | Rotating Equipment | Blowers & Fans | CAD | 102304 | CAD | 7060 | 95244 | Frame Agreements | 2021-08-02 | 2021-09-26 | 2021-08-27 | 2021-08-03 | 2021-09-14 | 2021-09-26 | 2021-08-04 | 2021-09-14 | 2021-10-20 | 2021-11-21 | 2021-11-05 | 16 | 30 | -12
508246 | Diageo Gimli RO | Minnetonka | LS - PUMPS | PFC EQUIPMENT | 4503637708 | Rotating Equipment | Centrifugal Pumps | CAD | 17414 | USD | 17985 | -571 | Single Sourced | 2021-07-23 | 2021-07-23 | 2021-07-23 | 2021-08-19 | 2021-08-17 | 2021-09-16 | 2021-08-19 | 2021-08-18 | 2021-11-11 | 2021-11-10 | 2021-11-10 | 0 | 30 | 26
508246 | Diageo Gimli RO | Minnetonka | DS - STORAGE TANK | Preferred Stainless Holdings | 4503616938 | Fabrication | Stainless Steel | CAD | 95163 | USD | 97666 | -2503 | Not included in Proposal / RFQ | 2021-06-04 | 2021-06-03 | 2021-06-04 | 2021-06-14 | 2021-07-07 | 2021-08-05 | 2021-06-14 | 2021-07-07 | 2021-10-08 | 2021-10-03 | 2021-10-05 | -2 | 12 | 34
508246 | Diageo Gimli RO | Minnetonka | CIP - HEATER | Chromalox Inc. | 4503637263 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | CAD | 9577 | USD | 9891 | -314 | Estimate Without Market Reference(No Quote) | 2021-06-03 | 2021-06-03 | 2021-06-03 | 2021-08-18 | 2021-08-17 | 2021-07-17 | 2021-08-19 | 2021-08-18 | 2021-08-31 | 2021-08-30 | 2021-08-30 | 0 | 18 | 76
508246 | Diageo Gimli RO | Minnetonka | LS VALVE | Duncan Co. | 4503685358 | Flow Control | Metal Control Valves | CAD | 10529 | USD | 10874 | -345 | Proposed Supplier Incapable Of Executing | 2021-08-27 | 2021-08-28 | 2021-11-11 | 2021-09-02 | 2021-11-10 | 2021-11-04 | 2021-09-02 | 2021-11-12 | 2021-09-30 | 2022-01-13 | 2021-11-21 | 53 | 12 | 76
508246 | Diageo Gimli RO | Minnetonka | LS - GTM | Duncan Co. | 4503642939 | Rotating Equipment | Others | CAD | 23968 | USD | 23968 | 0 | Market Impact | 2021-06-21 | 2021-06-21 | 2021-07-15 | 2021-06-29 | 2021-08-29 | 2021-08-16 | 2021-07-30 | 2021-08-30 | 2021-10-11 | 2021-10-11 | 2021-10-11 | 0 | 30 | 70
508246 | Diageo Gimli RO | Minnetonka | LS - INSTRUMENTS | MICRO-MOTION, INC | 4503648668 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | CAD | 15061 | USD | 15061 | 0 | Supplier Competitions / Negotiation | 2021-09-15 | 2021-08-31 | 2021-09-09 | 2021-09-15 | 2021-09-09 | 2021-09-15 | 2021-09-15 | 2021-09-09 | 2021-09-15 | 2021-09-30 | 2021-09-22 | 8 | 18 | 9
508246 | Diageo Gimli RO | Minnetonka | LS-RO MCE | WERNER ELECTRIC | 4503629298 | Electrical & Instrumentation | Ele-nclosures | CAD | 77537 | USD | 80079 | -2542 | Estimate Without Market Reference(No Quote) | 2021-07-13 | 2021-07-13 | 2021-07-27 | 2021-08-02 | 2021-08-04 | 2021-08-23 | 2021-08-04 | 2021-08-04 | 2021-09-21 | 2021-10-04 | 2021-09-27 | 7 | 18 | 22
508261 | Intel F42 UPW System 7th Train Expansion | Guelph | RO Membranes | FILMTEC CORPORATION | 4503607591 | Flow Control | RO membrane housings | USD | 48240 | USD | 46800 | 1440 | Size/ Weight/ Quantity Underestimated | 2021-06-21 | 2021-06-15 | 2021-06-23 | 2021-06-23 | 2021-06-22 | 2021-08-20 | 2021-06-25 | 2021-06-24 | 2021-10-20 | 2021-10-20 | 2021-10-26 | -6 | 12 | 9
508261 | Intel F42 UPW System 7th Train Expansion | Guelph | Control Panels | ISG | 4503607699 | Electrical & Instrumentation | Ele-Control Panels | USD | 80407 | USD | 61042 | 19365 | Size/ Weight/ Quantity Underestimated | 2021-07-09 | 2021-06-23 | 2021-06-23 | 2021-07-16 | 2021-06-21 | 2021-09-15 | 2021-07-16 | 2021-06-22 | 2021-09-24 | 2021-12-10 | 2021-11-01 | 39 | 12 | -1
508266 | Nestle Anderson MBR Expansion | Guelph | Control Panels | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503649643 | Electrical & Instrumentation | Ele-Control Panels | USD | 16441 | USD | 7636 | 8805 | Supplier Competitions / Negotiation | 2021-07-30 | 2021-08-11 | 2021-08-30 | 2021-08-27 | 2021-09-05 | 2021-09-20 | 2021-09-10 | 2021-09-12 | 2021-11-12 | 2021-09-12 | 2021-10-12 | -30 | 18 | 32
508266 | Nestle Anderson MBR Expansion | Guelph | Blower | AERZEN CANADA INC | 4503658473 | Rotating Equipment | Blowers & Fans | USD | 12933 | USD | 12180 | 753 | Supplier Competitions / Negotiation | 2021-07-30 | 2021-09-07 | 2021-09-14 | 2021-08-27 | 2021-09-21 | 2021-09-20 | 2021-09-10 | 2021-09-28 | 2021-11-12 | 2021-09-28 | 2021-10-20 | -22 | 30 | 21
508266 | Nestle Anderson MBR Expansion | Guelph | Centrifugal Pumps | FLOWSERVE INC. | 4503650207 | Rotating Equipment | Centrifugal Pumps | USD | 7550 | USD | 12892 | -5342 | Single Sourced | 2021-07-30 | 2021-08-23 | 2021-08-30 | 2021-08-27 | 2021-09-06 | 2021-09-20 | 2021-09-10 | 2021-09-13 | 2021-11-12 | 2021-09-13 | 2021-10-13 | -30 | 30 | 21
508266 | Nestle Anderson MBR Expansion | Guelph | Rotary Lobe Pump | BOERGER LLC | 4503650362 | Rotating Equipment | PD Pumps | USD | 20191 | USD | 13191 | 7000 | Frame Agreements | 2021-07-30 | 2021-08-23 | 2021-08-30 | 2021-08-27 | 2021-09-06 | 2021-09-20 | 2021-09-10 | 2021-09-13 | 2021-11-12 | 2021-09-13 | 2021-10-13 | -30 | 30 | 21
508266 | Nestle Anderson MBR Expansion | Guelph | Pump Skid Frame | Plasfab Inc | 4503655553 | Fabrication | Carbon Steel | USD | 11984 | USD | 11673 | 311 | Design Optimizations | 2021-07-30 | 2021-08-11 | 2021-09-08 | 2021-08-27 | 2021-09-15 | 2021-09-20 | 2021-09-10 | 2021-09-22 | 2021-11-12 | 2021-09-22 | 2021-10-17 | -25 | 12 | 42
508266 | Nestle Anderson MBR Expansion | Guelph | Piping Spool | NV PIPING SYSTEMS INC. | 4503663692 | Fabrication | Stainless Steel | USD | 10000 | USD | 16084 | -6084 | Specs / Requirements Misinterpreted in Proposal | 2021-09-25 | 2021-09-15 | 2021-09-22 | 2021-09-25 | 2021-09-29 | 2021-09-25 | 2021-09-25 | 2021-10-06 | 2021-09-25 | 2021-10-06 | 2021-09-30 | 6 | 12 | 21
508266 | Nestle Anderson MBR Expansion | Guelph | Frames | 3D MECHANICAL | 4503668640 | Fabrication | Stainless Steel | USD | 13000 | USD | 12787 | 213 | Frame Agreements | 2021-10-04 | 2021-09-24 | 2021-10-01 | 2021-10-04 | 2021-10-07 | 2021-10-04 | 2021-10-04 | 2021-10-14 | 2021-10-04 | 2021-10-14 | 2021-10-09 | 5 | 12 | 20
508266 | Nestle Anderson MBR Expansion | Guelph | Membrane Tank | D&R CUSTOM STEEL | 4503651947 | Fabrication | Stainless Steel | USD | 174813 | USD | 124028 | 50785 | Supplier Competitions / Negotiation | 2021-07-30 | 2021-08-25 | 2021-09-01 | 2021-08-27 | 2021-09-07 | 2021-09-20 | 2021-09-10 | 2021-09-14 | 2021-11-12 | 2021-09-14 | 2021-10-13 | -29 | 12 | 20
508280 | Stevensville | Oakville | Process Pumps | GOULDS PUMPS | 4503637642 | Rotating Equipment | PD Pumps | USD | 52554 | USD | 69855 | -17301 | Market Impact | 2021-03-03 | 2021-08-05 | 2021-08-05 | 2021-10-27 | 2021-08-17 | 2021-08-20 | 2021-11-17 | 2021-11-19 | 2021-01-30 | 2022-03-11 | 2021-08-20 | 203 | 30 | 106
508280 | Stevensville | Oakville | Control Panel | KELTOUR CONTROLS INC. | 4503689562 | Electrical & Instrumentation | Ele-Control Panels | USD | 51558 | CAD | 49784 | 1774 | Frame Agreements | 2021-03-03 | 2021-11-20 | 2021-11-20 | 2021-10-27 | 2021-11-18 | 2021-08-06 | 2021-11-17 | 2021-11-18 | 2021-01-30 | 2022-02-10 | 2021-08-06 | 188 | 18 | -2
508280 | Stevensville | Oakville | Fabrications- Spools | NV PIPING SYSTEMS INC. | 4503687542 | Fabrication | Stainless Steel | USD | 36417 | CAD | 33048 | 3369 | Frame Agreements | 2021-03-03 | 2021-11-04 | 2021-11-04 | 2021-10-27 | 2021-11-15 | 2021-07-31 | 2021-11-17 | 2021-11-15 | 2021-01-30 | 2022-01-29 | 2021-07-31 | 182 | 12 | 11
508280 | Stevensville | Oakville | Auto Stainers | BOLL FILTER CORPORATION | 4503682596 | Flow Control | Filters And Strainers (Incl Housings) | USD | 33240 | USD | 31656 | 1584 | Supplier Competitions / Negotiation | 2021-03-03 | 2021-07-23 | 2021-07-23 | 2021-10-27 | 2021-11-08 | 2021-08-17 | 2021-11-17 | 2021-11-08 | 2021-01-30 | 2022-03-04 | 2021-08-17 | 199 | 12 | 108
508280 | Stevensville | Oakville | Fabrications- Frames | PLASFAB LIMITED | 4503690909 | Fabrication | Stainless Steel | USD | 17108 | CAD | 34895 | -17787 | Specs / Requirements Misinterpreted in Proposal | 2021-03-03 | 2021-11-16 | 2021-11-16 | 2021-10-27 | 2021-11-22 | 2021-08-01 | 2021-11-17 | 2021-11-22 | 2021-01-30 | 2022-01-31 | 2021-08-01 | 183 | 12 | 6
508280 | Stevensville | Oakville | Blower | AERZEN CANADA INC | 4503700306 | Rotating Equipment | Blowers & Fans | USD | 13228 | CAD | 14625 | -1397 | Not included in Proposal / RFQ | 2021-03-03 | 2021-07-31 | 2021-11-18 | 2021-10-27 | 2021-12-08 | 2021-07-31 | 2021-11-17 | 2021-12-08 | 2021-01-30 | 2022-01-30 | 2021-07-31 | 183 | 30 | 130
508280 | Stevensville | Oakville | Tanks | ACO CONTAINER SYSTEMS LTD. | 4503693011 | Fabrication | Non-Metal Equipment | USD | 10789 | CAD | 18218 | -7429 | Size/ Weight/ Quantity Underestimated | 2021-03-03 | 2021-11-27 | 2021-11-27 | 2021-10-27 | 2021-07-23 | 2021-07-23 | 2021-11-17 | 2021-11-26 | 2021-01-30 | 2022-01-13 | 2021-07-23 | 174 | 12 | -1
508280 | Stevensville | Oakville | Air Compressor | Compressor Science Inc. | 4503700266 | Rotating Equipment | Compressors | USD | 8833 | USD | 17844 | -9011 | Specs / Requirements Misinterpreted in Proposal | 2021-03-03 | 2021-07-28 | 2021-07-20 | 2021-10-27 | 2021-12-02 | 2021-07-28 | 2021-11-17 | 2021-12-09 | 2021-01-30 | 2022-01-24 | 2021-07-28 | 180 | 30 | 134
508280 | Stevensville | Oakville | Dosing Pump | PROMINENT FLUID CONTROLS LTD. | 4503674921 | Rotating Equipment | Dosing Pump | USD | 8575 | CAD | 16967 | -8392 | Proposed Supplier Incapable Of Executing | 2021-03-03 | 2021-10-23 | 2021-10-23 | 2021-10-27 | 2021-11-21 | 2021-07-25 | 2021-11-17 | 2021-11-23 | 2021-01-30 | 2022-01-18 | 2021-07-25 | 177 | 30 | 31
508280 | Stevensville | Oakville | Flow Transmitter | ENDRESS & HAUSER | 4503694758 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 10702 | USD | 11857 | -1155 | Specs / Requirements Misinterpreted in Proposal | 2021-03-03 | 2021-11-30 | 2021-11-30 | 2021-10-27 | 2021-11-29 | 2021-08-11 | 2021-11-17 | 2021-11-29 | 2021-01-30 | 2022-02-21 | 2021-08-11 | 194 | 18 | -1
508280 | Stevensville | Oakville | Angle Seat Valve | BURKERT CONTROMATIC PRIVATE LIMITED | 4503698384 | Flow Control | Metal Isolation Valves | USD | 5723 | CAD | 8633 | -2910 | Proposed Supplier Incapable Of Executing | 2021-03-03 | 2021-07-31 | 2021-07-27 | 2021-10-27 | 2021-11-28 | 2021-07-31 | 2021-11-17 | 2021-12-04 | 2021-01-30 | 2022-01-29 | 2021-07-31 | 182 | 12 | 126
508280 | Stevensville | Oakville | Butterfly Valve | BRAY CONTROLS CANADA LTD. | 4503682106 | Flow Control | Metal Control Valves | USD | 14456 | USD | 15065 | -609 | Market Impact | 2021-03-03 | 2021-11-02 | 2021-11-02 | 2021-10-27 | 2021-11-05 | 2021-07-31 | 2021-11-17 | 2021-11-07 | 2021-01-30 | 2022-01-30 | 2021-07-31 | 183 | 12 | 5
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | TEKLEEN FILTER SKID_ASSY | TITAN PIPING SYSTEMS INC. | 4503623186 | Fabrication | Skid Assembly Outsourced | CAD | 26634 | CAD | 17931 | 8703 | Supplier Competitions / Negotiation | 2021-06-30 | 2021-06-30 | 2021-07-20 | 2021-07-08 | 2021-07-19 | 2021-08-14 | 2021-07-08 | 2021-07-22 | 2021-09-17 | 2021-08-19 | 2021-09-28 | -40 | 12 | 22
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | TEKLEEN FILTERS | TEKLEEN | 4503622173 | Flow Control | Filters And Strainers (Incl Housings) | CAD | 24321 | CAD | 21076 | 3245 | Frame Agreements | 2021-06-28 | 2021-06-10 | 2021-06-09 | 2021-06-29 | 2021-07-13 | 2021-07-17 | 2021-06-29 | 2021-07-13 | 2021-08-04 | 2021-08-24 | 2021-08-23 | 1 | 12 | 33
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | LS_CITY WATER TANK RETROFIT KIT | AMERICAN ULTRAVIOLET | 4513615381 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 5925 | USD | 6111 | -186 | Single Sourced | 2021-07-06 | 2021-07-05 | 2021-07-05 | 2021-07-15 | 2021-07-04 | 2021-08-10 | 2021-07-15 | 2021-07-05 | 2021-09-17 | 2021-08-02 | 2021-08-30 | -28 | 18 | 0
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | LS_CITY WATER TANK RETROFIT KIT | Duncan Co. | 4513616121 | Flow Control | Metal Control Valves | CAD | 13498 | CAD | 7190 | 6308 | Frame Agreements | 2021-07-27 | 2021-07-09 | 2021-07-09 | 2021-07-27 | 2021-07-07 | 2021-07-27 | 2021-07-27 | 2021-07-07 | 2021-07-27 | 2021-08-04 | 2021-08-16 | -12 | 12 | -2
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | LS_RECLAIM TANK RETROFIT KIT | AMERICAN ULTRAVIOLET | 4523615381 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 5925 | USD | 6111 | -186 | Size/ Weight/ Quantity Underestimated | 2021-07-06 | 2021-07-05 | 2021-07-05 | 2021-07-15 | 2021-07-02 | 2021-08-09 | 2021-07-15 | 2021-07-02 | 2021-09-17 | 2021-07-30 | 2021-08-30 | -31 | 18 | -3
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | LS_RECLAIM TANK RETROFIT KIT | Duncan Co. | 4523616121 | Flow Control | Metal Control Valves | CAD | 13498 | CAD | 7235 | 6263 | Design Optimizations | 2021-07-27 | 2021-07-09 | 2021-07-09 | 2021-07-27 | 2021-07-08 | 2021-07-27 | 2021-07-27 | 2021-07-08 | 2021-07-27 | 2021-08-05 | 2021-08-16 | -11 | 12 | -1
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | LS_TWRO TANK UPGRADE KIT | AMERICAN ULTRAVIOLET | 4503615381 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 11849 | USD | 12222 | -373 | Not included in Proposal / RFQ | 2021-07-06 | 2021-07-05 | 2021-07-05 | 2021-07-15 | 2021-07-06 | 2021-08-11 | 2021-07-15 | 2021-07-06 | 2021-09-17 | 2021-08-03 | 2021-08-30 | -27 | 18 | 1
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | LS_ACID PANEL | PROMINENT FLUID CONTROLS LTD. | 4503622931 | Electrical & Instrumentation | Ele-Control Panels | CAD | 17791 | CAD | 22971 | -5180 | Market Impact | 2021-07-06 | 2021-07-08 | 2021-07-15 | 2021-07-15 | 2021-07-19 | 2021-08-20 | 2021-07-15 | 2021-07-19 | 2021-09-17 | 2021-08-30 | 2021-10-05 | -36 | 18 | 11
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | LS_REMOTE I/O PANEL | Keltour Controls Inc. | 4503630933 | Electrical & Instrumentation | Ele-Control Panels | CAD | 25033 | USD | 23116 | 1917 | Frame Agreements | 2021-07-06 | 2021-07-29 | 2021-07-29 | 2021-07-15 | 2021-08-05 | 2021-08-25 | 2021-07-15 | 2021-08-05 | 2021-09-17 | 2021-09-28 | 2021-10-15 | -17 | 18 | 7
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | DS_UV STERILIZERS | AQUIONICS, INC. | 4503614649 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 110123 | USD | 112809 | -2686 | Market Impact | 2021-06-08 | 2021-06-08 | 2021-06-09 | 2021-06-08 | 2021-07-05 | 2021-07-30 | 2021-06-08 | 2021-07-05 | 2021-08-23 | 2021-08-15 | 2021-09-21 | -37 | 18 | 27
508284 | COKE WESTON NF TO RO (MONSTER) | Guelph | LS_POLISHING FILTERS Fitrek Cartridges - Change Order | Duncan Co. | 4503641409 | Flow Control | Filters And Strainers (Incl Housings) | CAD | 35740 | CAD | 25953 | 9787 | Supplier Competitions / Negotiation | 2021-07-27 | 2021-07-27 | 2021-07-27 | 2021-07-30 | 2021-08-25 | 2021-09-05 | 2021-07-30 | 2021-08-25 | 2021-10-15 | 2021-10-13 | 2021-10-14 | -1 | 12 | 29
508293 | SQM SALAR AS | Guelph | Piston Pump | Danfoss LLC | 4503631862 | Rotating Equipment | PD Pumps | USD | 45224 | USD | 46202 | -978 | Estimate Without Market Reference(No Quote) | 2021-09-06 | 2021-07-19 | 2021-07-26 | 2021-09-06 | 2021-08-01 | 2021-09-06 | 2021-09-06 | 2021-08-08 | 2021-09-06 | 2021-10-25 | 2021-09-30 | 25 | 30 | 20
508301 | CRYSTAL GEYSER ORLANDO | Minnetonka | ASSY_BEV RO SKID - MCE AND MCP | Wunderlich-Malec Systems Inc | 4503625968 | Electrical & Instrumentation | Ele-Control Panels | USD | 26638 | USD | 26368 | 270 | Supplier Competitions / Negotiation | 2021-09-02 | 2021-07-12 | 2021-07-19 | 2021-09-02 | 2021-07-27 | 2021-09-02 | 2021-09-02 | 2021-07-27 | 2021-09-02 | 2021-10-24 | 2021-09-28 | 26 | 18 | 15
508301 | CRYSTAL GEYSER ORLANDO | Minnetonka | ASSY_BEV RO SKID | Trojan Technologies INC. | 4503617185 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 10825 | USD | 10825 | 0 | Size/ Weight/ Quantity Underestimated | 2021-07-30 | 2021-06-01 | 2021-07-07 | 2021-08-04 | 2021-07-12 | 2021-08-16 | 2021-08-06 | 2021-07-12 | 2021-11-01 | 2021-10-04 | 2021-10-18 | -14 | 18 | 41
508301 | CRYSTAL GEYSER ORLANDO | Minnetonka | LS_PUMPS / CIP / CHEM SYSTEM | PFC EQUIPMENT | 4503617204 | Rotating Equipment | Centrifugal Pumps | USD | 6553 | USD | 6553 | 0 | Supplier Competitions / Negotiation | 2021-07-30 | 2021-07-01 | 2021-07-01 | 2021-08-04 | 2021-07-11 | 2021-08-31 | 2021-08-06 | 2021-07-11 | 2021-11-01 | 2021-09-12 | 2021-10-07 | -25 | 30 | 10
508301 | CRYSTAL GEYSER ORLANDO | Minnetonka | LS - MCE | Wunderlich-Malec Systems Inc | 4513625968 | Electrical & Instrumentation | Ele-Control Panels | USD | 50000 | USD | 38733 | 11267 | Supplier Competitions / Negotiation | 2021-07-30 | 2021-07-12 | 2021-07-23 | 2021-08-04 | 2021-07-28 | 2021-09-06 | 2021-08-06 | 2021-07-28 | 2021-11-01 | 2021-10-25 | 2021-10-28 | -3 | 18 | 16
508301 | CRYSTAL GEYSER ORLANDO | Minnetonka | ASSY BEV RO - ELECTRICAL PANEL PARTS | Duncan Co. | 4503671161 | Electrical & Instrumentation | Ele-PLCs, HMIs | USD | 18937 | USD | 18937 | 0 | Frame Agreements | 2021-10-18 | 2021-10-18 | 2021-10-19 | 2021-10-19 | 2021-10-18 | 2021-10-22 | 2021-10-19 | 2021-10-19 | 2021-10-26 | 2021-10-26 | 2021-10-26 | 0 | 18 | 1
508304 | Intel RA | Oakville | Electrical - VFD | WERNER ELECTRIC | 4503688639 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 8478 | USD | 12519 | -4041 | Market Impact | 2021-05-10 | 2021-10-19 | 2021-11-04 | 2021-07-15 | 2021-11-11 | 2021-10-19 | 2021-09-15 | 2021-11-18 | 2022-03-30 | 2022-03-10 | 2022-03-20 | -10 | 18 | 30
508304 | Intel RA | Oakville | Instrumentation - TOC Analyzer | Keltour Controls Inc. | 4503657906 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 47239 | CAD | 49770 | -2531 | Not included in Proposal / RFQ | 2021-05-10 | 2021-10-19 | 2021-09-13 | 2021-07-15 | 2021-09-20 | 2021-10-19 | 2021-09-15 | 2021-09-27 | 2022-03-30 | 2022-02-28 | 2022-03-15 | -15 | 18 | -22
508304 | Intel RA | Oakville | Amiad Filter | AMIAD USA INC. | 4503655706 | Flow Control | Filters And Strainers (Incl Housings) | USD | 10521 | USD | 10215 | 306 | Design Optimizations | 2021-05-10 | 2021-10-19 | 2021-09-08 | 2021-07-15 | 2021-09-15 | 2021-10-19 | 2021-09-15 | 2021-09-22 | 2022-03-30 | 2022-01-12 | 2022-02-19 | -38 | 12 | -27
508304 | Intel RA | Oakville | Heat Exchanger | ALFA LAVAL | 4503663660 | Electrical & Instrumentation | Ele-Electrical Others | USD | 36954 | USD | 38177 | -1223 | Estimate Without Market Reference(No Quote) | 2021-05-10 | 2021-10-19 | 2021-09-29 | 2021-07-15 | 2021-10-04 | 2021-10-19 | 2021-09-15 | 2021-10-06 | 2022-03-30 | 2021-11-17 | 2022-01-22 | -66 | 18 | -13
508307 | Pace Richardson | Guelph | Atmospheric Tanks - HDPE | ACO CONTAINER SYSTEMS LTD. | 4503739614 | Fabrication | Non-Metal Equipment | CAD | 14718 | CAD | 23681 | -8963 | Size/ Weight/ Quantity Underestimated | 2021-10-25 | 2021-08-04 | 2022-01-28 | 2021-11-15 | 2022-02-03 | 2022-01-11 | 2021-12-06 | 2022-02-16 | 2022-02-21 | 2022-04-22 | 2022-06-21 | -60 | 12 | 196
508307 | Pace Richardson | Guelph | Blower | AERZEN CANADA INC. | 4503747338 | Rotating Equipment | Blowers & Fans | CAD | 43155 | CAD | 61950 | -18795 | Size/ Weight/ Quantity Underestimated | 2021-09-13 | 2021-08-08 | 2022-02-16 | 2021-10-04 | 2022-02-23 | 2021-12-28 | 2021-10-25 | 2022-03-01 | 2022-02-21 | 2022-05-20 | 2022-04-06 | 44 | 36 | 205
508307 | Pace Richardson | Guelph | Centrifugal Pumps | SULZER PUMPS (CANADA) INC. | 4503707763 | Rotating Equipment | Electric Motors | CAD | 98887 | CAD | 98040 | 847 | Supplier Competitions / Negotiation | 2021-09-13 | 2021-10-29 | 2022-03-16 | 2021-09-27 | 2021-12-07 | 2021-12-14 | 2021-10-11 | 2021-12-15 | 2022-01-10 | 2022-02-23 | 2022-02-01 | 22 | 24 | 47
508307 | Pace Richardson | Guelph | AUTO - Butterfly/Ball Check/Check Valves | BRAY CONTROLS CANADA LTD. | 4503747344 | Flow Control | Metal Control Valves | CAD | 38273 | USD | 10178 | 28095 | Supplier Competitions / Negotiation | 2021-09-13 | 2021-11-05 | 2022-01-05 | 2021-10-04 | 2022-03-06 | 2022-01-20 | 2021-10-25 | 2022-02-28 | 2022-01-10 | 2022-05-30 | 2022-03-21 | 70 | 36 | 115
508307 | Pace Richardson | Guelph | Aeration - Diffusers and Aerators | ENVIRONMENTAL DYNAMICS | 4503655500 | Flow Control | Injection Quills, Ejectors, Diffusers | CAD | 33420 | USD | 34250 | -830 | Size/ Weight/ Quantity Underestimated | 2021-07-19 | 2021-07-23 | 2021-09-08 | 2021-08-09 | 2021-09-16 | 2021-11-05 | 2021-08-30 | 2021-09-21 | 2022-02-21 | 2022-02-22 | 2022-02-21 | 1 | 18 | 60
508307 | Pace Richardson | Guelph | Electrical Panels | MACHINE CONTROL SYSTEMS | 4503762752 | Electrical & Instrumentation | Ele-Control Panels | CAD | 63936 | CAD | 14429 | 49507 | Supplier Competitions / Negotiation | 2021-09-27 | 2021-11-22 | 2022-03-18 | 2021-10-11 | 2022-03-23 | 2022-01-27 | 2021-11-01 | 2022-03-25 | 2022-02-21 | 2022-05-30 | 2022-04-11 | 49 | 12 | 123
508307 | Pace Richardson | Guelph | Pressure Gauge & Switch - SKIDDED | CONVAL PROCESS SOLUTIONS INC | 4503745940 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | CAD | 6600 | USD | 12049 | -5449 | Supplier Competitions / Negotiation | 2021-11-01 | 2021-11-04 | 2021-12-29 | 2021-11-15 | 2022-02-24 | 2022-02-05 | 2021-11-29 | 2022-02-28 | 2022-01-10 | 2022-04-15 | 2022-05-12 | -27 | 18 | 116
508307 | Pace Richardson | Guelph | Turbidity/pH Sensor + Transmitters | ENDRESS & HAUSER | 4503747337 | Electrical & Instrumentation | Inst-Analytical Instruments | CAD | 5801 | USD | 27593 | -21792 | Supplier Competitions / Negotiation | 2021-11-01 | 2021-11-08 | 2021-11-04 | 2021-11-15 | 2022-02-24 | 2022-01-12 | 2021-11-29 | 2022-02-25 | 2022-01-10 | 2022-03-25 | 2022-02-16 | 37 | 36 | 109
508307 | Pace Richardson | Guelph | Transmitter Level, Pressure & Temp | LAKESIDE PROCESS CONTROLS LTD. | 4503747328 | Electrical & Instrumentation | Inst-Analytical Instruments | CAD | 9181 | USD | 23635 | -14454 | Supplier Competitions / Negotiation | 2021-11-01 | 2021-11-15 | 2022-01-14 | 2022-02-25 | 2022-02-25 | 2022-03-21 | 2022-03-21 | 2022-02-26 | 2022-03-21 | 2022-08-08 | 2022-05-30 | 70 | 24 | 103
508307 | Pace Richardson | Guelph | Rotary Lobe Pumps | BOERGER LLC | 4503712086 | Rotating Equipment | Electric Motors | CAD | 24244 | USD | 24956 | -712 | Supplier Competitions / Negotiation | 2021-11-01 | 2021-10-29 | 2021-12-21 | 2022-02-25 | 2021-12-23 | 2022-02-28 | 2022-02-28 | 2022-01-04 | 2022-02-28 | 2022-03-25 | 2022-06-30 | -97 | 24 | 67
508309 | City of Chandler Reclaimed Water Interconnect Facility | Oakville | Pipe Spools (SS) | BENNETT MECHANICAL INSTALLATIONS | 4503852387 | Fabrication | Stainless Steel | USD | 66216 | CAD | 89815 | -23599 | Market Impact | 2022-06-25 | 2022-07-18 | 2022-08-29 | 2022-07-16 | 2022-08-31 | 2022-10-11 | 2022-07-23 | 2022-09-06 | 2022-10-01 | 2023-01-27 | 2022-11-29 | 59 | 12 | 50
508309 | City of Chandler Reclaimed Water Interconnect Facility | Oakville | Air Compressor - 2 Qty | Compressor Science | 4503798897 | Rotating Equipment | Compressors | USD | 46801 | USD | 29280 | 17521 | Supplier Competitions / Negotiation | 2022-06-11 | 2022-01-19 | 2022-02-02 | 2022-07-02 | 2022-05-26 | 2022-05-23 | 2022-07-09 | 2022-05-27 | 2022-10-01 | 2023-01-30 | 2022-11-30 | 61 | 30 | 128
508309 | City of Chandler Reclaimed Water Interconnect Facility | Oakville | Air Scour Blower - 2 Qty | KAESER COMPRESSORS | 4503806035 | Rotating Equipment | Blowers & Fans | USD | 98086 | CAD | 77168 | 20918 | Supplier Competitions / Negotiation | 2022-02-19 | 2022-01-18 | 2022-01-27 | 2022-03-12 | 2022-06-08 | 2022-05-23 | 2022-03-19 | 2022-06-09 | 2022-10-01 | 2022-12-08 | 2022-11-04 | 34 | 30 | 142
508309 | City of Chandler Reclaimed Water Interconnect Facility | Oakville | Process Pump + CIP Pump | GOULDS PUMPS | 4503770612 | Rotating Equipment | Centrifugal Pumps | USD | 348945 | USD | 365361 | -16416 | Market Impact | 2022-01-08 | 2022-01-17 | 2022-04-04 | 2022-01-29 | 2022-04-04 | 2022-04-04 | 2022-02-05 | 2022-04-06 | 2022-10-01 | 2022-11-16 | 2022-10-24 | 23 | 30 | 79
508309 | City of Chandler Reclaimed Water Interconnect Facility | Oakville | Automatic Valves - Butterfly (Bray) | BRAY CONTROLS CANADA LTD. | 4503791172 | Flow Control | Metal Control Valves | USD | 18570 | USD | 18570 | 0 | Supplier Competitions / Negotiation | 2022-02-19 | 2022-03-23 | 2022-05-04 | 2022-03-12 | 2022-05-04 | 2022-05-04 | 2022-03-19 | 2022-05-15 | 2022-10-01 | 2022-12-16 | 2022-11-08 | 38 | 12 | 53
508309 | City of Chandler Reclaimed Water Interconnect Facility | Oakville | Butterfly Valves & Check Valves | BRAY CONTROLS CANADA LTD | 4503838206 | Flow Control | Metal Isolation Valves | USD | 71845 | USD | 83415 | -11570 | Size/ Weight/ Quantity Underestimated | 2022-06-11 | 2022-08-02 | 2022-08-05 | 2022-07-02 | 2022-08-08 | 2022-09-08 | 2022-07-09 | 2022-08-09 | 2022-10-01 | 2022-12-06 | 2022-11-03 | 33 | 12 | 7
508309 | City of Chandler Reclaimed Water Interconnect Facility | Oakville | Frames & Brackets | 3D MECHANICAL | 4503826377 | Fabrication | Platform & Module | USD | 30102 | CAD | 54230 | -24128 | Single Sourced | 2022-05-28 | 2022-07-05 | 2022-07-12 | 2022-06-18 | 2022-07-13 | 2022-07-30 | 2022-06-25 | 2022-07-14 | 2022-10-01 | 2022-09-09 | 2022-09-20 | -11 | 12 | 9
508309 | City of Chandler Reclaimed Water Interconnect Facility | Oakville | Instruments | CAROTEK | 4503843962 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 20725 | USD | 27293 | -6568 | Size/ Weight/ Quantity Underestimated | 2022-08-17 | 2022-04-14 | 2022-04-14 | 2022-08-17 | 2022-08-12 | 2022-08-17 | 2022-08-17 | 2022-08-16 | 2022-08-17 | 2022-12-21 | 2022-10-19 | 63 | 18 | 124
508327 | Smithfield Foods | Minnetonka | Brackets SS316 (Loose shipped) | 3D MECHANICAL | 4503699031 | Fabrication | Stainless Steel | USD | 7766 | USD | 7714 | 52 | Frame Agreements | 2021-09-15 | 2021-11-16 | 2021-11-23 | 2021-09-29 | 2021-11-30 | 2021-11-14 | 2021-10-13 | 2021-12-06 | 2021-11-24 | 2022-01-14 | 2021-12-19 | 26 | 12 | 20
508327 | Smithfield Foods | Minnetonka | Hypo & Acid Feed Skid | PROMINENT FLUID CONTROLS LTD. | 4503675407 | Fabrication | Skid Assembly Outsourced | USD | 24000 | USD | 22270 | 1730 | Design Optimizations | 2021-09-03 | 2021-10-05 | 2021-10-12 | 2021-09-24 | 2021-10-16 | 2021-11-12 | 2021-10-08 | 2021-10-23 | 2022-01-21 | 2022-01-05 | 2022-01-13 | -8 | 12 | 18
508327 | Smithfield Foods | Minnetonka | Process Pump Skids | ASLAN TECHNOLOGIES | 4503693835 | Fabrication | Skid Assembly Outsourced | USD | 49702 | USD | 52361 | -2659 | Market Impact | 2021-09-03 | 2021-11-08 | 2021-11-15 | 2021-09-24 | 2021-11-20 | 2021-11-12 | 2021-10-08 | 2021-11-27 | 2022-01-21 | 2021-11-27 | 2021-12-24 | -27 | 12 | 19
508327 | Smithfield Foods | Minnetonka | Spools SS316 (Shipped Loose) | NV PIPING SYSTEMS INC. | 4503695754 | Fabrication | Stainless Steel | USD | 65000 | USD | 63960 | 1040 | Design Optimizations | 2021-09-30 | 2021-11-10 | 2021-11-18 | 2021-10-21 | 2021-11-24 | 2021-12-06 | 2021-10-28 | 2021-12-01 | 2021-12-09 | 2022-02-11 | 2022-01-10 | 32 | 12 | 21
508327 | Smithfield Foods | Minnetonka | Spools SS316 (Shipped Loose) | NV PIPING SYSTEMS INC. | 4503716634 | Fabrication | Stainless Steel | USD | 23000 | USD | 22128 | 872 | Frame Agreements | 2021-09-30 | 2021-11-02 | 2021-11-09 | 2021-10-14 | 2021-11-14 | 2021-11-14 | 2021-10-21 | 2021-11-21 | 2021-12-09 | 2021-12-29 | 2021-12-19 | 10 | 12 | 19
508327 | Smithfield Foods | Minnetonka | Frame Weldment (SS) | PROCESS GROUP INTERNATIONAL LIMITED | 4503716571 | Fabrication | Stainless Steel | USD | 40000 | USD | 25280 | 14720 | Design Optimizations | 2021-12-02 | 2021-11-05 | 2021-11-12 | 2021-12-02 | 2021-11-16 | 2021-12-02 | 2021-12-02 | 2021-11-23 | 2021-12-02 | 2021-12-29 | 2021-12-15 | 14 | 12 | 18
508327 | Smithfield Foods | Minnetonka | Frame Weldment (SS) | 3D MECHANICAL | 4503700192 | Fabrication | Stainless Steel | USD | 50000 | USD | 49044 | 956 | Design Optimizations | 2021-12-02 | 2021-12-01 | 2021-11-25 | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2021-12-02 | 2021-12-09 | 2021-12-02 | 2021-12-09 | 2021-12-05 | 4 | 12 | 8
508327 | Smithfield Foods | Minnetonka | Piston Compressor (lead time?) | DV Systems Inc | 4503692964 | Rotating Equipment | Compressors | USD | 13440 | USD | 19570 | -6130 | Size/ Weight/ Quantity Underestimated | 2021-09-30 | 2021-09-29 | 2021-10-06 | 2021-10-14 | 2021-10-10 | 2021-11-07 | 2021-10-21 | 2021-10-17 | 2021-12-16 | 2021-12-15 | 2021-12-15 | 0 | 30 | 18
508327 | Smithfield Foods | Minnetonka | Blowers | AERZEN CANADA INC | 4503655845 | Rotating Equipment | Blowers & Fans | USD | 64290 | USD | 69360 | -5070 | Proposed Supplier Incapable Of Executing | 2021-09-15 | 2021-09-01 | 2021-09-08 | 2021-10-06 | 2021-09-14 | 2021-11-07 | 2021-10-13 | 2021-09-21 | 2021-12-01 | 2022-01-14 | 2021-12-23 | 22 | 30 | 20
508327 | Smithfield Foods | Minnetonka | Rotary Lobe Pumps (Skidded) | BOERGER LLC | 4503655826 | Rotating Equipment | PD Pumps | USD | 100880 | USD | 96364 | 4516 | Design Optimizations | 2021-09-03 | 2021-09-01 | 2021-09-08 | 2021-09-24 | 2021-09-14 | 2021-10-31 | 2021-10-01 | 2021-09-21 | 2021-11-26 | 2021-12-30 | 2021-12-13 | 17 | 30 | 20
508327 | Smithfield Foods | Minnetonka | Rotary Lobe Pumps (Loose) | BOERGER LLC | 4503670195 | Rotating Equipment | PD Pumps | USD | 17720 | USD | 13550 | 4170 | Design Optimizations | 2021-09-03 | 2021-09-28 | 2021-10-04 | 2021-09-24 | 2021-10-10 | 2021-11-12 | 2021-10-01 | 2021-10-17 | 2021-11-26 | 2022-01-21 | 2021-12-24 | 28 | 30 | 19
508327 | Smithfield Foods | Minnetonka | FRP Tanks Cover | Fiberglass Fabricators, INc | 4503705877 | Fabrication | Non-Metal Equipment | USD | 144302 | USD | 87000 | 57302 | Design Optimizations | 2021-10-29 | 2021-12-01 | 2021-12-03 | 2021-11-12 | 2021-12-10 | 2021-11-22 | 2021-11-19 | 2021-12-17 | 2021-12-17 | 2021-12-17 | 2021-12-17 | 0 | 12 | 16
508327 | Smithfield Foods | Minnetonka | Master Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503692092 | Electrical & Instrumentation | Ele-Control Panels | USD | 22275 | USD | 25804 | -3529 | Proposed Supplier Incapable Of Executing | 2021-10-08 | 2021-11-04 | 2021-11-11 | 2021-10-29 | 2021-11-16 | 2021-11-12 | 2021-11-05 | 2021-11-23 | 2021-12-17 | 2021-11-23 | 2021-12-05 | -12 | 18 | 19
508327 | Smithfield Foods | Minnetonka | RIO Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503717316 | Electrical & Instrumentation | Ele-Control Panels | USD | 46000 | USD | 48320 | -2320 | Market Impact | 2021-12-16 | 2021-11-04 | 2021-11-11 | 2021-12-16 | 2021-11-16 | 2021-12-16 | 2021-12-16 | 2021-11-23 | 2021-12-16 | 2022-01-27 | 2022-01-06 | 21 | 18 | 19
508327 | Smithfield Foods | Minnetonka | Level Transmitters (Loose Shipped) | ENDRESS + HAUSER CANADA LTD. | 4503677243 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 19726 | USD | 6918 | 12808 | Supplier Competitions / Negotiation | 2021-09-15 | 2021-10-07 | 2021-10-14 | 2021-10-06 | 2021-10-20 | 2021-11-10 | 2021-10-20 | 2021-10-27 | 2021-11-17 | 2022-01-05 | 2021-12-11 | 25 | 18 | 20
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | AC FILTERS, 96X144 | Arrow Tanks | 4503642322 | Fabrication | Stainless Steel | USD | 120000 | USD | 120000 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-25 | 2021-08-30 | 2021-10-20 | 2021-08-26 | 2021-08-30 | 2021-12-14 | 2021-12-16 | 2021-12-15 | 1 | 12 | 5
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | RO MEMBRANE RACK_HOUSINGS | PROTEC ARISAWA AMERICA INC | 4503635377 | Flow Control | Filters And Strainers (Incl Housings) | USD | 31316 | USD | 31316 | 0 | Frame Agreements | 2021-09-15 | 2021-08-16 | 2021-08-16 | 2021-09-17 | 2021-10-15 | 2021-10-15 | 2021-09-17 | 2021-12-09 | 2021-12-14 | 2021-12-09 | 2021-12-11 | -2 | 12 | 115
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | CIP SYSTEM TANK | Preferred Stainless Holdings | 4503652494 | Fabrication | Stainless Steel | USD | 34688 | USD | 45716 | -11028 | Estimate Without Market Reference(No Quote) | 2021-08-12 | 2021-08-29 | 2021-09-08 | 2021-08-30 | 2021-09-13 | 2021-10-14 | 2021-08-30 | 2021-09-16 | 2021-12-14 | 2021-12-16 | 2021-12-15 | 1 | 12 | 18
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | LS_BAG FILTER HOUSINGS | Duncan Co. | 4503640732 | Flow Control | Filters And Strainers (Incl Housings) | USD | 22847 | USD | 29428 | -6581 | Single Sourced | 2021-09-15 | 2021-08-25 | 2021-08-25 | 2021-09-17 | 2021-08-25 | 2021-11-04 | 2021-09-17 | 2021-08-25 | 2021-12-14 | 2022-01-14 | 2021-12-29 | 16 | 12 | 0
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | LS_CARTRIDGE FILTER HOUSINGS | Duncan Co. | 4513640732 | Flow Control | Filters And Strainers (Incl Housings) | USD | 12227 | USD | 15386 | -3159 | Single Sourced | 2021-09-15 | 2021-08-25 | 2021-08-25 | 2021-09-17 | 2021-08-25 | 2021-11-04 | 2021-09-17 | 2021-08-25 | 2021-12-14 | 2022-01-14 | 2021-12-29 | 16 | 12 | 0
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | LS_PRE-RO UV STERILIZER | ATLANTIUM | 4503653370 | Electrical & Instrumentation | Ele-Electrical Others | USD | 55144 | USD | 31225 | 23919 | Estimate Without Market Reference(No Quote) | 2021-09-15 | 2021-07-23 | 2021-07-23 | 2021-09-17 | 2021-09-09 | 2021-10-18 | 2021-09-17 | 2021-09-19 | 2021-12-14 | 2022-01-14 | 2021-12-29 | 16 | 12 | 58
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | LS_POST-RO UV STERILIZER | ATLANTIUM | 4513653370 | Electrical & Instrumentation | Ele-Electrical Others | USD | 60279 | USD | 37123 | 23156 | Estimate Without Market Reference(No Quote) | 2021-09-15 | 2021-07-23 | 2021-07-23 | 2021-09-17 | 2021-09-09 | 2021-10-21 | 2021-09-17 | 2021-09-19 | 2021-12-14 | 2022-01-19 | 2022-01-01 | 18 | 12 | 58
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | LS_MAIN CONTROL PANEL | PTS Products | 4503659206 | Electrical & Instrumentation | Ele-Control Panels | USD | 41834 | USD | 38567 | 3267 | Supplier Competitions / Negotiation | 2021-08-06 | 2021-09-21 | 2021-09-26 | 2021-08-18 | 2021-09-25 | 2021-09-27 | 2021-08-26 | 2021-09-26 | 2021-12-14 | 2021-12-08 | 2021-12-11 | -3 | 12 | 5
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | LS_MCE AND POEWER DIST PANEL | WERNER ELECTRIC | 4503641978 | Electrical & Instrumentation | Ele-Control Panels | USD | 134326 | USD | 106099 | 28227 | Supplier Competitions / Negotiation | 2021-09-02 | 2021-08-06 | 2021-08-17 | 2021-09-07 | 2021-08-23 | 2021-10-10 | 2021-09-08 | 2021-08-29 | 2021-12-14 | 2021-11-21 | 2021-12-02 | -11 | 12 | 23
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | DS_CHEMICAL FEED SKIDS | WASTECH CONTROLS & ENGINEERING, INC | 4503659214 | Flow Control | Other | USD | 99830 | USD | 94200 | 5630 | Supplier Competitions / Negotiation | 2021-10-15 | 2021-09-17 | 2021-09-27 | 2021-10-15 | 2021-09-28 | 2021-11-18 | 2021-10-15 | 2021-09-28 | 2021-12-14 | 2022-01-20 | 2022-01-01 | 19 | 12 | 11
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | DS_FEED, TREATED & TRICKLE WATER STORAGE TANKS | Augusta Fiberglass | 4503657989 | Fabrication | Stainless Steel | USD | 117048 | USD | 29315 | 87733 | Supplier Competitions / Negotiation | 2021-09-15 | 2021-08-26 | 2021-09-16 | 2021-09-17 | 2021-09-26 | 2021-11-14 | 2021-09-17 | 2021-09-26 | 2021-12-14 | 2022-02-03 | 2022-01-08 | 26 | 12 | 31
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | DS_ACF BW COLLECTION TANK | Augusta Fiberglass | 4513657989 | Fabrication | Non-Metal Equipment | USD | 15327 | USD | 21138 | -5811 | Estimate Without Market Reference(No Quote) | 2021-09-15 | 2021-08-26 | 2021-09-03 | 2021-09-17 | 2021-09-26 | 2021-11-12 | 2021-09-17 | 2021-09-26 | 2021-12-14 | 2022-01-30 | 2022-01-06 | 24 | 12 | 31
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | DS_TRICKLE TANK | Augusta Fiberglass | 4523657989 | Fabrication | Non-Metal Equipment | USD | 20754 | USD | 20754 | 0 | Design Optimizations | 2021-09-15 | 2021-08-26 | 2021-09-03 | 2021-09-17 | 2021-09-27 | 2021-11-15 | 2021-09-17 | 2021-09-27 | 2021-12-14 | 2022-02-04 | 2022-01-09 | 26 | 12 | 32
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | DS_TREATED WATER STORAGE TANKS | Preferred Stainless Holdings | 4513652494 | Fabrication | Stainless Steel | USD | 62373 | USD | 62373 | 0 | Market Impact | 2021-11-11 | 2021-08-29 | 2021-09-08 | 2021-11-11 | 2021-09-13 | 2021-11-11 | 2021-11-11 | 2021-09-16 | 2021-11-11 | 2022-01-25 | 2021-12-18 | 38 | 12 | 18
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | INSTALL - MECHANICAL | QUALITY STAINLESS | 4503753846 | Fabrication | Stainless Steel | USD | 31420 | USD | 31420 | 0 | Frame Agreements | 2022-02-24 | 2022-02-24 | 2022-02-10 | 2022-02-24 | 2022-02-10 | 2022-02-24 | 2022-02-24 | 2022-02-10 | 2022-02-24 | 2022-03-10 | 2022-03-03 | 7 | 12 | -14
508349 | PEPSI CHICAGO LTS UPGRADE | Minnetonka | LS_LOOSE SHIP KITS | AMERICAN ULTRAVIOLET | 4503674320 | Flow Control | Metal Control Valves | USD | 5980 | USD | 5980 | 0 | Not included in Proposal / RFQ | 2021-11-13 | 2021-11-13 | 2021-10-08 | 2021-11-13 | 2021-10-08 | 2021-11-13 | 2021-11-13 | 2021-10-25 | 2021-11-13 | 2021-12-20 | 2021-12-01 | 19 | 12 | -19
508353 | HP Hood Oneida | Minnetonka | CARBON TOWERS, 60X120, ASSY | Arrow Tanks | 4503632716 | Fabrication | Carbon Steel | USD | 92325 | USD | 92325 | 0 | Not included in Proposal / RFQ | 2021-08-10 | 2021-09-30 | 2021-08-10 | 2021-08-10 | 2021-08-10 | 2021-09-30 | 2021-08-10 | 2021-08-10 | 2021-10-21 | 2021-11-20 | 2021-11-05 | 15 | 12 | -51
508353 | HP Hood Oneida | Minnetonka | LS_CONTROL PANEL &LS KITS | BW Systems | 4503639902 | Electrical & Instrumentation | Ele-Control Panels | USD | 21465 | USD | 22100 | -635 | Not included in Proposal / RFQ | 2021-08-09 | 2021-09-24 | 2021-08-09 | 2021-08-12 | 2021-09-24 | 2021-09-24 | 2021-08-24 | 2021-08-24 | 2021-11-10 | 2021-10-12 | 2021-10-26 | -14 | 18 | -31
508353 | HP Hood Oneida | Minnetonka | LS_CARTRIDGE FILTERS/HOUSING | Duncan Co. | 4503638270 | Flow Control | Filters And Strainers (Incl Housings) | USD | 17627 | USD | 11505 | 6122 | Supplier Competitions / Negotiation | 2021-08-12 | 2021-09-14 | 2021-08-12 | 2021-08-12 | 2021-08-12 | 2021-09-14 | 2021-08-21 | 2021-08-12 | 2021-10-18 | 2021-10-15 | 2021-10-16 | -1 | 12 | -33
508378 | New Iberia | Richmond | Accelerator Mechanism ( Metal) | BURKES MECHANICAL | 4503679083 | Fabrication | Carbon Steel | USD | 509897 | USD | 350691 | 159206 | Design Optimizations | 2021-09-15 | 2021-08-26 | 2021-09-16 | 2021-10-28 | 2021-10-26 | 2021-12-16 | 2021-11-11 | 2021-10-31 | 2022-04-07 | 2022-03-27 | 2022-04-01 | -5 | 12 | 66
508378 | New Iberia | Richmond | Rotor/ Scrapper Drive- Eurodrive | SEW EURODRIVE | 4503655478 | Rotating Equipment | Electric Motors | USD | 47503 | USD | 26935 | 20568 | Design Optimizations | 2021-09-15 | 2021-08-14 | 2021-08-18 | 2021-11-22 | 2021-09-21 | 2021-12-10 | 2021-12-09 | 2021-09-22 | 2022-04-07 | 2021-11-06 | 2022-01-21 | -76 | 30 | 39
508390 | Pepsico Santa Anita Peru | Minnetonka | RAS Pump | GRUNDFOS PUMPS CORPORATION | 4503693906 | Rotating Equipment | Centrifugal Pumps | USD | 38695 | USD | 15907 | 22788 | Frame Agreements | 2021-10-19 | 2021-11-04 | 2021-11-18 | 2021-11-02 | 2021-11-24 | 2021-11-24 | 2021-11-16 | 2021-11-28 | 2022-02-15 | 2022-01-24 | 2022-02-04 | -11 | 30 | 24
508390 | Pepsico Santa Anita Peru | Minnetonka | Process Pump VFD | WERNER ELECTRIC | 4503693633 | Electrical & Instrumentation | Ele-Electrical Others | USD | 12827 | USD | 10254 | 2573 | Frame Agreements | 2021-11-02 | 2021-11-02 | 2021-11-08 | 2021-11-16 | 2021-11-24 | 2021-11-25 | 2021-11-30 | 2021-11-29 | 2022-02-15 | 2022-01-10 | 2022-01-28 | -18 | 18 | 27
508395 | Gods Lake First Nation (West WTP) | Oakville | Dosing Panel-System-CFO | PROMINENT FLUID CONTROLS LTD. | 4503822685 | Rotating Equipment | Chem. Feed Skids (Turnkey) | CAD | 21664 | USD | 21664 | 0 | Proposed Supplier Incapable Of Executing | 2022-07-10 | 2022-04-28 | 2021-10-26 | 2022-07-17 | 2022-04-28 | 2022-04-28 | 2022-07-24 | 2022-07-17 | 2022-10-30 | 2022-10-02 | 2022-10-16 | -14 | 30 | 80
508395 | Gods Lake First Nation (West WTP) | Oakville | Air Compressor | Compressor Science | 4503820569 | Rotating Equipment | Compressors | CAD | 22845 | USD | 25747 | -2902 | Proposed Supplier Incapable Of Executing | 2022-02-06 | 2022-07-07 | 2022-06-21 | 2022-02-13 | 2022-07-07 | 2022-07-07 | 2022-02-20 | 2022-07-04 | 2022-10-30 | 2022-12-05 | 2022-11-17 | 18 | 30 | -3
508395 | Gods Lake First Nation (West WTP) | Oakville | Storage Tanks | ACO CONTAINER SYSTEMS LTD. | 4503820468 | Fabrication | Non-Metal Equipment | CAD | 13266 | CAD | 9828 | 3438 | Supplier Competitions / Negotiation | 2022-07-24 | 2022-08-25 | 2022-06-21 | 2022-07-31 | 2022-08-25 | 2022-08-25 | 2022-08-07 | 2022-07-15 | 2022-10-30 | 2022-09-23 | 2022-10-11 | -18 | 12 | -41
508395 | Gods Lake First Nation (West WTP) | Oakville | Control panels | KELTOUR CONTROLS INC. | 4503828999 | Electrical & Instrumentation | Ele-Control Panels | CAD | 49648 | CAD | 48590 | 1058 | Supplier Competitions / Negotiation | 2022-04-17 | 2022-09-30 | 2022-07-06 | 2022-04-24 | 2022-09-30 | 2022-09-30 | 2022-05-01 | 2022-07-20 | 2022-10-30 | 2023-03-15 | 2023-01-06 | 68 | 18 | -72
508395 | Gods Lake First Nation (West WTP) | Oakville | Piping | NV PIPING SYSTEMS INC. | 4503821769 | Fabrication | Stainless Steel | CAD | 7200 | CAD | 6585 | 615 | Design Optimizations | 2022-07-10 | 2022-09-01 | 2022-07-04 | 2022-07-17 | 2022-09-01 | 2022-09-01 | 2022-07-24 | 2022-07-07 | 2022-10-30 | 2022-09-29 | 2022-10-14 | -15 | 12 | -56
508395 | Gods Lake First Nation (West WTP) | Oakville | Tank Mixer | DYNAMIX | 4503820502 | Rotating Equipment | Mixers | CAD | 10000 | CAD | 10861 | -861 | Not included in Proposal / RFQ | 2022-05-29 | 2022-08-14 | 2022-06-22 | 2022-06-05 | 2022-08-14 | 2022-08-14 | 2022-06-12 | 2022-07-04 | 2022-10-30 | 2022-09-12 | 2022-10-06 | -24 | 30 | -41
508417 | MP Materials Lifecycle Project | Oakville | PIPE,SPOOLS,FITTINGS,FLANGES,VALVES | Samuel Engineering | 4503677795 | Fabrication | Stainless Steel | USD | 320930 | USD | 320930 | 0 | Proposed Supplier Incapable Of Executing | 2021-10-01 | 2021-12-12 | 2021-10-15 | 2021-10-15 | 2021-10-15 | 2021-12-12 | 2021-10-29 | 2021-10-29 | 2022-02-22 | 2022-02-22 | 2022-02-22 | 0 | 12 | -44
508417 | MP Materials Lifecycle Project | Oakville | Pump | Flowserve US Inc. | 4503683294 | Rotating Equipment | Centrifugal Pumps | USD | 27120 | USD | 88008 | -60888 | Estimate Without Market Reference(No Quote) | 2021-10-19 | 2021-12-22 | 2021-10-25 | 2021-10-26 | 2021-10-24 | 2021-12-22 | 2021-11-09 | 2021-11-08 | 2022-02-24 | 2022-02-23 | 2022-02-23 | 0 | 30 | -44
508444 | Texas Quality Bev | Minnetonka | ACTIVATED CARBON TOWERS | Arrow Tanks | 4503640763 | Fabrication | Stainless Steel | USD | 119000 | USD | 103600 | 15400 | Supplier Competitions / Negotiation | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-08-17 | 2021-08-25 | 2021-10-15 | 2021-08-24 | 2021-08-25 | 2021-12-13 | 2021-12-13 | 2021-12-13 | 0 | 12 | 8
508444 | Texas Quality Bev | Minnetonka | LS_RO PERMEATE UV STERILIZER | Trojan Technologies INC. | 4503657366 | Electrical & Instrumentation | Ele-Electrical Others | USD | 19800 | USD | 10825 | 8975 | Design Optimizations | 2021-09-17 | 2021-10-29 | 2021-09-23 | 2021-09-20 | 2021-09-24 | 2021-10-29 | 2021-09-20 | 2021-09-24 | 2021-12-10 | 2021-11-19 | 2021-11-29 | -10 | 18 | -35
508469 | Intel Kulim CO2DI Skid | Oakville | Electrical Panels | MACHINE CONTROL SYSTEMS | 4503674294 | Electrical & Instrumentation | Ele-Control Panels | USD | 52638 | CAD | 55032 | -2394 | Supplier Competitions / Negotiation | 2021-10-11 | 2021-10-10 | 2021-10-08 | 2021-11-22 | 2021-10-16 | 2021-12-01 | 2021-11-29 | 2021-10-21 | 2022-01-24 | 2021-12-16 | 2022-01-04 | -19 | 18 | 11
508469 | Intel Kulim CO2DI Skid | Oakville | Motor Starter | ISG | 4503671657 | Electrical & Instrumentation | Ele-Control Panels | USD | 8532 | USD | 8532 | 0 | Supplier Competitions / Negotiation | 2021-11-30 | 2021-09-30 | 2021-09-21 | 2021-11-30 | 2021-09-26 | 2021-11-30 | 2021-11-30 | 2021-10-16 | 2021-11-30 | 2022-02-09 | 2022-01-04 | 36 | 18 | 16
508469 | Intel Kulim CO2DI Skid | Oakville | Skids assembly (Including Mechanical & Electrical Bulk) | ASLAN TECHNOLOGIES | 450370289 | Fabrication | Skid Assembly Outsourced | USD | 78660 | CAD | 141942 | -63282 | Estimate Without Market Reference(No Quote) | 2021-10-25 | 2021-11-10 | 2021-11-29 | 2021-12-06 | 2021-12-03 | 2022-01-01 | 2021-12-13 | 2021-12-13 | 2022-01-24 | 2022-03-10 | 2022-02-15 | 23 | 12 | 33
508469 | Intel Kulim CO2DI Skid | Oakville | Ultrasonic Flow Transmitters | ENDRESS + HAUSER CANADA LTD. | 4503664850 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 25708 | USD | 21716 | 3992 | Design Optimizations | 2021-10-18 | 2021-10-01 | 2021-09-10 | 2021-11-01 | 2021-09-24 | 2021-11-17 | 2021-11-08 | 2021-10-04 | 2022-01-24 | 2021-11-19 | 2021-12-22 | -33 | 18 | 3
508469 | Intel Kulim CO2DI Skid | Oakville | Transmitters | LAKESIDE PROCESS CONTROLS LTD. | 4503674281 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 11706 | USD | 11706 | 0 | Market Impact | 2021-11-01 | 2021-10-01 | 2021-10-12 | 2021-11-01 | 2021-10-08 | 2021-11-01 | 2021-11-01 | 2021-10-22 | 2021-11-01 | 2021-12-02 | 2021-11-16 | 16 | 18 | 21
508469 | Intel Kulim CO2DI Skid | Oakville | HDPE Tanks | TERRACON CORP | 4503666998 | Fabrication | Non-Metal Equipment | USD | 15978 | USD | 14806 | 1172 | Supplier Competitions / Negotiation | 2021-09-06 | 2021-08-31 | 2021-09-01 | 2021-10-11 | 2021-09-17 | 2021-11-12 | 2021-10-18 | 2021-10-08 | 2022-01-24 | 2021-12-28 | 2022-01-10 | -13 | 12 | 38
508469 | Intel Kulim CO2DI Skid | Oakville | PVC Valves (Ball, Diaphragm, Needle) | GEORG FISCHER PIPING SYSTEMS LTD | 4503672023 | Flow Control | Plastic Valves (All) | USD | 7548 | USD | 10362 | -2814 | Not included in Proposal / RFQ | 2021-11-11 | 2021-10-10 | 2021-10-18 | 2021-12-16 | 2021-10-08 | 2021-12-01 | 2021-12-20 | 2021-10-12 | 2022-01-24 | 2021-11-19 | 2021-12-22 | -33 | 12 | 2
508469 | Intel Kulim CO2DI Skid | Oakville | Sliding Gate and Fractional Flow Control Valves | Jenkinson an Company | 4503682498 | Flow Control | Metal Control Valves | USD | 21642 | CAD | 22653 | -1011 | Single Sourced | 2021-10-04 | 2021-09-08 | 2021-09-21 | 2021-11-08 | 2021-10-23 | 2021-11-16 | 2021-11-15 | 2021-11-06 | 2022-01-24 | 2021-12-14 | 2022-01-03 | -20 | 12 | 59
508469 | Intel Kulim CO2DI Skid | Oakville | Globe Valves (Baumann) | LAKESIDE PROCESS CONTROLS LTD. | 4503663093 | Flow Control | Metal Control Valves | USD | 11702 | USD | 13644 | -1942 | Market Impact | 2021-10-04 | 2021-09-08 | 2021-09-15 | 2021-11-08 | 2021-09-21 | 2021-11-16 | 2021-11-15 | 2021-10-03 | 2022-01-24 | 2022-01-19 | 2022-01-21 | -2 | 12 | 25
508469 | Intel Kulim CO2DI Skid | Oakville | Conservation and N2 Blanketing Valves (Protectoseal) | Great Lakes Industrial Controls | 4503664859 | Flow Control | Metal Safety(relief) Valves | USD | 23108 | CAD | 26240 | -3132 | Not included in Proposal / RFQ | 2021-08-23 | 2021-09-10 | 2021-09-21 | 2021-09-27 | 2021-10-01 | 2021-11-08 | 2021-10-04 | 2021-10-05 | 2022-01-24 | 2021-12-31 | 2022-01-12 | -12 | 12 | 25
508500 | Chobani City Water ROs | Minnetonka | RO PROFLEX-72_MCP | BW Systems | 4503654475 | Electrical & Instrumentation | Ele-Control Panels | USD | 39000 | USD | 36070 | 2930 | Design Optimizations | 2021-09-21 | 2021-11-08 | 2021-09-21 | 2021-09-21 | 2021-09-17 | 2021-11-08 | 2021-09-22 | 2021-09-17 | 2021-12-30 | 2021-12-26 | 2021-12-28 | -2 | 18 | -52
508500 | Chobani City Water ROs | Minnetonka | CIP SYSTEM_ASSY | Chromalox Inc. | 4503662782 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | USD | 8296 | USD | 8296 | 0 | Not included in Proposal / RFQ | 2021-11-09 | 2021-10-05 | 2021-10-05 | 2021-11-09 | 2021-10-05 | 2021-11-09 | 2021-11-09 | 2021-10-05 | 2021-11-09 | 2021-12-14 | 2021-11-26 | 18 | 18 | 0
508500 | Chobani City Water ROs | Minnetonka | RO PROFLEX-72_ASSY | R&R Metalworks | 4503675188 | Fabrication | Stainless Steel | USD | 11700 | USD | 11700 | 0 | Size/ Weight/ Quantity Underestimated | 2021-11-08 | 2021-10-26 | 2021-10-26 | 2021-11-08 | 2021-10-26 | 2021-11-08 | 2021-11-08 | 2021-10-26 | 2021-11-08 | 2021-11-22 | 2021-11-15 | 7 | 12 | 0
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Chemical dosing system | PROMINENT FLUID CONTROLS (FE) PTE L | 4503763567 | Rotating Equipment | Chem. Feed Skids (Turnkey) | CAD | 161620 | CAD | 154459 | 7161 | Frame Agreements | 2021-11-05 | 2022-01-21 | 2022-02-17 | 2021-11-18 | 2022-03-23 | 2022-01-29 | 2021-12-21 | 2022-03-27 | 2021-07-24 | 2022-08-07 | 2022-01-29 | 190 | 30 | 65
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Control panels | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503729236 | Electrical & Instrumentation | Ele-Control Panels | CAD | 94000 | CAD | 111105 | -17105 | Proposed Supplier Incapable Of Executing | 2021-11-05 | 2021-12-02 | 2021-12-10 | 2021-11-18 | 2022-01-23 | 2021-12-22 | 2021-12-21 | 2022-01-30 | 2021-07-24 | 2022-05-22 | 2021-12-22 | 151 | 18 | 59
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Process Pump | FLOWSERVE | 4503734120 | Rotating Equipment | PD Pumps | CAD | 70694 | USD | 58775 | 11919 | Design Optimizations | 2021-11-05 | 2021-11-20 | 2021-11-24 | 2021-11-18 | 2022-02-03 | 2021-12-17 | 2021-12-21 | 2022-02-08 | 2021-07-24 | 2022-05-12 | 2021-12-17 | 146 | 30 | 80
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Floculataion Tanks | PRECISIONEERING | 4503722665 | Fabrication | Non-Metal Equipment | CAD | 69223 | CAD | 69500 | -277 | Specs / Requirements Misinterpreted in Proposal | 2021-11-05 | 2021-12-18 | 2021-12-20 | 2021-11-18 | 2022-01-18 | 2021-12-09 | 2021-12-21 | 2022-01-19 | 2021-07-24 | 2022-04-27 | 2021-12-09 | 139 | 12 | 32
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Mixers | DYNAMIX | 4503710114 | Rotating Equipment | Mixers | CAD | 27785 | CAD | 17296 | 10489 | Supplier Competitions / Negotiation | 2021-11-05 | 2020-12-12 | 2020-12-13 | 2021-11-18 | 2021-12-30 | 2021-09-19 | 2021-12-21 | 2021-12-30 | 2021-07-24 | 2022-06-27 | 2022-01-09 | 169 | 30 | 383
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Auto strainer | BOLL FILTER CORPORATION | 4503710062 | Flow Control | Other | CAD | 30061 | USD | 25184 | 4877 | Supplier Competitions / Negotiation | 2021-11-05 | 2021-11-13 | 2021-11-17 | 2021-11-18 | 2021-12-28 | 2022-01-14 | 2021-12-21 | 2021-12-30 | 2021-07-24 | 2022-07-07 | 2022-01-14 | 174 | 12 | 47
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Fabrication - Frames & Lifting Modules | PLASFAB LIMITED | 4503729235 | Fabrication | Stainless Steel | CAD | 32705 | CAD | 51004 | -18299 | Single Sourced | 2021-11-05 | 2022-01-10 | 2022-01-17 | 2021-11-18 | 2021-12-31 | 2021-12-20 | 2021-12-21 | 2022-01-31 | 2021-07-24 | 2022-05-18 | 2021-12-20 | 149 | 12 | 21
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Membrane Kit | 3D MECHANICAL | 4503758203 | Fabrication | Stainless Steel | CAD | 7420 | CAD | 7420 | 0 | Size/ Weight/ Quantity Underestimated | 2021-11-05 | 2021-12-17 | 2022-03-28 | 2021-11-18 | 2022-03-11 | 2021-12-17 | 2021-12-21 | 2022-03-17 | 2021-07-24 | 2022-05-12 | 2021-12-17 | 146 | 12 | 90
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Blower | AERZEN CANADA INC | 4503709939 | Rotating Equipment | Blowers & Fans | CAD | 19860 | CAD | 20900 | -1040 | Not included in Proposal / RFQ | 2021-11-05 | 2021-12-15 | 2021-12-22 | 2021-11-18 | 2021-12-27 | 2021-11-28 | 2021-12-21 | 2021-12-28 | 2021-07-24 | 2022-04-05 | 2021-11-28 | 128 | 30 | 13
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Chemical Tanks | ACO CONTAINER SYSTEMS LTD. | 4503708403 | Fabrication | Non-Metal Equipment | CAD | 26199 | CAD | 28785 | -2586 | Size/ Weight/ Quantity Underestimated | 2021-11-05 | 2021-11-25 | 2021-11-30 | 2021-11-18 | 2021-12-21 | 2021-11-04 | 2021-12-21 | 2021-12-21 | 2021-07-24 | 2022-02-15 | 2021-11-04 | 103 | 12 | 26
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Air Compressor | Compressor Science | 4503709932 | Rotating Equipment | Compressors | CAD | 19040 | USD | 19788 | -748 | Not included in Proposal / RFQ | 2021-11-05 | 2021-12-25 | 2021-12-28 | 2021-11-18 | 2021-12-28 | 2021-12-28 | 2021-12-21 | 2021-12-29 | 2021-07-24 | 2022-06-04 | 2021-12-28 | 158 | 30 | 4
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Heater | ASB HEATING ELEMENTS LIMITED | 4503709937 | Fabrication | Process Equipment | CAD | 8403 | CAD | 8190 | 213 | Design Optimizations | 2021-11-05 | 2020-12-12 | 2020-12-16 | 2021-11-18 | 2021-12-17 | 2021-09-20 | 2021-12-21 | 2021-12-29 | 2021-07-24 | 2022-06-30 | 2022-01-10 | 171 | 12 | 382
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Turbidity Meter | SCG Process | 4503734131 | Electrical & Instrumentation | Inst-Analytical Instruments | CAD | 21133 | CAD | 16420 | 4713 | Supplier Competitions / Negotiation | 2021-11-05 | 2021-12-12 | 2021-12-15 | 2021-11-18 | 2022-02-06 | 2021-12-06 | 2021-12-21 | 2022-02-06 | 2021-07-24 | 2022-04-20 | 2021-12-06 | 135 | 18 | 56
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Level Transmitter | ENDRESS & HAUSER | 4503734112 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | CAD | 22241 | USD | 25486 | -3245 | Specs / Requirements Misinterpreted in Proposal | 2021-11-05 | 2021-11-20 | 2021-11-26 | 2021-11-18 | 2022-02-07 | 2021-12-05 | 2021-12-21 | 2022-02-07 | 2021-07-24 | 2022-04-18 | 2021-12-05 | 134 | 18 | 79
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Skid Butterfly Valve | BRAY CONTROLS CANADA LTD. | 4503737897 | Flow Control | Metal Control Valves | CAD | 32485 | USD | 33138 | -653 | Size/ Weight/ Quantity Underestimated | 2021-11-05 | 2021-11-29 | 2021-12-01 | 2021-11-18 | 2022-02-08 | 2021-12-14 | 2021-12-21 | 2022-02-12 | 2021-07-24 | 2022-05-07 | 2021-12-14 | 144 | 12 | 75
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Static Mixer | STATIFLO INC. | 4503709974 | Rotating Equipment | Mixers | CAD | 21290 | CAD | 21320 | -30 | Market Impact | 2022-03-12 | 2021-11-25 | 2021-11-30 | 2022-03-12 | 2021-12-28 | 2022-03-12 | 2022-03-12 | 2021-12-29 | 2022-03-12 | 2022-06-27 | 2022-05-04 | 54 | 30 | 34
508614 | Chisasibi Water Treatment Plant - Equipment Order | Oakville | Spares Butterfly Valve | BRAY CONTROLS CANADA LTD. | 4503738369 | Flow Control | Metal Control Valves | CAD | 6238 | USD | 6434 | -196 | Not included in Proposal / RFQ | 2022-03-23 | 2022-02-12 | 2022-02-15 | 2022-03-23 | 2022-02-15 | 2022-03-23 | 2022-03-23 | 2022-02-15 | 2022-03-23 | 2022-05-02 | 2022-04-12 | 20 | 12 | 3
508703 | 3M Cottage Grove, MN | Oakville | Electrical Panels | ENGINEERING ELECTRIC CONTROLS | 4503764768 | Electrical & Instrumentation | Ele-Control Panels | USD | 195559 | USD | 158975 | 36584 | Supplier Competitions / Negotiation | 2021-12-03 | 2022-01-24 | 2022-02-24 | 2021-12-31 | 2022-03-17 | 2022-04-17 | 2022-01-14 | 2022-03-20 | 2022-05-20 | 2022-08-30 | 2022-07-10 | 51 | 18 | 55
508703 | 3M Cottage Grove, MN | Oakville | Panel - Long Lead AB | ELECTRICAL EQUIPMENT COMP | 4503735682 | Electrical & Instrumentation | Ele-PLCs, HMIs | USD | 170000 | USD | 163590 | 6410 | Supplier Competitions / Negotiation | 2021-12-03 | 2022-01-27 | 2022-01-20 | 2021-12-31 | 2022-02-07 | 2022-02-25 | 2022-01-14 | 2022-02-10 | 2022-05-20 | 2022-04-22 | 2022-05-06 | -14 | 18 | 14
508703 | 3M Cottage Grove, MN | Oakville | Self Cleaning Strainer | BOLL FILTER CORPORATION | 4503730344 | Flow Control | Filters And Strainers (Incl Housings) | USD | 153084 | USD | 147033 | 6051 | Specs / Requirements Misinterpreted in Proposal | 2021-12-03 | 2022-01-06 | 2022-01-13 | 2021-12-31 | 2022-01-05 | 2022-02-27 | 2022-01-14 | 2022-02-02 | 2022-05-20 | 2022-05-25 | 2022-05-22 | 3 | 12 | 27
508703 | 3M Cottage Grove, MN | Oakville | Cartridge Filter Housing | JOHN BROOKS COMPANY LTD. | 4503730781 | Fabrication | Process Equipment | USD | 225917 | CAD | 253488 | -27571 | Single Sourced | 2021-12-09 | 2021-12-07 | 2021-12-10 | 2022-01-06 | 2021-12-09 | 2022-03-01 | 2022-01-20 | 2022-02-02 | 2022-05-20 | 2022-05-25 | 2022-05-22 | 3 | 12 | 57
508703 | 3M Cottage Grove, MN | Oakville | Static Mixer | Komax Systems | 4503773183 | Flow Control | Static Mixer | USD | 56461 | USD | 149120 | -92659 | Market Impact | 2021-12-15 | 2022-01-17 | 2022-02-21 | 2022-01-12 | 2022-03-29 | 2022-05-18 | 2022-01-26 | 2022-04-12 | 2022-10-20 | 2022-08-30 | 2022-09-24 | -25 | 12 | 85
508703 | 3M Cottage Grove, MN | Oakville | Basket Strainers | JOHN BROOKS COMPANY LTD. | 4503736907 | Flow Control | Filters And Strainers (Incl Housings) | USD | 37143 | CAD | 51252 | -14109 | Single Sourced | 2021-12-09 | 2021-11-26 | 2021-12-10 | 2022-01-06 | 2021-12-12 | 2022-02-25 | 2022-01-20 | 2022-02-11 | 2022-05-20 | 2022-05-27 | 2022-05-23 | 4 | 12 | 77
508703 | 3M Cottage Grove, MN | Oakville | UF Blower | AERZEN CANADA INC | 4503755896 | Rotating Equipment | Blowers & Fans | USD | 57679 | CAD | 62416 | -4737 | Specs / Requirements Misinterpreted in Proposal | 2021-12-28 | 2022-01-04 | 2022-02-28 | 2022-01-25 | 2022-03-09 | 2022-05-25 | 2022-02-08 | 2022-03-15 | 2022-10-21 | 2022-10-03 | 2022-10-12 | -9 | 30 | 70
508703 | 3M Cottage Grove, MN | Oakville | MBR Blower - Aerzen | AERZEN CANADA INC | 4503755869 | Rotating Equipment | Blowers & Fans | USD | 14797 | CAD | 24792 | -9995 | Specs / Requirements Misinterpreted in Proposal | 2021-12-28 | 2022-11-12 | 2022-02-28 | 2022-01-25 | 2022-03-09 | 2022-06-05 | 2022-02-08 | 2022-03-15 | 2022-10-21 | 2022-10-03 | 2022-10-12 | -9 | 30 | -242
508703 | 3M Cottage Grove, MN | Oakville | Pumps Sulzer | SULZER PUMPS (CANADA) IN | 4503737931 | Rotating Equipment | Centrifugal Pumps | USD | 433545 | USD | 405897 | 27648 | Single Sourced | 2021-12-03 | 2021-11-26 | 2022-01-17 | 2021-12-31 | 2022-01-30 | 2022-03-05 | 2022-01-14 | 2022-02-14 | 2022-05-20 | 2022-06-13 | 2022-06-01 | 12 | 30 | 80
508703 | 3M Cottage Grove, MN | Oakville | Frames - Guelph | 3D MECHANICAL | 4503760600 | Fabrication | Carbon Steel | USD | 509440 | CAD | 502850 | 6590 | Supplier Competitions / Negotiation | 2022-01-19 | 2022-01-28 | 2022-02-14 | 2022-02-16 | 2022-02-20 | 2022-03-20 | 2022-03-02 | 2022-03-02 | 2022-05-20 | 2022-05-14 | 2022-05-17 | -3 | 12 | 33
508703 | 3M Cottage Grove, MN | Oakville | Frames - Minnetonka | GRUPO METELMEX SA DE CV | 4503756127 | Fabrication | Carbon Steel | USD | 40000 | USD | 34268 | 5732 | Supplier Competitions / Negotiation | 2022-01-19 | 2022-01-28 | 2022-03-09 | 2022-02-16 | 2022-03-03 | 2022-04-05 | 2022-03-02 | 2022-03-15 | 2022-05-20 | 2022-06-20 | 2022-06-04 | 16 | 12 | 46
508703 | 3M Cottage Grove, MN | Oakville | SS Piping - Guelph | NV PIPING SYSTEMS INC. | 4503759891 | Fabrication | Stainless Steel | USD | 929746 | CAD | 948772 | -19026 | Supplier Competitions / Negotiation | 2022-01-19 | 2022-01-28 | 2022-02-16 | 2022-02-16 | 2022-02-23 | 2022-03-20 | 2022-03-02 | 2022-02-28 | 2022-05-20 | 2022-05-19 | 2022-05-19 | 0 | 12 | 31
508703 | 3M Cottage Grove, MN | Oakville | SS Piping - Mn | NV PIPING SYSTEMS INC. | 4503771124 | Fabrication | Stainless Steel | USD | 70000 | CAD | 57600 | 12400 | Supplier Competitions / Negotiation | 2022-01-19 | 2022-01-28 | 2022-04-06 | 2022-02-16 | 2022-04-07 | 2022-04-24 | 2022-03-02 | 2022-04-08 | 2022-05-20 | 2022-07-29 | 2022-06-24 | 35 | 12 | 70
508703 | 3M Cottage Grove, MN | Oakville | RO Housings Protec | PROTEC ARISAWA AMERICA INC | 4503730331 | Fabrication | Process Equipment | USD | 367671 | USD | 351979 | 15692 | Supplier Competitions / Negotiation | 2021-12-03 | 2021-11-25 | 2021-12-10 | 2021-12-31 | 2021-12-15 | 2022-02-21 | 2022-01-14 | 2022-02-02 | 2022-05-20 | 2022-04-13 | 2022-05-01 | -18 | 12 | 69
508703 | 3M Cottage Grove, MN | Oakville | HDPE Tank | ACO CONTAINER SYSTEMS LTD. | 4503772385 | Fabrication | Non-Metal Equipment | USD | 120868 | CAD | 108983 | 11885 | Single Sourced | 2021-12-16 | 2021-12-21 | 2022-01-03 | 2022-01-13 | 2022-04-06 | 2022-05-19 | 2022-01-27 | 2022-04-10 | 2022-10-21 | 2022-10-20 | 2022-10-20 | 0 | 12 | 110
508703 | 3M Cottage Grove, MN | Oakville | FRP Tank | PRECISIONEERING | 4503802027 | Fabrication | Non-Metal Equipment | USD | 98027 | CAD | 114400 | -16373 | Supplier Competitions / Negotiation | 2021-12-23 | 2022-01-31 | 2022-03-29 | 2022-01-20 | 2022-05-31 | 2022-05-23 | 2022-02-03 | 2022-06-02 | 2022-10-21 | 2022-10-21 | 2022-10-21 | 0 | 12 | 122
508703 | 3M Cottage Grove, MN | Oakville | Instrumentation - Hach | Hach Sales & Service Canada Ltd. | 4503770575 | Electrical & Instrumentation | Ele-Control Panels | USD | 38220 | CAD | 18729 | 19491 | Single Sourced | 2021-12-24 | 2022-03-21 | 2022-02-17 | 2022-01-21 | 2022-04-05 | 2022-03-21 | 2022-02-04 | 2022-04-07 | 2022-05-20 | 2022-06-16 | 2022-06-02 | 14 | 18 | 17
508703 | 3M Cottage Grove, MN | Oakville | Valves - PRV Farris - CFO | Great Lakes Industrial Controls | 4503778409 | Flow Control | Metal Control Valves | USD | 42443 | CAD | 44864 | -2421 | Single Sourced | 2021-12-16 | 2022-04-23 | 2022-02-09 | 2022-01-13 | 2022-04-14 | 2022-04-23 | 2022-01-27 | 2022-04-21 | 2022-05-20 | 2022-08-29 | 2022-07-09 | 51 | 12 | -2
508703 | 3M Cottage Grove, MN | Oakville | Valves - Fischer - Will remain with Lakeside / Fischer | LAKESIDE PROCESS CONTROLS LTD. | 4503791825 | Flow Control | Metal Control Valves | USD | 141498 | USD | 144845 | -3347 | Estimate Without Market Reference(No Quote) | 2021-12-13 | 2022-04-25 | 2022-05-02 | 2022-01-10 | 2022-05-09 | 2022-04-25 | 2022-01-24 | 2022-05-16 | 2022-05-20 | 2022-09-05 | 2022-07-13 | 54 | 12 | 21
508703 | 3M Cottage Grove, MN | Oakville | Jet Mixer Eductor + Pump | SULZER PUMPS (CANADA) IN | 4503802510 | Flow Control | Other | USD | 29612 | USD | 12629 | 16983 | Supplier Competitions / Negotiation | 2022-03-11 | 2022-06-30 | 2022-06-03 | 2022-03-25 | 2022-06-03 | 2022-06-30 | 2022-04-08 | 2022-06-03 | 2022-10-20 | 2022-10-07 | 2022-10-13 | -6 | 12 | -27
508704 | 3M Decatur, AL | Oakville | Chem Feed Skids & Injection Quills | PROMINENT FLUID CONTROLS LTD. | 4503756011 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 279527 | CAD | 239545 | 39982 | Supplier Competitions / Negotiation | 2022-04-28 | 2021-01-19 | 2022-02-07 | 2022-05-19 | 2022-03-03 | 2021-12-15 | 2022-05-26 | 2022-03-08 | 2022-11-10 | 2022-07-12 | 2022-09-10 | -60 | 30 | 413
508704 | 3M Decatur, AL | Oakville | SBS Chem Feed Skids | PROMINENT FLUID CONTROLS LTD. | 4503850639 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 40890 | CAD | 24359 | 16531 | Supplier Competitions / Negotiation | 2022-07-11 | 2022-07-11 | 2022-07-11 | 2022-09-08 | 2022-08-14 | 2022-09-08 | 2022-09-08 | 2022-08-29 | 2022-09-08 | 2022-11-07 | 2022-10-08 | 30 | 30 | 49
508704 | 3M Decatur, AL | Oakville | Electrical Panels (Guelph) | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503787049 | Electrical & Instrumentation | Ele-Control Panels | USD | 123530 | USD | 93760 | 29770 | Supplier Competitions / Negotiation | 2021-11-04 | 2022-02-18 | 2022-03-31 | 2021-11-25 | 2022-04-09 | 2022-03-29 | 2021-12-09 | 2022-05-01 | 2022-05-26 | 2022-08-21 | 2022-07-08 | 44 | 18 | 72
508704 | 3M Decatur, AL | Oakville | Electrical Panels (MNKA) | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503787020 | Electrical & Instrumentation | Ele-Control Panels | USD | 123529 | USD | 47185 | 76344 | Supplier Competitions / Negotiation | 2021-11-04 | 2022-02-18 | 2022-03-31 | 2022-02-18 | 2022-04-08 | 2022-03-29 | 2022-04-15 | 2022-05-02 | 2022-05-26 | 2022-08-22 | 2022-07-09 | 44 | 18 | 73
508704 | 3M Decatur, AL | Oakville | Self-cleaning Strainer | BOLL FILTER CORPORATION | 4503742578 | Flow Control | Filters And Strainers (Incl Housings) | USD | 147590 | USD | 120207 | 27383 | Supplier Competitions / Negotiation | 2021-09-16 | 2021-01-19 | 2022-01-26 | 2021-10-14 | 2022-02-04 | 2021-09-30 | 2021-10-28 | 2022-02-05 | 2022-05-26 | 2022-06-11 | 2022-06-03 | 8 | 12 | 382
508704 | 3M Decatur, AL | Oakville | Automatic Screen | NEPTUNE BENSON LLC | 4503782976 | Rotating Equipment | Others | USD | 52839 | USD | 50355 | 2484 | Supplier Competitions / Negotiation | 2022-07-14 | 2021-12-15 | 2022-01-14 | 2022-08-04 | 2022-02-01 | 2022-05-29 | 2022-08-18 | 2022-04-29 | 2022-11-10 | 2022-09-30 | 2022-10-20 | -20 | 30 | 135
508704 | 3M Decatur, AL | Oakville | Cartridge Filters | JOHN BROOKS COMPANY LTD. | 4503749763 | Flow Control | Filters And Strainers (Incl Housings) | USD | 62338 | CAD | 175280 | -112942 | Size/ Weight/ Quantity Underestimated | 2022-01-06 | 2021-12-15 | 2021-12-23 | 2022-01-13 | 2021-12-30 | 2022-04-02 | 2022-01-20 | 2022-02-04 | 2022-05-26 | 2022-07-20 | 2022-06-22 | 28 | 12 | 51
508704 | 3M Decatur, AL | Oakville | RO CIP Tanks | Indelco Plastics | 4503779736 | Fabrication | Non-Metal Equipment | USD | 17650 | USD | 17627 | 23 | Supplier Competitions / Negotiation | 2022-04-04 | 2022-04-04 | 2022-04-04 | 2022-06-18 | 2022-04-05 | 2022-06-18 | 2022-06-18 | 2022-04-25 | 2022-06-18 | 2022-09-02 | 2022-07-26 | 38 | 12 | 21
508704 | 3M Decatur, AL | Oakville | Electrical Heater | ASB HEATING ELEMENTS LIMITED | 4503762690 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | USD | 26592 | CAD | 21196 | 5396 | Supplier Competitions / Negotiation | 2021-12-30 | 2022-02-02 | 2022-02-04 | 2022-01-27 | 2022-02-12 | 2022-03-27 | 2022-02-03 | 2022-03-24 | 2022-05-26 | 2022-06-23 | 2022-06-09 | 14 | 18 | 50
508704 | 3M Decatur, AL | Oakville | RO CIP Heaters | Chromalox Inc. | 4503768742 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | USD | 23300 | USD | 23269 | 31 | Supplier Competitions / Negotiation | 2022-02-15 | 2022-02-15 | 2022-03-10 | 2022-05-20 | 2022-03-10 | 2022-05-20 | 2022-05-20 | 2022-04-05 | 2022-05-26 | 2022-08-23 | 2022-07-09 | 45 | 18 | 49
508704 | 3M Decatur, AL | Oakville | Static mixers | Komax Systems | 4503783721 | Flow Control | Static Mixer | USD | 16253 | USD | 91372 | -75119 | Size/ Weight/ Quantity Underestimated | 2022-07-14 | 2022-02-16 | 2022-02-25 | 2022-08-04 | 2022-04-24 | 2022-06-29 | 2022-08-18 | 2022-05-02 | 2022-11-10 | 2022-08-08 | 2022-09-24 | -47 | 12 | 75
508704 | 3M Decatur, AL | Oakville | Blowers (Aerzen) | AERZEN CANADA INC | 4503756910 | Rotating Equipment | Blowers & Fans | USD | 69299 | CAD | 84240 | -14941 | Estimate Without Market Reference(No Quote) | 2022-07-14 | 2022-02-08 | 2022-02-15 | 2022-07-28 | 2022-02-16 | 2022-06-25 | 2022-08-04 | 2022-03-16 | 2022-11-10 | 2022-09-02 | 2022-10-06 | -34 | 30 | 36
508704 | 3M Decatur, AL | Oakville | Jet Mix Pumps | XYLEM CANADA COMPANY | 4503771319 | Rotating Equipment | Mixers | USD | 63826 | CAD | 34454 | 29372 | Supplier Competitions / Negotiation | 2022-07-28 | 2022-03-25 | 2022-03-25 | 2022-08-18 | 2022-03-23 | 2022-07-17 | 2022-09-01 | 2022-04-07 | 2022-11-10 | 2022-06-30 | 2022-09-04 | -66 | 30 | 13
508704 | 3M Decatur, AL | Oakville | Jet Mix Pumps | SULZER PUMPS (CANADA) INC. | 4503771380 | Rotating Equipment | Mixers | USD | 8800 | USD | 8200 | 600 | Supplier Competitions / Negotiation | 2022-07-28 | 2022-03-25 | 2022-03-17 | 2022-08-18 | 2022-04-07 | 2022-06-09 | 2022-09-01 | 2022-04-08 | 2022-06-09 | 2022-08-12 | 2022-07-11 | 32 | 30 | 14
508704 | 3M Decatur, AL | Oakville | Centrifugal Pumps (Guelph) | SULZER PUMPS (CANADA) INC. | 4503750954 | Rotating Equipment | PD Pumps | USD | 253325 | USD | 244519 | 8806 | Frame Agreements | 2021-12-09 | 2021-12-17 | 2022-01-08 | 2021-12-30 | 2022-01-19 | 2022-03-13 | 2022-01-06 | 2022-02-09 | 2022-05-26 | 2022-06-15 | 2022-06-05 | 10 | 30 | 54
508704 | 3M Decatur, AL | Oakville | Centrifugal Pumps (Minnetonka) | SULZER PUMPS (CANADA) INC. | 4503750912 | Rotating Equipment | PD Pumps | USD | 15500 | USD | 15484 | 16 | Frame Agreements | 2021-12-09 | 2021-12-17 | 2022-01-08 | 2021-12-30 | 2022-03-19 | 2022-03-29 | 2022-01-06 | 2022-03-02 | 2022-05-26 | 2022-07-18 | 2022-06-21 | 27 | 30 | 75
508704 | 3M Decatur, AL | Oakville | Frames and brackets (GUELPH) | PROCESS GROUP INTERNATIONAL LIMITED | 4503774964 | Fabrication | Carbon Steel | USD | 367785 | CAD | 147834 | 219951 | Supplier Competitions / Negotiation | 2021-12-02 | 2022-03-10 | 2022-03-31 | 2021-12-23 | 2022-03-23 | 2022-04-01 | 2022-01-06 | 2022-04-02 | 2022-05-26 | 2022-07-30 | 2022-06-27 | 33 | 12 | 23
508704 | 3M Decatur, AL | Oakville | Frames and brackets (MNKA) | GRUPO METELMEX SA DE CV | 4503778417 | Fabrication | Carbon Steel | USD | 76000 | USD | 75741 | 259 | Supplier Competitions / Negotiation | 2021-12-02 | 2022-03-10 | 2022-03-29 | 2021-12-23 | 2022-03-20 | 2022-03-03 | 2022-03-03 | 2022-03-24 | 2022-03-03 | 2022-06-02 | 2022-04-17 | 46 | 12 | 14
508704 | 3M Decatur, AL | Oakville | SS Spools (MNKA) | J.F. AHERN | 4503783976 | Fabrication | Stainless Steel | USD | 95419 | USD | 114274 | -18855 | Market Impact | 2021-12-02 | 2022-03-10 | 2022-03-25 | 2021-12-23 | 2022-04-11 | 2022-03-29 | 2022-01-06 | 2022-04-18 | 2022-05-26 | 2022-07-25 | 2022-06-25 | 30 | 12 | 39
508704 | 3M Decatur, AL | Oakville | SS Spools (GUELPH) | Cambridge Pro Fab Inc. | 4503783794 | Fabrication | Stainless Steel | USD | 280000 | CAD | 293823 | -13823 | Market Impact | 2021-12-02 | 2022-03-10 | 2022-03-29 | 2022-03-29 | 2022-03-26 | 2022-03-29 | 2022-03-29 | 2022-04-04 | 2022-03-29 | 2022-07-25 | 2022-05-27 | 59 | 12 | 25
508704 | 3M Decatur, AL | Oakville | SS Spools (MNKA) | J.F. AHERN | 4503794522 | Fabrication | Stainless Steel | USD | 61571 | USD | 61571 | 0 | Not included in Proposal / RFQ | 2022-05-20 | 2022-03-10 | 2022-05-25 | 2022-05-20 | 2022-04-13 | 2022-05-20 | 2022-05-20 | 2022-05-18 | 2022-05-20 | 2022-07-31 | 2022-06-25 | 36 | 12 | 69
508704 | 3M Decatur, AL | Oakville | HDPE Tanks | ACO CONTAINER SYSTEMS LTD. | 4503773451 | Fabrication | Non-Metal Equipment | USD | 81757 | CAD | 85861 | -4104 | Market Impact | 2022-06-02 | 2021-01-10 | 2022-01-24 | 2022-07-14 | 2022-03-17 | 2021-12-10 | 2022-07-21 | 2022-04-12 | 2022-11-10 | 2022-07-05 | 2022-09-07 | -64 | 12 | 457
508704 | 3M Decatur, AL | Oakville | FRP Tanks | STRAND COMPOSITES | 4503783010 | Fabrication | Non-Metal Equipment | USD | 159293 | USD | 151544 | 7749 | Supplier Competitions / Negotiation | 2022-05-26 | 2021-01-10 | 2022-02-07 | 2022-07-07 | 2022-04-03 | 2022-01-07 | 2022-07-21 | 2022-04-28 | 2022-11-10 | 2023-01-05 | 2022-12-08 | 28 | 12 | 473
508704 | 3M Decatur, AL | Oakville | Chlorine Analyzer and Sodium Permanganate Analyzer | Hach Company | 4503777741 | Electrical & Instrumentation | Ele-Control Panels | USD | 16901 | CAD | 14796 | 2105 | Frame Agreements | 2022-01-27 | 2022-02-16 | 2022-02-17 | 2022-02-24 | 2022-04-05 | 2022-05-25 | 2022-03-03 | 2022-04-20 | 2022-05-26 | 2022-09-21 | 2022-07-24 | 59 | 18 | 63
508704 | 3M Decatur, AL | Oakville | Ball, Butterfly, Check Valves | BRAY CONTROLS CANADA LTD. | 4503781523 | Flow Control | Metal Control Valves | USD | 47700 | USD | 45005 | 2695 | Frame Agreements | 2021-12-30 | 2022-02-18 | 2022-02-28 | 2022-01-27 | 2022-04-21 | 2022-04-01 | 2022-02-03 | 2022-04-24 | 2022-05-26 | 2022-07-03 | 2022-06-14 | 19 | 12 | 65
508704 | 3M Decatur, AL | Oakville | Valves Locks Kit (Minnetonka) | BRAY CONTROLS CANADA LTD | 4503829908 | Flow Control | Metal Control Valves | USD | 18700 | USD | 10450 | 8250 | Supplier Competitions / Negotiation | 2022-08-11 | 2022-07-07 | 2022-07-07 | 2022-08-11 | 2022-07-07 | 2022-08-11 | 2022-08-11 | 2022-07-21 | 2022-08-11 | 2022-09-15 | 2022-08-28 | 18 | 12 | 14
508704 | 3M Decatur, AL | Oakville | Check Valve (US Valves) | US VALVES | 4503792050 | Flow Control | Metal Control Valves | USD | 18715 | USD | 19915 | -1200 | Not included in Proposal / RFQ | 2022-05-06 | 2022-02-18 | 2022-02-21 | 2022-05-06 | 2022-05-04 | 2022-05-06 | 2022-05-06 | 2022-05-14 | 2022-05-06 | 2022-07-23 | 2022-06-14 | 39 | 12 | 85
508704 | 3M Decatur, AL | Oakville | Pressure Safety Valves (Minnetonka) | Great Lakes Industrial Controls | 4503777747 | Flow Control | Metal Safety(relief) Valves | USD | 29147 | CAD | 32640 | -3493 | Size/ Weight/ Quantity Underestimated | 2022-01-27 | 2022-02-11 | 2022-02-22 | 2022-02-24 | 2022-04-05 | 2022-05-08 | 2022-03-03 | 2022-04-20 | 2022-05-26 | 2022-08-17 | 2022-07-06 | 42 | 12 | 68
508704 | 3M Decatur, AL | Oakville | Pressure Safety Valves (Guelph) | Great Lakes Industrial Controls | 4503777744 | Flow Control | Metal Safety(relief) Valves | USD | 6050 | CAD | 6016 | 34 | Size/ Weight/ Quantity Underestimated | 2022-01-27 | 2022-02-11 | 2022-02-22 | 2022-02-24 | 2022-04-05 | 2022-05-08 | 2022-03-03 | 2022-04-20 | 2022-05-26 | 2022-08-17 | 2022-07-06 | 42 | 12 | 68
508897 | PEPSI CINCINNATI | Minnetonka | ASSY_AC FILTERS - SS (2) 96X144 | Arrow Tanks | 4503679036 | Fabrication | Stainless Steel | USD | 120000 | USD | 120000 | 0 | Proposed Supplier Incapable Of Executing | 2021-11-01 | 2021-12-28 | 2021-11-02 | 2021-11-04 | 2021-11-02 | 2021-12-28 | 2021-11-04 | 2021-11-02 | 2022-02-23 | 2022-02-22 | 2022-02-22 | 0 | 12 | -56
508897 | PEPSI CINCINNATI | Minnetonka | ASSY_CIP SYSTEM - SS 1.5K GAL | Preferred Stainless Holdings | 4503680125 | Fabrication | Stainless Steel | USD | 46940 | USD | 46940 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-10-29 | 2021-12-01 | 2021-09-08 | 2021-11-04 | 2021-11-03 | 2021-12-01 | 2021-11-04 | 2021-11-03 | 2022-02-23 | 2022-02-17 | 2022-02-20 | -3 | 12 | -28
508897 | PEPSI CINCINNATI | Minnetonka | LS_PRE-RO UV STERILIZER | ATLANTIUM | 4503679520 | Electrical & Instrumentation | Ele-Electrical Others | USD | 55392 | USD | 34018 | 21374 | Design Optimizations | 2021-11-01 | 2021-11-21 | 2021-07-23 | 2021-11-04 | 2021-11-02 | 2021-11-21 | 2021-11-04 | 2021-11-02 | 2022-02-23 | 2022-03-22 | 2022-03-08 | 14 | 18 | -19
508897 | PEPSI CINCINNATI | Minnetonka | LS_Y-STRAINER | OPTIMUM FILTER, INC. | 4503678245 | Flow Control | Filters And Strainers (Incl Housings) | USD | 8685 | USD | 5150 | 3535 | Estimate Without Market Reference(No Quote) | 2021-11-01 | 2022-01-10 | 2021-11-01 | 2021-11-04 | 2021-11-01 | 2022-01-10 | 2021-11-04 | 2021-11-01 | 2022-02-23 | 2022-03-22 | 2022-03-08 | 14 | 12 | -70
508897 | PEPSI CINCINNATI | Minnetonka | LS_POST-RO UV STERILIZER | ATLANTIUM | 4513679520 | Electrical & Instrumentation | Ele-Electrical Others | USD | 63400 | USD | 43480 | 19920 | Design Optimizations | 2021-11-01 | 2021-11-21 | 2021-07-23 | 2021-11-04 | 2021-11-02 | 2021-11-21 | 2021-11-04 | 2021-11-02 | 2022-02-23 | 2022-03-22 | 2022-03-08 | 14 | 18 | -19
508897 | PEPSI CINCINNATI | Minnetonka | LS_MCE AND POWER DIST PANEL | WERNER ELECTRIC | 4503683060 | Electrical & Instrumentation | Ele-Control Panels | USD | 94104 | USD | 106099 | -11995 | Estimate Without Market Reference(No Quote) | 2021-11-01 | 2021-12-10 | 2021-09-01 | 2021-11-04 | 2021-11-08 | 2021-12-10 | 2021-11-04 | 2021-11-08 | 2022-02-23 | 2022-03-21 | 2022-03-08 | 13 | 18 | -32
508897 | PEPSI CINCINNATI | Minnetonka | LS_MAIN CONTROL PANEL | PTS Products | 4503683306 | Electrical & Instrumentation | Ele-Control Panels | USD | 79354 | USD | 92058 | -12704 | Estimate Without Market Reference(No Quote) | 2021-11-01 | 2021-12-28 | 2021-11-02 | 2021-11-04 | 2021-11-08 | 2021-12-28 | 2021-11-04 | 2021-11-08 | 2022-02-23 | 2022-02-06 | 2022-02-14 | -8 | 18 | -50
508897 | PEPSI CINCINNATI | Minnetonka | DS_CHEMICAL FEED SKIDS | WASTECH CONTROLS & ENGINEERING, INC | 4503677919 | Fabrication | Skid Assembly Outsourced | USD | 88600 | USD | 88000 | 600 | Estimate Without Market Reference(No Quote) | 2021-11-08 | 2021-12-27 | 2021-09-27 | 2021-11-09 | 2021-10-29 | 2021-12-27 | 2021-11-09 | 2021-10-30 | 2022-02-23 | 2022-03-29 | 2022-03-12 | 17 | 12 | -58
508897 | PEPSI CINCINNATI | Minnetonka | DS_TREATED WATER STORAGE TANK | Preferred Stainless Holdings | 4503683020 | Fabrication | Stainless Steel | USD | 110665 | USD | 66152 | 44513 | Supplier Competitions / Negotiation | 2021-10-29 | 2022-01-10 | 2021-11-09 | 2021-11-04 | 2021-11-07 | 2022-01-10 | 2021-11-04 | 2021-11-07 | 2022-03-25 | 2022-03-20 | 2022-03-22 | -2 | 12 | -64
508897 | PEPSI CINCINNATI | Minnetonka | DS_ACF BW COLLECTION TANK | PRECISIONENG | 4503685044 | Fabrication | Non-Metal Equipment | USD | 22127 | USD | 36143 | -14016 | Supplier Competitions / Negotiation | 2021-10-29 | 2022-01-10 | 2021-11-10 | 2021-11-04 | 2021-11-11 | 2022-01-10 | 2021-11-04 | 2021-11-11 | 2022-03-25 | 2022-03-24 | 2022-03-24 | 0 | 12 | -60
508897 | PEPSI CINCINNATI | Minnetonka | DS_TRICKLE TANK | PRECISIONENG | 4513685044 | Fabrication | Non-Metal Equipment | USD | 26764 | USD | 36003 | -9239 | Estimate Without Market Reference(No Quote) | 2021-10-29 | 2022-01-10 | 2021-11-10 | 2021-11-04 | 2021-11-11 | 2022-01-10 | 2021-11-04 | 2021-11-11 | 2022-03-25 | 2022-03-24 | 2022-03-24 | 0 | 12 | -60
508897 | PEPSI CINCINNATI | Minnetonka | DS_FEEDWATER STORAGE TANK | PRECISIONENG | 4523685044 | Fabrication | Non-Metal Equipment | USD | 54402 | USD | 40253 | 14149 | Supplier Competitions / Negotiation | 2021-10-29 | 2022-01-10 | 2021-11-10 | 2021-11-04 | 2021-11-11 | 2022-01-10 | 2021-11-04 | 2021-11-11 | 2022-03-25 | 2022-03-24 | 2022-03-24 | 0 | 12 | -60
508900 | Quesnel River Pulp, Mangazur | Richmond | Pressure Vessel | BE PETERSON | 4503767239 | Fabrication | Carbon Steel | CAD | 609276 | USD | 602212 | 7064 | Design Optimizations | 2022-01-28 | 2022-03-15 | 2022-03-24 | 2022-02-21 | 2022-03-28 | 2022-06-09 | 2022-03-01 | 2022-03-31 | 2022-08-24 | 2022-10-20 | 2022-09-21 | 29 | 12 | 16
508900 | Quesnel River Pulp, Mangazur | Richmond | Air Blower | AERZEN CANADA INC | 4503764878 | Rotating Equipment | Blowers & Fans | CAD | 72664 | CAD | 15950 | 56714 | Design Optimizations | 2022-01-28 | 2021-12-03 | 2021-12-07 | 2022-02-21 | 2022-03-15 | 2022-04-14 | 2022-03-01 | 2022-03-27 | 2022-08-24 | 2022-08-14 | 2022-08-19 | -5 | 30 | 114
508909 | National Beverage | Minnetonka | FEED WATER PUMP SKID | PFC EQUIPMENT | 4503687804 | Rotating Equipment | Centrifugal Pumps | USD | 17892 | USD | 17892 | 0 | Estimate Without Market Reference(No Quote) | 2021-11-08 | 2021-12-31 | 2021-11-17 | 2021-11-09 | 2021-11-17 | 2021-12-31 | 2021-11-10 | 2021-11-17 | 2022-02-14 | 2022-02-22 | 2022-02-18 | 4 | 30 | -44
508909 | National Beverage | Minnetonka | AC FILTER 96X144 | Arrow Tanks | 4503689522 | Fabrication | Stainless Steel | USD | 60000 | USD | 60000 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-10-29 | 2021-09-16 | 2021-09-16 | 2021-10-29 | 2021-11-19 | 2021-12-08 | 2021-10-29 | 2021-11-20 | 2022-02-18 | 2022-03-01 | 2022-02-23 | 6 | 12 | 65
508909 | National Beverage | Minnetonka | BEV RO SKID | PTS Products | 4503699791 | Electrical & Instrumentation | Ele-Control Panels | USD | 37850 | USD | 47256 | -9406 | Market Impact | 2021-11-08 | 2021-11-29 | 2021-12-08 | 2021-11-09 | 2021-12-08 | 2021-12-28 | 2021-11-10 | 2021-12-08 | 2022-02-14 | 2022-02-16 | 2022-02-15 | 1 | 18 | 9
508909 | National Beverage | Minnetonka | CIP SKID - SS 0 750 GAL | Preferred Stainless Holdings | 4503685236 | Fabrication | Stainless Steel | USD | 35000 | USD | 34501 | 499 | Estimate Without Market Reference(No Quote) | 2021-11-08 | 2021-11-08 | 2021-11-10 | 2021-11-09 | 2021-11-12 | 2022-01-08 | 2021-11-10 | 2021-11-12 | 2022-03-04 | 2022-03-11 | 2022-03-07 | 4 | 12 | 4
508909 | National Beverage | Minnetonka | DISTRIBUTION PUMP SKID | PFC EQUIPMENT | 4503687802 | Rotating Equipment | Centrifugal Pumps | USD | 20820 | USD | 15988 | 4832 | Estimate Without Market Reference(No Quote) | 2021-11-08 | 2022-01-05 | 2021-11-17 | 2021-11-09 | 2022-01-05 | 2022-01-05 | 2021-11-10 | 2021-11-16 | 2022-03-04 | 2021-12-15 | 2022-01-23 | -39 | 30 | -50
508909 | National Beverage | Minnetonka | LS_PRE RO UV | AQUIONICS, INC. | 4513686041 | Electrical & Instrumentation | Ele-Electrical Others | USD | 26750 | USD | 23600 | 3150 | Estimate Without Market Reference(No Quote) | 2021-11-08 | 2021-11-03 | 2021-11-03 | 2021-11-09 | 2021-11-15 | 2022-01-18 | 2021-11-10 | 2021-11-15 | 2022-04-04 | 2022-02-14 | 2022-03-10 | -24 | 18 | 12
508909 | National Beverage | Minnetonka | LS_TREATED WATER UV | AQUIONICS, INC. | 4503686041 | Electrical & Instrumentation | Ele-Electrical Others | USD | 33591 | USD | 26922 | 6669 | Estimate Without Market Reference(No Quote) | 2021-11-08 | 2021-11-03 | 2021-11-03 | 2021-11-09 | 2021-11-14 | 2022-01-17 | 2021-11-10 | 2021-11-02 | 2022-04-04 | 2022-02-08 | 2022-03-07 | -27 | 18 | -1
508909 | National Beverage | Minnetonka | LS_MCE | BW Systems | 4503701280 | Electrical & Instrumentation | Ele-Control Panels | USD | 90000 | USD | 92900 | -2900 | Market Impact | 2021-11-08 | 2021-11-20 | 2021-12-07 | 2021-11-09 | 2021-12-10 | 2022-01-20 | 2021-11-10 | 2021-12-10 | 2022-04-04 | 2022-02-04 | 2022-03-05 | -29 | 18 | 20
508909 | National Beverage | Minnetonka | DS_FEED WATER TANK - FRP - 10K GAL | PRECISIONENG | 4503685209 | Fabrication | Non-Metal Equipment | USD | 38983 | CAD | 36785 | 2198 | Estimate Without Market Reference(No Quote) | 2021-11-08 | 2021-11-08 | 2021-11-10 | 2021-11-11 | 2021-11-11 | 2022-01-21 | 2021-11-12 | 2021-11-12 | 2022-04-04 | 2022-04-05 | 2022-04-04 | 1 | 12 | 4
508909 | National Beverage | Minnetonka | DS_TREATED WATER TANK - SS - 10K GAL | Preferred Stainless Holdings | 4503685170 | Fabrication | Stainless Steel | USD | 72962 | USD | 66286 | 6676 | Estimate Without Market Reference(No Quote) | 2021-11-08 | 2021-11-03 | 2021-11-08 | 2021-11-11 | 2021-11-12 | 2022-01-18 | 2021-11-12 | 2021-11-12 | 2022-04-04 | 2022-03-31 | 2022-04-02 | -2 | 12 | 9
508909 | National Beverage | Minnetonka | DS_MOBILE SYS.ACC. & INSTALL | Indelco Plastics | 4503672737 | Fabrication | Non-Metal Equipment | USD | 12100 | USD | 12022 | 78 | Estimate Without Market Reference(No Quote) | 2021-10-28 | 2021-10-21 | 2021-10-21 | 2021-10-28 | 2021-10-21 | 2021-11-09 | 2021-10-28 | 2021-10-21 | 2021-11-15 | 2021-11-29 | 2021-11-22 | 7 | 12 | 0
508909 | National Beverage | Minnetonka | DS_MOBILE SYS.ACC. & INSTALL | PFC EQUIPMENT | 4503676816 | Rotating Equipment | Centrifugal Pumps | USD | 8946 | USD | 8946 | 0 | Proposed Supplier Incapable Of Executing | 2021-11-01 | 2021-10-28 | 2021-10-28 | 2021-11-01 | 2021-10-28 | 2021-11-06 | 2021-11-01 | 2021-10-28 | 2021-11-15 | 2021-11-09 | 2021-11-12 | -3 | 30 | 0
508909 | National Beverage | Minnetonka | BEV RO - PROTEC HOUSINGS | PROTEC ARISAWA AMERICA INC | 4503689524 | Fabrication | Non-Metal Equipment | USD | 23130 | USD | 25672 | -2542 | Single Sourced | 2021-11-08 | 2021-11-08 | 2021-11-10 | 2021-11-10 | 2021-11-17 | 2021-12-30 | 2021-11-22 | 2021-11-20 | 2022-02-21 | 2022-02-07 | 2022-02-14 | -7 | 12 | 12
508909 | National Beverage | Minnetonka | BEV RO VALVES RELIEF - PERLICK | Duncan Co. | 4503689528 | Flow Control | Metal Safety(relief) Valves | USD | 9031 | USD | 9031 | 0 | Design Optimizations | 2021-11-08 | 2021-11-05 | 2021-11-08 | 2021-11-17 | 2021-11-16 | 2021-11-28 | 2021-11-22 | 2021-11-20 | 2021-12-22 | 2021-12-20 | 2021-12-21 | -1 | 12 | 15
508909 | National Beverage | Minnetonka | BEV RO - VALVES - CHECK | QUALITY STAINLESS | 4503711166 | Flow Control | Metal Control Valves | USD | 6165 | USD | 6930 | -765 | Market Impact | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-01-11 | 2022-01-03 | 2022-01-11 | 2022-01-11 | 2022-01-03 | 2022-01-11 | 2022-01-19 | 2022-01-15 | 4 | 12 | -8
508909 | National Beverage | Minnetonka | BEV RO - VALVES VBALL | BRAY SALES MINNEAPOLIS | 4503689531 | Flow Control | Metal Control Valves | USD | 7089 | USD | 7089 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-11-15 | 2021-11-15 | 2021-11-20 | 2021-11-18 | 2021-11-17 | 2021-12-13 | 2021-11-22 | 2021-11-20 | 2022-01-10 | 2022-01-10 | 2022-01-10 | 0 | 12 | 5
508909 | National Beverage | Minnetonka | LS FLOWMETERS - FILTER | OPTIMUM FILTER, INC. | 4503697243 | Flow Control | Filters And Strainers (Incl Housings) | USD | 5400 | USD | 5400 | 0 | Frame Agreements | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-03 | 2021-12-02 | 2022-01-12 | 2021-12-06 | 2021-12-05 | 2022-02-22 | 2022-02-22 | 2022-02-22 | 0 | 12 | 2
508909 | National Beverage | Minnetonka | LS - FLOWMETERS | QUALITY STAINLESS | 4503702964 | Flow Control | Metal Control Valves | USD | 9391 | USD | 28017 | -18626 | Estimate Without Market Reference(No Quote) | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-14 | 2021-12-12 | 2022-01-17 | 2021-12-14 | 2021-12-13 | 2022-02-22 | 2022-02-21 | 2022-02-21 | 0 | 12 | -1
508909 | National Beverage | Minnetonka | TRICKLE TANK | Indelco Plastics | 4503763033 | Fabrication | Non-Metal Equipment | USD | 26322 | USD | 24723 | 1599 | Estimate Without Market Reference(No Quote) | 2022-02-23 | 2022-02-23 | 2022-02-23 | 2022-03-25 | 2022-03-24 | 2022-04-12 | 2022-03-25 | 2022-03-25 | 2022-05-31 | 2022-05-31 | 2022-05-31 | 0 | 12 | 30
508938 | SIRWA WTP | Richmond | SS Fabrication | JOB SHOP FABRICATORS | 4503733232 | Fabrication | Stainless Steel | USD | 27898 | USD | 28790 | -892 | Size/ Weight/ Quantity Underestimated | 2022-01-12 | 2022-01-31 | 2022-02-03 | 2022-01-15 | 2022-02-04 | 2022-03-03 | 2022-01-22 | 2022-02-04 | 2022-04-23 | 2022-03-20 | 2022-04-06 | -17 | 12 | 4
508938 | SIRWA WTP | Richmond | Stop log gates | RW Gate | 4503774972 | Fabrication | Non-Metal Equipment | USD | 59472 | USD | 48450 | 11022 | Frame Agreements | 2022-01-12 | 2021-11-15 | 2021-12-22 | 2022-01-15 | 2022-04-04 | 2022-02-27 | 2022-01-22 | 2022-04-11 | 2022-04-23 | 2022-06-12 | 2022-05-18 | 25 | 12 | 147
508938 | SIRWA WTP | Richmond | Vaccum Pump | Tencarva Machinery Co. | 4503783513 | Rotating Equipment | Others | USD | 22854 | USD | 9756 | 13098 | Design Optimizations | 2022-01-12 | 2021-11-15 | 2021-11-29 | 2022-01-15 | 2022-04-28 | 2022-02-22 | 2022-01-22 | 2022-05-01 | 2022-04-23 | 2022-06-02 | 2022-05-13 | 20 | 30 | 167
508938 | SIRWA WTP | Richmond | Mixers | SPX FLOW US LLC | 4503777734 | Rotating Equipment | Mixers | USD | 55575 | CAD | 37632 | 17943 | Supplier Competitions / Negotiation | 2022-01-12 | 2021-11-15 | 2021-12-01 | 2022-01-15 | 2022-04-14 | 2022-03-23 | 2022-01-22 | 2022-04-19 | 2022-04-23 | 2022-07-30 | 2022-06-11 | 49 | 30 | 155
508938 | SIRWA WTP | Richmond | Control Panel | KELTOUR CONTROLS INC. | 4503808165 | Electrical & Instrumentation | Ele-Control Panels | USD | 51786 | CAD | 29513 | 22273 | Supplier Competitions / Negotiation | 2022-01-12 | 2022-05-31 | 2022-05-30 | 2022-01-15 | 2022-05-26 | 2022-05-31 | 2022-01-22 | 2022-06-14 | 2022-04-23 | 2022-10-18 | 2022-07-21 | 89 | 18 | 14
508938 | SIRWA WTP | Richmond | Tube Settlers | BRENTWOOD INDUSTRIES | 4503793995 | Fabrication | Non-Metal Equipment | USD | 42716 | USD | 41376 | 1340 | Supplier Competitions / Negotiation | 2022-01-12 | 2022-01-24 | 2022-01-31 | 2022-01-15 | 2022-05-19 | 2022-04-17 | 2022-01-22 | 2022-05-19 | 2022-04-23 | 2022-07-21 | 2022-06-06 | 45 | 12 | 115
508938 | SIRWA WTP | Richmond | Plug Valves | TECHNICAL COMPONENTS CO. - USA | 4503783593 | Flow Control | Metal Control Valves | USD | 48923 | USD | 82040 | -33117 | Single Sourced | 2022-01-12 | 2021-11-15 | 2021-12-28 | 2022-01-15 | 2022-04-21 | 2022-03-20 | 2022-01-22 | 2022-05-01 | 2022-04-23 | 2022-07-24 | 2022-06-08 | 46 | 12 | 167
508938 | SIRWA WTP | Richmond | Cross Member | EASTERN METAL | 4503713531 | Fabrication | Alloy Steel | USD | 35007 | USD | 33147 | 1860 | Supplier Competitions / Negotiation | 2021-12-16 | 2022-01-04 | 2022-01-04 | 2021-12-20 | 2022-01-03 | 2022-04-03 | 2021-12-22 | 2022-01-05 | 2022-03-23 | 2022-07-20 | 2022-05-21 | 60 | 12 | 1
508938 | SIRWA WTP | Richmond | PVC Fabrication | Indelco Plastics | 4503735406 | Fabrication | Non-Metal Equipment | USD | 42688 | USD | 60367 | -17679 | Single Sourced | 2022-01-12 | 2022-01-14 | 2022-01-24 | 2022-01-15 | 2022-02-08 | 2022-05-23 | 2022-01-22 | 2022-02-08 | 2022-04-23 | 2022-10-01 | 2022-07-12 | 81 | 12 | 25
508938 | SIRWA WTP | Richmond | FRP Settling Plates | KAL-LITE | 4503777710 | Fabrication | Non-Metal Equipment | USD | 17246 | USD | 17662 | -416 | Specs / Requirements Misinterpreted in Proposal | 2022-01-12 | 2022-01-31 | 2022-02-04 | 2022-01-15 | 2022-04-18 | 2022-03-23 | 2022-01-22 | 2022-04-18 | 2022-04-23 | 2022-06-02 | 2022-05-13 | 20 | 12 | 77
508938 | SIRWA WTP | Richmond | Aluminium | JOB SHOP FABRICATORS | 4503783436 | Fabrication | Stainless Steel | USD | 50272 | USD | 86818 | -36546 | Specs / Requirements Misinterpreted in Proposal | 2022-05-16 | 2022-03-22 | 2022-04-01 | 2022-05-16 | 2022-05-01 | 2022-05-16 | 2022-05-16 | 2022-05-01 | 2022-05-16 | 2022-07-10 | 2022-06-12 | 28 | 12 | 40
508938 | SIRWA WTP | Richmond | Safety climbing device | Safeware | 4503735519 | Fabrication | Alloy Steel | USD | 6771 | USD | 9875 | -3104 | Market Impact | 2022-01-12 | 2022-01-01 | 2022-02-09 | 2022-01-15 | 2022-02-08 | 2022-02-26 | 2022-01-22 | 2022-02-08 | 2022-04-23 | 2022-04-23 | 2022-04-23 | 0 | 12 | 38
508938 | SIRWA WTP | Richmond | DI Embedments | BURKES MECHANICAL | 4503737504 | Fabrication | Non-Metal Equipment | USD | 22357 | USD | 28224 | -5867 | Market Impact | 2022-01-12 | 2022-02-05 | 2022-02-10 | 2022-01-15 | 2022-02-08 | 2022-03-03 | 2022-01-22 | 2022-02-12 | 2022-04-23 | 2022-03-15 | 2022-04-03 | -19 | 12 | 7
508967 | West River | Richmond | Mixers | Philadelphia Mixing Solutions | 4503792094 | Rotating Equipment | Mixers | USD | 149234 | USD | 168480 | -19246 | Market Impact | 2021-11-11 | 2021-11-11 | 2021-12-03 | 2022-01-23 | 2022-05-12 | 2022-04-22 | 2022-02-15 | 2022-05-16 | 2022-06-23 | 2022-10-01 | 2022-08-12 | 50 | 30 | 186
508967 | West River | Richmond | Recyle Pumps | SULZER PUMPS (CANADA) INC. | 4503784671 | Rotating Equipment | Others | USD | 108870 | CAD | 93527 | 15343 | Frame Agreements | 2021-11-11 | 2021-11-11 | 2022-01-12 | 2022-01-23 | 2022-04-27 | 2022-04-16 | 2022-02-15 | 2022-05-02 | 2022-06-23 | 2022-09-19 | 2022-08-06 | 44 | 30 | 172
508967 | West River | Richmond | Saturation Tank | BE Peterson | 4503784666 | Fabrication | Stainless Steel | USD | 157203 | USD | 139957 | 17246 | Frame Agreements | 2021-12-28 | 2022-04-09 | 2022-04-11 | 2022-01-23 | 2022-05-02 | 2022-04-30 | 2022-02-15 | 2022-05-03 | 2022-06-23 | 2022-09-01 | 2022-07-28 | 35 | 12 | 24
508967 | West River | Richmond | Control Panels | Keltour Controls Inc. | 4503802843 | Electrical & Instrumentation | Ele-Control Panels | USD | 60075 | CAD | 16991 | 43084 | Supplier Competitions / Negotiation | 2021-12-28 | 2022-04-14 | 2022-04-27 | 2022-01-23 | 2022-06-04 | 2022-05-10 | 2022-02-15 | 2022-06-04 | 2022-06-23 | 2022-09-20 | 2022-08-06 | 45 | 18 | 51
508967 | West River | Richmond | electrical Components | ELECTRICAL EQUIPMENT COMP | 4503752889 | Electrical & Instrumentation | Ele-Control Panels | USD | 11262 | USD | 24999 | -13737 | Estimate Without Market Reference(No Quote) | 2022-05-07 | 2022-03-03 | 2022-03-09 | 2022-05-07 | 2022-03-07 | 2022-05-07 | 2022-05-07 | 2022-03-07 | 2022-05-07 | 2022-07-11 | 2022-06-08 | 33 | 18 | 4
508967 | West River | Richmond | Weir Plate | 3D MECHANICAL | 4503807586 | Fabrication | Stainless Steel | USD | 36227 | CAD | 74879 | -38652 | Estimate Without Market Reference(No Quote) | 2021-12-28 | 2022-06-01 | 2022-06-10 | 2022-01-23 | 2022-06-09 | 2022-04-29 | 2022-02-15 | 2022-06-12 | 2022-06-23 | 2022-08-30 | 2022-07-27 | 34 | 12 | 11
508967 | West River | Richmond | PVC Laterals | Indelco Plastics | 4503747227 | Flow Control | Plastic Pipe and Fittings | USD | 28475 | USD | 23979 | 4496 | Design Optimizations | 2021-12-28 | 2022-01-07 | 2022-01-13 | 2022-01-23 | 2022-03-01 | 2022-04-11 | 2022-02-15 | 2022-05-01 | 2022-06-23 | 2022-07-24 | 2022-07-08 | 16 | 12 | 114
508967 | West River | Richmond | Weir Actuator | COLUMBUS MCKINNON | 4503783958 | Rotating Equipment | Others | USD | 21129 | USD | 27999 | -6870 | Specs / Requirements Misinterpreted in Proposal | 2021-12-28 | 2022-02-27 | 2022-02-01 | 2022-01-23 | 2022-04-27 | 2022-05-02 | 2022-02-15 | 2022-05-01 | 2022-06-23 | 2022-09-04 | 2022-07-29 | 37 | 30 | 63
508967 | West River | Richmond | Air Compressor | ATLAS COPCO COMPRESSORS | 4503832547 | Rotating Equipment | Compressors | USD | 15971 | CAD | 22288 | -6317 | Size/ Weight/ Quantity Underestimated | 2021-11-11 | 2021-11-11 | 2021-11-16 | 2022-01-23 | 2022-07-24 | 2022-04-29 | 2022-02-15 | 2022-07-24 | 2022-06-23 | 2022-10-16 | 2022-08-19 | 58 | 30 | 255
508967 | West River | Richmond | Pressure Transmitter | Foxboro | 4503789560 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 15297 | CAD | 7122 | 8175 | Supplier Competitions / Negotiation | 2021-12-28 | 2022-01-27 | 2022-01-31 | 2022-01-23 | 2022-05-10 | 2022-04-24 | 2022-02-15 | 2022-05-10 | 2022-06-23 | 2022-08-19 | 2022-07-21 | 29 | 18 | 103
508967 | West River | Richmond | Butterfly Valve | DEZURIK | 4503794989 | Flow Control | Metal Control Valves | USD | 8146 | USD | 21742 | -13596 | Estimate Without Market Reference(No Quote) | 2021-12-28 | 2021-12-09 | 2021-12-22 | 2022-01-23 | 2022-05-20 | 2022-05-16 | 2022-02-15 | 2022-05-20 | 2022-06-23 | 2022-10-21 | 2022-08-22 | 60 | 12 | 162
508967 | West River | Richmond | Safety relief valve | MCMASTER-CARR | 4503794966 | Flow Control | Metal Control Valves | USD | 8064 | USD | 10416 | -2352 | Estimate Without Market Reference(No Quote) | 2021-12-28 | 2021-12-09 | 2022-01-13 | 2022-01-23 | 2022-05-20 | 2022-04-04 | 2022-02-15 | 2022-05-20 | 2022-06-23 | 2022-07-29 | 2022-07-11 | 18 | 12 | 162
508997 | NIAGARA TACOMA EXP | Minnetonka | AC TOWER 96X144 | Arrow Tanks | 4503693882 | Fabrication | Stainless Steel | USD | 60000 | USD | 60000 | 0 | Size/ Weight/ Quantity Underestimated | 2021-11-09 | 2021-12-14 | 2021-11-29 | 2021-11-09 | 2021-11-29 | 2021-12-14 | 2021-11-09 | 2021-11-29 | 2022-01-18 | 2022-01-19 | 2022-01-18 | 1 | 12 | -15
508999 | Lovely Hill | Oakville | Process Pumps | Vogelsang | 4503705097 | Rotating Equipment | PD Pumps | USD | 58942 | USD | 63522 | -4580 | Specs / Requirements Misinterpreted in Proposal | 2021-11-19 | 2022-01-08 | 2021-12-14 | 2021-11-19 | 2022-01-08 | 2022-01-08 | 2021-11-26 | 2021-12-16 | 2022-02-28 | 2022-02-24 | 2022-02-26 | -2 | 30 | -23
508999 | Lovely Hill | Oakville | Spools | NV PIPING SYSTEMS INC. | 4503715870 | Fabrication | Stainless Steel | USD | 103704 | CAD | 117561 | -13857 | Single Sourced | 2021-11-19 | 2022-01-16 | 2022-01-07 | 2021-11-19 | 2022-01-16 | 2022-01-16 | 2022-01-04 | 2022-01-10 | 2022-03-15 | 2022-03-15 | 2022-03-15 | 0 | 12 | -6
508999 | Lovely Hill | Oakville | Frames, lifting Module, Inst.Bracket | 3D MECHANICAL | 4503715864 | Fabrication | Stainless Steel | USD | 165725 | USD | 197216 | -31491 | Specs / Requirements Misinterpreted in Proposal | 2021-11-19 | 2022-01-14 | 2022-01-06 | 2021-11-19 | 2022-01-14 | 2022-01-14 | 2021-12-31 | 2022-01-10 | 2022-03-11 | 2022-03-11 | 2022-03-11 | 0 | 12 | -4
508999 | Lovely Hill | Oakville | Butterfly Valves | BRAY CONTROLS CANADA LTD. | 4503725781 | Flow Control | Metal Control Valves | USD | 10205 | USD | 8282 | 1923 | Supplier Competitions / Negotiation | 2021-10-14 | 2022-01-02 | 2022-01-18 | 2021-10-28 | 2022-01-02 | 2022-01-02 | 2021-11-04 | 2022-01-25 | 2022-03-24 | 2022-03-01 | 2022-03-12 | -11 | 12 | 23
508999 | Lovely Hill | Oakville | Air Flow Transmitter | AVENSYS | 4503724849 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 19515 | CAD | 12160 | 7355 | Supplier Competitions / Negotiation | 2021-11-25 | 2022-02-05 | 2022-01-18 | 2021-12-09 | 2022-02-05 | 2022-02-05 | 2021-12-16 | 2022-01-24 | 2022-03-24 | 2022-04-18 | 2022-04-05 | 13 | 18 | -12
509000 | Intel Sparrow | Oakville | Pressure Vessels | Alps Welding Ltd. | 4503665416 | Fabrication | Carbon Steel | USD | 233000 | CAD | 374087 | -141087 | Proposed Supplier Incapable Of Executing | 2021-05-17 | 2021-08-20 | 2021-09-25 | 2021-05-27 | 2021-09-23 | 2021-10-05 | 2021-06-10 | 2021-10-06 | 2022-01-17 | 2022-02-23 | 2022-02-04 | 19 | 12 | 47
509000 | Intel Sparrow | Oakville | Painting and Lining for Vessels | BRANT CORROSION CONTROL, | 4503676983 | Fabrication | Carbon Steel | USD | 115000 | CAD | 129390 | -14390 | Estimate Without Market Reference(No Quote) | 2021-11-28 | 2021-08-20 | 2021-08-25 | 2021-11-28 | 2021-10-09 | 2021-11-28 | 2021-11-28 | 2021-10-28 | 2021-11-28 | 2022-03-08 | 2022-01-17 | 50 | 12 | 69
509000 | Intel Sparrow | Oakville | Pressure Vessel Internals | NV PIPING SYSTEMS INC. | 4503686973 | Fabrication | Stainless Steel | USD | 142000 | CAD | 144841 | -2841 | Estimate Without Market Reference(No Quote) | 2021-07-15 | 2021-09-24 | 2021-10-19 | 2021-08-05 | 2021-11-04 | 2021-11-14 | 2021-08-12 | 2021-11-14 | 2022-01-17 | 2022-03-16 | 2022-02-15 | 29 | 12 | 51
509000 | Intel Sparrow | Oakville | Heat Exchanger - Lot 1 | ALFA LAVAL | 4503678306 | Fabrication | Alloy Steel | USD | 195000 | USD | 186388 | 8612 | Single Sourced | 2021-09-02 | 2021-10-05 | 2021-10-06 | 2021-09-16 | 2021-10-20 | 2021-11-27 | 2021-09-23 | 2021-11-01 | 2022-02-21 | 2022-01-31 | 2022-02-10 | -10 | 12 | 27
509000 | Intel Sparrow | Oakville | Heat Exchanger - Lot 2 | ALFA LAVAL | 4503692599 | Fabrication | Alloy Steel | USD | 310000 | USD | 302841 | 7159 | Supplier Competitions / Negotiation | 2022-01-04 | 2021-11-10 | 2021-06-30 | 2022-01-04 | 2021-11-09 | 2022-01-04 | 2022-01-04 | 2021-11-26 | 2022-01-04 | 2022-07-12 | 2022-04-08 | 95 | 12 | 16
509000 | Intel Sparrow | Oakville | Pumps - Grundfos | GRUNDFOS CANADA INC. | 4503668113 | Rotating Equipment | PD Pumps | USD | 346000 | USD | 284583 | 61417 | Single Sourced | 2021-06-21 | 2021-10-04 | 2021-09-19 | 2021-06-28 | 2021-10-05 | 2021-10-27 | 2021-07-05 | 2021-10-14 | 2022-01-24 | 2022-03-05 | 2022-02-13 | 20 | 30 | 10
509000 | Intel Sparrow | Oakville | Pumps - Other Flowserve | FLOWSERVE INC. | 4503664356 | Rotating Equipment | Centrifugal Pumps | USD | 418000 | USD | 410370 | 7630 | Supplier Competitions / Negotiation | 2021-07-15 | 2021-09-17 | 2021-08-31 | 2021-07-29 | 2021-09-30 | 2021-11-19 | 2021-08-05 | 2021-10-03 | 2022-02-28 | 2022-03-27 | 2022-03-13 | 14 | 30 | 16
509000 | Intel Sparrow | Oakville | Pumps - Other Richter | RICHTER | 4503694704 | Rotating Equipment | Centrifugal Pumps | USD | 130000 | USD | 121665 | 8335 | Not included in Proposal / RFQ | 2022-01-11 | 2021-11-15 | 2021-11-29 | 2022-01-11 | 2021-11-29 | 2022-01-11 | 2022-01-11 | 2021-11-29 | 2022-01-11 | 2022-03-09 | 2022-02-08 | 29 | 30 | 14
509000 | Intel Sparrow | Oakville | Amiad Filters | AMIAD USA INC. | 4503662740 | Flow Control | Other | USD | 80000 | USD | 80000 | 0 | Supplier Competitions / Negotiation | 2021-08-26 | 2021-08-26 | 2021-08-31 | 2021-09-09 | 2021-09-28 | 2021-11-27 | 2021-09-16 | 2021-10-03 | 2022-02-28 | 2022-02-20 | 2022-02-24 | -4 | 12 | 38
509000 | Intel Sparrow | Oakville | Blower skid package | GARDNER DENVER ENGINEERED PRODUCTS | 4503808458 | Rotating Equipment | Blowers & Fans | USD | 222829 | CAD | 158369 | 64460 | Specs / Requirements Misinterpreted in Proposal | 2021-10-01 | 2022-03-08 | 2022-04-25 | 2021-10-19 | 2022-05-31 | 2022-04-20 | 2021-10-26 | 2022-06-13 | 2022-03-01 | 2022-11-08 | 2022-07-05 | 126 | 30 | 97
509000 | Intel Sparrow | Oakville | Chemical Feeding System | PROMINENT FLUID CONTROLS (FE) PTE L | 4503744754 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 185000 | CAD | 220204 | -35204 | Supplier Competitions / Negotiation | 2021-08-27 | 2021-10-25 | 2021-12-22 | 2021-09-17 | 2022-02-14 | 2022-01-30 | 2021-09-24 | 2022-02-23 | 2022-03-01 | 2022-07-06 | 2022-05-03 | 64 | 30 | 121
509000 | Intel Sparrow | Oakville | Electrical Panels - PLC | Integrated Systems Group | 4503745538 | Electrical & Instrumentation | Ele-PLCs, HMIs | USD | 478415 | USD | 461341 | 17074 | Single Sourced | 2021-08-26 | 2022-02-11 | 2022-01-28 | 2021-09-09 | 2022-02-18 | 2022-02-25 | 2021-09-16 | 2022-02-26 | 2022-01-17 | 2022-08-27 | 2022-05-08 | 111 | 18 | 15
509000 | Intel Sparrow | Oakville | Storage Tanks, incl. Decarbonator (FRP) | Plasticon Canada Inc. | 4503679887 | Fabrication | Non-Metal Equipment | USD | 1010000 | EUR | 1050088 | -40088 | Market Impact | 2021-08-27 | 2021-08-31 | 2021-09-24 | 2021-09-14 | 2021-10-13 | 2021-12-12 | 2021-09-21 | 2021-11-01 | 2022-03-01 | 2022-03-29 | 2022-03-15 | 14 | 12 | 62
509000 | Intel Sparrow | Oakville | Instrumentation -Cond. Sensor MT Lot 2 | METTLER TOLEDO THORNTON INC. | 4503692608 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 14000 | USD | 13648 | 352 | Single Sourced | 2021-12-14 | 2021-11-10 | 2021-11-18 | 2021-12-14 | 2021-11-23 | 2021-12-14 | 2021-12-14 | 2021-11-26 | 2021-12-14 | 2022-01-17 | 2021-12-31 | 17 | 18 | 16
509000 | Intel Sparrow | Oakville | Instrumentation - TOC Analyzer (CFO) | Lumitron Ltd | 4503699849 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 72000 | USD | 77422 | -5422 | Estimate Without Market Reference(No Quote) | 2022-01-04 | 2021-11-10 | 2021-11-17 | 2022-01-04 | 2021-12-01 | 2022-01-04 | 2022-01-04 | 2021-12-07 | 2022-01-04 | 2022-03-01 | 2022-02-01 | 28 | 18 | 27
509000 | Intel Sparrow | Oakville | N2 Manifold and Blanketing Skid | SWAGELOK SOUTHWESTERN ONTARIO | 4503711255 | Fabrication | Stainless Steel | USD | 44000 | CAD | 55603 | -11603 | Estimate Without Market Reference(No Quote) | 2021-09-28 | 2021-10-13 | 2021-10-21 | 2021-10-08 | 2021-12-12 | 2022-02-03 | 2021-10-15 | 2022-01-02 | 2022-03-01 | 2022-06-12 | 2022-04-21 | 52 | 12 | 81
509000 | Intel Sparrow | Oakville | RO Housing | CODELINE | 4503656620 | Flow Control | RO membrane housings | USD | 218000 | USD | 191520 | 26480 | Single Sourced | 2021-07-15 | 2021-09-01 | 2021-09-10 | 2021-07-22 | 2021-09-11 | 2021-10-19 | 2021-07-29 | 2021-09-23 | 2022-01-24 | 2021-12-30 | 2022-01-11 | -12 | 12 | 22
509000 | Intel Sparrow | Oakville | Skid Fabrication - Lot 1 (MCF) | 3D MECHANICAL | 4503665352 | Fabrication | Carbon Steel | USD | 38000 | CAD | 16504 | 21496 | Supplier Competitions / Negotiation | 2021-07-26 | 2021-09-17 | 2021-10-01 | 2021-08-16 | 2021-10-04 | 2021-10-21 | 2021-08-23 | 2021-10-06 | 2022-01-17 | 2022-01-10 | 2022-01-13 | -3 | 12 | 19
509000 | Intel Sparrow | Oakville | Skid Fabrication - Lot 2 (RO Skids 1st and 2nd pass) all 10 frames | 3D MECHANICAL | 4503699850 | Fabrication | Carbon Steel | USD | 100000 | CAD | 328957 | -228957 | Market Impact | 2021-08-30 | 2021-11-17 | 2021-10-21 | 2021-09-13 | 2021-12-03 | 2021-12-14 | 2021-09-20 | 2021-12-08 | 2022-02-14 | 2022-03-30 | 2022-03-08 | 22 | 12 | 21
509000 | Intel Sparrow | Oakville | Skid Fabrication - Lot 5a | PLASFAB LIMITED | 4503721135 | Fabrication | Carbon Steel | USD | 100000 | CAD | 67111 | 32889 | Supplier Competitions / Negotiation | 2021-09-10 | 2022-01-03 | 2022-01-10 | 2021-10-01 | 2022-01-11 | 2021-12-11 | 2021-10-08 | 2022-01-17 | 2022-03-04 | 2022-03-14 | 2022-03-09 | 5 | 12 | 14
509000 | Intel Sparrow | Oakville | Skid Fabrication - Lot 1a (PAB/AJ) | 3D MECHANICAL | 4503685168 | Fabrication | Carbon Steel | USD | 62000 | CAD | 53228 | 8772 | Supplier Competitions / Negotiation | 2021-12-15 | 2021-09-30 | 2021-11-11 | 2021-12-15 | 2021-11-10 | 2021-12-15 | 2021-12-15 | 2021-11-11 | 2021-12-15 | 2022-03-02 | 2022-01-22 | 39 | 12 | 42
509000 | Intel Sparrow | Oakville | Spool - Stainless - Lot 1 (MCF) | PANDA PIPING LTD | 4503660607 | Fabrication | Stainless Steel | USD | 40000 | CAD | 32088 | 7912 | Supplier Competitions / Negotiation | 2021-07-26 | 2021-09-17 | 2021-09-18 | 2021-08-16 | 2021-09-25 | 2021-10-21 | 2021-08-23 | 2021-09-30 | 2022-01-17 | 2022-01-05 | 2022-01-11 | -6 | 12 | 13
509000 | Intel Sparrow | Oakville | Spool - Stainless - Lot 2 - Dec | NV PIPING SYSTEMS INC. | 4503740469 | Fabrication | Stainless Steel | USD | 140000 | CAD | 117992 | 22008 | Supplier Competitions / Negotiation | 2021-08-23 | 2021-12-03 | 2022-02-10 | 2021-09-13 | 2022-02-10 | 2021-12-31 | 2021-09-20 | 2022-02-16 | 2022-02-14 | 2022-05-11 | 2022-03-29 | 43 | 12 | 75
509000 | Intel Sparrow | Oakville | Spool - Stainless - Lot 5 | PANDA PIPING LTD | 4503727465 | Fabrication | Stainless Steel | USD | 173223 | CAD | 173223 | 0 | Supplier Competitions / Negotiation | 2021-09-10 | 2022-01-03 | 2022-01-08 | 2021-10-01 | 2022-01-22 | 2021-12-29 | 2021-10-08 | 2022-02-21 | 2022-03-04 | 2022-04-18 | 2022-03-26 | 23 | 12 | 49
509000 | Intel Sparrow | Oakville | Spool - Stainless - Lot 3a - (PAB) | PANDA PIPING LTD | 4503665470 | Fabrication | Stainless Steel | USD | 70000 | CAD | 78623 | -8623 | Market Impact | 2021-11-21 | 2021-09-29 | 2021-10-01 | 2021-11-21 | 2021-10-02 | 2021-11-21 | 2021-11-21 | 2021-10-08 | 2021-11-21 | 2022-01-14 | 2021-12-18 | 27 | 12 | 9
509000 | Intel Sparrow | Oakville | Spool - Stainless - Lot 5 - Panda 2 | PANDA PIPING LTD | 4503733258 | Fabrication | Stainless Steel | USD | 147077 | CAD | 286146 | -139069 | Estimate Without Market Reference(No Quote) | 2022-02-25 | 2021-12-22 | 2022-01-27 | 2022-02-25 | 2022-02-04 | 2022-02-25 | 2022-02-25 | 2022-02-06 | 2022-02-25 | 2022-05-01 | 2022-03-29 | 33 | 12 | 46
509000 | Intel Sparrow | Oakville | Spools - Non Metallic - Lot 1 (Amiad AL, Ro Prefilter AG, CIP AJ) | GEORG FISCHER PIPING SYSTEMS LTD | 4503688817 | Flow Control | Plastic works, Spools | USD | 10000 | USD | 7421 | 2579 | Supplier Competitions / Negotiation | 2021-09-09 | 2021-09-17 | 2021-11-13 | 2021-09-16 | 2021-11-16 | 2021-12-08 | 2021-09-23 | 2021-11-19 | 2022-01-17 | 2022-03-09 | 2022-02-11 | 26 | 12 | 63
509000 | Intel Sparrow | Oakville | Spools - Non Metallic - Lot 2 | GEORG FISCHER PIPING SYSTEMS LTD | 4503718377 | Flow Control | Plastic works, Spools | USD | 49700 | USD | 49700 | 0 | Supplier Competitions / Negotiation | 2021-09-23 | 2021-12-03 | 2022-01-05 | 2021-09-30 | 2022-01-03 | 2021-12-15 | 2021-10-07 | 2022-01-11 | 2022-02-14 | 2022-03-09 | 2022-02-25 | 12 | 12 | 39
509000 | Intel Sparrow | Oakville | Spools - Non Metallic - Lot 5 - Jan | GEORG FISCHER PIPING SYSTEMS LTD | 4503726554 | Flow Control | Plastic works, Spools | USD | 100000 | USD | 210886 | -110886 | Estimate Without Market Reference(No Quote) | 2021-10-25 | 2021-01-03 | 2022-01-15 | 2021-11-01 | 2022-01-21 | 2021-08-26 | 2021-11-08 | 2022-01-25 | 2022-03-04 | 2022-04-19 | 2022-03-27 | 23 | 12 | 387
509000 | Intel Sparrow | Oakville | Valves - Pressure Control | LAKESIDE INDUSTRIAL SERVI | 4503710356 | Flow Control | Metal Control Valves | USD | 68500 | USD | 76079 | -7579 | Estimate Without Market Reference(No Quote) | 2021-07-15 | 2021-11-15 | 2021-12-09 | 2021-07-22 | 2021-12-17 | 2021-11-28 | 2021-07-29 | 2021-12-30 | 2022-02-21 | 2022-04-14 | 2022-03-19 | 26 | 12 | 45
509000 | Intel Sparrow | Oakville | VFD - Lot 1 | Integrated Systems Group | 4503684201 | Electrical & Instrumentation | Ele-PLCs, HMIs | USD | 190000 | USD | 359229 | -169229 | Single Sourced | 2021-07-01 | 2021-10-01 | 2021-10-07 | 2021-07-08 | 2021-11-08 | 2021-10-23 | 2021-07-15 | 2021-11-08 | 2022-02-07 | 2022-02-14 | 2022-02-10 | 4 | 18 | 38
509000 | Intel Sparrow | Oakville | Valves - Diaphragm | ITT INDUSTRIES HOLDINGS INC | 4503730101 | Flow Control | Metal Control Valves | USD | 12000 | USD | 7909 | 4091 | Supplier Competitions / Negotiation | 2021-07-08 | 2021-09-27 | 2022-01-05 | 2021-07-15 | 2022-01-31 | 2021-12-02 | 2021-07-22 | 2022-02-02 | 2022-01-17 | 2022-04-29 | 2022-03-09 | 51 | 12 | 128
509000 | Intel Sparrow | Oakville | Valves - Pressure Relief (CFO) | Great Lakes Industrial Controls | 4503707977 | Flow Control | Metal Safety(relief) Valves | USD | 18500 | CAD | 27331 | -8831 | Estimate Without Market Reference(No Quote) | 2021-07-22 | 2021-11-11 | 2021-10-15 | 2021-07-29 | 2021-12-14 | 2021-11-23 | 2021-08-05 | 2021-12-20 | 2022-01-17 | 2022-03-28 | 2022-02-21 | 35 | 12 | 39
509000 | Intel Sparrow | Oakville | Electrical Panels (Loose) | KELTOUR CONTROLS INC. | 4503702134 | Electrical & Instrumentation | Ele-Control Panels | USD | 30000 | CAD | 27841 | 2159 | Supplier Competitions / Negotiation | 2021-10-14 | 2021-10-08 | 2021-11-05 | 2021-10-28 | 2021-12-06 | 2022-01-03 | 2021-11-04 | 2021-12-09 | 2022-02-28 | 2022-03-31 | 2022-03-15 | 16 | 18 | 62
509000 | Intel Sparrow | Oakville | Motor Starter | Integrated Systems Group | 4503707975 | Electrical & Instrumentation | Ele-PLCs, HMIs | USD | 20000 | USD | 16974 | 3026 | Single Sourced | 2021-12-22 | 2021-10-10 | 2021-10-15 | 2021-12-22 | 2021-12-16 | 2021-12-22 | 2021-12-22 | 2021-12-20 | 2021-12-22 | 2022-03-06 | 2022-01-28 | 37 | 18 | 71
509000 | Intel Sparrow | Oakville | Instrumentation - Swan Analyzer | SWAN ANALYTICAL INSTRUMENTS | 4503709606 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 20000 | USD | 20171 | -171 | Size/ Weight/ Quantity Underestimated | 2022-01-03 | 2021-12-10 | 2021-12-23 | 2022-01-03 | 2021-12-21 | 2022-01-03 | 2022-01-03 | 2021-12-27 | 2022-01-03 | 2022-01-27 | 2022-01-15 | 12 | 18 | 17
509000 | Intel Sparrow | Oakville | Instrumentation - Flowmeters | Engineered Process Control | 4503721761 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 494000 | USD | 492208 | 1792 | Supplier Competitions / Negotiation | 2022-02-17 | 2021-10-25 | 2021-11-12 | 2022-02-17 | 2021-12-21 | 2022-02-17 | 2022-02-17 | 2022-01-17 | 2022-02-17 | 2022-06-12 | 2022-04-15 | 58 | 18 | 84
509000 | Intel Sparrow | Oakville | Electrical - Safety Switches | KELTOUR CONTROLS INC. | 4503713986 | Electrical & Instrumentation | Ele-Electrical Supply (Inc Cable Tray) | USD | 52000 | CAD | 52416 | -416 | Estimate Without Market Reference(No Quote) | 2022-01-25 | 2021-12-06 | 2021-12-10 | 2022-01-25 | 2021-12-19 | 2022-01-25 | 2022-01-25 | 2022-01-05 | 2022-01-25 | 2022-03-16 | 2022-02-19 | 25 | 18 | 30
509000 | Intel Sparrow | Oakville | Valves - Pressure Relief (Lot 2 - CFO) | Great Lakes Industrial Controls | 4503717683 | Flow Control | Metal Safety(relief) Valves | USD | 8000 | CAD | 7142 | 858 | Supplier Competitions / Negotiation | 2022-02-13 | 2021-12-23 | 2022-01-06 | 2022-02-13 | 2022-01-07 | 2022-02-13 | 2022-02-13 | 2022-01-12 | 2022-02-13 | 2022-04-07 | 2022-03-11 | 27 | 12 | 20
509000 | Intel Sparrow | Oakville | Instrumentation - Chlorine & Turb Analyzer | HACH SALES & SERVICE CANADA LTD-REM | 4503717769 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 9500 | CAD | 7551 | 1949 | Supplier Competitions / Negotiation | 2021-12-13 | 2021-11-12 | 2021-12-23 | 2021-12-13 | 2021-12-23 | 2021-12-13 | 2021-12-13 | 2022-01-13 | 2021-12-13 | 2022-01-13 | 2021-12-28 | 16 | 18 | 62
509000 | Intel Sparrow | Oakville | Instrumentation - Pressure Transmitters | LAKESIDE PROCESS CONTROLS LTD. | 4503717774 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 13000 | USD | 12907 | 93 | Market Impact | 2022-01-01 | 2021-11-09 | 2021-12-22 | 2022-01-01 | 2021-12-23 | 2022-01-01 | 2022-01-01 | 2022-01-13 | 2022-01-01 | 2022-02-24 | 2022-01-28 | 27 | 18 | 65
509000 | Intel Sparrow | Oakville | HUPW - GF Skid | GEORG FISCHER LLC | 4503721138 | Rotating Equipment | Others | USD | 75043 | USD | 81053 | -6010 | Market Impact | 2022-02-17 | 2021-12-10 | 2021-12-15 | 2022-02-17 | 2021-12-13 | 2022-02-17 | 2022-02-17 | 2022-01-16 | 2022-02-17 | 2022-04-28 | 2022-03-24 | 35 | 30 | 37
509000 | Intel Sparrow | Oakville | Spool - Carbon Steel - Lot 5 | Alps Welding Ltd. | 4503730103 | Fabrication | Carbon Steel | USD | 58000 | CAD | 133897 | -75897 | Market Impact | 2022-02-18 | 2022-01-03 | 2022-01-18 | 2022-02-18 | 2022-01-24 | 2022-02-18 | 2022-02-18 | 2022-01-30 | 2022-02-18 | 2022-04-06 | 2022-03-13 | 24 | 12 | 27
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | FEEDWATER / PERMEATE PUMP SKID | ALFA LAVAL | 4503731575 | Rotating Equipment | Centrifugal Pumps | USD | 30000 | USD | 28129 | 1871 | Estimate Without Market Reference(No Quote) | 2022-01-26 | 2021-12-28 | 2022-02-03 | 2022-02-03 | 2022-02-02 | 2022-02-20 | 2022-02-07 | 2022-02-02 | 2022-04-15 | 2022-04-13 | 2022-04-14 | -1 | 30 | 36
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | STRAINER SKID | FORSTA FILTERS | 4503731553 | Fabrication | Skid Assembly Outsourced | USD | 210900 | USD | 214170 | -3270 | Proposed Supplier Incapable Of Executing | 2022-01-24 | 2022-01-27 | 2022-02-01 | 2022-01-26 | 2022-02-03 | 2022-03-05 | 2022-01-27 | 2022-02-02 | 2022-04-15 | 2022-03-28 | 2022-04-06 | -9 | 12 | 6
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | ACTIVATED CARBON FILTER_ASSY | ARC SERVICES | 4503782192 | Fabrication | Skid Assembly Outsourced | USD | 28425 | USD | 83131 | -54706 | Proposed Supplier Incapable Of Executing | 2021-12-16 | 2021-12-28 | 2022-04-28 | 2022-01-29 | 2022-04-28 | 2022-04-07 | 2022-02-07 | 2022-04-28 | 2022-05-27 | 2022-07-29 | 2022-06-27 | 32 | 12 | 121
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | ACTIVATED CARBON FILTER- POLISHED | Arrow Tanks | 4503727468 | Fabrication | Stainless Steel | USD | 233500 | USD | 233500 | 0 | Not included in Proposal / RFQ | 2021-11-16 | 2021-11-16 | 2021-11-19 | 2022-12-28 | 2022-01-27 | 2022-06-07 | 2022-01-26 | 2022-01-27 | 2022-04-25 | 2022-05-17 | 2022-05-06 | 11 | 12 | 72
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | ASSY_PRIMARY RO SKIDS | ALFA LAVAL | 4503734217 | Rotating Equipment | Centrifugal Pumps | USD | 43072 | USD | 43072 | 0 | Supplier Competitions / Negotiation | 2022-03-15 | 2022-01-20 | 2022-01-20 | 2022-03-15 | 2022-02-08 | 2022-03-15 | 2022-03-15 | 2022-02-08 | 2022-03-15 | 2022-05-09 | 2022-04-11 | 28 | 30 | 19
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | ASSY_RECOVERY RO SKID | ALFA LAVAL | 4513734217 | Rotating Equipment | Centrifugal Pumps | USD | 14357 | USD | 14357 | 0 | Market Impact | 2022-03-15 | 2022-01-20 | 2022-01-20 | 2022-03-15 | 2022-02-08 | 2022-03-15 | 2022-03-15 | 2022-02-08 | 2022-03-15 | 2022-05-09 | 2022-04-11 | 28 | 30 | 19
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | ASSY_RECOVERY RO SKID | ALFA LAVAL | 4513760373 | Rotating Equipment | Centrifugal Pumps | USD | 21335 | USD | 21335 | 0 | Proposed Supplier Incapable Of Executing | 2022-04-05 | 2022-04-05 | 2022-02-08 | 2022-04-05 | 2022-03-22 | 2022-04-05 | 2022-04-05 | 2022-03-22 | 2022-04-05 | 2022-05-31 | 2022-05-03 | 28 | 30 | -14
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | LS_FEEDWATER UV | AQUIONICS, INC. | 4503726561 | Electrical & Instrumentation | Ele-Electrical Others | USD | 65008 | USD | 32889 | 32119 | Estimate Without Market Reference(No Quote) | 2022-01-24 | 2021-11-13 | 2021-11-15 | 2022-01-25 | 2022-01-27 | 2022-01-28 | 2022-01-26 | 2022-01-27 | 2022-04-15 | 2022-04-11 | 2022-04-13 | -2 | 18 | 75
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | LS_CARTRIDGE FILTER HOUSING | Duncan Co. | 4503725822 | Flow Control | Filters And Strainers (Incl Housings) | USD | 29000 | USD | 12853 | 16147 | Frame Agreements | 2022-01-25 | 2022-01-25 | 2022-01-25 | 2022-01-25 | 2022-01-24 | 2022-03-05 | 2022-01-25 | 2022-01-24 | 2022-04-15 | 2022-04-10 | 2022-04-12 | -2 | 12 | -1
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | LS_PERMEATE UV | AQUIONICS, INC. | 4513726561 | Electrical & Instrumentation | Ele-Electrical Others | USD | 117656 | USD | 117656 | 0 | Design Optimizations | 2022-01-24 | 2021-11-13 | 2021-11-15 | 2022-01-25 | 2022-01-27 | 2022-01-28 | 2022-01-26 | 2022-01-27 | 2022-04-15 | 2022-04-11 | 2022-04-13 | -2 | 18 | 75
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | LS_MOTOR CONTROL ENCLOSURE | WERNER ELECTRIC | 4503741136 | Electrical & Instrumentation | Ele-Control Panels | USD | 190000 | USD | 149775 | 40225 | Supplier Competitions / Negotiation | 2022-01-27 | 2022-01-26 | 2022-02-11 | 2022-02-03 | 2022-02-16 | 2022-04-17 | 2022-02-03 | 2022-02-18 | 2022-04-29 | 2022-07-08 | 2022-06-03 | 35 | 18 | 23
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | DS_FEEDWATER TANK | Augusta Fiberglass | 4503731577 | Fabrication | Non-Metal Equipment | USD | 58690 | USD | 67291 | -8601 | Market Impact | 2022-01-26 | 2022-01-20 | 2022-02-03 | 2022-01-31 | 2022-02-02 | 2022-03-31 | 2022-01-31 | 2022-02-02 | 2022-06-10 | 2022-05-30 | 2022-06-04 | -5 | 12 | 13
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | DS_PERMEATE TANK | Westec Tank & Equipment Co. | 4503751802 | Fabrication | Stainless Steel | USD | 130000 | USD | 153700 | -23700 | Market Impact | 2022-01-22 | 2022-01-20 | 2022-02-01 | 2022-01-27 | 2022-03-07 | 2022-04-03 | 2022-01-31 | 2022-03-07 | 2022-06-10 | 2022-06-16 | 2022-06-13 | 3 | 12 | 46
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | DS_VALVE MATRIX | ALFA LAVAL | 4503737784 | Flow Control | Metal Control Valves | USD | 322781 | USD | 304577 | 18204 | Estimate Without Market Reference(No Quote) | 2022-03-01 | 2022-01-27 | 2022-02-11 | 2022-03-01 | 2022-02-10 | 2022-04-07 | 2022-03-01 | 2022-02-13 | 2022-06-17 | 2022-06-05 | 2022-06-11 | -6 | 12 | 17
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | ASSY_RECOVERY RO SKIDS | BW Systems | 4523733972 | Electrical & Instrumentation | Ele-Control Panels | USD | 15728 | USD | 15728 | 0 | Estimate Without Market Reference(No Quote) | 2022-03-25 | 2022-01-26 | 2022-02-08 | 2022-03-25 | 2022-02-08 | 2022-03-25 | 2022-03-25 | 2022-02-08 | 2022-03-25 | 2022-05-23 | 2022-04-23 | 30 | 18 | 13
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | ASSY_PRIMARY RO SKIDS | BW Systems | 4513733972 | Electrical & Instrumentation | Ele-Control Panels | USD | 49770 | USD | 49770 | 0 | Specs / Requirements Misinterpreted in Proposal | 2022-03-16 | 2022-01-26 | 2022-02-03 | 2022-03-16 | 2022-02-08 | 2022-03-16 | 2022-03-16 | 2022-02-08 | 2022-03-16 | 2022-05-05 | 2022-04-10 | 25 | 18 | 13
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | ACTIVATED CARBON TOWERS - ELEC | BW Systems | 4503733972 | Electrical & Instrumentation | Ele-Control Panels | USD | 30130 | USD | 30130 | 0 | Frame Agreements | 2022-03-16 | 2022-01-26 | 2022-02-08 | 2022-03-16 | 2022-02-08 | 2022-03-16 | 2022-03-16 | 2022-02-08 | 2022-03-16 | 2022-05-04 | 2022-04-09 | 25 | 18 | 13
509065 | RO EXP RAUCH N/AMERICA | Minnetonka | ASSY_PRIMARY RO SKIDS | ALFA LAVAL | 4503760373 | Rotating Equipment | Centrifugal Pumps | USD | 64004 | USD | 64004 | 0 | Proposed Supplier Incapable Of Executing | 2022-04-05 | 2022-04-05 | 2022-02-08 | 2022-04-05 | 2022-03-22 | 2022-04-05 | 2022-04-05 | 2022-03-22 | 2022-04-05 | 2022-05-31 | 2022-05-03 | 28 | 30 | -14
509089 | Standard Lithium DLC Pilot | Oakville | Simulated Moving Bed (SMB) - Used Unit | CALGON CARBON CORPORATION | 4503749177 | Fabrication | Process Equipment | USD | 100000 | USD | 100000 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-12-10 | 2021-12-03 | 2021-12-08 | 2021-12-24 | 2022-02-16 | 2022-02-14 | 2022-02-25 | 2022-03-02 | 2022-04-28 | 2022-04-10 | 2022-04-19 | -9 | 6 | 89
509089 | Standard Lithium DLC Pilot | Oakville | Simulated Moving Bed (SMB) - Resin Cells | Chicago Plastics Systems, Inc | 4503000099 | Fabrication | Process Equipment | USD | 18000 | USD | 16896 | 1104 | Supplier Competitions / Negotiation | 2022-02-23 | 2022-02-23 | 2022-02-25 | 2022-02-23 | 2022-02-22 | 2022-03-20 | 2022-02-25 | 2022-02-24 | 2022-04-05 | 2022-04-15 | 2022-04-10 | 5 | 12 | 1
509089 | Standard Lithium DLC Pilot | Oakville | Phys-Chem Pre-Treatment Clarifier | Chicago Plastics Systems, Inc | 4503756444 | Fabrication | Process Equipment | USD | 40000 | USD | 12418 | 27582 | Supplier Competitions / Negotiation | 2021-12-10 | 2022-02-16 | 2022-02-18 | 2022-02-23 | 2022-03-14 | 2022-02-11 | 2022-02-25 | 2022-02-23 | 2022-04-01 | 2022-04-15 | 2022-04-08 | 7 | 12 | 7
509089 | Standard Lithium DLC Pilot | Oakville | Containerized Pilot | TRIVACO | 4503738873 | Fabrication | Skid Assembly Outsourced | USD | 297800 | USD | 312772 | -14972 | Supplier Competitions / Negotiation | 2021-12-20 | 2021-12-07 | 2021-12-17 | 2021-12-27 | 2021-12-23 | 2022-03-02 | 2021-12-29 | 2021-12-26 | 2022-05-27 | 2021-12-26 | 2022-03-12 | -76 | 12 | 19
509089 | Standard Lithium DLC Pilot | Oakville | Pumps - Macroy | Milton Roy | 4503748265 | Rotating Equipment | Centrifugal Pumps | USD | 6347 | USD | 6216 | 131 | Supplier Competitions / Negotiation | 2022-02-04 | 2022-02-04 | 2022-02-15 | 2022-02-15 | 2022-02-17 | 2022-03-02 | 2022-02-18 | 2022-02-28 | 2022-03-01 | 2022-03-28 | 2022-03-14 | 14 | 36 | 24
509089 | Standard Lithium DLC Pilot | Oakville | Pumps - MicroPumps & Fluid-O-Tech | BURT PROCESS | 4503752962 | Rotating Equipment | Centrifugal Pumps | USD | 9075 | USD | 7170 | 1905 | Supplier Competitions / Negotiation | 2022-02-14 | 2022-02-14 | 2022-03-03 | 2022-02-22 | 2022-02-27 | 2022-03-10 | 2022-02-28 | 2022-02-28 | 2022-03-01 | 2022-04-04 | 2022-03-18 | 17 | 36 | 14
509110 | NXP Semiconductor ATMC | Guelph | RO HP Pump | Pumps Unlimited | 4503742877 | Rotating Equipment | PD Pumps | USD | 79790 | USD | 80634 | -844 | Supplier Competitions / Negotiation | 2022-02-11 | 2022-02-16 | 2022-02-17 | 2022-02-18 | 2022-02-17 | 2022-04-01 | 2022-02-25 | 2022-02-21 | 2022-05-20 | 2022-05-16 | 2022-05-18 | -2 | 30 | 5
509110 | NXP Semiconductor ATMC | Guelph | RO Housings | PENTAIR FILTRATION SOLUTIONS, LLC | 4503742878 | Fabrication | Process Equipment | USD | 18739 | USD | 18535 | 204 | Supplier Competitions / Negotiation | 2021-12-17 | 2022-02-15 | 2022-02-18 | 2021-12-24 | 2022-02-17 | 2022-04-06 | 2021-12-31 | 2022-02-21 | 2022-05-20 | 2022-07-25 | 2022-06-22 | 33 | 12 | 6
509110 | NXP Semiconductor ATMC | Guelph | Butterfly Valves - Auto (Acris) | Amresist | 4503760723 | Flow Control | Metal Control Valves | USD | 5692 | USD | 10551 | -4859 | Supplier Competitions / Negotiation | 2022-03-25 | 2022-02-24 | 2022-03-11 | 2022-03-25 | 2022-03-13 | 2022-04-26 | 2022-04-22 | 2022-03-20 | 2022-05-20 | 2022-06-26 | 2022-06-07 | 19 | 12 | 24
509110 | NXP Semiconductor ATMC | Guelph | Ball Valves - Man (Apollo) | Aalberts Integrated Piping Systems | 4503759500 | Flow Control | Metal Control Valves | USD | 9111 | CAD | 9111 | 0 | Supplier Competitions / Negotiation | 2022-02-15 | 2022-02-24 | 2022-03-14 | 2022-03-25 | 2022-03-15 | 2022-04-03 | 2022-02-25 | 2022-03-19 | 2022-05-20 | 2022-05-19 | 2022-05-19 | 0 | 12 | 23
509110 | NXP Semiconductor ATMC | Guelph | Ball Valves - Man (SVF) | Sylvan Automation Ltd. | 4503759411 | Flow Control | Metal Control Valves | USD | 6330 | CAD | 6330 | 0 | Not included in Proposal / RFQ | 2022-02-15 | 2022-02-24 | 2022-03-14 | 2022-03-25 | 2022-03-16 | 2022-04-03 | 2022-02-25 | 2022-03-21 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 0 | 12 | 25
509110 | NXP Semiconductor ATMC | Guelph | Globe Valve (Lakeside) | LAKESIDE PROCESS CONTROLS LTD. | 4503759479 | Flow Control | Metal Control Valves | USD | 18053 | USD | 19146 | -1093 | Market Impact | 2022-02-15 | 2022-02-25 | 2022-03-14 | 2022-02-20 | 2022-03-14 | 2022-05-05 | 2022-02-25 | 2022-03-20 | 2022-05-20 | 2022-07-24 | 2022-06-21 | 33 | 12 | 23
509110 | NXP Semiconductor ATMC | Guelph | Frame & Platform | PROCESS GROUP INTERNATIONAL LTD. | 4503760296 | Fabrication | Platform & Module | USD | 28455 | CAD | 20574 | 7881 | Supplier Competitions / Negotiation | 2022-02-11 | 2022-02-28 | 2022-03-16 | 2022-03-17 | 2022-03-22 | 2022-04-01 | 2022-02-25 | 2022-03-22 | 2022-05-20 | 2022-03-22 | 2022-04-20 | -29 | 12 | 22
509110 | NXP Semiconductor ATMC | Guelph | Flow Meter | KEYENCE CORPORATION | 4503754566 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 20517 | USD | 12796 | 7721 | Supplier Competitions / Negotiation | 2022-03-25 | 2022-02-24 | 2022-03-01 | 2022-04-01 | 2022-03-01 | 2022-04-07 | 2022-04-08 | 2022-03-09 | 2022-05-20 | 2022-05-19 | 2022-05-19 | 0 | 18 | 13
509110 | NXP Semiconductor ATMC | Guelph | Conductivity Analyzer | METTLER TOLEDO THORNTON INC. | 4503759273 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 16409 | USD | 7698 | 8711 | Supplier Competitions / Negotiation | 2022-03-29 | 2022-02-24 | 2022-03-09 | 2022-04-12 | 2022-03-14 | 2022-04-07 | 2022-04-26 | 2022-03-19 | 2022-05-20 | 2022-03-19 | 2022-04-19 | -31 | 18 | 23
509110 | NXP Semiconductor ATMC | Guelph | Stainless Steel Piping | NV PIPING SYSTEMS INC. | 4503763090 | Fabrication | Stainless Steel | USD | 26922 | CAD | 31204 | -4282 | Market Impact | 2022-03-25 | 2022-02-18 | 2022-03-23 | 2022-04-01 | 2022-03-22 | 2022-05-18 | 2022-04-08 | 2022-03-24 | 2022-05-20 | 2022-08-16 | 2022-07-03 | 44 | 12 | 34
509110 | NXP Semiconductor ATMC | Guelph | Soleoid Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503768690 | Electrical & Instrumentation | Ele-Control Panels | USD | 5000 | CAD | 5580 | -580 | Market Impact | 2022-03-11 | 2022-03-21 | 2022-04-04 | 2022-03-25 | 2022-03-31 | 2022-04-15 | 2022-04-08 | 2022-04-05 | 2022-05-20 | 2022-05-20 | 2022-05-20 | 0 | 18 | 15
509114 | NXP MB Vessel | Oakville | Pressure Vessels | Alps Welding Ltd. | 4503766381 | Fabrication | Carbon Steel | USD | 97215 | CAD | 62960 | 34255 | Design Optimizations | 2022-02-13 | 2022-02-15 | 2022-03-18 | 2022-02-27 | 2022-03-22 | 2022-04-25 | 2022-03-06 | 2022-03-22 | 2022-05-29 | 2022-07-05 | 2022-06-16 | 19 | 12 | 35
509114 | NXP MB Vessel | Oakville | Pressure Vessels - Painting and EFTE Lining | Fisher Utah | 4503769754 | Fabrication | Carbon Steel | USD | 96646 | USD | 91400 | 5246 | Frame Agreements | 2022-05-15 | 2022-02-15 | 2022-03-28 | 2022-05-22 | 2022-03-28 | 2022-05-19 | 2022-05-29 | 2022-04-04 | 2022-07-10 | 2022-08-20 | 2022-07-30 | 21 | 12 | 48
509114 | NXP MB Vessel | Oakville | Pressure Vessels - Internals - SS | NV PIPING SYSTEMS INC. | 4503763093 | Fabrication | Stainless Steel | USD | 27736 | CAD | 70880 | -43144 | Market Impact | 2022-03-18 | 2022-03-03 | 2022-03-23 | 2022-04-01 | 2022-03-22 | 2022-04-11 | 2022-04-08 | 2022-03-23 | 2022-05-20 | 2022-03-23 | 2022-04-21 | -29 | 12 | 20
509114 | NXP MB Vessel | Oakville | Instrument - Level Switch & Transmitter - Flow | Engineered Process Control | 4503762983 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 26423 | CAD | 9832 | 16591 | Supplier Competitions / Negotiation | 2022-03-11 | 2022-03-07 | 2022-03-16 | 2022-03-18 | 2022-03-17 | 2022-05-25 | 2022-03-25 | 2022-03-25 | 2022-05-20 | 2022-08-12 | 2022-07-01 | 42 | 18 | 18
509114 | NXP MB Vessel | Oakville | Valves - Diaphragm | ITT ENGINEERED VALVES LLC | 4503766374 | Flow Control | Metal Control Valves | USD | 56578 | USD | 46605 | 9973 | Supplier Competitions / Negotiation | 2022-03-11 | 2022-03-07 | 2022-03-17 | 2022-03-18 | 2022-03-29 | 2022-04-29 | 2022-03-25 | 2022-03-30 | 2022-05-20 | 2022-06-22 | 2022-06-05 | 17 | 12 | 23
509114 | NXP MB Vessel | Oakville | Spool Piping - Carbon Steel Lined | BAUM AMERICA CORP | 4503808402 | Fabrication | Stainless Steel | USD | 69444 | USD | 79256 | -9812 | Market Impact | 2022-03-11 | 2022-03-24 | 2022-05-09 | 2022-03-18 | 2022-06-07 | 2022-06-07 | 2022-03-25 | 2022-06-12 | 2022-05-20 | 2022-09-04 | 2022-07-12 | 54 | 12 | 80
509114 | NXP MB Vessel | Oakville | Electrical - Junction Box | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503772508 | Electrical & Instrumentation | Ele-nclosures | USD | 12832 | CAD | 5176 | 7656 | Frame Agreements | 2022-03-11 | 2022-03-24 | 2022-04-04 | 2022-03-18 | 2022-03-31 | 2022-04-28 | 2022-03-25 | 2022-04-12 | 2022-05-20 | 2022-06-15 | 2022-06-02 | 13 | 18 | 19
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | Control panel | Integrated Systems Group | 4503810723 | Electrical & Instrumentation | Ele-Control Panels | USD | 154950 | USD | 182284 | -27334 | Proposed Supplier Incapable Of Executing | 2022-01-02 | 2022-04-08 | 2022-06-15 | 2022-01-09 | 2022-06-17 | 2022-07-04 | 2022-01-14 | 2022-07-19 | 2022-05-06 | 2023-01-03 | 2022-09-04 | 121 | 18 | 102
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | VFD / Starter | Integrated Systems Group | 4503758179 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 15300 | USD | 19408 | -4108 | Market Impact | 2022-02-13 | 2022-02-18 | 2022-02-25 | 2022-02-20 | 2022-03-11 | 2022-04-26 | 2022-02-25 | 2022-03-17 | 2022-05-06 | 2022-07-07 | 2022-06-06 | 31 | 18 | 27
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | Control panel | KELTOUR CONTROLS INC. | 4503777856 | Electrical & Instrumentation | Ele-Control Panels | USD | 7000 | USD | 7942 | -942 | Market Impact | 2022-01-02 | 2022-04-08 | 2022-04-18 | 2022-01-09 | 2022-04-19 | 2022-04-29 | 2022-04-29 | 2022-04-20 | 2022-04-29 | 2022-08-24 | 2022-06-26 | 59 | 18 | 12
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | Painted Frames | PLASFAB LIMITED | 4503763278 | Fabrication | Carbon Steel | USD | 7276 | CAD | 7276 | 0 | Supplier Competitions / Negotiation | 2022-02-27 | 2022-03-10 | 2022-03-16 | 2022-03-06 | 2022-03-18 | 2022-04-13 | 2022-03-11 | 2022-03-27 | 2022-05-06 | 2022-05-29 | 2022-05-17 | 12 | 12 | 17
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | Painted Frames | Process Group INC | 4503807568 | Fabrication | Carbon Steel | USD | 7782 | USD | 8408 | -626 | Market Impact | 2022-02-27 | 2022-05-25 | 2022-06-08 | 2022-06-05 | 2022-06-10 | 2022-06-04 | 2022-06-10 | 2022-06-13 | 2022-09-10 | 2022-08-22 | 2022-08-31 | -9 | 12 | 19
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | Cartridge Filter | 3M Company | 4503797487 | Flow Control | Filters And Strainers (Incl Housings) | USD | 102389 | USD | 80986 | 21403 | Supplier Competitions / Negotiation | 2022-03-28 | 2022-05-17 | 2022-05-19 | 2022-04-04 | 2022-05-24 | 2022-06-14 | 2022-04-09 | 2022-05-25 | 2022-07-02 | 2022-08-31 | 2022-08-01 | 30 | 12 | 8
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | UF Skid | GEORG FISCHER LLC | 4503768142 | Fabrication | Skid Assembly Outsourced | USD | 38883 | USD | 51272 | -12389 | Market Impact | 2022-02-28 | 2022-03-25 | 2022-03-15 | 2022-03-07 | 2022-03-25 | 2022-05-12 | 2022-03-12 | 2022-04-04 | 2022-07-02 | 2022-07-25 | 2022-07-13 | 12 | 12 | 10
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | Process Pump | MTCR Site Service | 4503769820 | Rotating Equipment | Centrifugal Pumps | USD | 62316 | USD | 69176 | -6860 | Market Impact | 2022-02-14 | 2022-03-24 | 2022-04-01 | 2022-02-21 | 2022-04-03 | 2022-06-17 | 2022-02-26 | 2022-04-06 | 2022-09-17 | 2022-10-19 | 2022-10-03 | 16 | 30 | 13
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | Spool fabrication - Plastic | GEORG FISCHER LLC | 4503774251 | Fabrication | Non-Metal Equipment | USD | 20000 | USD | 21800 | -1800 | Market Impact | 2022-01-02 | 2022-04-06 | 2022-04-07 | 2022-05-02 | 2022-04-08 | 2022-05-02 | 2022-05-02 | 2022-04-13 | 2022-05-02 | 2022-08-31 | 2022-07-01 | 61 | 12 | 7
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | Spool fabrication - Plastic | GEORG FISCHER LLC | 4503767217 | Fabrication | Non-Metal Equipment | USD | 14180 | USD | 14667 | -487 | Market Impact | 2022-01-02 | 2022-03-10 | 2022-03-23 | 2022-04-26 | 2022-03-24 | 2022-04-26 | 2022-04-26 | 2022-03-31 | 2022-04-26 | 2022-08-18 | 2022-06-22 | 57 | 12 | 21
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | Spool fabrication - Carbon Steel | Alps Welding Ltd. | 4503798312 | Fabrication | Stainless Steel | USD | 7009 | USD | 7300 | -291 | Market Impact | 2022-02-27 | 2022-04-12 | 2022-05-05 | 2022-03-06 | 2022-05-24 | 2022-05-17 | 2022-03-11 | 2022-05-26 | 2022-05-06 | 2022-08-04 | 2022-06-20 | 45 | 12 | 44
509131 | Intel MSB IMO Carbonator Syst and RA4 Redundancy Upgrade Kit | Guelph | Transmitter | Engineered Process Control | 4503780775 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 51667 | USD | 57234 | -5567 | Specs / Requirements Misinterpreted in Proposal | 2022-02-13 | 2022-04-02 | 2022-04-14 | 2022-02-20 | 2022-04-19 | 2022-06-13 | 2022-02-25 | 2022-04-26 | 2022-05-06 | 2022-10-11 | 2022-07-24 | 79 | 18 | 24
509147 | CHOBANI RO WATER REUSE TWIN FALLS | Minnetonka | MAIN CONTROL PANEL | BW Systems | 4503717704 | Electrical & Instrumentation | Ele-Control Panels | USD | 25000 | USD | 17855 | 7145 | Design Optimizations | 2022-01-04 | 2022-01-04 | 2022-01-12 | 2022-01-13 | 2022-01-10 | 2022-02-26 | 2022-01-13 | 2022-01-10 | 2022-04-20 | 2022-04-05 | 2022-04-12 | -7 | 18 | 6
509147 | CHOBANI RO WATER REUSE TWIN FALLS | Minnetonka | ASSY_RO PROFLEX-72_CONTROL PANELS | BW Systems | 4513717704 | Electrical & Instrumentation | Ele-Control Panels | USD | 33690 | USD | 33690 | 0 | Estimate Without Market Reference(No Quote) | 2022-01-04 | 2022-01-04 | 2022-01-12 | 2022-01-13 | 2022-01-12 | 2022-02-26 | 2022-01-13 | 2022-01-12 | 2022-04-20 | 2022-04-07 | 2022-04-13 | -6 | 18 | 8
509147 | CHOBANI RO WATER REUSE TWIN FALLS | Minnetonka | ASSY_CIP SYSTEM_PUMP | PFC EQUIPMENT | 4503716882 | Rotating Equipment | Centrifugal Pumps | USD | 6883 | USD | 6969 | -86 | Market Impact | 2022-01-10 | 2022-01-10 | 2022-01-12 | 2022-01-12 | 2022-01-11 | 2022-02-19 | 2022-01-12 | 2022-01-11 | 2022-04-01 | 2022-03-01 | 2022-03-16 | -15 | 30 | 1
509147 | CHOBANI RO WATER REUSE TWIN FALLS | Minnetonka | ASSY_RO PROFLEX-72 | R&R Metalworks | 4503749077 | Fabrication | Stainless Steel | USD | 53614 | USD | 59775 | -6161 | Estimate Without Market Reference(No Quote) | 2022-03-23 | 2022-03-23 | 2022-03-03 | 2022-03-23 | 2022-03-03 | 2022-03-23 | 2022-03-23 | 2022-03-03 | 2022-03-23 | 2022-04-12 | 2022-04-02 | 10 | 12 | -20
509153 | Aquamex | Guelph | Blower | AERZEN CANADA INC | 4503717623 | Rotating Equipment | Compressors | USD | 17989 | CAD | 12497 | 5492 | Supplier Competitions / Negotiation | 2022-01-21 | 2021-12-22 | 2021-12-22 | 2022-01-28 | 2022-01-13 | 2022-02-24 | 2022-02-04 | 2022-01-13 | 2022-04-29 | 2022-03-28 | 2022-03-16 | 12 | 36 | 22
509157 | INTEL HEDGEHOG | Oakville | VFD | Integrated Systems Group | 4503793251 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 13395 | USD | 19270 | -5875 | Market Impact | 2022-02-28 | 2022-02-14 | 2022-05-11 | 2022-03-07 | 2022-05-16 | 2022-06-14 | 2022-03-14 | 2022-05-18 | 2022-08-01 | 2022-10-12 | 2022-09-06 | 36 | 18 | 93
509157 | INTEL HEDGEHOG | Oakville | Starter | Integrated Systems Group | 4503751501 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 9000 | USD | 9480 | -480 | Market Impact | 2022-02-28 | 2022-02-18 | 2022-02-23 | 2022-05-09 | 2022-02-28 | 2022-05-09 | 2022-05-09 | 2022-03-08 | 2022-05-09 | 2022-07-28 | 2022-06-18 | 40 | 18 | 18
509157 | INTEL HEDGEHOG | Oakville | Control panel | Machine Control Systems | 4503747004 | Electrical & Instrumentation | Ele-Control Panels | USD | 52000 | USD | 57434 | -5434 | Market Impact | 2022-02-17 | 2022-02-18 | 2022-02-28 | 2022-05-07 | 2022-03-01 | 2022-05-07 | 2022-05-07 | 2022-03-01 | 2022-05-07 | 2022-07-26 | 2022-06-16 | 40 | 18 | 11
509157 | INTEL HEDGEHOG | Oakville | Control panel | Keltour Controls Inc. | 4503773117 | Electrical & Instrumentation | Ele-Control Panels | USD | 8000 | USD | 7584 | 416 | Supplier Competitions / Negotiation | 2022-02-17 | 2022-03-22 | 2022-04-01 | 2022-04-20 | 2022-04-11 | 2022-04-20 | 2022-04-20 | 2022-04-12 | 2022-04-20 | 2022-06-21 | 2022-05-21 | 31 | 18 | 21
509157 | INTEL HEDGEHOG | Oakville | Tank | TERRACON CORP | 4503747006 | Fabrication | Non-Metal Equipment | USD | 17000 | USD | 17467 | -467 | Market Impact | 2022-02-15 | 2022-02-10 | 2022-02-23 | 2022-02-22 | 2022-03-22 | 2022-04-13 | 2022-03-01 | 2022-02-28 | 2022-06-14 | 2022-05-24 | 2022-06-03 | -10 | 12 | 18
509157 | INTEL HEDGEHOG | Oakville | Heat Exchanger | ALFA LAVAL | 4503758181 | Fabrication | Process Equipment | USD | 87434 | USD | 84222 | 3212 | Supplier Competitions / Negotiation | 2022-02-10 | 2022-03-11 | 2022-02-17 | 2022-02-17 | 2022-03-15 | 2022-05-23 | 2022-02-24 | 2022-03-16 | 2022-09-01 | 2022-09-02 | 2022-09-01 | 1 | 12 | 5
509157 | INTEL HEDGEHOG | Oakville | Skid Frame - Carbonator | Process Group INC | 4503785534 | Fabrication | Carbon Steel | USD | 21257 | USD | 21971 | -714 | Market Impact | 2022-03-01 | 2022-04-08 | 2022-04-29 | 2022-03-08 | 2022-05-02 | 2022-05-07 | 2022-03-15 | 2022-05-04 | 2022-07-05 | 2022-07-13 | 2022-07-09 | 4 | 12 | 26
509157 | INTEL HEDGEHOG | Oakville | HX/ Pump/ Filter Skids | Process Group INC | 4503793621 | Fabrication | Carbon Steel | USD | 13000 | USD | 13105 | -105 | Market Impact | 2022-03-01 | 2022-04-18 | 2022-05-11 | 2022-05-14 | 2022-05-17 | 2022-05-14 | 2022-05-14 | 2022-05-18 | 2022-05-14 | 2022-07-27 | 2022-06-20 | 37 | 12 | 30
509157 | INTEL HEDGEHOG | Oakville | HX/ Pump/ Filter Skids | 3D MECHANICAL | 4503794732 | Fabrication | Carbon Steel | USD | 11500 | USD | 11527 | -27 | Market Impact | 2022-03-01 | 2022-05-02 | 2022-05-16 | 2022-05-15 | 2022-05-19 | 2022-05-15 | 2022-05-15 | 2022-05-20 | 2022-05-15 | 2022-07-29 | 2022-06-21 | 38 | 12 | 18
509157 | INTEL HEDGEHOG | Oakville | Spool Fabrication - Non- Metallic | GEORG FISCHER LLC | 4503781136 | Fabrication | Non-Metal Equipment | USD | 40000 | USD | 44282 | -4282 | Market Impact | 2022-02-14 | 2022-03-29 | 2022-04-15 | 2022-05-10 | 2022-04-18 | 2022-05-10 | 2022-05-10 | 2022-04-27 | 2022-05-10 | 2022-08-03 | 2022-06-21 | 43 | 12 | 29
509157 | INTEL HEDGEHOG | Oakville | Spool Fabrication - Non- Metallic | GEORGE FISCHER SLOANE INC. | 4503793151 | Fabrication | Non-Metal Equipment | USD | 20000 | USD | 24576 | -4576 | Market Impact | 2022-02-14 | 2022-05-03 | 2022-05-11 | 2022-04-30 | 2022-05-16 | 2022-04-30 | 2022-04-30 | 2022-05-18 | 2022-04-30 | 2022-07-15 | 2022-06-07 | 38 | 12 | 15
509157 | INTEL HEDGEHOG | Oakville | Spool Fabrication - Metallic | NV PIPING SYSTEMS INC. | 4503793164 | Fabrication | Stainless Steel | USD | 30000 | USD | 32593 | -2593 | Market Impact | 2022-02-14 | 2022-05-03 | 2022-05-11 | 2022-05-08 | 2022-05-15 | 2022-05-08 | 2022-05-08 | 2022-05-28 | 2022-05-08 | 2022-07-30 | 2022-06-18 | 42 | 12 | 25
509157 | INTEL HEDGEHOG | Oakville | Spool Fabrication - Metallic | Alps Welding Ltd. | 4503798231 | Fabrication | Carbon Steel | USD | 9000 | USD | 9499 | -499 | Market Impact | 2022-02-14 | 2022-04-11 | 2022-05-19 | 2022-05-14 | 2022-05-24 | 2022-05-14 | 2022-05-14 | 2022-05-26 | 2022-05-14 | 2022-08-11 | 2022-06-27 | 45 | 12 | 45
509157 | INTEL HEDGEHOG | Oakville | Instruments and Analyzers | ENDRESS + HAUSER CANADA LTD. | 4503745404 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 20769 | USD | 20769 | 0 | Market Impact | 2022-02-14 | 2022-02-14 | 2022-02-24 | 2022-02-21 | 2022-02-24 | 2022-03-22 | 2022-02-28 | 2022-02-24 | 2022-03-22 | 2022-04-28 | 2022-04-09 | 19 | 18 | 10
509157 | INTEL HEDGEHOG | Oakville | Instruments and Analyzers | SRB CONTROLS INC | 4503748725 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 7870 | USD | 7870 | 0 | Specs / Requirements Misinterpreted in Proposal | 2022-02-14 | 2022-02-14 | 2022-02-23 | 2022-02-21 | 2022-03-24 | 2022-03-22 | 2022-02-28 | 2022-03-02 | 2022-03-22 | 2022-04-28 | 2022-04-09 | 19 | 18 | 16
509157 | INTEL HEDGEHOG | Oakville | Instruments and Analyzers | LAKESIDE PROCESS CONTROLS LTD. | 4503751666 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 12308 | USD | 12092 | 216 | Frame Agreements | 2022-02-14 | 2022-02-14 | 2022-02-24 | 2022-02-21 | 2022-03-03 | 2022-03-22 | 2022-02-28 | 2022-03-08 | 2022-03-22 | 2022-04-28 | 2022-04-09 | 19 | 18 | 22
509157 | INTEL HEDGEHOG | Oakville | Instruments and Analyzers | ENDRESS + HAUSER CANADA LTD. | 4503791778 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 10858 | USD | 10858 | 0 | Specs / Requirements Misinterpreted in Proposal | 2022-02-14 | 2022-05-03 | 2022-05-11 | 2022-04-18 | 2022-05-13 | 2022-04-18 | 2022-04-18 | 2022-05-16 | 2022-04-18 | 2022-06-20 | 2022-05-19 | 32 | 18 | 13
509157 | INTEL HEDGEHOG | Oakville | Cartridge Filter | 3M Company | 4503763770 | Flow Control | Filters And Strainers (Incl Housings) | USD | 174287 | USD | 155618 | 18669 | Design Optimizations | 2022-03-01 | 2022-03-14 | 2022-03-07 | 2022-03-08 | 2022-03-15 | 2022-05-24 | 2022-03-15 | 2022-03-27 | 2022-08-02 | 2022-08-16 | 2022-08-09 | 7 | 12 | 13
509157 | INTEL HEDGEHOG | Oakville | Process Pump | Flowserve US Inc. | 4503759765 | Rotating Equipment | Centrifugal Pumps | USD | 61202 | USD | 54100 | 7102 | Supplier Competitions / Negotiation | 2022-02-10 | 2022-03-14 | 2022-03-17 | 2022-02-17 | 2022-03-17 | 2022-06-14 | 2022-02-24 | 2022-03-20 | 2022-08-11 | 2022-10-17 | 2022-09-13 | 34 | 30 | 6
509157 | INTEL HEDGEHOG | Oakville | Valves - Globe | LAKESIDE PROCESS CONTROLS LTD. | 4503800811 | Flow Control | Metal Control Valves | USD | 12894 | USD | 38934 | -26040 | Size/ Weight/ Quantity Underestimated | 2022-02-14 | 2022-04-15 | 2022-05-05 | 2022-02-21 | 2022-05-25 | 2022-06-10 | 2022-02-28 | 2022-06-01 | 2022-06-20 | 2022-10-05 | 2022-08-12 | 54 | 12 | 47
509157 | INTEL HEDGEHOG | Oakville | Valves - Globe | Great Lakes Industrial Controls | 4503784350 | Flow Control | Metal Control Valves | USD | 25000 | USD | 27334 | -2334 | Estimate Without Market Reference(No Quote) | 2022-02-14 | 2022-04-20 | 2022-04-25 | 2022-04-27 | 2022-04-29 | 2022-04-27 | 2022-04-27 | 2022-05-03 | 2022-04-27 | 2022-07-08 | 2022-06-02 | 36 | 12 | 13
509157 | INTEL HEDGEHOG | Oakville | Valves - Globe | LAKESIDE PROCESS CONTROLS LTD. | 4503796659 | Flow Control | Metal Control Valves | USD | 12000 | USD | 14975 | -2975 | Specs / Requirements Misinterpreted in Proposal | 2022-02-14 | 2022-05-07 | 2022-05-17 | 2022-05-17 | 2022-05-20 | 2022-05-17 | 2022-05-17 | 2022-05-24 | 2022-05-17 | 2022-08-17 | 2022-07-02 | 46 | 12 | 17
509164 | Doaktown WTP | Richmond | Tank+Skid | BE PETERSON | 4503768163 | Fabrication | Carbon Steel | CAD | 103585 | USD | 66765 | 36820 | Frame Agreements | 2022-02-18 | 2022-03-08 | 2022-03-16 | 2022-03-04 | 2022-04-03 | 2022-05-14 | 2022-03-18 | 2022-04-04 | 2022-08-05 | 2022-08-08 | 2022-08-06 | 2 | 12 | 27
509164 | Doaktown WTP | Richmond | Control Panel | KELTOUR CONTROLS INC. | 4503813716 | Electrical & Instrumentation | Ele-Control Panels | CAD | 59807 | CAD | 7995 | 51812 | Supplier Competitions / Negotiation | 2022-03-04 | 2022-04-13 | 2022-04-15 | 2022-03-18 | 2022-06-23 | 2022-06-16 | 2022-04-01 | 2022-06-23 | 2022-08-05 | 2022-09-29 | 2022-09-01 | 28 | 18 | 71
509164 | Doaktown WTP | Richmond | Air Compressor | PNEU AIR COMPRESSORS LTD | 4503809656 | Rotating Equipment | Compressors | CAD | 14156 | CAD | 15122 | -966 | Not included in Proposal / RFQ | 2022-03-04 | 2022-05-10 | 2022-05-11 | 2022-03-18 | 2022-06-15 | 2022-05-22 | 2022-04-01 | 2022-06-15 | 2022-08-05 | 2022-08-10 | 2022-08-07 | 3 | 30 | 36
509164 | Doaktown WTP | Richmond | Pressure /PH meter/DO meter/ORP meter transmitter | ENDRESS + HAUSER CANADA LTD. | 4503811613 | Electrical & Instrumentation | Inst-Analytical Instruments | CAD | 15944 | USD | 5503 | 10441 | Supplier Competitions / Negotiation | 2022-05-13 | 2022-03-08 | 2022-03-11 | 2022-05-27 | 2022-06-15 | 2022-05-22 | 2022-06-10 | 2022-06-18 | 2022-08-05 | 2022-08-06 | 2022-08-05 | 1 | 18 | 102
509164 | Doaktown WTP | Richmond | Butterfly valve | BRAY CONTROLS CANADA LTD. | 4503811867 | Flow Control | Metal Control Valves | CAD | 5832 | USD | 6117 | -285 | Estimate Without Market Reference(No Quote) | 2022-04-01 | 2022-02-21 | 2022-02-24 | 2022-04-15 | 2022-06-20 | 2022-05-22 | 2022-04-29 | 2022-06-20 | 2022-08-05 | 2022-08-21 | 2022-08-13 | 8 | 12 | 119
509176 | Niagara Seguin Expansion | Minnetonka | ASSY_RO SKID_MCE | WERNER ELECTRIC | 4503716895 | Electrical & Instrumentation | Ele-Control Panels | USD | 32294 | USD | 31048 | 1246 | Frame Agreements | 2022-01-11 | 2022-02-20 | 2022-01-11 | 2022-01-11 | 2022-01-11 | 2022-02-20 | 2022-01-11 | 2022-01-11 | 2022-04-01 | 2022-04-02 | 2022-04-01 | 1 | 18 | -40
509176 | Niagara Seguin Expansion | Minnetonka | ASSY_RO SKID_CONTROL PANEL | BW Systems | 4503757207 | Electrical & Instrumentation | Ele-Control Panels | USD | 25981 | USD | 34328 | -8347 | Estimate Without Market Reference(No Quote) | 2022-04-09 | 2022-03-04 | 2022-03-14 | 2022-03-10 | 2022-03-10 | 2022-04-09 | 2022-03-10 | 2022-03-15 | 2022-04-15 | 2022-05-15 | 2022-04-30 | 15 | 18 | 11
509176 | Niagara Seguin Expansion | Minnetonka | ASSY_RO SKID_PROTEC HOUSINGS | PROTEC ARISAWA AMERICA INC | 4503722885 | Flow Control | Filters And Strainers (Incl Housings) | USD | 24000 | USD | 22436 | 1564 | Supplier Competitions / Negotiation | 2022-01-11 | 2022-02-20 | 2022-01-19 | 2022-01-18 | 2022-01-20 | 2022-02-20 | 2022-01-19 | 2022-01-20 | 2022-04-01 | 2022-03-31 | 2022-03-31 | 0 | 12 | -31
509176 | Niagara Seguin Expansion | Minnetonka | ASSY_RO SKID_PUMP | ALFA LAVAL | 4503724840 | Rotating Equipment | Centrifugal Pumps | USD | 64500 | USD | 41553 | 22947 | Estimate Without Market Reference(No Quote) | 2022-01-11 | 2022-03-07 | 2022-01-13 | 2022-01-18 | 2022-01-23 | 2022-03-07 | 2022-01-19 | 2022-01-23 | 2022-04-01 | 2022-05-01 | 2022-04-16 | 15 | 30 | -43
509176 | Niagara Seguin Expansion | Minnetonka | ASSY_RO SKID FRAME | ARC SERVICES | 4503736929 | Fabrication | Skid Assembly Outsourced | USD | 35000 | USD | 38551 | -3551 | Single Sourced | 2022-01-11 | 2022-02-20 | 2022-02-10 | 2022-01-11 | 2022-02-09 | 2022-02-20 | 2022-01-11 | 2022-02-09 | 2022-04-01 | 2022-03-09 | 2022-03-20 | -11 | 12 | -11
509176 | Niagara Seguin Expansion | Minnetonka | ASSY_RO - MATERIAL, FRAMES AND SPOOLS | ARC SERVICES | 4523736929 | Fabrication | Skid Assembly Outsourced | USD | 41095 | USD | 20682 | 20413 | Design Optimizations | 2022-03-20 | 2022-03-20 | 2022-02-22 | 2022-03-20 | 2022-02-22 | 2022-03-20 | 2022-03-20 | 2022-03-11 | 2022-03-20 | 2022-04-15 | 2022-04-02 | 13 | 12 | -9
509176 | Niagara Seguin Expansion | Minnetonka | ASSY_RO LABOR | ARC SERVICES | 4533736929 | Fabrication | Skid Assembly Outsourced | USD | 76925 | USD | 65997 | 10928 | Frame Agreements | 2022-03-20 | 2022-03-20 | 2022-02-22 | 2022-03-20 | 2022-02-22 | 2022-03-20 | 2022-03-20 | 2022-03-11 | 2022-03-20 | 2022-04-15 | 2022-04-02 | 13 | 12 | -9
509186 | Lake Tawakoni WTP | Richmond | CW Pumps W/ LCP (Qty 2) | GOULDS PUMPS | 4503729592 | Rotating Equipment | Centrifugal Pumps | USD | 15600 | USD | 27876 | -12276 | Proposed Supplier Incapable Of Executing | 2021-11-18 | 2022-03-07 | 2022-03-15 | 2021-10-29 | 2022-03-17 | 2022-03-07 | 2021-11-08 | 2022-03-24 | 2022-03-14 | 2022-07-14 | 2022-05-14 | 61 | 30 | 17
509186 | Lake Tawakoni WTP | Richmond | Air Cooled Chiller (Qty 2) | TRANE COMMECIAL SYSTEMS | 4503778391 | Fabrication | Stainless Steel | USD | 119450 | USD | 143085 | -23635 | Market Impact | 2021-12-09 | 2022-06-16 | 2022-01-27 | 2021-12-30 | 2022-04-12 | 2022-06-16 | 2022-01-09 | 2022-04-21 | 2022-05-15 | 2022-12-23 | 2022-09-03 | 111 | 12 | -56
509186 | Lake Tawakoni WTP | Richmond | LCPs for CW Pumps (Qty 2) | MACHINE CONTROL SYSTEMS | 4503762448 | Electrical & Instrumentation | Ele-Control Panels | USD | 35230 | CAD | 19586 | 15644 | Design Optimizations | 2021-12-27 | 2022-03-18 | 2022-02-25 | 2022-01-10 | 2022-03-17 | 2022-03-18 | 2022-01-20 | 2022-03-24 | 2022-04-14 | 2022-06-08 | 2022-05-11 | 28 | 18 | 6
509186 | Lake Tawakoni WTP | Richmond | Skidded Manual Valves (Bray) | Bray Controls Canada Ltd. | 4503757820 | Flow Control | Metal Isolation Valves | USD | 6000 | USD | 5810 | 190 | Supplier Competitions / Negotiation | 2022-03-21 | 2022-03-21 | 2022-02-18 | 2022-03-21 | 2022-03-03 | 2022-03-21 | 2022-03-21 | 2022-03-17 | 2022-03-21 | 2022-04-21 | 2022-04-05 | 16 | 12 | -4
509186 | Lake Tawakoni WTP | Richmond | Skid Frames | Plasfab Inc | 4503789350 | Fabrication | Stainless Steel | USD | 11000 | CAD | 12902 | -1902 | Size/ Weight/ Quantity Underestimated | 2021-11-05 | 2022-02-21 | 2022-05-02 | 2021-11-19 | 2022-05-16 | 2022-02-21 | 2021-11-29 | 2022-05-11 | 2022-03-14 | 2022-06-10 | 2022-04-27 | 44 | 12 | 79
509186 | Lake Tawakoni WTP | Richmond | Skid Piping | NV PIPING SYSTEMS INC. | 4503803994 | Fabrication | Stainless Steel | USD | 18260 | CAD | 18652 | -392 | Single Sourced | 2021-11-05 | 2022-02-20 | 2022-06-03 | 2021-11-19 | 2022-06-03 | 2022-02-20 | 2021-11-29 | 2022-06-07 | 2022-03-14 | 2022-06-07 | 2022-04-25 | 43 | 12 | 107
509186 | Lake Tawakoni WTP | Oakville | Ductile Iron Spools and Fittings | Ferguson Waterworks | 4503804100 | Fabrication | Alloy Steel | USD | 10840 | USD | 10751 | 89 | Design Optimizations | 2022-04-19 | 2022-06-03 | 2022-05-26 | 2022-05-28 | 2022-05-25 | 2022-06-03 | 2022-05-31 | 2022-06-06 | 2022-07-17 | 2022-07-18 | 2022-07-17 | 1 | 12 | 3
509189 | Nutrien | Guelph | Pressure Vessels - Fabrication | Udelhoven Oilfield System Services | 4503782914 | Fabrication | Carbon Steel | USD | 1448169 | USD | 1615803 | -167634 | Single Sourced | 2022-02-18 | 2022-02-19 | 2022-03-24 | 2022-03-18 | 2022-03-30 | 2022-06-17 | 2022-04-01 | 2022-04-02 | 2022-09-16 | 2022-07-09 | 2022-10-14 | -97 | 18 | 42
509189 | Nutrien | Guelph | Electrical Enclosures & Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503802828 | Electrical & Instrumentation | Ele-Control Panels | USD | 106128 | CAD | 28954 | 77174 | Supplier Competitions / Negotiation | 2022-03-04 | 2022-05-02 | 2022-05-24 | 2022-05-20 | 2022-05-17 | 2022-05-30 | 2022-06-03 | 2022-05-23 | 2022-08-12 | 2022-08-26 | 2022-08-16 | 10 | 24 | 21
509189 | Nutrien | Guelph | Instruments - Transmitters- Pressure & Flow | LAKESIDE PROCESS CONTROLS LTD. | 4503764886 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 38692 | USD | 42035 | -3343 | Size/ Weight/ Quantity Underestimated | 2022-03-04 | 2022-03-14 | 2022-03-29 | 2022-06-03 | 2022-03-24 | 2022-05-23 | 2022-06-17 | 2022-03-27 | 2022-08-12 | 2022-07-03 | 2022-07-26 | -23 | 24 | 13
509189 | Nutrien | Guelph | Valves - Butterfly - Auto | BRAY CONTROLS CANADA LTD. | 4503763972 | Flow Control | Metal Control Valves | USD | 92046 | USD | 60129 | 31917 | Supplier Competitions / Negotiation | 2022-02-11 | 2022-02-14 | 2022-03-18 | 2022-04-29 | 2022-03-13 | 2022-05-14 | 2022-05-13 | 2022-03-25 | 2022-08-12 | 2022-06-17 | 2022-08-15 | -59 | 36 | 39
509189 | Nutrien | Guelph | Valves - Veeball | LAKESIDE PROCESS CONTROLS LTD. | 4503764827 | Flow Control | Metal Control Valves | USD | 146720 | USD | 116720 | 30000 | Supplier Competitions / Negotiation | 2022-03-04 | 2022-03-14 | 2022-03-14 | 2022-06-17 | 2022-03-25 | 2022-05-23 | 2022-07-01 | 2022-03-29 | 2022-08-12 | 2022-07-01 | 2022-06-28 | 3 | 24 | 15
509189 | Nutrien | Guelph | Valves - Ball - Man | Aalberts Integrated Piping Systems | 4503758164 | Flow Control | Metal Control Valves | USD | 23588 | CAD | 19360 | 4228 | Supplier Competitions / Negotiation | 2022-03-04 | 2022-02-14 | 2022-02-16 | 2022-02-25 | 2022-02-15 | 2022-05-14 | 2022-03-11 | 2022-03-20 | 2022-08-12 | 2022-07-07 | 2022-07-07 | 0 | 12 | 34
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | ASSY_RO SYSTEM | ASLAN TECHNOLOGIES | 4503759848 | Fabrication | Skid Assembly Outsourced | CAD | 306276 | CAD | 201390 | 104886 | Design Optimizations | 2022-02-15 | 2022-04-23 | 2022-03-03 | 2022-02-15 | 2022-03-21 | 2022-04-23 | 2022-02-15 | 2022-03-21 | 2022-06-15 | 2022-06-30 | 2022-06-22 | 8 | 12 | -33
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | ASSY_CIP SYSTEM | ASLAN TECHNOLOGIES | 4513759848 | Fabrication | Skid Assembly Outsourced | CAD | 32560 | CAD | 32560 | 0 | Not included in Proposal / RFQ | 2022-02-15 | 2022-04-23 | 2022-03-03 | 2022-02-15 | 2022-03-21 | 2022-04-23 | 2022-02-15 | 2022-03-21 | 2022-06-15 | 2022-06-30 | 2022-06-22 | 8 | 12 | -33
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | ASSY_CIP SYSTEM_TANK | QUALTECH SOLUTIONS | 4503764022 | Fabrication | Stainless Steel | CAD | 49375 | USD | 42620 | 6755 | Supplier Competitions / Negotiation | 2022-02-09 | 2022-03-09 | 2022-03-25 | 2022-02-03 | 2022-03-28 | 2022-05-17 | 2022-02-04 | 2022-03-28 | 2022-06-15 | 2022-08-29 | 2022-07-22 | 38 | 12 | 19
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_EVOQUA FILTER SKID | NEPTUNE BENSON LLC | 4503766343 | Fabrication | Skid Assembly Outsourced | CAD | 156030 | USD | 112036 | 43994 | Frame Agreements | 2022-01-25 | 2022-01-25 | 2022-01-26 | 2022-02-03 | 2022-03-31 | 2022-04-13 | 2022-02-04 | 2022-03-31 | 2022-06-15 | 2022-06-30 | 2022-06-22 | 8 | 12 | 65
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_CITY WATER TANK_FRP | Design Tanks, LLC | 4503750922 | Fabrication | Non-Metal Equipment | CAD | 44437 | USD | 43858 | 579 | Design Optimizations | 2022-01-26 | 2022-01-25 | 2022-02-16 | 2022-02-03 | 2022-03-07 | 2022-04-11 | 2022-02-03 | 2022-03-07 | 2022-06-15 | 2022-06-27 | 2022-06-21 | 6 | 12 | 41
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_CITY WATER PUMP SKID | ASLAN TECHNOLOGIES | 4523759848 | Fabrication | Skid Assembly Outsourced | CAD | 8814 | CAD | 32723 | -23909 | Proposed Supplier Incapable Of Executing | 2021-12-30 | 2022-01-25 | 2022-03-03 | 2022-02-10 | 2022-03-21 | 2022-03-31 | 2022-02-10 | 2022-03-21 | 2022-06-15 | 2022-06-30 | 2022-06-22 | 8 | 12 | 55
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_CITY WATER PUMP SKID_PUMPS | PTS Products | 4503751502 | Rotating Equipment | Centrifugal Pumps | CAD | 30893 | USD | 16096 | 14797 | Design Optimizations | 2022-02-03 | 2022-01-25 | 2022-01-25 | 2022-02-06 | 2022-03-08 | 2022-03-13 | 2022-02-06 | 2022-03-08 | 2022-04-01 | 2022-04-29 | 2022-04-15 | 14 | 30 | 42
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_PRE-RO, FINAL & RRO UVS 701 | AQUIONICS, INC. | 4503731325 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 122652 | USD | 101989 | 20663 | Design Optimizations | 2022-01-28 | 2022-01-19 | 2022-01-21 | 2022-02-02 | 2022-02-03 | 2022-04-02 | 2022-02-02 | 2022-02-03 | 2022-06-15 | 2022-05-12 | 2022-05-29 | -17 | 18 | 15
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_CHEMICAL FEED SYSTEM (3) | GRUNDFOS CANADA INC. | 4503769639 | Rotating Equipment | Centrifugal Pumps | CAD | 19552 | USD | 9332 | 10220 | Supplier Competitions / Negotiation | 2022-02-10 | 2022-04-24 | 2022-04-06 | 2022-02-15 | 2022-04-06 | 2022-04-24 | 2022-02-15 | 2022-04-06 | 2022-06-15 | 2022-07-07 | 2022-06-26 | 11 | 30 | -18
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_RO PERMEATE TANK | QUALTECH SOLUTIONS | 4503800701 | Fabrication | Stainless Steel | CAD | 111430 | CAD | 141285 | -29855 | Single Sourced | 2022-01-28 | 2021-11-01 | 2022-02-28 | 2022-02-01 | 2022-03-15 | 2022-03-12 | 2022-02-01 | 2022-03-17 | 2022-06-15 | 2022-07-22 | 2022-07-03 | 19 | 12 | 136
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_DISTRIBUTION SKID | ASLAN TECHNOLOGIES | 4533759848 | Fabrication | Skid Assembly Outsourced | CAD | 49163 | CAD | 35586 | 13577 | Design Optimizations | 2021-12-30 | 2022-01-25 | 2022-02-16 | 2022-02-15 | 2022-03-21 | 2022-03-31 | 2022-02-15 | 2022-03-21 | 2022-06-15 | 2022-06-30 | 2022-06-22 | 8 | 12 | 55
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_DISTRIBUTION SKID_PUMPS | ALFA LAVAL | 4503751586 | Rotating Equipment | Centrifugal Pumps | CAD | 80469 | USD | 21933 | 58536 | Frame Agreements | 2022-02-03 | 2022-01-25 | 2022-02-25 | 2022-02-06 | 2022-03-07 | 2022-04-13 | 2022-02-06 | 2022-03-08 | 2022-04-15 | 2022-07-01 | 2022-05-23 | 39 | 30 | 42
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_RECOVERY RO FEEED PUMP SKID | ASLAN TECHNOLOGIES | 4543759848 | Fabrication | Skid Assembly Outsourced | CAD | 20606 | CAD | 18573 | 2033 | Frame Agreements | 2021-12-30 | 2022-01-25 | 2022-03-03 | 2022-02-15 | 2022-03-21 | 2022-03-31 | 2022-02-15 | 2022-03-21 | 2022-06-15 | 2022-06-30 | 2022-06-22 | 8 | 12 | 55
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_FACE-PIPING WITH ENCLOSURE FOR ACF SK | ASLAN TECHNOLOGIES | 4553759848 | Fabrication | Skid Assembly Outsourced | CAD | 38541 | CAD | 40412 | -1871 | Single Sourced | 2021-12-30 | 2022-01-25 | 2022-03-03 | 2022-02-15 | 2022-03-21 | 2022-03-31 | 2022-02-15 | 2022-03-21 | 2022-06-15 | 2022-06-30 | 2022-06-22 | 8 | 12 | 55
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | LS_RO RECOVERY | Duncan Co. | 4503769661 | Flow Control | Metal Control Valves | CAD | 36184 | USD | 38753 | -2569 | Specs / Requirements Misinterpreted in Proposal | 2022-03-01 | 2022-04-30 | 2022-04-06 | 2022-03-01 | 2022-04-06 | 2022-04-30 | 2022-03-07 | 2022-04-06 | 2022-06-15 | 2022-06-29 | 2022-06-22 | 7 | 12 | -24
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | DS_MCE | KELTOUR CONTROLS INC. | 4503756740 | Electrical & Instrumentation | Ele-Power Mgmt Assemblies | CAD | 137628 | CAD | 170028 | -32400 | Estimate Without Market Reference(No Quote) | 2022-02-02 | 2022-02-02 | 2022-03-01 | 2022-02-10 | 2022-03-08 | 2022-05-24 | 2022-02-10 | 2022-03-14 | 2022-06-15 | 2022-09-12 | 2022-07-29 | 45 | 18 | 40
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | ELECTRICAL PANELS | KELTOUR CONTROLS INC. | 4503757036 | Electrical & Instrumentation | Ele-Control Panels | CAD | 53285 | CAD | 53285 | 0 | Not included in Proposal / RFQ | 2022-03-09 | 2022-03-09 | 2022-03-14 | 2022-03-15 | 2022-03-09 | 2022-05-04 | 2022-03-16 | 2022-03-15 | 2022-05-11 | 2022-06-29 | 2022-06-04 | 25 | 18 | 6
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | ELECTRICAL PANELS | KELTOUR CONTROLS INC. | 4503764477 | Electrical & Instrumentation | Ele-Control Panels | CAD | 42537 | CAD | 42537 | 0 | Size/ Weight/ Quantity Underestimated | 2022-05-22 | 2022-05-22 | 2022-03-14 | 2022-05-22 | 2022-03-29 | 2022-05-22 | 2022-05-22 | 2022-03-29 | 2022-05-22 | 2022-07-30 | 2022-06-25 | 35 | 18 | -54
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | ASSY_CIP SYSTEM_PUMP | PTS Products | 4523751502 | Rotating Equipment | Centrifugal Pumps | CAD | 7181 | USD | 7181 | 0 | Single Sourced | 2022-03-13 | 2022-01-25 | 2022-01-25 | 2022-03-13 | 2022-03-07 | 2022-03-13 | 2022-03-13 | 2022-03-08 | 2022-03-13 | 2022-04-29 | 2022-04-05 | 24 | 30 | 42
509196 | COKE CALGARY 500 GPM TREATED WATER | Minnetonka | ASSY_CIP SYSTEM - HEATER | CHROMALOX 102 PRECISION HEAT | 4503759177 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | CAD | 11494 | CAD | 11494 | 0 | Estimate Without Market Reference(No Quote) | 2022-03-17 | 2022-03-17 | 2022-02-07 | 2022-03-17 | 2022-02-07 | 2022-03-17 | 2022-03-17 | 2022-03-21 | 2022-03-17 | 2022-04-25 | 2022-04-05 | 20 | 18 | 4
509201 | NIAGARA JACKSONVILLE WTR FARM | Minnetonka | AC TOWER 108x168_ASSY | ARC SERVICES | 4503754612 | Fabrication | Skid Assembly Outsourced | USD | 48998 | USD | 69084 | -20086 | Proposed Supplier Incapable Of Executing | 2021-12-16 | 2021-12-16 | 2022-02-22 | 2022-02-01 | 2022-03-08 | 2022-03-25 | 2022-02-01 | 2022-03-08 | 2022-05-12 | 2022-07-02 | 2022-06-06 | 26 | 12 | 82
509201 | NIAGARA JACKSONVILLE WTR FARM | Minnetonka | AC TOWER 108x168 | Arrow Tanks | 4503718457 | Fabrication | Stainless Steel | USD | 78000 | USD | 91404 | -13404 | Estimate Without Market Reference(No Quote) | 2021-12-22 | 2021-12-22 | 2021-12-30 | 2022-01-13 | 2022-01-12 | 2022-02-15 | 2022-01-13 | 2021-12-21 | 2022-04-13 | 2022-04-12 | 2022-04-12 | 0 | 12 | -1
509201 | NIAGARA JACKSONVILLE WTR FARM | Minnetonka | RO SYSTEM - MATERIAL | ARC SERVICES | 4503732219 | Fabrication | Skid Assembly Outsourced | USD | 155000 | USD | 170936 | -15936 | Proposed Supplier Incapable Of Executing | 2022-02-21 | 2022-02-21 | 2022-02-04 | 2022-02-21 | 2022-01-31 | 2022-02-21 | 2022-02-21 | 2022-01-31 | 2022-02-21 | 2022-03-14 | 2022-03-03 | 11 | 12 | -21
509201 | NIAGARA JACKSONVILLE WTR FARM | Minnetonka | RO SYSTEM PROTEC HOUSINGS (18) | PROTEC ARISAWA AMERICA INC | 4503729209 | Flow Control | Filters And Strainers (Incl Housings) | USD | 15768 | USD | 15768 | 0 | Specs / Requirements Misinterpreted in Proposal | 2021-01-20 | 2021-08-26 | 2022-01-19 | 2021-01-20 | 2022-01-31 | 2021-08-26 | 2021-01-20 | 2022-01-31 | 2022-04-01 | 2022-03-21 | 2022-03-26 | -5 | 12 | 158
509201 | NIAGARA JACKSONVILLE WTR FARM | Minnetonka | CHEM SYSTEMS | GRUNDFOS PUMPS CORPORATION | 4503745186 | Rotating Equipment | Centrifugal Pumps | USD | 5000 | USD | 12142 | -7142 | Estimate Without Market Reference(No Quote) | 2021-02-15 | 2021-10-14 | 2022-02-25 | 2022-02-20 | 2022-02-24 | 2021-10-14 | 2022-02-20 | 2022-02-24 | 2022-05-01 | 2022-06-13 | 2022-05-22 | 22 | 30 | 133
509201 | NIAGARA JACKSONVILLE WTR FARM | Minnetonka | RO SYSTEM - PANEL | BW Systems | 4503764114 | Electrical & Instrumentation | Ele-Control Panels | USD | 24080 | USD | 24080 | 0 | Estimate Without Market Reference(No Quote) | 2022-04-30 | 2022-03-10 | 2022-03-21 | 2022-04-30 | 2022-03-28 | 2022-04-30 | 2022-04-30 | 2022-03-28 | 2022-04-30 | 2022-06-20 | 2022-05-25 | 26 | 18 | 18
509212 | FAYGO BEVERAGE CARBON TOWER | Minnetonka | AC TOWER 96X144 FABRICATION | TRIVACO | 4503743545 | Fabrication | Skid Assembly Outsourced | USD | 21738 | USD | 25375 | -3637 | Proposed Supplier Incapable Of Executing | 2021-12-28 | 2022-02-07 | 2022-02-23 | 2022-02-01 | 2022-03-09 | 2022-04-06 | 2022-02-01 | 2022-03-09 | 2022-07-15 | 2022-04-13 | 2022-05-29 | -46 | 12 | 30
509212 | FAYGO BEVERAGE CARBON TOWER | Minnetonka | AC TOWER 96X144LABOR | TRIVACO | 4513743545 | Fabrication | Skid Assembly Outsourced | USD | 9090 | USD | 21262 | -12172 | Proposed Supplier Incapable Of Executing | 2022-04-28 | 2022-04-28 | 2022-02-23 | 2022-04-28 | 2022-03-09 | 2022-04-28 | 2022-04-28 | 2022-03-09 | 2022-04-28 | 2022-07-01 | 2022-05-30 | 32 | 12 | -50
509212 | FAYGO BEVERAGE CARBON TOWER | Minnetonka | AC TOWER 96X144 | Arrow Tanks | 4503723476 | Fabrication | Stainless Steel | USD | 60000 | USD | 81777 | -21777 | Estimate Without Market Reference(No Quote) | 2021-12-28 | 2021-12-28 | 2022-01-18 | 2021-12-28 | 2022-01-21 | 2022-03-30 | 2022-01-20 | 2022-01-21 | 2022-06-01 | 2022-07-01 | 2022-06-16 | 15 | 12 | 24
509212 | FAYGO BEVERAGE CARBON TOWER | Minnetonka | DS_ FILTER SKIDS FABRICATION | FORSTA FILTERS | 4503737638 | Fabrication | Skid Assembly Outsourced | USD | 80000 | USD | 73620 | 6380 | Proposed Supplier Incapable Of Executing | 2022-02-01 | 2022-02-09 | 2022-02-09 | 2022-02-10 | 2022-02-13 | 2022-04-24 | 2022-02-10 | 2022-02-13 | 2022-07-15 | 2022-04-14 | 2022-05-30 | -46 | 12 | 4
509213 | Intel F12 RO Replacement | Guelph | VFD (75 kW) | Integrated Systems Group | 4503768968 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 54838 | USD | 53816 | 1022 | Supplier Competitions / Negotiation | 2022-04-15 | 2022-03-30 | 2022-03-22 | 2022-04-25 | 2022-03-30 | 2022-06-24 | 2022-05-02 | 2022-04-04 | 2022-09-05 | 2022-09-26 | 2022-09-15 | 11 | 18 | 5
509213 | Intel F12 RO Replacement | Guelph | RO Train PLC - Control Panel | Keltour Controls Inc. | 4503774222 | Electrical & Instrumentation | Ele-Control Panels | USD | 53664 | USD | 45805 | 7859 | Design Optimizations | 2022-03-01 | 2022-03-23 | 2022-03-29 | 2022-03-08 | 2022-04-01 | 2022-06-07 | 2022-03-15 | 2022-04-13 | 2022-08-02 | 2022-09-14 | 2022-08-23 | 22 | 18 | 21
509213 | Intel F12 RO Replacement | Guelph | Grundfos Pump | GRUNDFOS CANADA INC. | 4503754493 | Rotating Equipment | Centrifugal Pumps | USD | 123600 | USD | 128408 | -4808 | Market Impact | 2022-02-15 | 2022-02-11 | 2022-02-15 | 2022-02-16 | 2022-03-09 | 2022-05-22 | 2022-02-23 | 2022-03-14 | 2022-08-10 | 2022-08-30 | 2022-08-20 | 10 | 30 | 31
509213 | Intel F12 RO Replacement | Guelph | Frame | PROCESS GROUP INTERNATIONAL LTD. | 4503785536 | Fabrication | Carbon Steel | USD | 44198 | USD | 79208 | -35010 | Market Impact | 2022-03-15 | 2022-04-12 | 2022-04-29 | 2022-03-25 | 2022-05-02 | 2022-05-25 | 2022-04-01 | 2022-05-05 | 2022-08-05 | 2022-07-14 | 2022-07-25 | -11 | 12 | 23
509213 | Intel F12 RO Replacement | Guelph | Piping - Metal | PANDA PIPING LTD | 4503795955 | Fabrication | Stainless Steel | USD | 267569 | USD | 271327 | -3758 | Market Impact | 2022-04-15 | 2022-04-28 | 2022-05-17 | 2022-04-25 | 2022-05-17 | 2022-06-15 | 2022-05-02 | 2022-05-23 | 2022-07-25 | 2022-08-15 | 2022-08-04 | 11 | 12 | 25
509213 | Intel F12 RO Replacement | Guelph | Piping - Non- Metal | GEORG FISCHER LLC | 4503790925 | Fabrication | Non-Metal Equipment | USD | 15757 | USD | 60996 | -45239 | Market Impact | 2022-04-15 | 2022-04-28 | 2022-05-05 | 2022-04-25 | 2022-05-06 | 2022-06-24 | 2022-05-02 | 2022-05-13 | 2022-08-08 | 2022-09-02 | 2022-08-20 | 13 | 12 | 15
509213 | Intel F12 RO Replacement | Guelph | Valve - Butterfly | Sylvan Automation Ltd. | 4503774960 | Flow Control | Metal Isolation Valves | USD | 13515 | USD | 8072 | 5443 | Supplier Competitions / Negotiation | 2022-04-15 | 2022-03-18 | 2022-04-05 | 2022-04-25 | 2022-04-13 | 2022-06-16 | 2022-05-02 | 2022-04-14 | 2022-07-25 | 2022-09-15 | 2022-08-20 | 26 | 12 | 27
509213 | Intel F12 RO Replacement | Guelph | Transmitter - Flow & Pressure | Engineered Process Control | 4503774219 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 42191 | USD | 69444 | -27253 | Estimate Without Market Reference(No Quote) | 2022-04-15 | 2022-03-29 | 2022-04-19 | 2022-04-25 | 2022-04-20 | 2022-06-11 | 2022-05-02 | 2022-04-21 | 2022-07-11 | 2022-08-25 | 2022-08-02 | 23 | 18 | 23
509213 | Intel F12 RO Replacement | Guelph | Transmitter - Flow & Pressure | ENDRESS + HAUSER CANADA LTD. | 4503768902 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 10000 | USD | 11725 | -1725 | Size/ Weight/ Quantity Underestimated | 2022-04-15 | 2022-03-29 | 2022-03-30 | 2022-04-25 | 2022-04-01 | 2022-05-27 | 2022-05-27 | 2022-04-05 | 2022-05-27 | 2022-07-26 | 2022-06-26 | 30 | 18 | 7
509226 | Mountarie Farms | Oakville | Process pumps_Guelph | FLOWSERVE INC. | 4503805516 | Rotating Equipment | PD Pumps | USD | 169252 | USD | 117600 | 51652 | Frame Agreements | 2022-02-23 | 2022-06-18 | 2022-06-22 | 2022-03-28 | 2022-06-21 | 2022-06-29 | 2022-08-05 | 2022-06-08 | 2022-11-03 | 2022-09-11 | 2022-10-07 | -26 | 30 | -10
509226 | Mountarie Farms | Oakville | Pumps_MTKA | PFC EQUIPMENT | 4503820535 | Rotating Equipment | PD Pumps | USD | 7397 | USD | 7397 | 0 | Size/ Weight/ Quantity Underestimated | 2022-07-15 | 2022-06-28 | 2022-06-30 | 2022-07-15 | 2022-07-04 | 2022-07-15 | 2022-07-15 | 2022-07-04 | 2022-07-15 | 2022-08-01 | 2022-07-23 | 9 | 30 | 6
509226 | Mountarie Farms | Oakville | Control Panel _Guelph | KELTOUR CONTROLS INC. | 4503814792 | Electrical & Instrumentation | Ele-Control Panels | USD | 112024 | CAD | 109919 | 2105 | Frame Agreements | 2022-02-23 | 2022-06-14 | 2022-06-20 | 2022-03-28 | 2022-06-23 | 2022-06-29 | 2022-06-26 | 2022-06-23 | 2022-11-03 | 2022-10-16 | 2022-10-25 | -9 | 18 | 9
509226 | Mountarie Farms | Oakville | Control Panel_MTKA | KELTOUR CONTROLS INC. | 4503814794 | Electrical & Instrumentation | Ele-Control Panels | USD | 77805 | CAD | 77805 | 0 | Estimate Without Market Reference(No Quote) | 2022-08-30 | 2022-06-13 | 2022-06-20 | 2022-08-30 | 2022-06-23 | 2022-08-30 | 2022-08-30 | 2022-06-23 | 2022-08-30 | 2022-11-16 | 2022-10-08 | 39 | 18 | 10
509226 | Mountarie Farms | Oakville | SS Piping | Cambridge Pro Fab Inc. | 4503826949 | Fabrication | Stainless Steel | USD | 92140 | CAD | 108913 | -16773 | Not included in Proposal / RFQ | 2022-03-13 | 2022-07-01 | 2022-07-06 | 2022-03-28 | 2022-07-05 | 2022-07-08 | 2022-08-15 | 2022-07-14 | 2022-11-03 | 2022-11-03 | 2022-11-03 | 0 | 12 | 13
509226 | Mountarie Farms | Oakville | Butterfly valve_Guelph | BRAY CONTROLS CANADA LTD. | 4503814798 | Flow Control | Metal Control Valves | USD | 11348 | USD | 21514 | -10166 | Proposed Supplier Incapable Of Executing | 2022-03-13 | 2022-06-19 | 2022-06-24 | 2022-03-28 | 2022-06-23 | 2022-07-08 | 2022-09-04 | 2022-06-23 | 2022-11-03 | 2022-10-13 | 2022-10-23 | -10 | 12 | 4
509226 | Mountarie Farms | Oakville | Butterfly valve_MTKA | BRAY CONTROLS CANADA LTD | 4503814804 | Flow Control | Metal Control Valves | USD | 12724 | USD | 15929 | -3205 | Specs / Requirements Misinterpreted in Proposal | 2022-07-16 | 2022-06-13 | 2022-06-24 | 2022-07-16 | 2022-06-24 | 2022-07-16 | 2022-07-16 | 2022-06-23 | 2022-07-16 | 2022-08-18 | 2022-08-01 | 17 | 12 | 10
509226 | Mountarie Farms | Oakville | Ball Valves SS_ Guelph | Aalberts Integrated Piping Systems | 4503814819 | Flow Control | Metal Isolation Valves | USD | 10542 | CAD | 7590 | 2952 | Frame Agreements | 2022-03-13 | 2022-06-11 | 2022-06-16 | 2022-03-28 | 2022-06-24 | 2022-07-08 | 2022-09-04 | 2022-06-24 | 2022-11-03 | 2022-07-29 | 2022-09-15 | -48 | 12 | 13
509226 | Mountarie Farms | Oakville | Frames | 3D MECHANICAL | 4503826725 | Fabrication | Stainless Steel | USD | 71478 | CAD | 47264 | 24214 | Frame Agreements | 2022-03-13 | 2022-07-09 | 2022-07-13 | 2022-03-28 | 2022-07-11 | 2022-07-08 | 2022-08-25 | 2022-07-13 | 2022-11-03 | 2022-09-21 | 2022-10-12 | -21 | 12 | 4
509226 | Mountarie Farms | Oakville | Automatic Self stariner | BOLL FILTER CORPORATION | 4503782327 | Flow Control | Filters And Strainers (Incl Housings) | USD | 66940 | USD | 62056 | 4884 | Design Optimizations | 2022-02-23 | 2022-03-01 | 2022-03-04 | 2022-03-28 | 2022-04-28 | 2022-07-05 | 2022-08-05 | 2022-04-28 | 2022-11-03 | 2022-11-14 | 2022-11-08 | 6 | 12 | 58
509226 | Mountarie Farms | Oakville | Chemical Dosing skid | PROMINENT FLUID CONTROLS LTD. | 4503826958 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 66035 | CAD | 55714 | 10321 | Frame Agreements | 2022-02-23 | 2022-07-01 | 2022-07-05 | 2022-03-28 | 2022-07-12 | 2022-06-29 | 2022-08-15 | 2022-07-14 | 2022-11-03 | 2022-10-23 | 2022-10-28 | -5 | 30 | 13
509226 | Mountarie Farms | Oakville | Flow Transmitter_ Guelph | ENDRESS & HAUSER | 4503814806 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 10806 | USD | 15411 | -4605 | Market Impact | 2022-03-13 | 2022-06-20 | 2022-06-24 | 2022-03-28 | 2022-06-23 | 2022-07-08 | 2022-09-04 | 2022-06-23 | 2022-11-03 | 2022-09-01 | 2022-10-02 | -31 | 18 | 3
509226 | Mountarie Farms | Oakville | FRP Tank | PRECISIONEERING | 4503831735 | Fabrication | Non-Metal Equipment | USD | 89547 | CAD | 116521 | -26974 | Proposed Supplier Incapable Of Executing | 2022-02-23 | 2022-06-07 | 2022-06-15 | 2022-03-28 | 2022-07-25 | 2022-07-05 | 2022-08-05 | 2022-07-25 | 2022-11-03 | 2022-11-14 | 2022-11-08 | 6 | 12 | 48
509226 | Mountarie Farms | Oakville | Air Compressor | PNEU AIR COMPRESSORS LTD | 4503805506 | Rotating Equipment | Compressors | USD | 25567 | CAD | 16778 | 8789 | Supplier Competitions / Negotiation | 2022-02-23 | 2022-06-06 | 2022-06-09 | 2022-03-28 | 2022-06-09 | 2022-06-29 | 2022-07-31 | 2022-06-09 | 2022-11-03 | 2022-08-18 | 2022-09-25 | -38 | 30 | 3
509226 | Mountarie Farms | Oakville | HDPE Tank | POLY PROCESSING | 4503830131 | Fabrication | Non-Metal Equipment | USD | 18763 | USD | 22434 | -3671 | Not included in Proposal / RFQ | 2022-02-23 | 2022-04-21 | 2022-04-25 | 2022-03-28 | 2022-07-21 | 2022-06-29 | 2022-09-04 | 2022-07-21 | 2022-11-03 | 2022-10-13 | 2022-10-23 | -10 | 12 | 91
509226 | Mountarie Farms | Oakville | Blowers | AERZEN CANADA INC. | 4503805502 | Rotating Equipment | Blowers & Fans | USD | 17008 | CAD | 15226 | 1782 | Frame Agreements | 2022-02-23 | 2022-06-04 | 2022-06-09 | 2022-03-28 | 2022-06-09 | 2022-06-29 | 2022-08-05 | 2022-06-09 | 2022-11-03 | 2022-08-15 | 2022-09-24 | -40 | 30 | 5
509226 | Mountarie Farms | Oakville | Mixer | DYNAMIX | 4503830458 | Rotating Equipment | Mixers | USD | 11137 | CAD | 11700 | -563 | Single Sourced | 2022-02-23 | 2022-04-15 | 2022-04-20 | 2022-03-28 | 2022-07-22 | 2022-08-21 | 2022-08-15 | 2022-07-22 | 2022-11-03 | 2023-02-17 | 2022-12-26 | 53 | 30 | 98
509226 | Mountarie Farms | Oakville | Heater_Guelph | ASB HEATING ELEMENTS LIMITED | 4503817059 | Flow Control | Other | USD | 7696 | CAD | 5363 | 2333 | Design Optimizations | 2022-02-23 | 2022-06-13 | 2022-06-16 | 2022-03-28 | 2022-06-28 | 2022-06-29 | 2022-08-30 | 2022-06-28 | 2022-11-03 | 2022-10-11 | 2022-10-22 | -11 | 12 | 15
509226 | Mountarie Farms | Oakville | Heater _MTKA | Chromalox Inc. | 4503820531 | Flow Control | Other | USD | 10635 | USD | 10635 | 0 | Single Sourced | 2022-08-23 | 2022-06-28 | 2022-07-01 | 2022-08-23 | 2022-07-01 | 2022-08-23 | 2022-08-23 | 2022-07-05 | 2022-08-23 | 2022-10-18 | 2022-09-20 | 28 | 12 | 7
509231 | St. Paul RWS - McCarrons Water Treatment Process Improvements | Richmond | Accelerator | POSEIDON, INC | 4503791949 | Fabrication | Stainless Steel | USD | 4020897 | CAD | 3938935 | 81962 | Design Optimizations | 2022-08-28 | 2022-07-22 | 2021-12-15 | 2022-09-04 | 2022-07-22 | 2022-07-22 | 2022-09-11 | 2022-05-15 | 2023-02-12 | 2023-02-26 | 2023-02-19 | 7 | 12 | -68
509231 | St. Paul RWS - McCarrons Water Treatment Process Improvements | Richmond | Pinion & roller assembly, tag nameplate- Stock | 3W - Infilco Warehouse | 4503509231 | Fabrication | Stainless Steel | USD | 103954 | USD | 150295 | -46341 | Size/ Weight/ Quantity Underestimated | 2022-04-03 | 2022-06-26 | 2022-05-10 | 2022-04-10 | 2022-05-09 | 2022-06-26 | 2022-04-17 | 2022-05-09 | 2022-09-18 | 2022-05-09 | 2022-07-14 | -66 | 12 | -48
509234 | NIAGARA HAZLETON WTR FARM EXPANSION | Minnetonka | AC TOWER | Arrow Tanks | 4503723550 | Fabrication | Stainless Steel | USD | 78000 | USD | 91404 | -13404 | Estimate Without Market Reference(No Quote) | 2022-12-22 | 2022-06-25 | 2021-12-28 | 2022-12-22 | 2022-01-21 | 2022-06-25 | 2022-01-04 | 2022-01-21 | 2022-05-20 | 2022-05-13 | 2022-05-16 | -3 | 12 | -155
509234 | NIAGARA HAZLETON WTR FARM EXPANSION | Minnetonka | AC TOWER_FABRICATION LABOR AND MATERIAL | ARC SERVICES | 4503754615 | Fabrication | Skid Assembly Outsourced | USD | 51379 | USD | 62695 | -11316 | Proposed Supplier Incapable Of Executing | 2022-02-15 | 2022-04-22 | 2022-02-17 | 2022-02-15 | 2022-02-08 | 2022-04-22 | 2022-02-15 | 2022-03-10 | 2022-07-01 | 2022-07-04 | 2022-07-02 | 2 | 12 | -43
509234 | NIAGARA HAZLETON WTR FARM EXPANSION | Minnetonka | RO SKID_PROTEC HOUSINGS | PROTEC ARISAWA AMERICA INC | 4503729218 | Flow Control | Filters And Strainers (Incl Housings) | USD | 13824 | USD | 21560 | -7736 | Estimate Without Market Reference(No Quote) | 2022-01-31 | 2022-03-01 | 2022-01-19 | 2022-01-31 | 2022-01-31 | 2022-03-01 | 2022-01-31 | 2022-01-31 | 2022-03-31 | 2022-04-11 | 2022-04-05 | 6 | 12 | -29
509234 | NIAGARA HAZLETON WTR FARM EXPANSION | Minnetonka | RO SKID_FABRICATION - LABOR & MATERIAL | ARC SERVICES | 4503750769 | Fabrication | Skid Assembly Outsourced | USD | 107286 | USD | 166644 | -59358 | Proposed Supplier Incapable Of Executing | 2022-02-20 | 2022-02-20 | 2021-12-28 | 2022-02-20 | 2022-02-07 | 2022-02-20 | 2022-02-20 | 2022-03-05 | 2022-02-20 | 2022-04-16 | 2022-03-19 | 28 | 12 | 13
509234 | NIAGARA HAZLETON WTR FARM EXPANSION | Minnetonka | RRO SKID_FABRICATION LABOR & - MATERIALS | ARC SERVICES | 4503735116 | Fabrication | Skid Assembly Outsourced | USD | 92736 | USD | 127600 | -34864 | Proposed Supplier Incapable Of Executing | 2022-02-20 | 2022-02-20 | 2021-12-28 | 2022-02-20 | 2022-02-07 | 2022-02-20 | 2022-02-20 | 2022-03-05 | 2022-02-20 | 2022-04-16 | 2022-03-19 | 28 | 12 | 13
509234 | NIAGARA HAZLETON WTR FARM EXPANSION | Minnetonka | Chem Feed | Grundfos Kft | 4513744424 | Rotating Equipment | Centrifugal Pumps | USD | 12000 | USD | 5756 | 6244 | Estimate Without Market Reference(No Quote) | 2022-02-15 | 2022-04-24 | 2022-02-24 | 2022-02-15 | 2022-02-22 | 2022-04-24 | 2022-02-15 | 2022-02-22 | 2022-07-01 | 2022-03-22 | 2022-05-11 | -50 | 30 | -61
509234 | NIAGARA HAZLETON WTR FARM EXPANSION | Minnetonka | CONTROL PANELS | BW Systems | 4503764117 | Electrical & Instrumentation | Ele-Control Panels | USD | 32000 | USD | 66084 | -34084 | Not included in Proposal / RFQ | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-03-25 | 2022-03-23 | 2022-04-26 | 2022-05-31 | 2022-03-27 | 2022-05-31 | 2022-05-30 | 2022-05-30 | 0 | 18 | 2
509235 | Haskell Gallo | Minnetonka | ASSY_RO SKID_Materials | Tristate Valves & Controls, INC | 4503770348 | Fabrication | Skid Assembly Outsourced | USD | 49133 | USD | 45735 | 3398 | Proposed Supplier Incapable Of Executing | 2022-02-24 | 2022-05-16 | 2022-03-24 | 2022-03-05 | 2022-04-07 | 2022-05-16 | 2022-03-11 | 2022-04-07 | 2022-08-05 | 2022-07-29 | 2022-08-01 | -3 | 12 | -39
509235 | Haskell Gallo | Minnetonka | ASSY_RO SKID_LABOR | Tristate Valves & Controls, INC | 4513770348 | Fabrication | Skid Assembly Outsourced | USD | 43989 | USD | 43989 | 0 | Single Sourced | 2022-02-24 | 2022-05-16 | 2022-03-24 | 2022-03-05 | 2022-04-07 | 2022-05-16 | 2022-03-11 | 2022-04-07 | 2022-08-05 | 2022-07-29 | 2022-08-01 | -3 | 12 | -39
509235 | Haskell Gallo | Minnetonka | ASSY_CIP EQUIPMENT_MATERIALS | Tristate Valves & Controls, INC | 4523770348 | Fabrication | Skid Assembly Outsourced | USD | 17880 | USD | 17880 | 0 | Supplier Competitions / Negotiation | 2022-02-24 | 2022-05-16 | 2022-03-24 | 2022-03-05 | 2022-04-07 | 2022-05-16 | 2022-03-11 | 2022-04-07 | 2022-08-05 | 2022-07-29 | 2022-08-01 | -3 | 12 | -39
509235 | Haskell Gallo | Minnetonka | ASSY_CIP EQUIPMENT_LABOR | Tristate Valves & Controls, INC | 4533770348 | Fabrication | Skid Assembly Outsourced | USD | 17673 | USD | 17673 | 0 | Specs / Requirements Misinterpreted in Proposal | 2022-02-24 | 2022-05-16 | 2022-03-24 | 2022-03-05 | 2022-04-07 | 2022-05-16 | 2022-03-11 | 2022-04-07 | 2022-08-05 | 2022-07-29 | 2022-08-01 | -3 | 12 | -39
509235 | Haskell Gallo | Minnetonka | SUB_ASSY_AC TOWER_Materials | Tristate Valves & Controls, INC | 4543770348 | Fabrication | Skid Assembly Outsourced | USD | 16781 | USD | 16781 | 0 | Estimate Without Market Reference(No Quote) | 2022-02-24 | 2022-05-16 | 2022-03-24 | 2022-03-05 | 2022-04-07 | 2022-05-16 | 2022-03-11 | 2022-04-07 | 2022-08-05 | 2022-07-29 | 2022-08-01 | -3 | 12 | -39
509235 | Haskell Gallo | Minnetonka | SUB_ASSY_AC TOWER_Labor | Tristate Valves & Controls, INC | 4553770348 | Fabrication | Skid Assembly Outsourced | USD | 20983 | USD | 20983 | 0 | Design Optimizations | 2022-02-24 | 2022-05-16 | 2022-03-24 | 2022-03-05 | 2022-04-07 | 2022-05-16 | 2022-03-11 | 2022-04-07 | 2022-08-05 | 2022-07-29 | 2022-08-01 | -3 | 12 | -39
509235 | Haskell Gallo | Minnetonka | SUB_ASSY_AC TOWER_Tank | Arrow Tanks | 4503730105 | Fabrication | Stainless Steel | USD | 43521 | USD | 46907 | -3386 | Estimate Without Market Reference(No Quote) | 2021-12-29 | 2021-09-15 | 2022-01-18 | 2021-01-18 | 2022-02-01 | 2021-09-15 | 2021-02-01 | 2022-02-01 | 2022-05-13 | 2022-05-13 | 2022-05-13 | 0 | 12 | 139
509235 | Haskell Gallo | Minnetonka | LS_CITY WATER TANK | Augusta Fiberglass | 4503741405 | Fabrication | Non-Metal Equipment | USD | 34500 | USD | 18777 | 15723 | Supplier Competitions / Negotiation | 2022-02-08 | 2022-04-18 | 2022-02-22 | 2022-02-20 | 2022-02-22 | 2022-04-18 | 2022-02-20 | 2022-02-22 | 2022-06-26 | 2022-06-25 | 2022-06-25 | 0 | 12 | -55
509235 | Haskell Gallo | Minnetonka | LS_CITY WATER PUMPS | PFC EQUIPMENT | 4503755487 | Rotating Equipment | Centrifugal Pumps | USD | 13681 | USD | 13394 | 287 | Estimate Without Market Reference(No Quote) | 2022-03-07 | 2022-05-21 | 2022-03-14 | 2022-03-09 | 2022-03-13 | 2022-05-21 | 2022-03-09 | 2022-03-13 | 2022-08-05 | 2022-08-04 | 2022-08-04 | 0 | 30 | -69
509235 | Haskell Gallo | Minnetonka | LS_PRERO UV | AQUAFINE CORPORATION | 4503746263 | Electrical & Instrumentation | Ele-Electrical Others | USD | 11000 | USD | 11138 | -138 | Single Sourced | 2022-02-21 | 2022-05-02 | 2022-02-21 | 2022-05-02 | 2022-02-27 | 2022-05-02 | 2022-02-28 | 2022-02-27 | 2022-07-11 | 2022-07-10 | 2022-07-10 | 0 | 18 | -64
509235 | Haskell Gallo | Minnetonka | ASSY_RO SKID_MCP | ICSE | 4503762394 | Electrical & Instrumentation | Ele-Control Panels | USD | 31230 | USD | 31230 | 0 | Single Sourced | 2022-05-10 | 2022-05-10 | 2022-03-02 | 2022-05-10 | 2022-03-23 | 2022-05-10 | 2022-05-10 | 2022-03-24 | 2022-05-10 | 2022-07-18 | 2022-06-13 | 35 | 18 | -47
509235 | Haskell Gallo | Minnetonka | ASSY_RO SKID_MCP | TRIVACO DND | 4503829249 | Electrical & Instrumentation | Ele-Control Panels | USD | 6700 | USD | 6700 | 0 | Specs / Requirements Misinterpreted in Proposal | 2022-07-28 | 2022-07-28 | 2022-07-18 | 2022-07-28 | 2022-07-20 | 2022-07-28 | 2022-07-28 | 2022-07-20 | 2022-07-28 | 2022-08-08 | 2022-08-02 | 6 | 18 | -8
509243 | SHASTA CARBON TOWER | Minnetonka | AC TOWER 96X144 | Arrow Tanks | 4503723457 | Fabrication | Stainless Steel | USD | 120000 | USD | 162354 | -42354 | Estimate Without Market Reference(No Quote) | 2021-12-27 | 2021-12-27 | 2022-01-18 | 2021-12-27 | 2022-01-21 | 2022-02-19 | 2021-12-27 | 2022-01-21 | 2022-04-15 | 2022-04-08 | 2022-04-11 | -3 | 12 | 25
509243 | SHASTA CARBON TOWER | Minnetonka | AC TOWER 96X144 MATERIAL | TRIVACO | 4503752841 | Fabrication | Skid Assembly Outsourced | USD | 46000 | USD | 50760 | -4760 | Proposed Supplier Incapable Of Executing | 2021-12-28 | 2021-12-27 | 2022-02-17 | 2022-02-01 | 2022-03-07 | 2022-04-01 | 2022-02-01 | 2022-03-07 | 2022-05-23 | 2022-07-06 | 2022-06-14 | 22 | 12 | 70
509243 | SHASTA CARBON TOWER | Minnetonka | AC TOWER 96X144 LABOR | TRIVACO | 4513752841 | Fabrication | Skid Assembly Outsourced | USD | 18180 | USD | 42524 | -24344 | Proposed Supplier Incapable Of Executing | 2022-04-01 | 2021-12-27 | 2022-02-17 | 2022-04-01 | 2022-03-07 | 2022-04-01 | 2022-04-01 | 2022-03-07 | 2022-04-01 | 2022-07-06 | 2022-05-19 | 48 | 12 | 70
509243 | SHASTA CARBON TOWER | Minnetonka | DS_FILTER HOUSINGS | Duncan Co. | 4503734214 | Flow Control | Filters And Strainers (Incl Housings) | USD | 18000 | USD | 15990 | 2010 | Market Impact | 2022-02-01 | 2022-01-23 | 2022-01-24 | 2022-02-01 | 2022-02-08 | 2022-03-24 | 2022-02-01 | 2022-02-08 | 2022-05-23 | 2022-04-29 | 2022-05-11 | -12 | 12 | 16
509243 | SHASTA CARBON TOWER | Minnetonka | DS_FILTER SKIDS | FORSTA FILTERS | 4503737651 | Fabrication | Skid Assembly Outsourced | USD | 80000 | USD | 67460 | 12540 | Supplier Competitions / Negotiation | 2022-01-26 | 2022-02-09 | 2022-02-09 | 2022-02-01 | 2022-02-12 | 2022-03-25 | 2022-02-01 | 2022-02-12 | 2022-05-23 | 2022-04-13 | 2022-05-03 | -20 | 12 | 3
509243 | SHASTA CARBON TOWER | Minnetonka | DS_CONTROL ENCLOSURE | ICSE | 4503759485 | Electrical & Instrumentation | Ele-Control Panels | USD | 27000 | USD | 22994 | 4006 | Market Impact | 2022-01-26 | 2022-02-23 | 2022-03-02 | 2022-01-26 | 2022-03-21 | 2022-04-17 | 2022-01-26 | 2022-03-21 | 2022-05-23 | 2022-07-08 | 2022-06-15 | 23 | 18 | 26
509248 | BREC D.B. Wilson | Minnetonka | Filter Press | EVOQUA WATER TECHNOLOGIES, LLC | 4503791005 | Rotating Equipment | Filter Press | USD | 715300 | USD | 675790 | 39510 | Supplier Competitions / Negotiation | 2022-04-22 | 2022-03-04 | 2022-03-28 | 2022-05-13 | 2022-04-12 | 2022-08-29 | 2022-06-10 | 2022-05-12 | 2023-02-24 | 2023-01-27 | 2023-02-10 | -14 | 30 | 69
509248 | BREC D.B. Wilson | Minnetonka | Soda Ash Silo | Con-v-air | 4503799555 | Fabrication | Carbon Steel | USD | 589880 | CAD | 531689 | 58191 | Supplier Competitions / Negotiation | 2022-04-22 | 2022-03-04 | 2022-04-08 | 2022-05-13 | 2022-05-05 | 2022-08-10 | 2022-06-10 | 2022-05-30 | 2023-01-06 | 2023-01-16 | 2023-01-11 | 5 | 18 | 87
509248 | BREC D.B. Wilson | Minnetonka | Clarifier (Tank, internals, sample system) | SPS ENGINEERING INC | 4503797351 | Fabrication | Carbon Steel | USD | 393770 | USD | 368672 | 25098 | Supplier Competitions / Negotiation | 2022-03-11 | 2022-03-04 | 2022-03-30 | 2022-04-01 | 2022-04-23 | 2022-08-29 | 2022-04-29 | 2022-05-21 | 2023-02-24 | 2023-02-04 | 2023-02-14 | -10 | 30 | 78
509248 | BREC D.B. Wilson | Guelph | Centrifugal Pumps (Skids Assembler - Guelph) | SULZER PUMPS (CANADA) INC. | 4503805980 | Rotating Equipment | Centrifugal Pumps | USD | 17000 | USD | 15596 | 1404 | Frame Agreements | 2022-05-13 | 2022-04-18 | 2022-05-06 | 2022-05-27 | 2022-05-20 | 2022-07-23 | 2022-06-10 | 2022-06-07 | 2022-10-28 | 2022-10-25 | 2022-10-26 | -1 | 36 | 50
509248 | BREC D.B. Wilson | Minnetonka | Centrifugal Pumps (MNKA) | SULZER PUMPS (CANADA) IN | 4503806395 | Rotating Equipment | Centrifugal Pumps | USD | 9000 | USD | 8775 | 225 | Frame Agreements | 2022-05-13 | 2022-04-18 | 2022-05-27 | 2022-05-27 | 2022-05-22 | 2022-07-23 | 2022-06-10 | 2022-06-09 | 2022-10-28 | 2022-10-27 | 2022-10-27 | 0 | 36 | 52
509248 | BREC D.B. Wilson | Guelph | Centrifugal Pumps (Guelph) | SULZER PUMPS (CANADA) INC. | 4503806398 | Rotating Equipment | Centrifugal Pumps | USD | 32000 | USD | 33670 | -1670 | Frame Agreements | 2022-05-13 | 2022-04-18 | 2022-05-06 | 2022-05-27 | 2022-05-21 | 2022-07-23 | 2022-06-10 | 2022-06-08 | 2022-10-28 | 2022-10-26 | 2022-10-27 | -1 | 36 | 51
509248 | BREC D.B. Wilson | Minnetonka | Centrifugal Pumps (Skids Assembler - MNKA) | SULZER PUMPS (CANADA) INC. | 4503805975 | Rotating Equipment | Centrifugal Pumps | USD | 30000 | USD | 30322 | -322 | Frame Agreements | 2022-05-13 | 2022-04-18 | 2022-05-06 | 2022-05-27 | 2022-05-22 | 2022-07-23 | 2022-06-10 | 2022-06-09 | 2022-10-28 | 2022-10-27 | 2022-10-27 | 0 | 36 | 52
509248 | BREC D.B. Wilson | Minnetonka | Progress Cavity Pumps | SEEPEX - USA | 4503809230 | Rotating Equipment | PD Pumps | USD | 111328 | USD | 113701 | -2373 | Frame Agreements | 2022-05-13 | 2022-04-08 | 2022-04-21 | 2022-05-27 | 2022-05-01 | 2022-07-18 | 2022-06-14 | 2022-06-13 | 2022-10-28 | 2022-09-19 | 2022-10-08 | -19 | 36 | 66
509248 | BREC D.B. Wilson | Minnetonka | Chem Feed Skids | Prominent Fluid Controls Inc. | 4503825069 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 143922 | USD | 131375 | 12547 | Supplier Competitions / Negotiation | 2022-07-01 | 2022-04-19 | 2022-05-03 | 2022-07-15 | 2022-06-29 | 2022-08-28 | 2022-08-05 | 2022-07-13 | 2023-01-06 | 2022-11-09 | 2022-12-08 | -29 | 30 | 85
509248 | BREC D.B. Wilson | Minnetonka | Tanks - HDPE | ACO CONTAINER SYSTEMS LTD. | 4503791728 | Fabrication | Non-Metal Equipment | USD | 20743 | CAD | 16746 | 3997 | Supplier Competitions / Negotiation | 2022-05-27 | 2022-04-21 | 2022-04-28 | 2022-06-10 | 2022-05-09 | 2022-07-26 | 2022-06-24 | 2022-05-15 | 2022-10-28 | 2022-10-30 | 2022-10-29 | 1 | 12 | 24
509248 | BREC D.B. Wilson | Minnetonka | Tanks - FRP | Augusta Fiberglass | 4503832519 | Fabrication | Non-Metal Equipment | USD | 371097 | USD | 235621 | 135476 | Design Optimizations | 2022-07-01 | 2022-05-03 | 2022-06-21 | 2022-07-15 | 2022-07-10 | 2022-09-04 | 2022-08-05 | 2022-07-25 | 2023-01-06 | 2022-12-12 | 2022-12-24 | -12 | 12 | 83
509248 | BREC D.B. Wilson | Minnetonka | Automatic Self-Cleaning Strainer | BOLL FILTER CORPORATION | 4503799414 | Flow Control | Filters And Strainers (Incl Housings) | USD | 24140 | USD | 34590 | -10450 | Size/ Weight/ Quantity Underestimated | 2022-05-27 | 2022-04-22 | 2022-05-02 | 2022-06-10 | 2022-05-05 | 2022-07-25 | 2022-06-24 | 2022-05-30 | 2022-10-28 | 2022-10-03 | 2022-10-15 | -12 | 24 | 38
509248 | BREC D.B. Wilson | Minnetonka | Mixers | DYNAMIX | 4503844099 | Rotating Equipment | Mixers | USD | 103912 | CAD | 68551 | 35361 | Supplier Competitions / Negotiation | 2022-08-12 | 2022-04-28 | 2022-05-16 | 2022-08-26 | 2022-07-12 | 2022-09-01 | 2022-09-16 | 2022-08-16 | 2023-01-06 | 2022-12-19 | 2022-12-28 | -9 | 30 | 110
509248 | BREC D.B. Wilson | Minnetonka | Scraper Drive | DBS MANUFACTURING INC. | 4503809949 | Rotating Equipment | Electric Motors | USD | 13140 | USD | 12950 | 190 | Supplier Competitions / Negotiation | 2022-08-26 | 2022-04-15 | 2022-04-27 | 2022-09-02 | 2022-04-26 | 2022-08-26 | 2022-09-16 | 2022-06-16 | 2023-01-06 | 2022-12-15 | 2022-12-26 | -11 | 30 | 62
509253 | Duffin Creek 2.0 - HTFB | Oakville | Primary Heat Exchanger & Waste Heat Boiler | Arvos Schmidtsche Schack | 4503811671 | Fabrication | Stainless Steel | CAD | 12662597 | USD | 12939381 | -276784 | Single Sourced | 2022-03-22 | 2022-03-31 | 2022-04-19 | 2022-04-12 | 2022-05-13 | 2022-05-20 | 2022-04-22 | 2022-07-05 | 2025-04-21 | 2025-04-14 | 2025-04-17 | -3 | 12 | 96
509253 | Duffin Creek 2.0 - HTFB | Oakville | Wet Scrubber System & SPC System | ENVIROCARE INTL. INC | 4503794580 | Fabrication | Process Equipment | CAD | 6939858 | USD | 6917017 | 22841 | Supplier Competitions / Negotiation | 2022-03-17 | 2022-03-25 | 2022-04-14 | 2022-04-07 | 2022-05-07 | 2022-05-18 | 2022-04-22 | 2022-05-18 | 2025-04-21 | 2025-04-14 | 2025-04-17 | -3 | 12 | 54
509253 | Duffin Creek 2.0 - HTFB | Oakville | Fuel Train and Preheat | Fives North American Combustion Inc | 4503819817 | Fabrication | Process Equipment | CAD | 989437 | USD | 999161 | -9724 | Market Impact | 2022-03-31 | 2022-04-15 | 2022-06-01 | 2022-04-22 | 2022-06-28 | 2022-07-05 | 2022-05-06 | 2022-07-06 | 2025-04-21 | 2025-05-04 | 2025-04-27 | 7 | 12 | 82
509253 | Duffin Creek 2.0 - HTFB | Oakville | FAB Blower w/Turbine Package | GARDNER DENVER NASH LLC | 4503816788 | Rotating Equipment | Blowers & Fans | CAD | 195300 | USD | 195300 | 0 | Not included in Proposal / RFQ | 2022-04-05 | 2022-04-15 | 2022-05-19 | 2022-04-27 | 2022-06-19 | 2023-10-13 | 2022-05-06 | 2022-06-26 | 2025-04-21 | 2023-11-30 | 2024-08-10 | -254 | 30 | 72
509270 | SEMECS MBR EXPANSION | Oakville | Membrane tank cover (FRP) | PRECISIONEERING | 4503786857 | Fabrication | Non-Metal Equipment | CAD | 5000 | CAD | 5686 | -686 | Market Impact | 2022-04-18 | 2022-06-20 | 2022-04-27 | 2022-05-02 | 2022-06-20 | 2022-06-20 | 2022-05-16 | 2022-05-08 | 2022-08-22 | 2022-07-07 | 2022-07-30 | -23 | 12 | -43
509270 | SEMECS MBR EXPANSION | Oakville | Blowers+Spare | AERZEN CANADA INC | 4503766227 | Rotating Equipment | Blowers & Fans | CAD | 16910 | CAD | 18840 | -1930 | Specs / Requirements Misinterpreted in Proposal | 2022-05-02 | 2022-05-20 | 2022-02-15 | 2022-05-16 | 2022-05-20 | 2022-05-20 | 2022-05-30 | 2022-03-30 | 2022-08-22 | 2022-06-22 | 2022-07-22 | -30 | 30 | -51
509270 | SEMECS MBR EXPANSION | Oakville | Process pump (Boerger)+Spare | BOERGER LLC | 4503764659 | Rotating Equipment | PD Pumps | CAD | 13962 | USD | 16796 | -2834 | Market Impact | 2022-03-02 | 2022-04-21 | 2022-02-18 | 2022-03-16 | 2022-04-21 | 2022-04-21 | 2022-03-30 | 2022-03-28 | 2022-06-22 | 2022-06-20 | 2022-06-21 | -1 | 30 | -24
509270 | SEMECS MBR EXPANSION | Oakville | RAS/WAS pump (Rotech)+Spare | ROTECH PUMPS & SYSTEM INC | 4503770134 | Rotating Equipment | Centrifugal Pumps | CAD | 18218 | CAD | 22599 | -4381 | Estimate Without Market Reference(No Quote) | 2022-05-02 | 2022-06-03 | 2022-03-15 | 2022-05-16 | 2022-06-03 | 2022-06-03 | 2022-05-30 | 2022-04-07 | 2022-08-22 | 2022-06-03 | 2022-07-13 | -40 | 30 | -57
509270 | SEMECS MBR EXPANSION | Oakville | Dosing panels+Spare | PROMINENT FLUID CONTROLS LTD. | 4503769662 | Rotating Equipment | Chem. Feed Skids (Turnkey) | CAD | 19945 | CAD | 18202 | 1743 | Supplier Competitions / Negotiation | 2022-04-18 | 2022-06-13 | 2022-04-04 | 2022-05-02 | 2022-06-13 | 2022-06-13 | 2022-05-16 | 2022-04-06 | 2022-08-22 | 2022-06-15 | 2022-07-19 | -34 | 30 | -68
509270 | SEMECS MBR EXPANSION | Oakville | Main Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503784473 | Electrical & Instrumentation | Ele-Control Panels | CAD | 35468 | CAD | 8400 | 27068 | Design Optimizations | 2022-03-02 | 2022-05-07 | 2022-04-04 | 2022-03-16 | 2022-05-07 | 2022-05-07 | 2022-03-30 | 2022-05-03 | 2022-06-22 | 2022-07-12 | 2022-07-02 | 10 | 18 | -4
509270 | SEMECS MBR EXPANSION | Oakville | PLC Hardware | WESTBURNE INDUSTRIAL ONTARIO | 4503768148 | Electrical & Instrumentation | Ele-PLCs, HMIs | CAD | 15405 | CAD | 15405 | 0 | Market Impact | 2021-09-29 | 2022-01-17 | 2022-02-15 | 2021-10-13 | 2022-01-17 | 2022-01-17 | 2021-10-27 | 2022-04-02 | 2022-03-30 | 2022-05-07 | 2022-04-18 | 19 | 18 | 75
509270 | SEMECS MBR EXPANSION | Oakville | MCC/VFD's Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503785223 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | CAD | 35165 | CAD | 19400 | 15765 | Frame Agreements | 2021-11-17 | 2022-04-13 | 2022-04-18 | 2021-12-01 | 2022-04-13 | 2022-04-13 | 2021-12-15 | 2022-05-04 | 2022-03-30 | 2022-09-07 | 2022-06-18 | 81 | 18 | 21
509270 | SEMECS MBR EXPANSION | Oakville | VFD long-lead components | DAVIS CONTROLS LTD. | 4503768595 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | CAD | 9184 | USD | 9184 | 0 | Estimate Without Market Reference(No Quote) | 2022-07-15 | 2022-07-15 | 2022-03-15 | 2022-07-15 | 2022-07-15 | 2022-07-15 | 2022-07-15 | 2022-04-04 | 2022-07-15 | 2022-11-14 | 2022-09-14 | 61 | 18 | -102
509270 | SEMECS MBR EXPANSION | Oakville | Pump Skid | TITAN PIPING SYSTEMS INC. | 4503785439 | Fabrication | Carbon Steel | CAD | 29384 | CAD | 28000 | 1384 | Frame Agreements | 2022-04-18 | 2022-06-21 | 2022-04-14 | 2022-05-02 | 2022-06-21 | 2022-06-21 | 2022-05-16 | 2022-05-02 | 2022-08-22 | 2022-08-29 | 2022-08-25 | 4 | 12 | -50
509270 | SEMECS MBR EXPANSION | Oakville | BP Tank | ACO CONTAINER SYSTEMS LTD. | 4503771109 | Fabrication | Non-Metal Equipment | CAD | 6500 | CAD | 6486 | 14 | Design Optimizations | 2022-04-07 | 2022-05-24 | 2022-02-23 | 2022-04-08 | 2022-05-24 | 2022-05-24 | 2022-04-11 | 2022-04-06 | 2022-08-22 | 2022-05-11 | 2022-07-01 | -51 | 12 | -48
509280 | White Lake | Richmond | Pressure Vessel | BE Peterson | 4503768171 | Fabrication | Carbon Steel | USD | 215077 | USD | 225774 | -10697 | Single Sourced | 2022-03-01 | 2022-02-28 | 2022-03-02 | 2022-03-15 | 2022-03-31 | 2022-06-09 | 2022-04-12 | 2022-04-03 | 2022-09-10 | 2022-09-18 | 2022-09-14 | 4 | 12 | 34
509280 | White Lake | Richmond | Control Panel | HESCO Group, INC | 4503779080 | Electrical & Instrumentation | Ele-Control Panels | USD | 65000 | USD | 62000 | 3000 | Design Optimizations | 2022-03-01 | 2022-03-28 | 2022-04-01 | 2022-03-15 | 2022-04-08 | 2022-06-05 | 2022-04-12 | 2022-04-22 | 2022-09-10 | 2022-08-15 | 2022-08-28 | -13 | 18 | 25
509280 | White Lake | Richmond | Butterfly Valves | COMMONWEALTH CONTROLS CORPORATION | 4503809001 | Flow Control | Metal Control Valves | USD | 68197 | USD | 109703 | -41506 | Estimate Without Market Reference(No Quote) | 2022-03-01 | 2022-01-28 | 2022-02-03 | 2022-03-15 | 2022-06-14 | 2022-06-01 | 2022-04-12 | 2022-06-14 | 2022-09-10 | 2022-10-04 | 2022-09-22 | 12 | 12 | 137
509280 | White Lake | Richmond | Flowmeter | LAKESIDE PROCESS CONTROLS LTD. | 4503812404 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 9811 | USD | 12784 | -2973 | Proposed Supplier Incapable Of Executing | 2022-03-01 | 2022-06-16 | 2022-06-21 | 2022-03-15 | 2022-06-21 | 2022-06-05 | 2022-04-12 | 2022-06-21 | 2022-09-10 | 2022-08-30 | 2022-09-04 | -5 | 18 | 5
509280 | White Lake | Richmond | Transmitter | LAKESIDE PROCESS CONTROLS LTD. | 4503822142 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 8516 | USD | 11370 | -2854 | Market Impact | 2022-03-01 | 2022-07-01 | 2022-07-07 | 2022-03-15 | 2022-07-07 | 2022-06-15 | 2022-04-12 | 2022-07-07 | 2022-09-10 | 2022-09-29 | 2022-09-19 | 10 | 18 | 6
509280 | White Lake | Richmond | Static Mixer | KOFLO CORPORATION | 4503822669 | Flow Control | Static Mixer | USD | 10300 | USD | 9166 | 1134 | Design Optimizations | 2022-03-01 | 2022-04-21 | 2022-04-28 | 2022-03-15 | 2022-06-05 | 2022-06-05 | 2022-04-12 | 2022-07-08 | 2022-09-10 | 2022-08-05 | 2022-08-23 | -18 | 12 | 78
509281 | Niagara | Oakville | Cyclindrical Screen ( 44 Nos) | Federal Screens | 4503808429 | Fabrication | Stainless Steel | CAD | 236454 | CAD | 242964 | -6510 | Estimate Without Market Reference(No Quote) | 2022-02-01 | 2022-02-15 | 2022-03-04 | 2022-03-16 | 2022-06-14 | 2022-09-16 | 2023-04-14 | 2022-06-14 | 2023-04-14 | 2023-05-01 | 2023-04-22 | 9 | 12 | 119
509281 | Niagara | Oakville | Diffuser | XYLEM | 4503766326 | Flow Control | Other | CAD | 170600 | CAD | 162590 | 8010 | Frame Agreements | 2022-02-01 | 2022-02-15 | 2022-03-01 | 2022-03-16 | 2022-03-29 | 2022-07-25 | 2023-01-16 | 2022-03-31 | 2023-01-16 | 2022-11-10 | 2022-12-13 | -33 | 12 | 44
509312 | COKE EAGAN | Minnetonka | DM Filter Retrofit Kit | DSI PROCESS SYSTEMS | 4503853143 | Fabrication | Stainless Steel | USD | 108000 | USD | 51720 | 56280 | Supplier Competitions / Negotiation | 2021-12-28 | 2022-07-05 | 2022-07-26 | 2022-02-28 | 2022-09-01 | 2022-07-05 | 2022-03-01 | 2022-09-01 | 2022-08-17 | 2023-01-10 | 2022-10-29 | 73 | 12 | 58
509312 | COKE EAGAN | Minnetonka | Activated Carbon Towers 96x168 Vessels | Arrow Tanks | 4503730739 | Fabrication | Stainless Steel | USD | 245067 | USD | 245067 | 0 | Supplier Competitions / Negotiation | 2021-12-28 | 2022-12-29 | 2021-12-29 | 2022-02-02 | 2022-02-02 | 2022-06-29 | 2022-02-02 | 2022-02-02 | 2022-05-16 | 2022-05-09 | 2022-05-12 | -3 | 12 | -330
509312 | COKE EAGAN | Minnetonka | Activated Carbon Towers 96x168 - MATERIALS | ARC SERVICES | 4503834740 | Fabrication | Stainless Steel | USD | 69461 | USD | 139818 | -70357 | Proposed Supplier Incapable Of Executing | 2022-03-01 | 2022-06-20 | 2022-07-26 | 2022-02-28 | 2022-07-29 | 2022-08-05 | 2022-03-01 | 2022-07-29 | 2022-08-17 | 2023-01-10 | 2022-10-29 | 73 | 12 | 39
509312 | COKE EAGAN | Minnetonka | Activated Carbon Towers 96x168- LABOR | ARC SERVICES | 4513834740 | Fabrication | Skid Assembly Outsourced | USD | 39683 | USD | 80092 | -40409 | Proposed Supplier Incapable Of Executing | 2021-12-28 | 2022-06-20 | 2022-07-26 | 2022-02-28 | 2022-07-29 | 2022-07-05 | 2022-03-01 | 2022-07-29 | 2022-08-17 | 2023-01-10 | 2022-10-29 | 73 | 12 | 39
509312 | COKE EAGAN | Minnetonka | UV Pre-Main RO | AQUIONICS, INC. | 4503811461 | Electrical & Instrumentation | Ele-Electrical Others | USD | 55000 | USD | 35360 | 19640 | Estimate Without Market Reference(No Quote) | 2022-03-01 | 2022-06-13 | 2022-05-31 | 2022-03-03 | 2022-06-20 | 2022-06-13 | 2022-03-04 | 2022-06-20 | 2022-08-01 | 2022-09-26 | 2022-08-29 | 28 | 18 | 7
509312 | COKE EAGAN | Minnetonka | Main RO Skid - ULE - MATERIALS | ARC SERVICES | 4523834740 | Fabrication | Skid Assembly Outsourced | USD | 304998 | USD | 160876 | 144122 | Proposed Supplier Incapable Of Executing | 2022-03-01 | 2022-06-20 | 2022-07-26 | 2022-02-28 | 2022-07-29 | 2022-08-05 | 2022-03-01 | 2022-07-29 | 2022-06-15 | 2023-01-10 | 2022-09-27 | 105 | 12 | 39
509312 | COKE EAGAN | Minnetonka | Main RO Skid - ULE - LABOR | ARC SERVICES | 4533834740 | Fabrication | Skid Assembly Outsourced | USD | 122100 | USD | 211700 | -89600 | Proposed Supplier Incapable Of Executing | 2022-03-01 | 2022-06-20 | 2022-07-26 | 2022-02-28 | 2022-07-29 | 2022-08-05 | 2022-03-01 | 2022-07-29 | 2022-08-17 | 2023-01-10 | 2022-10-29 | 73 | 12 | 39
509312 | COKE EAGAN | Minnetonka | Permeate Tank Accessories - ULE | AQUIONICS, INC. | 4513811461 | Electrical & Instrumentation | Ele-Electrical Others | USD | 40000 | USD | 61182 | -21182 | Proposed Supplier Incapable Of Executing | 2022-03-15 | 2022-06-20 | 2022-05-31 | 2022-03-16 | 2022-06-20 | 2022-06-20 | 2022-03-16 | 2022-06-20 | 2022-07-15 | 2022-09-26 | 2022-08-20 | 37 | 18 | 0
509312 | COKE EAGAN | Minnetonka | Distribution Pump Skid - ULE - LABOR | ARC SERVICES | 4543834740 | Fabrication | Skid Assembly Outsourced | USD | 29288 | USD | 29288 | 0 | Specs / Requirements Misinterpreted in Proposal | 2022-03-01 | 2022-06-20 | 2022-07-26 | 2022-02-28 | 2022-07-29 | 2022-08-05 | 2022-03-01 | 2022-07-29 | 2022-08-01 | 2023-01-10 | 2022-10-21 | 81 | 12 | 39
509312 | COKE EAGAN | Minnetonka | CIP System - TANK | Preferred Stainless Holdings | 4503809207 | Fabrication | Stainless Steel | USD | 48438 | USD | 48438 | 0 | Estimate Without Market Reference(No Quote) | 2022-03-01 | 2022-07-01 | 2022-06-07 | 2022-03-03 | 2022-06-14 | 2022-07-01 | 2022-03-04 | 2022-06-14 | 2022-06-15 | 2022-11-01 | 2022-08-23 | 70 | 12 | -17
509312 | COKE EAGAN | Minnetonka | CIP System - MATERIALS | ARC SERVICES | 4553834740 | Fabrication | Skid Assembly Outsourced | USD | 42287 | USD | 37766 | 4521 | Proposed Supplier Incapable Of Executing | 2022-03-01 | 2022-06-20 | 2022-07-26 | 2022-02-28 | 2022-07-29 | 2022-08-05 | 2022-03-01 | 2022-07-29 | 2022-06-15 | 2023-01-10 | 2022-09-27 | 105 | 12 | 39
509312 | COKE EAGAN | Minnetonka | CIP System - LABOR | ARC SERVICES | 4563834740 | Fabrication | Skid Assembly Outsourced | USD | 16280 | USD | 27899 | -11619 | Proposed Supplier Incapable Of Executing | 2022-03-01 | 2022-08-05 | 2022-07-26 | 2022-02-28 | 2022-07-29 | 2022-08-05 | 2022-03-01 | 2022-07-29 | 2022-08-01 | 2023-01-10 | 2022-10-21 | 81 | 12 | -7
509312 | COKE EAGAN | Minnetonka | UV Recovery RO | AQUIONICS, INC. | 4523811461 | Electrical & Instrumentation | Ele-Electrical Others | USD | 31000 | USD | 23600 | 7400 | Proposed Supplier Incapable Of Executing | 2022-03-01 | 2022-06-13 | 2022-05-31 | 2022-03-03 | 2022-06-20 | 2022-06-13 | 2022-03-04 | 2022-06-20 | 2022-08-01 | 2022-09-26 | 2022-08-29 | 28 | 18 | 7
509312 | COKE EAGAN | Minnetonka | Main PLC Control System and Lab PC/Software | WERNER ELECTRIC | 4503809903 | Electrical & Instrumentation | Ele-Control Panels | USD | 64000 | USD | 20328 | 43672 | Proposed Supplier Incapable Of Executing | 2022-03-01 | 2022-06-21 | 2022-06-16 | 2022-03-03 | 2022-06-16 | 2022-07-04 | 2022-03-04 | 2022-06-16 | 2022-07-01 | 2022-11-07 | 2022-09-03 | 65 | 18 | -5
509312 | COKE EAGAN | Minnetonka | Motor Control Enclosure | WERNER ELECTRIC | 4503818376 | Electrical & Instrumentation | Ele-Control Panels | USD | 170000 | USD | 148710 | 21290 | Proposed Supplier Incapable Of Executing | 2022-03-01 | 2022-02-04 | 2022-06-10 | 2022-03-03 | 2022-06-25 | 2022-06-25 | 2022-03-04 | 2022-06-29 | 2022-07-01 | 2022-11-13 | 2022-09-06 | 68 | 18 | 145
509312 | COKE EAGAN | Minnetonka | CIP System - PUMP | PFC EQUIPMENT | 4503811566 | Rotating Equipment | Centrifugal Pumps | USD | 12275 | USD | 12275 | 0 | Design Optimizations | 2022-08-25 | 2022-08-25 | 2022-06-13 | 2022-08-25 | 2022-06-20 | 2022-08-25 | 2022-08-25 | 2022-06-20 | 2022-08-25 | 2022-11-07 | 2022-10-01 | 37 | 30 | -66
509364 | Intel Eagle Ocotillo | Oakville | Heat Exchanger | ALFA LAVAL | 4503769064 | Fabrication | Alloy Steel | USD | 323530 | USD | 326949 | -3419 | Market Impact | 2022-03-15 | 2022-03-15 | 2022-03-18 | 2022-03-29 | 2022-03-30 | 2022-07-15 | 2022-04-05 | 2022-04-04 | 2022-04-05 | 2022-11-14 | 2022-07-25 | 112 | 12 | 20
509364 | Intel Eagle Ocotillo | Oakville | Valves - Lakeside Lot 1 | LAKESIDE PROCESS CONTROLS LTD. | 4503787993 | Flow Control | Metal Control Valves | USD | 46759 | USD | 47322 | -563 | Single Sourced | 2022-04-20 | 2022-04-25 | 2022-05-06 | 2022-06-25 | 2022-05-06 | 2022-06-25 | 2022-05-31 | 2022-05-10 | 2022-06-25 | 2022-08-31 | 2022-07-28 | 34 | 12 | 15
509364 | Intel Eagle Ocotillo | Oakville | Pumps Centrifugal - Richter | IDEX Corporation | 4503798299 | Rotating Equipment | Centrifugal Pumps | USD | 142232 | USD | 133743 | 8489 | Supplier Competitions / Negotiation | 2022-03-31 | 2022-04-10 | 2022-05-04 | 2022-04-21 | 2022-05-25 | 2022-06-22 | 2022-04-28 | 2022-05-25 | 2022-04-28 | 2022-09-14 | 2022-07-06 | 70 | 30 | 45
509364 | Intel Eagle Ocotillo | Oakville | Spools - Non Metallic | GEORG FISCHER PIPING SYSTEMS LTD | 4503798273 | Flow Control | Plastic Pipe and Fittings | USD | 97219 | USD | 123063 | -25844 | Market Impact | 2022-04-25 | 2022-05-03 | 2022-05-05 | 2022-05-09 | 2022-05-23 | 2022-06-17 | 2022-05-16 | 2022-05-25 | 2022-05-16 | 2022-08-09 | 2022-06-27 | 43 | 12 | 22
509364 | Intel Eagle Ocotillo | Oakville | UF Skid Manifold | GEORG FISCHER LLC | 4503802864 | Rotating Equipment | Others | USD | 93800 | USD | 137169 | -43369 | Market Impact | 2022-03-31 | 2022-04-04 | 2022-03-18 | 2022-04-21 | 2022-04-14 | 2022-06-11 | 2022-04-28 | 2022-04-17 | 2022-04-28 | 2022-09-04 | 2022-07-01 | 65 | 30 | 13
509364 | Intel Eagle Ocotillo | Oakville | Fabrication - Skid | 3D MECHANICAL | 4503804399 | Fabrication | Carbon Steel | USD | 57664 | CAD | 49075 | 8589 | Supplier Competitions / Negotiation | 2022-04-25 | 2022-05-03 | 2022-06-03 | 2022-05-09 | 2022-06-10 | 2022-05-19 | 2022-05-16 | 2022-06-12 | 2022-05-16 | 2022-06-12 | 2022-05-29 | 14 | 12 | 40
509364 | Intel Eagle Ocotillo | Oakville | VFD | Integrated Systems Group | 4503823880 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 20600 | USD | 18686 | 1914 | Supplier Competitions / Negotiation | 2022-04-29 | 2022-05-31 | 2022-06-07 | 2022-05-13 | 2022-06-07 | 2022-08-06 | 2022-05-20 | 2022-07-11 | 2022-05-20 | 2022-11-14 | 2022-08-17 | 89 | 18 | 41
509364 | Intel Eagle Ocotillo | Oakville | Valves - Control | LAKESIDE PROCESS CONTROLS LTD. | 4503801261 | Flow Control | Metal Control Valves | USD | 20900 | USD | 29413 | -8513 | Estimate Without Market Reference(No Quote) | 2022-03-01 | 2022-05-15 | 2022-03-24 | 2022-03-15 | 2022-06-17 | 2022-06-10 | 2022-03-22 | 2022-05-31 | 2022-03-22 | 2022-09-19 | 2022-06-20 | 91 | 12 | 16
509364 | Intel Eagle Ocotillo | Oakville | Spools - Carbon Steel | Alps Welding Ltd. | 4503803409 | Fabrication | Carbon Steel | USD | 16124 | CAD | 21140 | -5016 | Estimate Without Market Reference(No Quote) | 2022-04-29 | 2022-05-03 | 2022-06-01 | 2022-05-13 | 2022-06-03 | 2022-07-07 | 2022-05-20 | 2022-06-06 | 2022-05-20 | 2022-09-15 | 2022-07-18 | 59 | 12 | 34
509364 | Intel Eagle Ocotillo | Oakville | Electrical Panels | KELTOUR CONTROLS INC. | 4503827879 | Electrical & Instrumentation | Ele-Control Panels | USD | 15000 | CAD | 13631 | 1369 | Frame Agreements | 2022-04-29 | 2022-06-15 | 2022-07-11 | 2022-05-13 | 2022-07-11 | 2022-07-13 | 2022-05-20 | 2022-07-18 | 2022-05-20 | 2022-09-26 | 2022-07-23 | 65 | 18 | 33
509364 | Intel Eagle Ocotillo | Oakville | Instrumentation - Flow Transmitters | ENDRESS + HAUSER CANADA LTD. | 4503786336 | Electrical & Instrumentation | Inst-Multiparam Transmitters, Controllers | USD | 12468 | USD | 21016 | -8548 | Proposed Supplier Incapable Of Executing | 2022-04-21 | 2022-04-25 | 2022-05-03 | 2022-05-05 | 2022-05-03 | 2022-05-19 | 2022-05-12 | 2022-05-05 | 2022-05-12 | 2022-06-16 | 2022-05-29 | 18 | 18 | 10
509364 | Intel Eagle Ocotillo | Oakville | Valves - PRV | Great Lakes Industrial Controls | 4503794544 | Flow Control | Metal Safety(relief) Valves | USD | 8180 | CAD | 9445 | -1265 | Estimate Without Market Reference(No Quote) | 2022-04-21 | 2022-04-20 | 2022-04-28 | 2022-05-05 | 2022-05-17 | 2022-06-29 | 2022-05-12 | 2022-05-19 | 2022-05-12 | 2022-09-08 | 2022-07-10 | 60 | 12 | 29
509412 | SunOpta Project Rodeo | Minnetonka | Blower - DS | AERZEN CANADA INC | 4503766931 | Rotating Equipment | Blowers & Fans | USD | 47390 | CAD | 49344 | -1954 | Market Impact | 2022-04-25 | 2020-03-03 | 2022-03-10 | 2022-05-09 | 2022-04-21 | 2021-05-24 | 2022-05-23 | 2022-04-01 | 2022-08-15 | 2022-06-10 | 2022-07-13 | -33 | 30 | 759
509412 | SunOpta Project Rodeo | Minnetonka | Dosing Pumps Skids - DS | PROMINENT FLUID CONTROLS LTD. | 4503770405 | Rotating Equipment | Dosing Pump | USD | 6866 | CAD | 17045 | -10179 | Market Impact | 2022-05-16 | 2022-03-18 | 2022-03-18 | 2022-05-30 | 2022-03-31 | 2022-06-01 | 2022-06-06 | 2022-04-06 | 2022-08-15 | 2022-04-06 | 2022-06-10 | -65 | 30 | 19
509412 | SunOpta Project Rodeo | Minnetonka | VFD - DS | Danfoss LLC | 4503795121 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 9508 | USD | 11035 | -1527 | Market Impact | 2022-03-21 | 2022-04-28 | 2022-05-20 | 2022-04-04 | 2022-05-20 | 2022-07-18 | 2022-04-11 | 2022-05-20 | 2022-06-20 | 2022-11-14 | 2022-09-01 | 74 | 18 | 22
509412 | SunOpta Project Rodeo | Minnetonka | Process Pumps - SKIDDED | BOERGER LLC | 4503772014 | Rotating Equipment | PD Pumps | USD | 16236 | USD | 16660 | -424 | Market Impact | 2022-03-18 | 2022-03-21 | 2022-03-05 | 2022-03-25 | 2022-04-05 | 2022-05-11 | 2022-04-01 | 2022-04-11 | 2022-06-20 | 2022-07-18 | 2022-07-04 | 14 | 30 | 21
509412 | SunOpta Project Rodeo | Minnetonka | RAS Pumps - DS | SULZER PUMPS (CANADA) IN | 4503762233 | Rotating Equipment | Centrifugal Pumps | USD | 22473 | CAD | 28738 | -6265 | Market Impact | 2022-03-25 | 2022-03-18 | 2022-03-21 | 2022-04-01 | 2022-03-20 | 2022-06-01 | 2022-04-11 | 2022-03-23 | 2022-08-15 | 2022-07-28 | 2022-08-06 | -9 | 30 | 5
509412 | SunOpta Project Rodeo | Minnetonka | Bioreactor Tank - CS - includes coating - DS | TANK CONNECTION | 4503767209 | Fabrication | Carbon Steel | USD | 102777 | USD | 116318 | -13541 | Market Impact | 2022-03-28 | 2022-03-10 | 2022-03-31 | 2022-04-11 | 2022-03-28 | 2022-05-28 | 2022-04-25 | 2022-03-30 | 2022-08-15 | 2022-07-20 | 2022-08-02 | -13 | 12 | 20
509412 | SunOpta Project Rodeo | Minnetonka | Membrane Tank - SS & Components - DS | POSEIDON, INC | 4503773265 | Fabrication | Stainless Steel | USD | 133455 | USD | 160768 | -27313 | Market Impact | 2022-03-28 | 2022-03-09 | 2022-03-17 | 2022-04-11 | 2022-03-28 | 2022-05-27 | 2022-04-25 | 2022-03-28 | 2022-08-15 | 2022-08-15 | 2022-08-15 | 0 | 12 | 19
509412 | SunOpta Project Rodeo | Minnetonka | Control Panel - DS | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503794301 | Electrical & Instrumentation | Ele-Control Panels | USD | 44637 | CAD | 27823 | 16814 | Supplier Competitions / Negotiation | 2022-04-11 | 2022-04-19 | 2022-05-12 | 2022-04-18 | 2022-05-08 | 2022-06-02 | 2022-04-29 | 2022-05-16 | 2022-06-20 | 2022-07-25 | 2022-07-07 | 18 | 18 | 27
509412 | SunOpta Project Rodeo | Minnetonka | Control Panel - SIDDED | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503824458 | Electrical & Instrumentation | Ele-Control Panels | USD | 17573 | CAD | 17573 | 0 | Specs / Requirements Misinterpreted in Proposal | 2022-06-26 | 2022-06-26 | 2022-05-12 | 2022-06-26 | 2022-05-09 | 2022-06-26 | 2022-06-26 | 2022-07-11 | 2022-06-26 | 2022-08-14 | 2022-07-20 | 25 | 18 | 15
509412 | SunOpta Project Rodeo | Minnetonka | Transmitter - Level, Flow | ENDRESS + HAUSER CANADA LTD. | 4503798750 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 9319 | USD | 9319 | 0 | Not included in Proposal / RFQ | 2022-03-28 | 2022-05-18 | 2022-04-11 | 2022-04-11 | 2022-05-18 | 2022-05-18 | 2022-04-25 | 2022-05-27 | 2022-06-20 | 2022-07-08 | 2022-06-29 | 9 | 18 | 9
509412 | SunOpta Project Rodeo | Minnetonka | Turbidity, Valve-Needle, Flow Sensor & Controller - SKIDDED | Hach Company | 4503823011 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 5424 | USD | 6986 | -1562 | Specs / Requirements Misinterpreted in Proposal | 2022-03-28 | 2022-06-17 | 2022-06-17 | 2022-04-11 | 2022-06-16 | 2022-05-31 | 2022-04-25 | 2022-07-11 | 2022-06-20 | 2022-08-03 | 2022-07-12 | 22 | 18 | 24
509412 | SunOpta Project Rodeo | Minnetonka | Diffuser - DS | ENVIRONMENTAL DYNAMICS | 4503774842 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 13265 | USD | 12685 | 580 | Supplier Competitions / Negotiation | 2022-03-14 | 2022-03-18 | 2022-03-28 | 2022-03-21 | 2022-04-07 | 2022-05-30 | 2022-03-28 | 2022-04-07 | 2022-08-15 | 2022-08-07 | 2022-08-11 | -4 | 12 | 20
509412 | SunOpta Project Rodeo | Minnetonka | Skid Frame & Assembly - DS | TITAN PIPING SYSTEMS INC. | 4503810012 | Fabrication | Carbon Steel | USD | 43103 | CAD | 45298 | -2195 | Market Impact | 2022-04-25 | 2022-05-30 | 2022-06-08 | 2022-05-09 | 2022-06-14 | 2022-06-24 | 2022-05-23 | 2022-06-16 | 2022-08-15 | 2022-08-23 | 2022-08-19 | 4 | 12 | 17
509422 | Allegheny | Richmond | Bio-Gas Compressor | GARDNER DENVER NASH LLC | 4503790922 | Rotating Equipment | Compressors | USD | 95976 | USD | 95000 | 976 | Frame Agreements | 2022-03-18 | 2022-03-25 | 2022-04-01 | 2022-04-01 | 2022-05-06 | 2022-10-14 | 2022-04-04 | 2022-05-13 | 2022-04-22 | 2023-05-12 | 2022-10-31 | 193 | 30 | 49
509422 | Allegheny | Richmond | Control Panel | Keltour Controls Inc. | 4503815752 | Electrical & Instrumentation | Ele-Control Panels | USD | 28073 | CAD | 21111 | 6962 | Frame Agreements | 2022-04-17 | 2022-06-11 | 2022-06-14 | 2022-04-15 | 2022-07-27 | 2022-11-16 | 2023-06-20 | 2022-07-27 | 2023-06-20 | 2022-12-28 | 2023-03-25 | -87 | 18 | 46
509422 | Allegheny | Richmond | Bubble Generators | POSEIDON, INC | 4503816674 | Fabrication | Stainless Steel | USD | 6852 | USD | 7080 | -228 | Size/ Weight/ Quantity Underestimated | 2022-03-18 | 2022-06-01 | 2022-06-06 | 2022-04-15 | 2022-06-28 | 2022-11-02 | 2023-06-20 | 2022-06-28 | 2023-06-20 | 2022-09-30 | 2023-02-08 | -131 | 12 | 27
509459 | Nanaimo - UV | Leonia | Wireway,Power Cables, Data Cables, PDDC Panel, &, 509459-0402M002, Bracket, X0063-G23,Gamlet, 316LSS | Paulette Fabricators INC | 4503801775 | Electrical & Instrumentation | Ele-Control Panels | CAD | 36468 | USD | 31340 | 5128 | Frame Agreements | 2022-03-18 | 2022-05-16 | 2022-05-18 | 2022-04-01 | 2022-05-18 | 2022-05-16 | 2022-04-08 | 2022-06-03 | 2022-06-30 | 2022-07-15 | 2022-07-07 | 8 | 18 | 18
509463 | WTS - US / St. Paul WTP - MN/O3/466017 | Leonia | LOX/LIN System | Chart Inc. | 4503814574 | Fabrication | Carbon Steel | USD | 630211 | USD | 614824 | 15387 | Supplier Competitions / Negotiation | 2023-06-16 | 2023-03-03 | 2021-11-30 | 2023-06-23 | 2021-11-30 | 2023-03-03 | 2023-06-30 | 2022-06-24 | 2024-03-01 | 2024-06-03 | 2024-04-17 | 47 | 12 | -252
509463 | WTS - US / St. Paul WTP - MN/O3/466017 | Leonia | Skidded Ozone Analyzers - TAPI | Teledyne API | 4503816306 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 28800 | USD | 28800 | 0 | Market Impact | 2023-05-29 | 2022-06-22 | 2022-06-22 | 2023-06-05 | 2023-02-03 | 2023-02-03 | 2023-06-12 | 2022-06-28 | 2023-09-18 | 2023-01-10 | 2023-05-15 | -125 | 18 | 6
509465 | NESTLE PURINA HARTWELL | Minnetonka | ASSY_Z-MOD L PUMP - RAS PUMP | SULZER | 4503841893 | Rotating Equipment | Centrifugal Pumps | USD | 26286 | CAD | 26286 | 0 | Proposed Supplier Incapable Of Executing | 2022-06-10 | 2022-07-05 | 2022-07-22 | 2022-06-24 | 2022-08-11 | 2022-09-12 | 2022-06-25 | 2022-08-11 | 2022-12-15 | 2022-10-11 | 2022-11-12 | -32 | 30 | 37
509465 | NESTLE PURINA HARTWELL | Minnetonka | ASSY_Z-MOD L PUMP - RAS PUMP | BOERGER LLC | 4503841899 | Rotating Equipment | Centrifugal Pumps | USD | 46564 | USD | 44443 | 2121 | Supplier Competitions / Negotiation | 2022-09-03 | 2022-09-03 | 2022-08-08 | 2022-09-03 | 2022-08-11 | 2022-09-03 | 2022-09-03 | 2022-08-11 | 2022-09-03 | 2022-09-30 | 2022-09-16 | 14 | 30 | -23
509465 | NESTLE PURINA HARTWELL | Minnetonka | LS_MAIN CONTROL PANEL | WERNER ELECTRIC | 4503806658 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 36746 | USD | 21469 | 15277 | Frame Agreements | 2022-08-23 | 2022-06-10 | 2022-06-10 | 2022-08-23 | 2022-06-10 | 2022-08-23 | 2022-08-23 | 2022-06-10 | 2022-08-23 | 2022-11-05 | 2022-09-29 | 37 | 18 | 0
509465 | NESTLE PURINA HARTWELL | Minnetonka | DS_BACK PULSE TANK | POLY PROCESSING | 4503841836 | Fabrication | Stainless Steel | USD | 10241 | USD | 18721 | -8480 | Estimate Without Market Reference(No Quote) | 2022-06-06 | 2022-06-23 | 2022-07-20 | 2022-06-08 | 2022-08-11 | 2022-09-10 | 2022-06-10 | 2022-08-11 | 2022-12-15 | 2022-10-31 | 2022-11-22 | -22 | 12 | 49
509465 | NESTLE PURINA HARTWELL | Minnetonka | DS_MEMBRANE BLOWERS | AERZEN | 4503846040 | Rotating Equipment | Blowers & Fans | USD | 19065 | CAD | 28567 | -9502 | Single Sourced | 2022-06-06 | 2022-06-23 | 2022-07-07 | 2022-06-08 | 2022-08-19 | 2022-09-22 | 2022-06-10 | 2022-08-19 | 2022-12-15 | 2023-01-09 | 2022-12-27 | 13 | 30 | 57
509465 | NESTLE PURINA HARTWELL | Minnetonka | DS_MEMBRANE TANK 316SS | D & R FABRICATION INC - BELDING TANKS | 4503846937 | Fabrication | Stainless Steel | USD | 154894 | CAD | 127624 | 27270 | Design Optimizations | 2022-06-06 | 2022-07-28 | 2022-07-28 | 2022-06-10 | 2022-08-22 | 2022-09-10 | 2022-06-10 | 2022-08-22 | 2022-12-15 | 2022-12-05 | 2022-12-10 | -5 | 12 | 25
509465 | NESTLE PURINA HARTWELL | Minnetonka | DS_MEMBRANE TANK FRP COVER | D & R FABRICATION INC - BELDING TANKS | 4513846937 | Fabrication | Non-Metal Equipment | USD | 23870 | CAD | 23870 | 0 | Specs / Requirements Misinterpreted in Proposal | 2022-06-06 | 2022-07-28 | 2022-07-29 | 2022-06-10 | 2022-08-22 | 2022-09-10 | 2022-06-10 | 2022-08-22 | 2022-12-15 | 2022-12-05 | 2022-12-10 | -5 | 12 | 25
509490 | ADI UPW | Oakville | Pumps - Centrifugal | FLOWSERVE INC. | 4503849295 | Rotating Equipment | Centrifugal Pumps | USD | 377064 | USD | 464707 | -87643 | Market Impact | 2022-06-28 | 2022-06-28 | 2022-07-21 | 2022-07-26 | 2022-08-19 | 2022-12-16 | 2022-08-09 | 2022-08-25 | 2023-06-06 | 2023-04-06 | 2023-05-06 | -30 | 30 | 58
509490 | ADI UPW | Oakville | Heat exchanger | ALFA LAVAL | 4503838101 | Rotating Equipment | Heat Exchangers | USD | 309143 | USD | 179971 | 129172 | Supplier Competitions / Negotiation | 2022-06-28 | 2022-06-28 | 2022-07-05 | 2022-07-19 | 2022-08-03 | 2023-01-11 | 2022-07-26 | 2022-08-04 | 2023-07-11 | 2023-07-27 | 2023-07-19 | 8 | 30 | 37
509490 | ADI UPW | Oakville | UV | Trojan Technologies INC. | 453853971 | Rotating Equipment | Others | USD | 472552 | USD | 375942 | 96610 | Design Optimizations | 2022-07-15 | 2022-07-14 | 2022-07-14 | 2022-08-05 | 2022-08-26 | 2022-12-19 | 2022-08-12 | 2022-09-03 | 2023-02-10 | 2023-05-26 | 2023-04-03 | 53 | 30 | 51
509525 | Alpha Wastewater Reuse | Oakville | Evaporator - Harris | HARRIS THERMAL TRANSFER | 4503792091 | Fabrication | Process Equipment | USD | 1378000 | USD | 1541500 | -163500 | Size/ Weight/ Quantity Underestimated | 2022-12-23 | 2022-04-08 | 2022-05-12 | 2023-01-20 | 2022-05-11 | 2022-10-17 | 2023-02-03 | 2022-05-16 | 2023-04-28 | 2023-04-24 | 2023-04-26 | -2 | 12 | 38
509525 | Alpha Wastewater Reuse | Oakville | Fabrication - Ti Tubes | NEOTISS, INC. | 4503797521 | Fabrication | Alloy Steel | USD | 467525 | USD | 414912 | 52613 | Supplier Competitions / Negotiation | 2022-01-27 | 2022-03-11 | 2022-04-12 | 2022-02-24 | 2022-05-26 | 2022-06-06 | 2022-03-10 | 2022-05-02 | 2022-10-14 | 2022-10-13 | 2022-10-13 | 0 | 12 | 52
509525 | Alpha Wastewater Reuse | Oakville | Blowers - Turbo / Process | SULZER PUMPS (CANADA) IN | 4503800767 | Rotating Equipment | Blowers & Fans | USD | 514150 | USD | 520000 | -5850 | Size/ Weight/ Quantity Underestimated | 2022-10-28 | 2022-04-22 | 2022-05-26 | 2022-11-25 | 2022-06-01 | 2022-08-15 | 2022-12-09 | 2022-06-01 | 2022-11-18 | 2022-12-08 | 2022-11-28 | 10 | 30 | 40
509525 | Alpha Wastewater Reuse | Oakville | Blowers - Membrane | AERZEN CANADA INC | 4503807374 | Rotating Equipment | Blowers & Fans | USD | 54399 | CAD | 54496 | -97 | Single Sourced | 2022-06-02 | 2022-04-26 | 2022-05-26 | 2022-06-30 | 2022-06-13 | 2022-08-07 | 2022-07-14 | 2022-06-13 | 2022-11-18 | 2022-11-14 | 2022-11-16 | -2 | 30 | 48
509525 | Alpha Wastewater Reuse | Oakville | Flow - Diffuser | Aquarius Technologies | 4503817120 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 425000 | USD | 464800 | -39800 | Size/ Weight/ Quantity Underestimated | 2022-08-05 | 2022-04-13 | 2022-04-28 | 2022-09-02 | 2022-06-08 | 2022-07-31 | 2022-09-16 | 2022-06-29 | 2022-11-18 | 2022-11-18 | 2022-11-18 | 0 | 12 | 77
509525 | Alpha Wastewater Reuse | Oakville | Tanks - Membrane (incl Hanger Arms) | POSEIDON, INC | 4503803354 | Fabrication | Stainless Steel | USD | 471965 | CAD | 454566 | 17399 | Size/ Weight/ Quantity Underestimated | 2022-03-11 | 2022-04-28 | 2022-05-19 | 2022-04-08 | 2022-06-06 | 2022-07-16 | 2022-04-22 | 2022-06-06 | 2022-11-18 | 2022-11-21 | 2022-11-19 | 2 | 12 | 39
509525 | Alpha Wastewater Reuse | Oakville | Vap Compressor (packing, install, acoustic etc.) | Piller Blowers & Compressors GMBH | 4503838727 | Rotating Equipment | Others | USD | 976986 | USD | 999660 | -22674 | Specs / Requirements Misinterpreted in Proposal | 2022-06-10 | 2022-04-14 | 2022-06-24 | 2022-07-08 | 2022-08-10 | 2022-10-24 | 2022-07-22 | 2022-08-10 | 2023-04-28 | 2023-05-05 | 2023-05-01 | 4 | 30 | 118
509525 | Alpha Wastewater Reuse | Oakville | Crystallizer Vapor Body | HARRIS THERMAL TRANSFER | 4503815624 | Fabrication | Process Equipment | USD | 240000 | USD | 275700 | -35700 | Size/ Weight/ Quantity Underestimated | 2022-05-19 | 2022-05-25 | 2022-06-03 | 2022-06-16 | 2022-06-07 | 2022-11-07 | 2022-06-30 | 2022-06-27 | 2023-04-28 | 2023-04-17 | 2023-04-22 | -5 | 12 | 33
509525 | Alpha Wastewater Reuse | Oakville | Evaporator HX | ALFA LAVAL | 4503809927 | Fabrication | Process Equipment | USD | 82500 | CAD | 82160 | 340 | Supplier Competitions / Negotiation | 2022-09-02 | 2022-05-03 | 2022-05-16 | 2022-09-30 | 2022-06-15 | 2022-10-30 | 2022-10-14 | 2022-06-16 | 2023-04-28 | 2022-10-06 | 2023-01-16 | -102 | 12 | 44
509525 | Alpha Wastewater Reuse | Oakville | Heater - CIP | Chromalox Inc. | 4503814629 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | USD | 8622 | USD | 15304 | -6682 | Market Impact | 2022-07-22 | 2022-06-15 | 2022-06-15 | 2022-08-19 | 2022-06-22 | 2022-08-10 | 2022-09-02 | 2022-06-23 | 2022-10-05 | 2022-09-20 | 2022-09-27 | -7 | 18 | 8
509525 | Alpha Wastewater Reuse | Oakville | Hydrocyclone | FLSmidth Krebs | 4503845251 | Fabrication | Process Equipment | USD | 105300 | USD | 129700 | -24400 | Specs / Requirements Misinterpreted in Proposal | 2022-04-01 | 2022-06-23 | 2022-06-30 | 2022-04-29 | 2022-08-22 | 2022-10-14 | 2022-05-13 | 2022-08-23 | 2023-04-28 | 2023-03-24 | 2023-04-10 | -17 | 12 | 61
509525 | Alpha Wastewater Reuse | Oakville | Electrical - Disconnects - FRP | VAN METER | 4503842108 | Electrical & Instrumentation | Ele-Electrical Others | USD | 12820 | USD | 17068 | -4248 | Size/ Weight/ Quantity Underestimated | 2022-09-16 | 2022-10-25 | 2022-08-09 | 2022-10-14 | 2022-08-10 | 2022-10-25 | 2022-10-28 | 2022-08-11 | 2023-01-10 | 2022-08-22 | 2022-10-31 | -70 | 18 | -75
509525 | Alpha Wastewater Reuse | Oakville | Electrical - RIO Panel | PTS Products | 4503845483 | Electrical & Instrumentation | Ele-Control Panels | USD | 29571 | USD | 76866 | -47295 | Proposed Supplier Incapable Of Executing | 2022-07-22 | 2022-06-29 | 2022-08-02 | 2022-08-19 | 2022-08-15 | 2022-09-18 | 2022-09-02 | 2022-08-18 | 2022-12-09 | 2022-11-10 | 2022-11-24 | -14 | 18 | 50
509525 | Alpha Wastewater Reuse | Oakville | Electrical - Long Lead AB Components | VAN METER | 4503813811 | Electrical & Instrumentation | Ele-Electrical Others | USD | 25000 | USD | 23254 | 1746 | Design Optimizations | 2022-06-16 | 2022-05-16 | 2022-06-14 | 2022-07-14 | 2022-06-23 | 2022-09-24 | 2022-07-28 | 2022-06-24 | 2022-11-04 | 2023-02-03 | 2022-12-19 | 46 | 18 | 39
509525 | Alpha Wastewater Reuse | Oakville | RO Housings - Protec | PROTEC ARISAWA AMERICA INC | 4503801196 | Fabrication | Skid Assembly Outsourced | USD | 100000 | USD | 99682 | 318 | Supplier Competitions / Negotiation | 2022-06-10 | 2022-05-18 | 2022-06-16 | 2022-07-08 | 2022-06-16 | 2022-08-10 | 2022-07-22 | 2022-06-17 | 2022-11-03 | 2022-10-21 | 2022-10-27 | -6 | 12 | 30
509525 | Alpha Wastewater Reuse | Oakville | Air Compressor | ATLAS COPCO COMPRESSORS | 4503849283 | Rotating Equipment | Compressors | USD | 25000 | CAD | 23783 | 1217 | Frame Agreements | 2022-08-05 | 2022-07-14 | 2022-08-19 | 2022-09-02 | 2022-08-21 | 2022-10-17 | 2022-09-16 | 2022-08-25 | 2023-01-20 | 2023-01-12 | 2023-01-16 | -4 | 30 | 42
509525 | Alpha Wastewater Reuse | Oakville | Pumps - Boerger | BOERGER LLC | 4503814786 | Rotating Equipment | PD Pumps | USD | 70661 | USD | 82415 | -11754 | Not included in Proposal / RFQ | 2022-06-03 | 2022-05-20 | 2022-06-16 | 2022-07-01 | 2022-06-23 | 2022-08-01 | 2022-07-15 | 2022-06-24 | 2022-10-05 | 2022-10-14 | 2022-10-09 | 5 | 30 | 35
509525 | Alpha Wastewater Reuse | Oakville | Pumps - RAS (Flowserve) | FLOWSERVE INC. | 4503823865 | Rotating Equipment | Centrifugal Pumps | USD | 76167 | USD | 100000 | -23833 | Supplier Competitions / Negotiation | 2022-05-05 | 2022-05-13 | 2022-05-15 | 2022-06-02 | 2022-07-08 | 2022-08-30 | 2022-06-16 | 2022-07-11 | 2022-10-05 | 2022-12-26 | 2022-11-15 | 41 | 30 | 59
509525 | Alpha Wastewater Reuse | Oakville | Pumps - RO CIP (Xylem) | XYLEM CANADA COMPANY | 4503826917 | Rotating Equipment | Centrifugal Pumps | USD | 14033 | CAD | 6168 | 7865 | Frame Agreements | 2022-05-05 | 2022-05-13 | 2022-07-14 | 2022-06-02 | 2022-07-15 | 2022-08-08 | 2022-08-08 | 2022-07-15 | 2022-08-08 | 2022-11-11 | 2022-09-24 | 48 | 30 | 63
509525 | Alpha Wastewater Reuse | Oakville | Pumps - IR RO FDD E+C R (Sulzer) | SULZER PUMPS (CANADA) IN | 4503836274 | Rotating Equipment | Centrifugal Pumps | USD | 242399 | USD | 325053 | -82654 | Single Sourced | 2022-05-05 | 2022-05-18 | 2022-06-21 | 2022-06-02 | 2022-07-28 | 2022-09-24 | 2022-06-16 | 2022-08-01 | 2022-10-05 | 2023-02-14 | 2022-12-10 | 66 | 30 | 75
509525 | Alpha Wastewater Reuse | Oakville | Piping - SS (MBR Header DS) | PANDA PIPING LTD | 4503838843 | Fabrication | Stainless Steel | USD | 54575 | CAD | 51756 | 2819 | Frame Agreements | 2022-07-08 | 2022-06-20 | 2022-07-04 | 2022-08-05 | 2022-07-29 | 2022-09-03 | 2022-08-19 | 2022-08-05 | 2022-11-18 | 2022-10-31 | 2022-11-09 | -9 | 12 | 46
509525 | Alpha Wastewater Reuse | Oakville | ZLD Pressure Vessels | PAGET EQUIPMENT CO | 4503838968 | Fabrication | Carbon Steel | USD | 332852 | USD | 280000 | 52852 | Supplier Competitions / Negotiation | 2022-06-16 | 2022-05-30 | 2022-07-22 | 2022-07-14 | 2022-08-03 | 2022-11-04 | 2022-07-28 | 2022-08-05 | 2023-01-20 | 2023-04-12 | 2023-03-02 | 41 | 12 | 67
509525 | Alpha Wastewater Reuse | Oakville | Tanks - Chlorine Contact | HIGHLAND TANK | 4503849066 | Fabrication | Non-Metal Equipment | USD | 135504 | USD | 135000 | 504 | Supplier Competitions / Negotiation | 2022-07-22 | 2022-06-20 | 2022-08-03 | 2022-08-19 | 2022-08-24 | 2022-10-05 | 2022-09-02 | 2022-08-25 | 2023-01-20 | 2023-01-20 | 2023-01-20 | 0 | 12 | 66
509525 | Alpha Wastewater Reuse | Oakville | FRP Tank Covers | PRECISIONEERING | 4503832255 | Fabrication | Non-Metal Equipment | USD | 64800 | CAD | 60040 | 4760 | Design Optimizations | 2022-06-14 | 2022-06-14 | 2022-07-04 | 2022-10-02 | 2022-07-25 | 2022-10-02 | 2022-07-22 | 2022-07-26 | 2023-01-20 | 2022-10-21 | 2022-12-05 | -45 | 12 | 42
509528 | Wellington UV | Leonia | Paulette: Wireway/Power cable/Data cable/ PDDC/ Blower starter panel | Paulette Fabricators INC | 4503833329 | Electrical & Instrumentation | Ele-Control Panels | USD | 34620 | USD | 33146 | 1474 | Frame Agreements | 2022-07-18 | 2022-08-17 | 2022-07-07 | 2022-07-25 | 2022-07-20 | 2022-08-17 | 2022-08-01 | 2022-07-27 | 2022-09-26 | 2022-09-27 | 2022-09-26 | 1 | 18 | -21
509528 | Wellington UV | Leonia | Jobshop Weirs/ Eyeshields/Lifting Bar/Bracket/cleaning Tank/ Air hose | JOB SHOP FABRICATORS | 4503833310 | Fabrication | Stainless Steel | USD | 13772 | USD | 13772 | 0 | Not included in Proposal / RFQ | 2022-08-12 | 2022-08-14 | 2022-07-13 | 2022-08-26 | 2022-07-20 | 2022-08-14 | 2022-09-02 | 2022-07-26 | 2022-09-16 | 2022-09-15 | 2022-09-15 | 0 | 12 | -19
509672 | Niagara Baltimore | Minnetonka | ASSY_OS AC TOWER 108X168 MATERIAL | TRIVACO DND | 4503827039 | Fabrication | Skid Assembly Outsourced | USD | 77000 | USD | 74266 | 2734 | Frame Agreements | 2022-06-15 | 2022-09-09 | 2022-07-05 | 2022-06-15 | 2022-07-15 | 2022-09-09 | 2022-06-20 | 2022-07-15 | 2022-09-20 | 2022-12-05 | 2022-10-28 | 38 | 12 | -56
509672 | Niagara Baltimore | Minnetonka | ASSY_OS AC TOWER 108X168 VESSELS | Arrow Tanks | 4503789647 | Fabrication | Stainless Steel | USD | 403455 | USD | 403455 | 0 | Proposed Supplier Incapable Of Executing | 2022-05-11 | 2022-07-16 | 2022-05-11 | 2022-05-11 | 2022-05-11 | 2022-07-16 | 2022-05-11 | 2022-05-11 | 2022-09-20 | 2022-09-20 | 2022-09-20 | 0 | 12 | -66
509672 | Niagara Baltimore | Minnetonka | ASSY_OS AC TOWER 108X168 LABOR | TRIVACO DND | 4513827039 | Fabrication | Skid Assembly Outsourced | USD | 45288 | USD | 76600 | -31312 | Proposed Supplier Incapable Of Executing | 2022-06-06 | 2022-09-08 | 2022-07-05 | 2022-06-20 | 2022-07-15 | 2022-09-08 | 2022-06-22 | 2022-07-15 | 2022-12-12 | 2022-12-05 | 2022-12-08 | -3 | 12 | -55
509672 | Niagara Baltimore | Minnetonka | ASSY_OS_NIAGARA RO 400DP_MATERIALS | TRIVACO DND | 4523827039 | Fabrication | Skid Assembly Outsourced | USD | 194594 | USD | 194594 | 0 | Supplier Competitions / Negotiation | 2022-06-15 | 2022-09-13 | 2022-07-05 | 2022-06-15 | 2022-07-15 | 2022-09-13 | 2022-06-20 | 2022-07-15 | 2022-12-12 | 2022-12-05 | 2022-12-08 | -3 | 12 | -60
509672 | Niagara Baltimore | Minnetonka | ASSY_OS_NIAGARA RO 400DP, PROTEC HOUSINGS | PROTEC ARISAWA AMERICA INC | 4503790270 | Flow Control | Filters And Strainers (Incl Housings) | USD | 51832 | USD | 52560 | -728 | Specs / Requirements Misinterpreted in Proposal | 2022-05-12 | 2022-01-20 | 2022-01-20 | 2022-05-12 | 2022-05-12 | 2022-05-27 | 2022-05-12 | 2022-05-12 | 2022-10-01 | 2022-10-01 | 2022-10-01 | 0 | 12 | 112
509672 | Niagara Baltimore | Minnetonka | ASSY_OS_NIAGARA RO 400DP, MCE VFDS | WERNER ELECTRIC | 4503790494 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 52151 | USD | 51440 | 711 | Frame Agreements | 2022-05-12 | 2022-07-26 | 2022-05-12 | 2022-05-12 | 2022-05-12 | 2022-07-26 | 2022-05-12 | 2022-05-12 | 2022-10-10 | 2022-10-10 | 2022-10-10 | 0 | 18 | -75
509672 | Niagara Baltimore | Minnetonka | ASSY_OS_NIAGARA RO 400DP, LABOR | TRIVACO DND | 4533827039 | Fabrication | Skid Assembly Outsourced | USD | 148158 | USD | 242932 | -94774 | Proposed Supplier Incapable Of Executing | 2022-06-06 | 2022-09-08 | 2022-07-05 | 2022-06-20 | 2022-07-15 | 2022-09-08 | 2022-06-22 | 2022-07-15 | 2022-12-12 | 2022-12-05 | 2022-12-08 | -3 | 12 | -55
509672 | Niagara Baltimore | Minnetonka | ASSY_OS_CIP_MATERIAL | TRIVACO DND | 4543827039 | Fabrication | Skid Assembly Outsourced | USD | 15144 | USD | 15144 | 0 | Design Optimizations | 2022-06-15 | 2022-09-13 | 2022-07-05 | 2022-06-15 | 2022-07-15 | 2022-09-13 | 2022-06-20 | 2022-07-15 | 2022-12-12 | 2022-12-05 | 2022-12-08 | -3 | 12 | -60
509672 | Niagara Baltimore | Minnetonka | ASSY_OS_CIP, MCE VFD | BW Systems | 4503816768 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 70402 | USD | 73750 | -3348 | Market Impact | 2022-05-12 | 2022-08-08 | 2022-06-22 | 2022-05-12 | 2022-06-28 | 2022-08-08 | 2022-05-12 | 2022-06-28 | 2022-10-10 | 2022-11-05 | 2022-10-23 | 13 | 18 | -41
509672 | Niagara Baltimore | Minnetonka | ASSY_OS_CIP TANK | Preferred Stainless Holdings | 4503809203 | Fabrication | Stainless Steel | USD | 37766 | USD | 38194 | -428 | Proposed Supplier Incapable Of Executing | 2022-05-16 | 2022-05-16 | 2022-05-19 | 2022-06-02 | 2022-06-15 | 2022-08-14 | 2022-06-02 | 2022-06-15 | 2022-11-12 | 2022-11-10 | 2022-11-11 | -1 | 12 | 30
509672 | Niagara Baltimore | Minnetonka | ASSY_OS_CIP, LABOR | TRIVACO DND | 4553827039 | Fabrication | Skid Assembly Outsourced | USD | 11600 | USD | 16713 | -5113 | Proposed Supplier Incapable Of Executing | 2022-09-19 | 2022-09-19 | 2022-07-05 | 2022-09-19 | 2022-07-15 | 2022-09-19 | 2022-09-19 | 2022-07-15 | 2022-09-19 | 2022-12-05 | 2022-10-27 | 39 | 12 | -66
509672 | Niagara Baltimore | Minnetonka | ASSY_OS_CIP,PUMP | ALFA LAVAL | 4503804321 | Rotating Equipment | Centrifugal Pumps | USD | 7600 | USD | 7593 | 7 | Supplier Competitions / Negotiation | 2022-06-06 | 2022-08-31 | 2022-05-20 | 2022-06-20 | 2022-06-07 | 2022-08-31 | 2022-06-22 | 2022-06-07 | 2022-12-12 | 2022-10-05 | 2022-11-08 | -34 | 30 | -85
509694 | Willamette Water Supply Program WTP-OZ | Leonia | OG vessels CFV-15 (3) | Jiangnan Boilers & Pressure Vessels | 4503849612 | Fabrication | Stainless Steel | USD | 78336 | USD | 70300 | 8036 | Design Optimizations | 2022-08-19 | 2022-10-13 | 2022-07-21 | 2022-09-02 | 2022-08-25 | 2022-10-13 | 2022-09-16 | 2022-08-29 | 2023-01-06 | 2022-12-19 | 2022-12-28 | -9 | 12 | -45
509694 | Willamette Water Supply Program WTP-OZ | Leonia | Injection System - DS(Injector) | MAZZEI INJECTOR CORPORATION | 4503848157 | Fabrication | Stainless Steel | USD | 24957 | USD | 41584 | -16627 | Estimate Without Market Reference(No Quote) | 2022-05-13 | 2022-09-09 | 2022-07-27 | 2022-05-27 | 2022-07-27 | 2022-09-09 | 2022-06-10 | 2022-08-26 | 2023-01-06 | 2023-01-04 | 2023-01-05 | -1 | 12 | -14
509694 | Willamette Water Supply Program WTP-OZ | Leonia | Injection System - DS(Manifod) | MAZZEI INJECTOR CORPORATION | 4503849292 | Fabrication | Stainless Steel | USD | 125182 | USD | 125182 | 0 | Estimate Without Market Reference(No Quote) | 2022-08-01 | 2022-12-12 | 2022-07-27 | 2022-08-15 | 2022-07-26 | 2022-12-12 | 2022-08-29 | 2022-08-25 | 2023-05-01 | 2023-04-25 | 2023-04-28 | -3 | 12 | -109
509694 | Willamette Water Supply Program WTP-OZ | Leonia | Injection System - DS(Spare) | MAZZEI INJECTOR CORPORATION | 4503849829 | Fabrication | Stainless Steel | USD | 13861 | USD | 13861 | 0 | Market Impact | 2022-09-05 | 2022-12-13 | 2022-07-27 | 2022-09-19 | 2022-07-27 | 2022-12-13 | 2022-10-03 | 2022-08-26 | 2023-05-01 | 2023-04-25 | 2023-04-28 | -3 | 12 | -109
509694 | Willamette Water Supply Program WTP-OZ | Leonia | Teledyne monitor | Teledyne API | 4503816291 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 85440 | USD | 88000 | -2560 | Estimate Without Market Reference(No Quote) | 2022-05-13 | 2022-09-18 | 2022-06-28 | 2022-05-27 | 2022-09-18 | 2022-09-18 | 2022-06-10 | 2022-06-28 | 2023-01-06 | 2023-01-24 | 2023-01-15 | 9 | 18 | -82
509805 | Osawatomie-UV | Leonia | Paulette-Wireway&UMCP&PSU | Paulette Fabricators INC | 4503843353 | Electrical & Instrumentation | Ele-Control Panels | USD | 56966 | USD | 32872 | 24094 | Supplier Competitions / Negotiation | 2022-07-18 | 2022-09-12 | 2022-08-05 | 2022-07-21 | 2022-08-15 | 2022-09-12 | 2022-07-28 | 2022-08-15 | 2022-10-20 | 2022-11-07 | 2022-10-29 | 9 | 18 | -28
509818 | Angels Fire-UV | Leonia | Paulette-Wireway,Power&Data cable, PDDC | Paulette Fabricators INC | 4503847278 | Electrical & Instrumentation | Ele-Control Panels | USD | 31112 | USD | 25156 | 5956 | Frame Agreements | 2022-08-22 | 2022-09-24 | 2022-08-19 | 2022-08-29 | 2022-08-21 | 2022-09-24 | 2022-09-05 | 2022-08-22 | 2022-10-31 | 2022-10-23 | 2022-10-27 | -4 | 18 | -33
510080 | NIAGARA MEXICO EXPANSION | Minnetonka | RO FRP HOUSINGS | PROTEC ARISAWA AMERICA INC | 4503852395 | Flow Control | Filters And Strainers (Incl Housings) | USD | 13374 | USD | 13374 | 0 | Not included in Proposal / RFQ | 2022-08-12 | 2022-08-11 | 2022-08-11 | 2022-08-12 | 2022-08-31 | 2022-10-20 | 2022-08-12 | 2022-08-31 | 2022-12-29 | 2022-12-29 | 2022-12-29 | 0 | 12 | 20
510080 | NIAGARA MEXICO EXPANSION | Minnetonka | AC 84"X144" | Arrow Tanks | 4503852881 | Fabrication | Stainless Steel | USD | 217450 | USD | 217450 | 0 | Size/ Weight/ Quantity Underestimated | 2022-08-12 | 2022-07-22 | 2022-07-22 | 2022-08-12 | 2022-09-01 | 2022-09-25 | 2022-08-12 | 2022-09-01 | 2022-11-30 | 2022-11-30 | 2022-11-30 | 0 | 12 | 41
| 001765 -EUROFARMA | Cotia | DECANTER CENTRIFUGUE | ALFA LAVAL | 4500419747 | Rotating Equipment | Centrifuge | BRL | 195891 | BRL | 147044 | 48847 | Design Optimizations | 2021-02-10 | 2021-04-28 | 2021-03-30 | 2021-07-03 | 2021-03-28 | 2021-04-28 | 2021-03-30 | 2021-03-19 | 2021-07-14 | 2021-03-19 | 2021-05-16 | -58 | 30 | -40
| 001765 -EUROFARMA | Cotia | Submersible Pumps | KSB Pumps Inc. | 4500420309 | Rotating Equipment | PD Pumps | BRL | 79612 | BRL | 35994 | 43618 | Frame Agreements | 2021-02-18 | 2021-05-04 | 2021-07-01 | 2021-07-01 | 2021-07-01 | 2021-05-04 | 2021-03-29 | 2021-03-29 | 2021-07-18 | 2021-03-29 | 2021-05-23 | -55 | 30 | -36
| 001765 -EUROFARMA | Cotia | Centrifugal Pumps | KSB Pumps Inc. | 4500422345 | Rotating Equipment | Centrifugal Pumps | BRL | 305686 | BRL | 139456 | 166230 | Design Optimizations | 2021-02-11 | 2021-05-02 | 2021-07-11 | 2021-07-11 | 2021-07-11 | 2021-05-02 | 2021-06-29 | 2021-07-15 | 2021-07-21 | 2021-07-15 | 2021-07-18 | -3 | 30 | 74
| 001765 -EUROFARMA | Cotia | DAF | KWI | 450042275 | Fabrication | Process Equipment | BRL | 318972 | BRL | 296651 | 22321 | Design Optimizations | 2021-02-23 | 2021-05-02 | 2021-04-15 | 2021-04-15 | 2021-04-15 | 2021-05-02 | 2021-04-30 | 2021-04-30 | 2021-07-10 | 2021-07-10 | 2021-07-10 | 0 | 12 | -2
| 001765 -EUROFARMA | Cotia | Oil | WTS'E | 450042275 | Rotating Equipment | Others | BRL | 124261 | BRL | 126400 | -2139 | Proposed Supplier Incapable Of Executing | 2021-02-11 | 2021-05-09 | 2021-02-21 | 2021-07-01 | 2021-02-21 | 2021-05-09 | 2021-07-10 | 2021-07-15 | 2021-08-04 | 2021-08-04 | 2021-08-04 | 0 | 30 | 67
| 001765 -EUROFARMA | Cotia | Blower | GARDNER DENVER ENGINEERED PRODUCTS | 4500422100 | Rotating Equipment | Blowers & Fans | BRL | 428949 | BRL | 367627 | 61322 | Design Optimizations | 2021-02-11 | 2021-04-23 | 2021-06-01 | 2021-06-01 | 2021-06-01 | 2021-04-23 | 2021-04-08 | 2021-04-08 | 2021-07-03 | 2021-04-08 | 2021-05-21 | -43 | 30 | -15
| 001765 -EUROFARMA | Cotia | Progressive Cavity Pumps | NETZSCH CANADA INC. | 4500420292 | Rotating Equipment | PD Pumps | BRL | 44905 | BRL | 59949 | -15044 | Market Impact | 2021-02-21 | 2021-05-10 | 2021-02-21 | 2021-06-18 | 2021-06-18 | 2021-05-10 | 2021-04-09 | 2021-04-09 | 2021-07-28 | 2021-04-09 | 2021-06-03 | -55 | 30 | -31
| 001765 -EUROFARMA | Cotia | CCM | INSETT | 4500424206 | Electrical & Instrumentation | Ele-Control Panels | BRL | 289150 | BRL | 377333 | -88183 | Specs / Requirements Misinterpreted in Proposal | 2021-02-10 | 2021-05-05 | 2021-02-21 | 2021-05-10 | 2021-05-10 | 2021-05-05 | 2021-05-20 | 2021-05-20 | 2021-07-28 | 2021-07-28 | 2021-07-28 | 0 | 18 | 15
| 001765 -EUROFARMA | Cotia | PLC | INSETT | 4500424200 | Electrical & Instrumentation | Ele-PLCs, HMIs | BRL | 190667 | BRL | 154612 | 36055 | Design Optimizations | 2021-02-10 | 2021-05-05 | 2021-02-10 | 2021-05-10 | 2021-05-10 | 2021-05-05 | 2021-05-20 | 2021-05-20 | 2021-07-28 | 2021-05-20 | 2021-06-23 | -34 | 18 | 15
| 001765 -EUROFARMA | Cotia | Self-cleaning filter | PURIFILL | 4500428920 | Rotating Equipment | Filter Press | BRL | 41462 | BRL | 69738 | -28276 | Market Impact | 2021-02-11 | 2021-05-09 | 2021-02-11 | 2021-05-30 | 2021-05-30 | 2021-05-09 | 2021-06-20 | 2021-06-20 | 2021-08-04 | 2021-08-04 | 2021-08-04 | 0 | 30 | 42
| 001765 -EUROFARMA | Cotia | backpulse tank | EQSAN | 4500423194 | Fabrication | Non-Metal Equipment | BRL | 18533 | BRL | 20844 | -2311 | Proposed Supplier Incapable Of Executing | 2021-05-10 | 2021-05-12 | 2021-02-22 | 2021-06-10 | 2021-06-10 | 2021-05-12 | 2021-07-21 | 2021-07-21 | 2021-07-30 | 2021-07-30 | 2021-07-30 | 0 | 12 | 70
| 001765 -EUROFARMA | Cotia | Dosing tank- | EQSAN | 4500424302 | Fabrication | Stainless Steel | BRL | 91753 | BRL | 14345 | 77408 | Frame Agreements | 2021-05-10 | 2021-06-19 | 2021-05-10 | 2021-06-10 | 2021-06-10 | 2021-06-19 | 2021-07-21 | 2021-07-21 | 2021-07-30 | 2021-07-21 | 2021-07-25 | -4 | 12 | 32
| 001765 -EUROFARMA | Cotia | Chem Feed Skids | PROMINENT FLUID CONTROLS LTD. | 4500422127 | Rotating Equipment | Chem. Feed Skids (Turnkey) | BRL | 385948 | BRL | 297215 | 88733 | Supplier Competitions / Negotiation | 2021-02-11 | 2021-04-24 | 2021-02-11 | 2021-06-15 | 2021-06-15 | 2021-04-24 | 2021-04-09 | 2021-04-09 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 0 | 30 | -15
| 001765 -EUROFARMA | Cotia | Polymer preparation system pumps ( | PROMINENT FLUID CONTROLS LTD. | 4500421623 | Rotating Equipment | Chem. Feed Skids (Turnkey) | BRL | 79275 | BRL | 75126 | 4149 | Frame Agreements | 2021-02-11 | 2021-04-24 | 2021-02-11 | 2021-06-15 | 2021-06-15 | 2021-04-24 | 2021-04-09 | 2021-04-06 | 2021-07-06 | 2021-07-06 | 2021-07-06 | 0 | 30 | -18
| 001765 -EUROFARMA | Cotia | Instrumentation | ENDRESS & HAUSER | 4500429924 | Electrical & Instrumentation | Inst-Instrumentation Others | BRL | 164891 | BRL | 180327 | -15436 | Size/ Weight/ Quantity Underestimated | 2021-05-10 | 2021-06-30 | 2021-05-10 | 2021-06-15 | 2021-06-15 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 2021-08-20 | 2021-08-20 | 2021-08-20 | 0 | 18 | 0
| 001765 -EUROFARMA | Cotia | Valve | Bray Controls Canada Ltd. | 4500427922 | Rotating Equipment | Others | BRL | 105000 | BRL | 66051 | 38949 | Frame Agreements | 2021-04-20 | 2021-05-25 | 2021-04-20 | 2021-05-30 | 2021-05-30 | 2021-05-25 | 2021-06-20 | 2021-06-20 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 0 | 30 | 26
| 001765 -EUROFARMA | Cotia | Pressure Gauges | NAKA | 4500428372 | Electrical & Instrumentation | Inst-Gauges | BRL | 5566 | BRL | 9953 | -4387 | Not included in Proposal / RFQ | 2021-05-10 | 2021-06-04 | 2021-05-10 | 2021-06-15 | 2021-06-15 | 2021-06-04 | 2021-06-20 | 2021-06-23 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 0 | 18 | 19
| 001765 -EUROFARMA | Cotia | Pressure Switch | WILLY | 4500428366 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | BRL | 966000 | BRL | 7544 | 958456 | Frame Agreements | 2021-05-10 | 2021-06-12 | 2021-05-10 | 2021-06-15 | 2021-06-15 | 2021-06-12 | 2021-06-30 | 2021-06-30 | 2021-07-15 | 2021-07-15 | 2021-07-15 | 0 | 18 | 18
| 001765 -EUROFARMA | Cotia | Valve | INTERATIVA | 4500427179 | Rotating Equipment | Others | BRL | 60000 | BRL | 58931 | 1069 | Frame Agreements | 2021-05-10 | 2021-05-30 | 2021-05-10 | 2021-06-15 | 2021-06-15 | 2021-05-30 | 2021-04-30 | 2021-05-21 | 2021-06-21 | 2021-06-30 | 2021-06-25 | 5 | 30 | -9
| 001765 -EUROFARMA | Cotia | Difuser | BF DIAS | 4500422094 | Flow Control | Injection Quills, Ejectors, Diffusers | BRL | 50654 | BRL | 44629 | 6025 | Frame Agreements | 2021-06-01 | 2021-05-20 | 2021-06-01 | 2021-07-01 | 2021-07-01 | 2021-05-20 | 2021-06-08 | 2021-04-08 | 2021-06-24 | 2021-06-24 | 2021-06-24 | 0 | 12 | -42
| 001765 -EUROFARMA | Cotia | Mixers | SIGMA-ALDRICH, INC | 4500420338 | Rotating Equipment | Mixers | BRL | 13650 | BRL | 12165 | 1485 | Frame Agreements | 2021-05-10 | 2021-05-11 | 2021-05-10 | 2021-02-01 | 2021-06-01 | 2021-05-11 | 2021-03-30 | 2021-03-30 | 2021-08-18 | 2021-08-18 | 2021-08-18 | 0 | 30 | -42
| 001765 -EUROFARMA | Cotia | Flow Swich | CONTECH | 4500430105 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | BRL | 12600 | BRL | 5499 | 7101 | Supplier Competitions / Negotiation | 2021-05-10 | 2021-06-04 | 2021-05-10 | 2021-06-15 | 2021-06-15 | 2021-06-04 | 2021-06-23 | 2021-06-23 | 2021-06-30 | 2021-06-30 | 2021-06-30 | 0 | 18 | 19
| B001712-Bacalhau FPSO | Cotia | Pumps | Sulzer Brazil | 4500398255 | Rotating Equipment | Centrifugal Pumps | USD | 3895000 | USD | 3982039 | -87039 | Proposed Supplier Incapable Of Executing | 2020-09-15 | 2021-04-15 | 2020-10-20 | 2020-10-13 | 2020-10-30 | 2021-04-15 | 2020-10-27 | 2020-11-20 | 2021-11-13 | 2021-10-26 | 2021-11-04 | -9 | 30 | -146
| B001712-Bacalhau FPSO | Cotia | PLC | ROCKWELL AUTOMATION LLC | 4500411393 | Electrical & Instrumentation | Centrifugal Pumps | USD | 464330 | USD | 684490 | -220160 | Estimate Without Market Reference(No Quote) | 2020-10-06 | 2021-03-19 | 2020-10-22 | 2020-12-09 | 2020-10-15 | 2021-03-19 | 2020-12-22 | 2020-12-02 | 2021-08-30 | 2021-07-09 | 2021-08-04 | -26 | 18 | -107
| B001712-Bacalhau FPSO | Cotia | VFD | WEG | 4500406529 | Electrical & Instrumentation | Metal Isolation Valves | USD | 309991 | USD | 389223 | -79232 | Specs / Requirements Misinterpreted in Proposal | 2020-11-06 | 2021-03-19 | 2020-12-16 | 2020-11-10 | 2020-12-09 | 2021-03-19 | 2020-11-23 | 2020-12-22 | 2021-07-31 | 2021-06-28 | 2021-07-14 | -16 | 18 | -87
| B001712-Bacalhau FPSO | Cotia | Dosing Pumps | LEWA | 4500410506 | Rotating Equipment | Dosing Pump | USD | 521690 | USD | 576832 | -55142 | Size/ Weight/ Quantity Underestimated | 2020-11-17 | 2021-04-19 | 2021-01-26 | 2020-12-22 | 2020-12-09 | 2021-04-19 | 2021-01-04 | 2021-01-21 | 2021-09-20 | 2021-08-09 | 2021-08-30 | -21 | 30 | -88
| B001712-Bacalhau FPSO | Cotia | Dosing Pumps - PSV Valves | LESER LLC | 4500409679 | Rotating Equipment | Dosing Pump | USD | 9918 | USD | 45973 | -36055 | Single Sourced | 2020-11-17 | 2021-06-04 | 2021-12-21 | 2020-12-22 | 2021-01-07 | 2021-06-04 | 2021-01-04 | 2021-01-18 | 2021-09-20 | 2021-03-29 | 2021-06-24 | -87 | 30 | -137
| B001712-Bacalhau FPSO | Cotia | Bently Nevada | CVSER | 4500410500 | Electrical & Instrumentation | Ele-Control Panels | USD | 255771 | USD | 246425 | 9346 | Supplier Competitions / Negotiation | 2020-10-06 | 2021-05-15 | 2021-12-22 | 2020-12-09 | 2021-12-18 | 2021-05-15 | 2020-12-22 | 2021-01-22 | 2021-08-30 | 2021-04-13 | 2021-06-21 | -69 | 18 | -113
| B001712-Bacalhau FPSO | Cotia | Coarse Filter | AMIAD FILTRATION SYSTEMS 102 PVT. | 4503522496 | Flow Control | Carbon Steel | USD | 575651 | USD | 550758 | 24893 | Frame Agreements | 2020-10-13 | 2021-03-26 | 2021-01-20 | 2020-12-09 | 2020-12-21 | 2021-03-26 | 2020-12-14 | 2021-01-25 | 2021-09-02 | 2021-09-06 | 2021-09-04 | 2 | 12 | -60
| B001712-Bacalhau FPSO | Cotia | Vacuum Skid - UK +Tower Internals Material | ETAAP | 4503517597 | Fabrication | Skid Assembly Outsourced | USD | 1516850 | USD | 1460000 | 56850 | Supplier Competitions / Negotiation | 2020-10-28 | 2021-05-05 | 2021-01-13 | 2020-11-14 | 2020-11-26 | 2021-05-05 | 2020-11-27 | 2021-01-18 | 2021-11-10 | 2021-08-10 | 2021-09-25 | -46 | 12 | -107
| B001712-Bacalhau FPSO | Cotia | Electrical Heater | VULCANIC | 4503522676 | Electrical & Instrumentation | Ele-Electrical Others | USD | 42804 | USD | 37713 | 5091 | Frame Agreements | 2020-12-20 | 2021-05-11 | 2021-01-22 | 2021-01-10 | 2020-12-21 | 2021-05-11 | 2021-01-21 | 2021-01-25 | 2021-09-30 | 2021-05-28 | 2021-07-29 | -62 | 18 | -106
| B001712-Bacalhau FPSO | Cotia | Dearation Tower | HIMILE | 4503519173 | Fabrication | Metal Isolation Valves | USD | 618004 | USD | 765117 | -147113 | Market Impact | 2020-10-28 | 2021-04-13 | 2021-01-22 | 2020-12-10 | 2020-12-22 | 2021-04-13 | 2020-12-23 | 2021-01-25 | 2021-09-27 | 2021-08-11 | 2021-09-03 | -23 | 12 | -78
| B001712-Bacalhau FPSO | Cotia | Tanks ( steel) | Bexcelle | 4503519472 | Fabrication | Alloy Steel | USD | 178007 | USD | 105800 | 72207 | Design Optimizations | 2020-10-28 | 2021-05-25 | 2021-01-22 | 2021-01-01 | 2021-12-21 | 2021-05-25 | 2021-01-14 | 2021-01-25 | 2021-08-23 | 2021-08-23 | 2021-08-23 | 0 | 12 | -120
| B001712-Bacalhau FPSO | Cotia | Tanks (FRP) | ZONGHY | 4503521756 | Fabrication | Ele-Control Panels | USD | 69800 | USD | 73150 | -3350 | Market Impact | 2020-10-05 | 2021-05-14 | 2021-01-06 | 2020-12-09 | 2021-12-21 | 2021-05-14 | 2020-12-22 | 2021-01-22 | 2021-06-11 | 2021-04-12 | 2021-05-12 | -30 | 12 | -112
| B001712-Bacalhau FPSO | Cotia | Membrane Vessels + Cartidge Filter | PROTEC ARISAWA AMERICA, INC. | 4503511480 | Flow Control | RO Membrane Housings | USD | 857049 | USD | 953508 | -96459 | Size/ Weight/ Quantity Underestimated | 2020-09-15 | 2021-02-12 | 2021-01-06 | 2020-12-09 | 2020-12-21 | 2021-02-12 | 2020-12-22 | 2021-01-22 | 2021-07-13 | 2021-05-14 | 2021-06-13 | -30 | 12 | -21
| South Austin WWTP | Richmond | Model 2A Climber Screen | HALL INDUSTRIES INC. | 4503397343 | Fabrication | Carbon Steel | USD | 192805 | USD | 185660 | 7145 | Supplier Competitions / Negotiation | 2020-04-24 | 2020-05-19 | 2020-03-14 | 2020-05-08 | 2020-03-28 | 2020-05-19 | 2020-05-15 | 2020-05-19 | 2020-07-24 | 2020-07-25 | 2020-07-24 | 1 | 12 | 0
| 000473-LAVAL | Richmond | 316SS Angle Support Shelf | JOB SHOP FABRICATORS | 4500320482 | Fabrication | Carbon Steel | USD | 26865 | USD | 26592 | 273 | Frame Agreements | 2020-04-20 | 2020-05-20 | 2020-03-10 | 2020-04-30 | 2020-03-10 | 2020-05-20 | 2020-05-04 | 2020-03-10 | 2020-07-30 | 2020-04-07 | 2020-06-03 | -57 | 12 | -71
| 000473-LAVAL | Richmond | Shear Plates 316SS | JOB SHOP FABRICATORS | 4500285874 | Fabrication | Metal Isolation Valves | USD | 19502 | USD | 56298 | -36796 | Size/ Weight/ Quantity Underestimated | 2020-04-01 | 2019-08-09 | 2020-03-08 | 2020-04-13 | 2018-09-07 | 2019-08-09 | 2020-04-17 | 2018-09-07 | 2020-07-10 | 2018-10-05 | 2019-08-23 | -322 | 12 | -336
| 000473-LAVAL | Richmond | Threaded Rod 316SS | JOB SHOP FABRICATORS | 4500368307 | Fabrication | Carbon Steel | USD | 52681 | USD | 68004 | -15323 | Single Sourced | 2020-04-20 | 2020-05-20 | 2020-03-10 | 2020-04-30 | 2020-05-20 | 2020-05-20 | 2020-05-04 | 2020-05-20 | 2020-07-30 | 2020-04-07 | 2020-06-03 | -57 | 12 | 0
| 000473-LAVAL | Richmond | Access Manways | JOB SHOP FABRICATORS | 4500319019 | Fabrication | Metal Isolation Valves | USD | 60000 | USD | 38400 | 21600 | Frame Agreements | 2020-04-20 | 2020-05-19 | 2020-03-10 | 2020-04-30 | 2020-03-09 | 2020-05-19 | 2020-05-04 | 2020-06-08 | 2020-07-30 | 2020-07-13 | 2020-07-21 | -8 | 12 | 20
| CRD Victoria | Ancaster | Mixers, Dosing, Prep., Dilution, Extrac. - Impeller for Rapid Mixer for Densadeg | DYNAMIX | 4500274857 | Rotating Equipment | Dosing Pump | USD | 147495 | USD | 162115 | -14620 | Specs / Requirements Misinterpreted in Proposal | 2017-11-03 | 2018-05-18 | 2018-01-23 | 2017-12-08 | 2018-06-21 | 2018-05-18 | 2017-12-15 | 2018-07-16 | 2018-08-24 | 2018-11-30 | 2018-10-12 | 49 | 30 | 59
| CRD Victoria | Ancaster | Drives for Clarifier (Scraper) | DBS MANUFACTURING INC. | 4500286268 | Rotating Equipment | Carbon Steel | USD | 142800 | USD | 97461 | 45339 | Supplier Competitions / Negotiation | 2017-11-03 | 2018-06-02 | 2018-02-27 | 2017-12-08 | 2018-08-16 | 2018-06-02 | 2017-12-15 | 2018-08-22 | 2018-07-20 | 2018-12-30 | 2018-10-09 | 82 | 30 | 81
| CRD Victoria | Ancaster | Bridges & Mechanisms for Reactor - Draft Tube, Transfer pipe, vortex baffles, collection Trough for DENSADEG | Pro-Metal Plus | 4500322432 | Fabrication | Metal Isolation Valves | USD | 1130406 | USD | 1066665 | 63741 | Supplier Competitions / Negotiation | 2017-11-24 | 2018-11-07 | 2018-05-29 | 2017-12-29 | 2018-07-30 | 2018-11-07 | 2018-01-05 | 2019-04-29 | 2018-06-08 | 2019-10-21 | 2019-02-13 | 250 | 12 | 173
| CRD Victoria | Ancaster | Plastic Work, Tubes Settlers for Densadeg | MFG WATER TREATMENT | 4500283713 | Fabrication | Metal Isolation Valves | USD | 103402 | USD | 184218 | -80816 | Proposed Supplier Incapable Of Executing | 2017-11-24 | 2018-05-28 | 2018-05-20 | 2017-12-29 | 2018-06-05 | 2018-05-28 | 2018-01-05 | 2018-08-17 | 2018-06-08 | 2018-11-30 | 2018-09-03 | 88 | 12 | 81
| CRD Victoria | Ancaster | Injectors, Diffusers and Aerators - Aeration Grids for Meteor (Internals) | Sureflo | 4500272514 | Fabrication | Metal Isolation Valves | USD | 70000 | USD | 29500 | 40500 | Frame Agreements | 2017-10-13 | 2018-04-06 | 2018-02-23 | 2017-11-17 | 2018-04-18 | 2018-04-06 | 2017-11-24 | 2018-05-28 | 2018-03-02 | 2018-09-28 | 2018-06-15 | 105 | 12 | 52
| CRD Victoria | Ancaster | Aeration Diffusers | EDI | 4500272393 | Fabrication | Metal Isolation Valves | USD | 30000 | USD | 22320 | 7680 | Frame Agreements | 2017-10-27 | 2018-03-14 | 2018-04-01 | 2017-12-01 | 2018-05-10 | 2018-03-14 | 2017-12-15 | 2018-05-14 | 2018-07-31 | 2018-07-13 | 2018-07-22 | -9 | 12 | 61
| CRD Victoria | Ancaster | Media - Biolite | LUFENG | 4500348355 | Flow Control | Metal Isolation Valves | USD | 1236396 | USD | 1254609 | -18213 | Size/ Weight/ Quantity Underestimated | 2017-12-08 | 2019-01-25 | 2018-07-13 | 2018-01-12 | 2019-10-25 | 2019-01-25 | 2018-01-19 | 2019-11-05 | 2018-09-07 | 2020-03-13 | 2019-06-10 | 277 | 12 | 284
| CRD Victoria | Ancaster | Piping: Supports, Spools, Protection, Fittings - Biofor Internals | LES ACIERS SOFATEC INC. | 4500304542 | Fabrication | Centrifugal Pumps | USD | 1317312 | USD | 1291659 | 25653 | Supplier Competitions / Negotiation | 2017-11-17 | 2018-09-08 | 2018-11-08 | 2017-12-22 | 2018-12-20 | 2018-09-08 | 2017-12-29 | 2019-01-07 | 2018-10-19 | 2019-06-30 | 2019-02-23 | 127 | 12 | 121
| CRD Victoria | Ancaster | Plastic Components for Biofor | PLASCO WELDING AND FABRICATION INC | 4500313906 | Fabrication | Ele-Control Panels | USD | 205617 | USD | 86850 | 118767 | Design Optimizations | 2017-09-20 | 2018-06-17 | 2019-01-10 | 2017-12-20 | 2019-03-05 | 2018-06-17 | 2017-12-29 | 2019-02-28 | 2018-09-07 | 2019-03-14 | 2018-12-10 | 94 | 12 | 256
| CRD Victoria | Ancaster | Control valves & Control Components for Biofor (On/Off) | DEZURIK | 4500285182 | Flow Control | Ele-Control Panels | USD | 878394 | USD | 717099 | 161295 | Supplier Competitions / Negotiation | 2017-12-29 | 2018-06-30 | 2018-02-23 | 2018-02-02 | 2018-05-25 | 2018-06-30 | 2018-02-09 | 2018-07-27 | 2018-11-02 | 2018-12-31 | 2018-12-01 | 30 | 12 | 27
| CRD Victoria | Ancaster | Instrumentation for Field - Flowmeters, Level Transmitter, Pressure Transmitter, Differential Pressure Transmitter, Temperature Transmitter | ENDRESS & HAUSER | 4500290673 | Electrical & Instrumentation | Inst-Instrumentation Accessories | USD | 314103 | USD | 94328 | 219775 | Design Optimizations | 2017-12-29 | 2018-06-25 | 2018-03-09 | 2018-02-02 | 2018-06-14 | 2018-06-25 | 2018-02-09 | 2018-09-28 | 2018-06-08 | 2018-12-21 | 2018-09-14 | 98 | 18 | 95
| CRD Victoria | Ancaster | Instrumentation - Pressure Ring | VIKING INSTRUMENT & CONTROL | 4500281146 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 31800 | USD | 33264 | -1464 | Market Impact | 2017-12-29 | 2018-05-10 | 2018-03-01 | 2018-02-02 | 2018-06-14 | 2018-05-10 | 2018-02-09 | 2018-07-13 | 2018-06-08 | 2018-09-20 | 2018-07-30 | 52 | 18 | 64
| CRD Victoria | Ancaster | Electrical Panels - Remote IO, Main Control Panel and PLC Panel | SOFCON SYSTEMS INDIA PVT LTD | 4500298831 | Electrical & Instrumentation | Ele-Electrical Others | USD | 685200 | USD | 355100 | 330100 | Supplier Competitions / Negotiation | 2018-03-15 | 2018-11-22 | 2018-05-16 | 2018-04-19 | 2018-10-05 | 2018-11-22 | 2018-04-26 | 2018-11-14 | 2018-11-29 | 2019-08-01 | 2019-03-31 | 123 | 18 | -8
| CRD Victoria | Ancaster | Rotary Lobe Pumps - DENSADEG Sludge Transfer & Recycle Pump | NETZSCH CANADA INC. | 4500270176 | Rotating Equipment | Centrifugal Pumps | USD | 130656 | USD | 113316 | 17340 | Supplier Competitions / Negotiation | 2017-10-27 | 2018-03-26 | 2018-01-03 | 2017-12-01 | 2018-04-04 | 2018-03-26 | 2017-12-08 | 2018-04-27 | 2018-08-17 | 2018-08-24 | 2018-08-20 | 4 | 30 | 32
| CRD Victoria | Ancaster | Vertical Turbine Backwash Pumps | KSB Pumps Inc. | 4500275237 | Rotating Equipment | Centrifugal Pumps | USD | 276907 | USD | 193557 | 83350 | Supplier Competitions / Negotiation | 2017-10-27 | 2018-05-07 | 2018-01-02 | 2017-12-01 | 2018-03-26 | 2018-05-07 | 2017-12-08 | 2018-06-15 | 2018-08-17 | 2018-11-15 | 2018-10-01 | 45 | 30 | 39
| CRD Victoria | Ancaster | UPS | GRAYBAR CANADA | 4500314094 | Electrical & Instrumentation | Ele-Control Panels | USD | 25000 | USD | 17213 | 7787 | Frame Agreements | 2018-07-31 | 2018-12-24 | 2018-08-20 | 2019-02-15 | 2019-02-13 | 2018-12-24 | 2019-02-22 | 2019-04-26 | 2019-04-30 | 2019-05-20 | 2019-05-10 | 10 | 18 | 123
| WaterOne | Leonia | Pipe Spools (Anaster) | PANDA PIPING LTD | 4500284969 | Fabrication | Ele-Control Panels | USD | 186977 | CAD | 59810 | 127167 | Frame Agreements | 2018-05-28 | 2018-07-20 | 2018-07-25 | 2018-06-18 | 2018-08-03 | 2018-09-21 | 2018-06-25 | 2018-08-09 | 2018-11-05 | 2018-08-30 | 2019-01-16 | -139 | 12 | 20
| WaterOne | Leonia | Instrumentation (ABB) (Skidded) | ABB INSTRUMENTATION | 4500285031 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 580414 | CAD | 21710 | 558704 | Design Optimizations | 2018-05-28 | 2018-07-02 | 2018-07-27 | 2018-06-18 | 2018-08-09 | 2018-08-30 | 2018-06-25 | 2018-08-14 | 2018-11-05 | 2018-10-18 | 2018-12-03 | -46 | 18 | 43
| Sacramento, CA – WWAM | Richmond | PVC POSTS | RICHLAND LLC | 4500390998 | Fabrication | Ele-Control Panels | USD | 84110 | USD | 72061 | 12049 | Supplier Competitions / Negotiation | 2020-11-04 | 2020-06-15 | 2020-07-07 | 2020-11-18 | 2020-09-02 | 2020-10-15 | 2020-11-25 | 2020-09-02 | 2020-12-31 | 2020-10-14 | 2020-11-22 | -39 | 12 | 79
| Town of Warrenton WWTP | Richmond | MEDIA | CHRISTIAN STOEHR GmbH & Co. | 4500349641 | Fabrication | Metal Isolation Valves | USD | 640557 | USD | 672240 | -31683 | Not included in Proposal / RFQ | 2018-07-27 | 2019-04-17 | 2019-09-07 | 2018-08-10 | 2019-11-07 | 2019-04-17 | 2018-08-15 | 2019-04-17 | 2018-11-16 | 2020-01-07 | 2019-06-12 | 209 | 12 | 0
| Town of Warrenton WWTP | Richmond | AERATION GRIDS | ENVIRONMENTAL DYNAMICS | 4500342569 | Fabrication | Metal Isolation Valves | USD | 103120 | USD | 103120 | 0 | Supplier Competitions / Negotiation | 2018-08-27 | 2019-07-01 | 2019-09-25 | 2018-09-10 | 2019-09-25 | 2019-07-01 | 2018-09-15 | 2019-09-25 | 2018-10-08 | 2020-05-05 | 2019-07-22 | 288 | 12 | 86
| Town of Warrenton WWTP | Richmond | BLOWERS | KAESER COMPRESSORS | 4500339010 | Rotating Equipment | Blowers & Fans | USD | 318434 | USD | 355513 | -37079 | Size/ Weight/ Quantity Underestimated | 2018-07-27 | 2019-08-13 | 2020-08-29 | 2018-08-10 | 2019-08-29 | 2019-08-13 | 2018-08-15 | 2019-08-29 | 2018-11-19 | 2020-07-07 | 2019-09-13 | 298 | 30 | 16
| Town of Warrenton WWTP | Richmond | INSTRUMENTS | FLOW CONTROL | 4500340370 | Flow Control | Metal Isolation Valves | USD | 48529 | USD | 43772 | 4757 | Frame Agreements | 2018-08-27 | 2019-04-15 | 2019-09-10 | 2018-09-10 | 2019-09-10 | 2019-04-15 | 2018-09-15 | 2019-09-10 | 2018-09-28 | 2019-12-03 | 2019-05-01 | 216 | 12 | 148
| Town of Warrenton WWTP | Richmond | VALVES | FLOW CONTROL | 4500340254 | Flow Control | Ele-Control Panels | USD | 44530 | USD | 152058 | -107528 | Market Impact | 2018-08-27 | 2019-07-18 | 2019-07-18 | 2018-09-10 | 2019-09-09 | 2019-07-18 | 2018-09-15 | 2019-09-09 | 2018-11-22 | 2020-06-07 | 2019-08-30 | 282 | 12 | 53
| Town of Warrenton WWTP | Richmond | FAB & SCREENS | JOB SHOP FABRICATORS | 4500342570 | Fabrication | Carbon Steel | USD | 147482 | USD | 198792 | -51310 | Proposed Supplier Incapable Of Executing | 2018-07-11 | 2019-08-09 | 2020-04-30 | 2018-07-25 | 2019-08-09 | 2019-08-09 | 2018-07-30 | 2020-08-17 | 2018-09-10 | 2020-09-07 | 2019-09-09 | 364 | 12 | 374
| TVA - Cumberland | Richmond | Filter press | EVOQUA | 4500330582 | Rotating Equipment | Filter Press | USD | 3111900 | USD | 2750901 | 360999 | Frame Agreements | 2019-04-19 | 2019-01-18 | 2019-08-09 | 2019-05-17 | 2019-05-18 | 2019-08-09 | 2019-05-24 | 2019-02-10 | 2020-02-28 | 2019-02-10 | 2019-08-20 | -191 | 30 | 23
| TVA - Cumberland | Richmond | Filter press Fiber Panel | EVOQUA | 4500353752 | Rotating Equipment | Filter Press | USD | 6985 | USD | 6985 | 0 | Market Impact | 2019-04-19 | 2019-11-20 | 2019-11-20 | 2019-05-17 | 2019-11-20 | 2019-07-09 | 2019-05-24 | 2019-12-05 | 2019-02-10 | 2019-12-05 | 2019-07-09 | 149 | 30 | 15
| TVA - Cumberland | Richmond | Horizontal Centrifugal Pumps | SULZER PUMP SOLUTIONS - USA | 4500341589 | Rotating Equipment | Centrifugal Pumps | USD | 398965 | USD | 226177 | 172788 | Design Optimizations | 2019-04-26 | 2019-05-10 | 2019-06-21 | 2019-05-31 | 2019-08-23 | 2019-09-02 | 2019-06-14 | 2019-09-19 | 2020-01-10 | 2019-09-19 | 2019-11-14 | -56 | 30 | 132
| TVA - Cumberland | Richmond | Progressive Cavity Pumps | SEEPEX | 4500337952 | Rotating Equipment | Centrifugal Pumps | USD | 118309 | USD | 115004 | 3305 | Design Optimizations | 2019-05-10 | 2019-05-10 | 2019-06-14 | 2019-06-28 | 2019-07-12 | 2019-09-09 | 2019-07-19 | 2019-08-21 | 2020-01-10 | 2019-08-21 | 2019-10-31 | -71 | 30 | 103
| TVA - Cumberland | Richmond | Submersible pumps | FOLSOM | 4500347255 | Rotating Equipment | Centrifugal Pumps | USD | 333984 | USD | 320178 | 13806 | Frame Agreements | 2019-05-10 | 2019-05-10 | 2019-08-09 | 2019-09-13 | 2019-10-08 | 2019-10-13 | 2019-10-04 | 2019-10-22 | 2020-03-17 | 2019-10-22 | 2020-01-03 | -73 | 30 | 165
| TVA - Cumberland | Richmond | Mixers - EQ tanks, sulfide/coagulation reaction tank, flocculation tank, sludge holding tank, sump internals | ENVIREQUIP W.T.E.M INC. | 4500348884 | Rotating Equipment | Mixers | USD | 622412 | USD | 513154 | 109258 | Design Optimizations | 2019-05-10 | 2019-05-09 | 2019-07-09 | 2019-06-28 | 2019-08-22 | 2019-10-03 | 2019-07-12 | 2019-11-03 | 2020-02-28 | 2019-11-03 | 2019-12-31 | -58 | 30 | 178
| TVA - Cumberland | Richmond | On-Off - Pinch Valves | RED VALVE | 4500347868 | Flow Control | Metal Isolation Valves | USD | 152896 | USD | 70752 | 82144 | Supplier Competitions / Negotiation | 2019-06-21 | 2019-09-30 | 2019-08-13 | 2019-07-26 | 2019-11-25 | 2019-09-30 | 2019-08-30 | 2019-12-03 | 2020-01-10 | 2019-12-03 | 2019-12-22 | -19 | 12 | 64
| TVA - Cumberland | Richmond | Manual -Butterfly Valves | BRAY CONTROLS CANADA LTD. | 4500355636 | Flow Control | Metal Isolation Valves | USD | 304281 | USD | 130394 | 173887 | Design Optimizations | 2019-06-21 | 2019-07-01 | 2019-08-28 | 2019-07-19 | 2019-11-03 | 2019-09-30 | 2019-07-26 | 2019-11-06 | 2020-01-10 | 2019-11-06 | 2019-12-08 | -32 | 12 | 128
| TVA - Cumberland | Richmond | Manual - Knife Gate Valves | ITT ENGINEERED VALVES LLC | 4500355093 | Flow Control | Metal Isolation Valves | USD | 547492 | USD | 327069 | 220423 | Supplier Competitions / Negotiation | 2019-06-21 | 2019-07-01 | 2019-08-26 | 2019-07-26 | 2019-09-16 | 2019-11-09 | 2019-08-09 | 2020-03-29 | 2020-01-10 | 2020-03-29 | 2020-02-18 | 40 | 12 | 272
| TVA - Cumberland | Richmond | Manual - Ball Valves | TRIVACO | 4500359566 | Flow Control | Metal Isolation Valves | USD | 108730 | USD | 198859 | -90129 | Specs / Requirements Misinterpreted in Proposal | 2019-06-21 | 2019-07-01 | 2019-10-11 | 2019-07-19 | 2019-12-12 | 2019-09-30 | 2019-07-26 | 2019-12-17 | 2020-01-10 | 2019-12-17 | 2019-12-29 | -12 | 12 | 169
| TVA - Cumberland | Richmond | Instrumentation - Flow, level, pressure | ROSEMOUNT INC | 4500354495 | Electrical & Instrumentation | Inst-Instrumentation Accessories | USD | 52848 | USD | 57090 | -4242 | Single Sourced | 2019-07-12 | 2019-07-11 | 2019-08-30 | 2019-08-16 | 2019-09-21 | 2019-10-10 | 2019-08-30 | 2019-12-07 | 2020-01-10 | 2019-12-07 | 2019-12-24 | -17 | 18 | 149
| TVA - Cumberland | Richmond | Instrumentation - Magmeters | MICRO-MOTION, INC | 4500361786 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 75396 | USD | 80097 | -4701 | Specs / Requirements Misinterpreted in Proposal | 2019-07-12 | 2019-07-11 | 2019-08-30 | 2019-08-16 | 2019-10-04 | 2019-11-10 | 2019-08-30 | 2020-02-13 | 2020-01-10 | 2020-03-11 | 2020-02-09 | 31 | 18 | 217
| TVA - Cumberland | Richmond | Instrumentation - Pressure Gauges | FLOMEC INC | 4500358984 | Electrical & Instrumentation | Inst-Instrumentation Accessories | USD | 22766 | USD | 5045 | 17721 | Supplier Competitions / Negotiation | 2019-07-12 | 2019-07-11 | 2019-07-29 | 2019-08-16 | 2019-09-20 | 2019-10-11 | 2019-08-30 | 2020-01-12 | 2020-01-10 | 2020-01-12 | 2020-01-11 | 1 | 18 | 185
| TVA - Cumberland | Richmond | Instrumentation - Pressure Sensor | AC CONTROLS INC. | 4500351292 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 5964 | USD | 28288 | -22324 | Market Impact | 2019-07-12 | 2019-07-11 | 2019-08-28 | 2019-08-16 | 2019-09-23 | 2019-10-10 | 2019-08-30 | 2019-11-25 | 2020-01-10 | 2020-01-10 | 2020-01-10 | 0 | 18 | 137
| TVA - Cumberland | Richmond | Metallic tank (Sulfide) | Burke's Mechanical, Inc. | 4500341274 | Fabrication | Metal Isolation Valves | USD | 70410 | USD | 131469 | -61059 | Estimate Without Market Reference(No Quote) | 2019-06-07 | 2019-06-04 | 2019-07-16 | 2019-08-30 | 2019-08-09 | 2019-10-18 | 2019-09-20 | 2019-09-18 | 2020-03-03 | 2020-01-24 | 2020-02-12 | -19 | 12 | 106
| TVA - Cumberland | Richmond | FRP Tanks (Ferric Chlorine) | DIAMOND FIBERGLASS | 4500342940 | Fabrication | Ele-Control Panels | USD | 27238 | USD | 37536 | -10298 | Size/ Weight/ Quantity Underestimated | 2019-06-07 | 2019-06-04 | 2019-07-16 | 2019-08-30 | 2019-08-27 | 2019-10-18 | 2019-09-20 | 2019-09-26 | 2020-03-03 | 2020-02-06 | 2020-02-19 | -13 | 12 | 114
| TVA - Cumberland | Richmond | Platforms (Gratings / Handrails / Hardware) | QUALICO | 4500365374 | Fabrication | Metal Isolation Valves | USD | 295140 | USD | 707665 | -412525 | Proposed Supplier Incapable Of Executing | 2019-07-12 | 2019-11-06 | 2019-12-06 | 2019-07-26 | 2020-01-20 | 2019-11-04 | 2019-08-16 | 2020-01-24 | 2020-02-28 | 2020-01-24 | 2020-02-10 | -17 | 12 | 79
| TVA - Cumberland | Richmond | Densadeg - Metal Work (Internals / Shaft / Hardware) | POSÉIDON INC. | 4500358445 | Fabrication | Non-Metal Equipment | USD | 263202 | USD | 512708 | -249506 | Estimate Without Market Reference(No Quote) | 2019-06-28 | 2019-09-20 | 2019-11-12 | 2019-07-26 | 2019-11-08 | 2019-09-21 | 2019-08-16 | 2019-11-08 | 2020-02-27 | 2019-04-16 | 2019-09-21 | -158 | 12 | 49
| TVA - Cumberland | Richmond | Densadeg - Metal Work (Embedded Steel Anchor Ring) | RICHLAND LLC | 4500333970 | Fabrication | Alloy Steel | USD | 62763 | USD | 54489 | 8274 | Frame Agreements | 2019-05-17 | 2019-05-14 | 2019-07-05 | 2019-06-28 | 2019-07-10 | 2019-07-23 | 2019-07-12 | 2019-07-19 | 2019-10-01 | 2019-09-13 | 2019-09-22 | -9 | 12 | 66
| TVA - Cumberland | Richmond | Densadeg - Metal Work (Shell - Knock down Section Alloy 2205 / Sample Sink/CS Legs) | CB & T | 4500344833 | Fabrication | Non-Metal Equipment | USD | 1944019 | USD | 1627364 | 316655 | Design Optimizations | 2019-06-28 | 2019-07-08 | 2019-08-23 | 2019-07-26 | 2019-08-28 | 2019-10-02 | 2019-08-09 | 2019-09-15 | 2020-01-07 | 2019-09-15 | 2019-11-11 | -57 | 12 | 69
| TVA - Cumberland | Richmond | Densadeg - Lamellas | PLASTITEL | 4500349393 | Fabrication | Ele-Control Panels | USD | 92015 | USD | 93175 | -1160 | Proposed Supplier Incapable Of Executing | 2019-10-11 | 2019-10-03 | 2019-10-17 | 2019-10-25 | 2019-10-23 | 2019-12-15 | 2019-11-15 | 2019-10-23 | 2020-02-27 | 2019-10-23 | 2019-12-25 | -63 | 12 | 20
| TVA - Cumberland | Richmond | Filtrafast - Tank & Internals & Screens (Alloy 2205) | CB & T | 4500344807 | Fabrication | Alloy Steel | USD | 563947 | USD | 742375 | -178428 | Estimate Without Market Reference(No Quote) | 2019-06-28 | 2019-07-17 | 2019-08-29 | 2019-07-26 | 2019-08-29 | 2019-11-15 | 2019-08-16 | 2019-09-16 | 2020-04-03 | 2019-09-16 | 2019-12-25 | -100 | 12 | 61
| TVA - Cumberland | Richmond | Filtrafast - Media | Ozone System Services Group | 4500348232 | Flow Control | Metal Isolation Valves | USD | 63116 | USD | 17066 | 46050 | Supplier Competitions / Negotiation | 2019-09-27 | 2019-07-17 | 2019-07-29 | 2019-10-11 | 2019-08-09 | 2019-11-17 | 2019-10-25 | 2019-10-30 | 2020-03-20 | 2019-12-06 | 2020-01-27 | -52 | 12 | 105
| TVA - Cumberland | Richmond | Blowers | AERZEN CANADA INC. | 4500342922 | Rotating Equipment | Blowers & Fans | USD | 103968 | USD | 72428 | 31540 | Design Optimizations | 2019-05-31 | 2019-05-24 | 2019-07-10 | 2019-10-11 | 2019-07-11 | 2019-10-28 | 2019-10-25 | 2019-09-26 | 2020-04-03 | 2020-02-27 | 2020-03-16 | -18 | 30 | 125
| TVA - Cumberland | Richmond | Lime Silo System | Con-V-Air | 4500349646 | Fabrication | Carbon Steel | USD | 950212 | USD | 990114 | -39902 | Market Impact | 2019-05-24 | 2019-05-30 | 2019-07-19 | 2019-06-14 | 2019-10-24 | 2019-10-20 | 2019-07-05 | 2019-11-01 | 2020-03-17 | 2019-11-01 | 2020-01-08 | -68 | 12 | 155
| TVA - Cumberland | Richmond | Skid Manufacturing Sub-out | TRIVACO | 4500361808 | Fabrication | Skid Assembly Outsourced | USD | 872109 | USD | 629553 | 242556 | Design Optimizations | 2019-06-28 | 2019-10-28 | 2019-11-11 | 2019-09-13 | 2019-11-15 | 2019-11-15 | 2019-10-11 | 2019-12-11 | 2020-04-03 | 2019-12-11 | 2020-02-06 | -57 | 12 | 44
| TVA - Cumberland | Richmond | VFDs | NEDROW | 4500369207 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 486277 | USD | 289000 | 197277 | Frame Agreements | 2019-09-04 | 2019-09-12 | 2019-10-01 | 2019-10-18 | 2020-01-10 | 2019-12-02 | 2020-01-15 | 2020-03-01 | 2020-01-31 | 2020-03-01 | 2020-02-15 | 15 | 18 | 171
| TVA - Cumberland | Richmond | Automatic Backwashable Filter | TEKLEEN | 4500372625 | Fabrication | Carbon Steel | USD | 13800 | USD | 32100 | -18300 | Estimate Without Market Reference(No Quote) | 2020-02-26 | 2020-02-26 | 2020-04-02 | 2020-02-26 | 2020-04-02 | 2020-05-08 | 2020-03-06 | 2020-04-06 | 2020-05-08 | 2020-07-20 | 2020-06-13 | 37 | 12 | 40
| TVA - Cumberland | Richmond | Skid Manufacturing Sub-out (Frames, Spools, JB, Mechanical & Electrical Bulk) | TRIVACO | 4500380907 | Fabrication | Skid Assembly Outsourced | USD | 9000 | USD | 49085 | -40085 | Specs / Requirements Misinterpreted in Proposal | 2020-05-01 | 2020-05-12 | 2020-06-12 | 2020-06-16 | 2020-06-13 | 2020-06-16 | 2020-04-10 | 2020-06-13 | 2020-06-16 | 2020-08-22 | 2020-07-19 | 34 | 12 | 32
| Lachute WTP - Lachute Quebec CA - Mangazur | Oakville | Pressure Vessel | LES ACIERS SOFATEC INC. | 4503523905 | Fabrication | Carbon Steel | CAD | 306622 | CAD | 269400 | 37222 | Design Optimizations | 2020-12-18 | 2020-12-15 | 2020-12-21 | 2021-01-13 | 2021-01-11 | 2021-03-01 | 2021-01-22 | 2021-01-24 | 2021-05-11 | 2021-05-16 | 2021-05-13 | 3 | 12 | 40
| Lachute WTP - Lachute Quebec CA - Mangazur | Oakville | Blower | AERZEN CANADA INC. | 4503538973 | Rotating Equipment | Ele-Control Panels | CAD | 12687 | CAD | 9960 | 2727 | Frame Agreements | 2021-01-22 | 2019-10-22 | 2019-10-29 | 2021-01-28 | 2021-02-17 | 2020-07-31 | 2021-02-05 | 2021-02-21 | 2021-04-15 | 2021-05-10 | 2021-04-27 | 13 | 30 | 488
| Lachute WTP - Lachute Quebec CA - Mangazur | Oakville | Air Compressor | ATLAS COPCO COMPRESSORS | 4503541545 | Rotating Equipment | Vapor Compressor | CAD | 33866 | CAD | 27680 | 6186 | Frame Agreements | 2021-12-29 | 2020-12-29 | 2021-01-13 | 2021-12-30 | 2021-02-16 | 2021-06-30 | 2021-02-05 | 2021-02-24 | 2021-04-28 | 2021-05-10 | 2021-05-04 | 6 | 30 | 57
| Lachute WTP - Lachute Quebec CA - Mangazur | Oakville | Flow Transmitter | ENDRESS + HAUSER CANADA LTD. | 4503537379 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | CAD | 39786 | USD | 38877 | 909 | Frame Agreements | 2021-01-07 | 2021-01-07 | 2021-02-16 | 2021-01-12 | 2021-02-15 | 2021-03-03 | 2021-01-22 | 2021-02-16 | 2021-04-28 | 2021-03-28 | 2021-04-12 | -15 | 18 | 40
| Lachute WTP - Lachute Quebec CA - Mangazur | Oakville | ReOxazur -Diffuser | LES ACIERS SOFATEC INC. | 450352390 | Fabrication | Centrifugal Pumps | CAD | 36703 | CAD | 12600 | 24103 | Supplier Competitions / Negotiation | 2021-01-06 | 2021-01-06 | 2021-01-12 | 2021-01-12 | 2021-01-13 | 2021-03-13 | 2021-01-22 | 2021-01-26 | 2021-05-11 | 2021-05-18 | 2021-05-14 | 4 | 12 | 20
| Lachute WTP - Lachute Quebec CA - Mangazur | Oakville | Butterfly | BRAY CONTROLS CANADA LTD. | 4503550144 | Flow Control | Centrifugal Pumps | CAD | 43194 | USD | 23554 | 19640 | Design Optimizations | 2021-01-07 | 2021-01-20 | 2021-02-18 | 2021-01-12 | 2021-03-09 | 2021-03-31 | 2021-02-05 | 2021-03-11 | 2021-04-15 | 2021-06-23 | 2021-05-19 | 35 | 12 | 50
| Lachute WTP - Lachute Quebec CA - Mangazur | Oakville | Media | RED FLINT SAND & GRAVEL | 4503576680 | Flow Control | Metal Isolation Valves | CAD | 25033 | USD | 17901 | 7132 | Design Optimizations | 2021-02-17 | 2021-03-11 | 2021-03-12 | 2021-04-15 | 2021-04-28 | 2021-04-27 | 2021-04-19 | 2021-04-29 | 2021-05-11 | 2021-07-05 | 2021-06-07 | 28 | 12 | 49
| Lachute WTP - Lachute Quebec CA - Mangazur | Oakville | Control Panel | ENGINEERED ELECTRIC CONTROLS LIMITED | 4503550803 | Electrical & Instrumentation | Ele-Control Panels | CAD | 74391 | CAD | 35995 | 38396 | Supplier Competitions / Negotiation | 2021-01-05 | 2021-01-05 | 2021-01-14 | 2021-01-14 | 2021-03-03 | 2021-02-24 | 2021-02-05 | 2021-03-10 | 2021-04-15 | 2021-03-10 | 2021-03-28 | -18 | 18 | 64
| Ste. Foy, QC - WWAM | Richmond | CHEMICAL FEED PUMPS/SKIDS | JOHN BROOKS COMPANY LTD. | 4500424487 | Electrical & Instrumentation | Ele-Control Panels | USD | 26177 | USD | 14156 | 12021 | Supplier Competitions / Negotiation | 2020-04-10 | 2020-11-08 | 2021-03-23 | 2020-04-23 | 2021-04-06 | 2020-11-08 | 2020-04-30 | 2021-04-13 | 2020-08-30 | 2021-06-08 | 2021-01-18 | 141 | 18 | 156
| Ste. Foy, QC - WWAM | Richmond | METAL WORK | JOB SHOP FABRICATORS | 4503397723 | Fabrication | Non-Metal Equipment | USD | 106725 | USD | 104675 | 2050 | Design Optimizations | 2020-04-20 | 2020-04-15 | 2020-04-30 | 2020-04-30 | 2020-04-25 | 2020-04-04 | 2020-05-04 | 2020-04-25 | 2020-08-30 | 2020-05-16 | 2020-07-08 | -53 | 12 | 10
| Ste. Foy, QC - WWAM | Richmond | COLLECTION TROUGH | Burke's Mechanical, Inc. | 4100361046 | Fabrication | Ele-Control Panels | USD | 12037 | USD | 37160 | -25123 | Estimate Without Market Reference(No Quote) | 2021-02-03 | 2021-02-03 | 2021-01-18 | 2021-02-03 | 2021-01-06 | 2021-02-03 | 2021-02-03 | 2021-01-06 | 2021-02-03 | 2021-03-03 | 2021-02-17 | 14 | 12 | -28
| Ste. Foy, QC - WWAM | Richmond | PLASTIC WORK | KAL-LITE | 4500355244 | Fabrication | Carbon Steel | USD | 47843 | USD | 10842 | 37001 | Supplier Competitions / Negotiation | 2020-04-20 | 2020-11-01 | 2020-11-10 | 2020-04-30 | 2020-12-01 | 2020-11-10 | 2020-05-04 | 2020-11-09 | 2020-08-30 | 2020-12-14 | 2020-10-22 | 53 | 12 | 8
| Ste. Foy, QC - WWAM | Richmond | EXTRUSIONS | KOFLO CORPORATION | 4500422739 | Fabrication | Ele-Control Panels | USD | 113082 | USD | 6286 | 106796 | Supplier Competitions / Negotiation | 2020-04-20 | 2020-11-15 | 2021-04-06 | 2020-04-30 | 2021-04-13 | 2020-12-11 | 2020-05-04 | 2021-04-16 | 2020-08-30 | 2021-05-14 | 2021-01-05 | 129 | 12 | 152
| Ste. Foy, QC - WWAM | Richmond | CONTROL VALVES & CONTROL COMPONENTS | AUTOMATIC CONTROLS OF VIRGINIA, INC | 4500422176 | Flow Control | Ele-Control Panels | USD | 27546 | USD | 27546 | 0 | Single Sourced | 2020-04-20 | 2020-11-09 | 2021-04-06 | 2020-04-30 | 2021-04-09 | 2020-11-09 | 2020-05-04 | 2021-04-13 | 2020-08-30 | 2021-06-01 | 2021-01-14 | 138 | 12 | 155
| Alexandria ED Bilboa | Richmond | FABRICATION (BUBBLE GENERATORS) | POSEIDON, INC | 4500332980 | Fabrication | Carbon Steel | USD | 86356 | USD | 90720 | -4364 | Proposed Supplier Incapable Of Executing | 2019-07-03 | 2019-09-03 | 2020-01-29 | 2019-07-10 | 2019-01-29 | 2019-09-03 | 2019-07-13 | 2020-01-29 | 2019-09-07 | 2020-04-08 | 2019-12-23 | 107 | 12 | 148
| Alexandria ED Bilboa | Richmond | PRESSURE GAUGES | FLOMEC INC | 4500346813 | Fabrication | Ele-Control Panels | USD | 29796 | USD | 66640 | -36844 | Proposed Supplier Incapable Of Executing | 2020-04-14 | 2020-04-14 | 2019-10-21 | 2020-04-14 | 2019-10-18 | 2020-04-14 | 2020-04-14 | 2020-08-16 | 2020-04-14 | 2020-10-11 | 2020-07-13 | 90 | 12 | 124
| Alexandria ED Bilboa | Richmond | INSTRUMENTS (FLOW METERS) | Brooks Instruments | 4500336444 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 71114 | USD | 68320 | 2794 | Design Optimizations | 2019-07-29 | 2019-10-14 | 2019-08-08 | 2019-08-05 | 2019-07-26 | 2019-10-14 | 2019-08-08 | 2019-10-14 | 2019-09-19 | 2020-01-02 | 2019-11-10 | 53 | 18 | 0
| Alexandria ED Bilboa | Richmond | DRIP TRAPS | SPIRAX SARCO CANADA LTD. | 4500351289 | Fabrication | Centrifugal Pumps | USD | 11606 | USD | 16466 | -4860 | Market Impact | 2019-11-09 | 2019-12-12 | 2019-11-19 | 2019-11-16 | 2019-11-19 | 2019-12-12 | 2019-11-19 | 2019-11-19 | 2019-12-24 | 2020-01-14 | 2020-01-03 | 11 | 12 | -23
| Alexandria ED Bilboa | Richmond | BALL VALVES | HAJOCA CORP | 4500356031 | Flow Control | Metal Isolation Valves | USD | 27054 | USD | 24623 | 2431 | Frame Agreements | 2019-11-03 | 2019-12-21 | 2019-12-18 | 2019-11-10 | 2019-12-13 | 2019-12-21 | 2019-11-13 | 2019-12-13 | 2019-12-18 | 2020-02-07 | 2020-01-12 | 26 | 12 | -8
| Alexandria ED Bilboa | Richmond | GLOBE VALVES | TUNING | 4500350375 | Flow Control | Metal Isolation Valves | USD | 25379 | USD | 24393 | 986 | Design Optimizations | 2019-12-08 | 2019-12-16 | 2019-11-13 | 2019-12-15 | 2019-11-13 | 2019-12-16 | 2019-12-18 | 2019-11-09 | 2020-01-22 | 2020-01-04 | 2020-01-13 | -9 | 12 | -37
| Alexandria ED Bilboa | Richmond | GAS BALANCING | PIPESPAIN S.L. | 4500357235 | Fabrication | Carbon Steel | USD | 110298 | USD | 141998 | -31700 | Market Impact | 2019-12-23 | 2020-04-15 | 2019-12-11 | 2019-12-30 | 2019-12-09 | 2020-04-15 | 2020-01-02 | 2020-08-18 | 2020-03-05 | 2020-08-22 | 2020-05-29 | 85 | 12 | 125
| Mont Wright | Richmond | Progressive Cavity Pumps (Netzsch) | NETZSCH CANADA INC. | 4500430706 | Rotating Equipment | PD Pumps | CAD | 217566 | USD | 186630 | 30936 | Frame Agreements | 2021-06-07 | 2021-05-28 | 2021-06-12 | 2021-06-21 | 2021-06-09 | 2021-08-14 | 2021-06-28 | 2021-06-13 | 2021-11-01 | 2021-10-17 | 2021-10-24 | -7 | 30 | 16
| Mont Wright | Richmond | Knifegate Valves (Clarkson) | LAKESIDE PROCESS CONTROLS LTD. | 4500436398 | Flow Control | Metal Isolation Valves | CAD | 142216 | USD | 107159 | 35057 | Supplier Competitions / Negotiation | 2021-06-07 | 2021-08-19 | 2021-07-29 | 2021-06-21 | 2021-08-02 | 2021-08-19 | 2021-06-28 | 2021-08-02 | 2021-11-01 | 2021-10-25 | 2021-10-28 | -3 | 12 | -17
| Mont Wright | Richmond | Ball Valves | SYLVAN AUTOMATION LTD | 4500438410 | Flow Control | Metal Isolation Valves | CAD | 50760 | USD | 32669 | 18091 | Frame Agreements | 2021-06-07 | 2021-08-19 | 2021-08-06 | 2021-06-21 | 2021-08-14 | 2021-08-19 | 2021-06-28 | 2021-08-24 | 2021-11-01 | 2021-10-05 | 2021-10-18 | -13 | 12 | 5
| LNG | Oakville | Diffuser (Areation Grid) | ENVIRONMENTAL DYNAMICS | 4500372943 | Flow Control | Injection Quills, Ejectors, Diffusers | CAD | 26824 | USD | 12503 | 14321 | Design Optimizations | 2019-11-15 | 2020-03-28 | 2020-04-10 | 2019-12-06 | 2020-04-12 | 2020-03-28 | 2019-12-27 | 2020-04-18 | 2020-03-06 | 2020-04-18 | 2020-08-10 | -114 | 30 | 21
| LNG | Oakville | Spray System (Spray Header Grid) | Bete Fog Nozzle, Inc. | 4500383844 | Flow Control | Injection Quills, Ejectors, Diffusers | CAD | 20000 | USD | 5455 | 14545 | Design Optimizations | 2020-08-21 | 2020-08-21 | 2020-07-10 | 2020-08-21 | 2020-06-22 | 2020-08-21 | 2020-08-21 | 2020-07-11 | 2020-08-21 | 2020-08-01 | 2020-10-20 | -80 | 18 | -41
| LNG | Oakville | Injection Quills | BURLINGTON PUMP INC. | 4500370060 | Flow Control | Injection Quills, Ejectors, Diffusers | CAD | 8361 | CAD | 6493 | 1868 | Design Optimizations | 2019-12-06 | 2020-04-15 | 2020-03-17 | 2019-12-27 | 2020-03-14 | 2020-04-15 | 2020-01-24 | 2020-03-25 | 2020-03-06 | 2020-08-17 | 2020-08-25 | -8 | 24 | -21
| LNG | Oakville | Tanks - CS | SHANGHAI HILTON INTERNATIONAL TRADE CO LTD | 4500370349 | Fabrication | Carbon Steel | CAD | 1087507 | USD | 1116012 | -28505 | Specs / Requirements Misinterpreted in Proposal | 2019-06-28 | 2020-06-22 | 2020-03-16 | 2019-10-25 | 2020-04-03 | 2020-06-22 | 2019-09-08 | 2020-04-26 | 2020-07-17 | 2020-04-26 | 2021-06-18 | -418 | 18 | -57
| LNG | Oakville | Tanks - FRP | THORPE INTERNATIONAL SERVICES INC | 4500349301 | Fabrication | Non-Metal Equipment | CAD | 592594 | USD | 589800 | 2794 | Supplier Competitions / Negotiation | 2019-06-28 | 2020-02-21 | 2019-08-21 | 2019-10-25 | 2019-08-12 | 2020-02-21 | 2019-09-08 | 2019-11-03 | 2020-07-17 | 2020-02-09 | 2020-10-16 | -250 | 18 | -110
| LNG | Oakville | Tanks - HDPE | ACO CONTAINER SYSTEMS LTD. | 4500346264 | Fabrication | Non-Metal Equipment | CAD | 9628 | CAD | 9628 | 0 | Design Optimizations | 2019-06-28 | 2020-01-31 | 2019-07-05 | 2019-07-26 | 2019-08-06 | 2020-01-31 | 2019-08-16 | 2019-10-17 | 2020-07-17 | 2020-07-03 | 2020-09-04 | -63 | 12 | -106
| LNG | Oakville | Pressure Vessels & Vessel components | WUXI HUALI PETRO. AND CHEM. ENG. CO.,LTD | 4500355810 | Fabrication | Carbon Steel | CAD | 282986 | USD | 192346 | 90640 | Supplier Competitions / Negotiation | 2019-06-22 | 2020-07-13 | 2019-08-12 | 2019-07-12 | 2019-11-03 | 2020-07-13 | 2019-07-26 | 2019-12-17 | 2020-03-06 | 2020-03-24 | 2021-08-05 | -499 | 56 | -209
| LNG | Oakville | GTM Contactors Membranes & Installation | 3M | 4500335884 | Fabrication | Non-Metal Equipment | CAD | 38720 | USD | 33778 | 4942 | Supplier Competitions / Negotiation | 2019-08-14 | 2019-09-25 | 2019-01-04 | 2019-08-29 | 2019-07-19 | 2019-09-25 | 2019-09-13 | 2019-09-27 | 2020-05-08 | 2020-05-22 | 2020-06-15 | -24 | 12 | 2
| LNG | Oakville | RO Housings | PENTAIR FILTRATION SOLUTIONS, LLC | 4500343505 | Fabrication | Carbon Steel | CAD | 12172 | USD | 15152 | -2980 | Single Sourced | 2019-11-09 | 2019-12-24 | 2019-07-02 | 2019-11-29 | 2019-08-15 | 2019-12-24 | 2019-12-14 | 2019-10-03 | 2020-03-06 | 2020-02-14 | 2020-06-17 | -124 | 12 | -82
| LNG | Oakville | Strainer | BOLL FILTER CORPORATION | 4500348868 | Flow Control | Filters And Strainers (Incl Housings) | CAD | 149228 | USD | 206514 | -57286 | Estimate Without Market Reference(No Quote) | 2019-08-16 | 2020-01-19 | 2019-08-22 | 2019-08-16 | 2020-01-19 | 2020-01-19 | 2019-08-16 | 2019-11-19 | 2020-03-06 | 2020-04-20 | 2020-06-24 | -65 | 12 | -61
| LNG | Oakville | Temporary Strainers | SURE FLOW EQUIPMENT INC. | 4500368607 | Flow Control | Filters And Strainers (Incl Housings) | CAD | 10509 | CAD | 7677 | 2832 | Design Optimizations | 2020-01-10 | 2020-01-13 | 2020-01-31 | 2019-08-16 | 2020-03-08 | 2020-01-13 | 2019-08-16 | 2020-03-11 | 2020-03-06 | 2020-03-11 | 2020-06-11 | -92 | 12 | 58
| LNG | Oakville | UV System | Aquafine | 4500342681 | Flow Control | Other | CAD | 84191 | USD | 87164 | -2973 | Specs / Requirements Misinterpreted in Proposal | 2019-07-07 | 2019-11-28 | 2019-07-26 | 2019-07-22 | 2019-08-01 | 2019-11-28 | 2019-08-06 | 2019-10-02 | 2020-03-06 | 2019-12-11 | 2020-04-20 | -131 | 18 | -57
| LNG | Oakville | Cartridge Filter | FIL-TREK CORPORATION | 4500346288 | Fabrication | Carbon Steel | CAD | 11356 | CAD | 21706 | -10350 | Single Sourced | 2019-10-20 | 2020-03-02 | 2019-07-26 | 2019-11-09 | 2019-08-13 | 2020-03-02 | 2019-11-29 | 2019-10-18 | 2020-03-06 | 2020-02-21 | 2020-10-08 | -230 | 24 | -136
| LNG | Oakville | Centrifugal Pumps (RW/DEMIN/POT/WW) | FLOWSERVE INC. | 4500343876 | Rotating Equipment | Centrifugal Pumps | CAD | 1059129 | USD | 770902 | 288227 | Supplier Competitions / Negotiation | 2019-07-31 | 2020-01-01 | 2019-08-07 | 2019-08-15 | 2019-09-26 | 2020-01-01 | 2019-08-30 | 2019-10-11 | 2020-03-13 | 2020-05-05 | 2020-06-03 | -29 | 18 | -82
| LNG | Oakville | Vacuum Pump | Busch Vacuum Technics Inc. | 4500351664 | Rotating Equipment | Others | CAD | 25007 | CAD | 23555 | 1452 | Design Optimizations | 2019-07-03 | 2020-02-25 | 2019-07-12 | 2019-07-18 | 2019-07-21 | 2020-02-25 | 2019-08-02 | 2019-11-21 | 2020-03-06 | 2020-06-05 | 2020-10-19 | -136 | 18 | -96
| LNG | Oakville | Static Mixer | BISAN TRADING AND INDUSTRIAL | 4500361592 | Flow Control | Static Mixer | CAD | 60838 | CAD | 75886 | -15048 | Market Impact | 2019-09-20 | 2020-02-23 | 2019-11-22 | 2019-10-11 | 2020-01-26 | 2020-02-23 | 2019-11-01 | 2020-01-28 | 2020-03-06 | 2020-04-07 | 2020-07-28 | -112 | 36 | -26
| LNG | Oakville | Top Entry Mixer | PROCESS & STEAM SPECIALTIES | 4500374659 | Rotating Equipment | Mixers | CAD | 87291 | USD | 292794 | -205503 | Not included in Proposal / RFQ | 2019-09-20 | 2020-07-19 | 2020-04-30 | 2019-10-11 | 2020-04-17 | 2020-07-19 | 2019-11-01 | 2020-04-27 | 2020-03-06 | 2020-12-16 | 2021-05-19 | -154 | 18 | -83
| LNG | Oakville | Heaters | Wattco Inc | 4500352179 | Rotating Equipment | Heat Exchangers | CAD | 147270 | CAD | 175683 | -28413 | Specs / Requirements Misinterpreted in Proposal | 2019-08-16 | 2020-03-01 | 2019-09-05 | 2019-09-06 | 2019-11-09 | 2020-03-01 | 2019-10-04 | 2019-11-27 | 2020-03-06 | 2020-01-08 | 2020-09-16 | -252 | 12 | -95
| LNG | Oakville | Blowers | AERZEN CANADA INC. | 4500344685 | Rotating Equipment | Blowers & Fans | CAD | 378458 | CAD | 214000 | 164458 | Design Optimizations | 2019-08-03 | 2020-02-18 | 2019-08-30 | 2019-08-24 | 2019-09-24 | 2020-02-18 | 2019-09-14 | 2019-11-15 | 2020-03-06 | 2020-03-27 | 2020-09-04 | -161 | 18 | -95
| LNG | Oakville | Filter Press | EVOQUA WATER TECHNOLOGIES, LLC | 4500343151 | Rotating Equipment | Filter Press | CAD | 781350 | CAD | 1014466 | -233116 | Estimate Without Market Reference(No Quote) | 2019-06-21 | 2020-04-15 | 2019-07-22 | 2019-07-26 | 2019-09-06 | 2020-04-15 | 2019-08-09 | 2019-09-24 | 2020-07-17 | 2020-04-21 | 2021-02-09 | -294 | 36 | -204
| LNG | Oakville | Junction Box | SILVA ELECTRIC | 4500376463 | Electrical & Instrumentation | Ele-nclosures | CAD | 155302 | CAD | 282414 | -127112 | Not included in Proposal / RFQ | 2019-11-29 | 2020-05-21 | 2020-05-14 | 2019-12-20 | 2020-04-29 | 2020-05-21 | 2020-01-24 | 2020-05-14 | 2020-03-06 | 2020-06-25 | 2020-11-11 | -139 | 12 | -7
| LNG | Oakville | Instrument - Flow Transmitter | Emerson Japan | 4500360689 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | CAD | 78116 | USD | 78094 | 22 | Frame Agreements | 2019-08-17 | 2019-10-17 | 2019-10-17 | 2019-09-07 | 2020-01-21 | 2020-03-12 | 2019-09-28 | 2020-02-04 | 2020-03-06 | 2020-10-07 | 2020-09-17 | 20 | 48 | 110
| LNG | Oakville | Instrument - Temp Transmitter | Emerson Japan | 4500371803 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | CAD | 625152 | USD | 365995 | 259157 | Supplier Competitions / Negotiation | 2019-08-17 | 2020-03-31 | 2020-04-02 | 2019-09-07 | 2020-03-26 | 2020-03-29 | 2019-09-28 | 2020-03-30 | 2020-03-06 | 2020-11-09 | 2020-09-17 | 53 | 48 | -1
| LNG | Oakville | Instrument - Flow Transmitter | Emerson Japan | 4500371816 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | CAD | 32000 | USD | 36234 | -4234 | Single Sourced | 2020-07-20 | 2020-04-02 | 2020-04-02 | 2020-07-20 | 2020-03-30 | 2020-07-20 | 2020-07-20 | 2020-04-05 | 2020-07-20 | 2020-11-10 | 2020-09-17 | 54 | 48 | 3
| LNG | Oakville | Instrument - Thermal Mass Flow Meter & BV | CONVAL PROCESS SOLUTIONS INC | 4500430298 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | CAD | 17660 | USD | 17655 | 5 | Design Optimizations | 2021-06-15 | 2021-06-15 | 2021-02-02 | 2021-06-15 | 2021-06-11 | 2021-06-15 | 2021-06-15 | 2021-06-11 | 2021-06-15 | 2021-09-17 | 2021-10-26 | -39 | 18 | -4
| LNG | Oakville | Instrument - Turbidity | ENDRESS & HAUSER | 4500381050 | Electrical & Instrumentation | Inst-Analytical Instruments | CAD | 39651 | USD | 118813 | -79162 | Proposed Supplier Incapable Of Executing | 2019-08-17 | 2019-10-09 | 2019-10-09 | 2019-09-07 | 2020-04-11 | 2020-02-27 | 2019-09-28 | 2020-06-19 | 2020-03-06 | 2020-06-19 | 2020-09-09 | -82 | 24 | 254
| LNG | Oakville | Skid Frames - Fabrication | CLARK MACHINE INC. | 4500354481 | Fabrication | Carbon Steel | CAD | 458662 | CAD | 817039 | -358377 | Estimate Without Market Reference(No Quote) | 2019-10-18 | 2019-10-30 | 2019-10-30 | 2019-11-08 | 2019-12-13 | 2020-05-17 | 2019-11-29 | 2019-12-13 | 2020-03-06 | 2020-03-06 | 2020-12-15 | -284 | 24 | 44
| LNG | Oakville | Platform - CWB Registartion/Certification | SHANGHAI HILTON INTERNATIONAL TRADE CO LTD | 4500371819 | Fabrication | Carbon Steel | CAD | 53246 | USD | 53246 | 0 | Market Impact | 2019-06-28 | 2020-01-05 | 2020-01-05 | 2019-10-25 | 2020-06-22 | 2020-06-22 | 2019-09-08 | 2020-04-06 | 2020-07-17 | 2020-04-06 | 2021-06-18 | -438 | 12 | 92
| LNG | Oakville | Platform - Fabrication & Paint | SHANGHAI HILTON INTERNATIONAL TRADE CO LTD | 4500384447 | Fabrication | Carbon Steel | CAD | 12411 | USD | 175038 | -162627 | Estimate Without Market Reference(No Quote) | 2020-12-30 | 2020-07-15 | 2020-07-16 | 2020-12-30 | 2020-07-13 | 2020-12-30 | 2020-12-30 | 2020-07-14 | 2020-12-30 | 2020-07-14 | 2021-06-18 | -339 | 18 | -1
| LNG | Oakville | Valves - Butterfly/Plug | LAKESIDE PROCESS CONTROLS LTD. | 4500354963 | Flow Control | Other | CAD | 420251 | USD | 927841 | -507590 | Size/ Weight/ Quantity Underestimated | 2019-07-13 | 2020-01-31 | 2019-10-12 | 2019-09-06 | 2019-11-12 | 2020-01-31 | 2019-10-18 | 2019-12-15 | 2020-03-06 | 2020-06-14 | 2020-08-21 | -68 | 24 | -47
| LNG | Oakville | Valves - Combo Air | Palmer Engineering Ltd. | 4500407708 | Flow Control | Air Emissions Control (Scrubbers, ESP) | CAD | 14263 | USD | 14259 | 4 | Frame Agreements | 2020-12-26 | 2020-12-26 | 2020-11-10 | 2020-12-26 | 2021-01-05 | 2020-12-26 | 2020-12-26 | 2021-01-06 | 2020-12-26 | 2021-02-03 | 2021-02-10 | -7 | 24 | 11
| LNG | Oakville | Valves - Ball | VIKING INSTRUMENT & CONTROL | 4500356778 | Flow Control | Metal Isolation Valves | CAD | 39284 | CAD | 61304 | -22020 | Market Impact | 2019-07-13 | 2019-12-11 | 2019-09-11 | 2019-09-06 | 2019-11-14 | 2019-12-11 | 2019-10-18 | 2019-12-17 | 2020-03-06 | 2020-01-28 | 2020-05-11 | -104 | 12 | 6
| LNG | Oakville | Solenoids | ASCO NUMATICS CANADA | 4500365940 | Flow Control | Metal Isolation Valves | CAD | 17212 | USD | 12322 | 4890 | Frame Agreements | 2019-07-13 | 2019-11-28 | 2020-01-25 | 2019-09-06 | 2020-02-04 | 2019-11-28 | 2019-10-18 | 2020-02-26 | 2020-03-06 | 2020-04-10 | 2020-04-14 | -4 | 12 | 90
| LNG | Oakville | Valves - Control | LAKESIDE PROCESS CONTROLS LTD. | 4500361289 | Flow Control | Ele-Control Panels | CAD | 14880 | USD | 162272 | -147392 | Estimate Without Market Reference(No Quote) | 2019-07-13 | 2020-01-21 | 2020-01-15 | 2019-09-06 | 2020-01-21 | 2020-01-21 | 2019-10-18 | 2020-01-26 | 2020-03-06 | 2020-04-26 | 2020-08-01 | -97 | 24 | 5
| LNG | Oakville | Valves - Back Pressure | GRIFFCO VALVE INC | 4500359776 | Flow Control | Metal Isolation Valves | CAD | 8841 | USD | 19395 | -10554 | Single Sourced | 2019-07-13 | 2019-12-22 | 2019-09-10 | 2019-09-06 | 2020-01-21 | 2019-12-22 | 2019-10-18 | 2020-01-25 | 2020-03-06 | 2020-02-22 | 2020-06-01 | -100 | 36 | 34
| LNG | Oakville | Valves - Globe | SYLVAN AUTOMATION LTD | 4500355008 | Flow Control | Metal Isolation Valves | CAD | 13476 | CAD | 122181 | -108705 | Not included in Proposal / RFQ | 2019-07-13 | 2020-02-21 | 2019-10-04 | 2019-09-06 | 2019-11-14 | 2020-02-21 | 2019-10-18 | 2019-12-16 | 2020-03-06 | 2020-04-20 | 2020-10-01 | -164 | 18 | -67
| LNG | Oakville | Valves - TRV | LAKESIDE PROCESS CONTROLS LTD. | 4500393303 | Flow Control | Metal Isolation Valves | CAD | 9392 | USD | 7492 | 1900 | Design Optimizations | 2020-09-07 | 2020-09-07 | 2020-06-15 | 2020-09-07 | 2020-09-17 | 2020-09-07 | 2020-09-07 | 2020-09-20 | 2020-09-07 | 2020-11-22 | 2020-12-01 | -9 | 24 | 13
| LNG | Oakville | Pressure Regulating Valve | LAKESIDE PROCESS CONTROLS LTD. | 4500413911 | Flow Control | Metal Isolation Valves | CAD | 6100 | USD | 6098 | 2 | Supplier Competitions / Negotiation | 2021-02-03 | 2021-02-03 | 2020-10-20 | 2021-02-03 | 2021-02-11 | 2021-02-03 | 2021-02-03 | 2021-02-11 | 2021-02-03 | 2021-05-20 | 2021-05-20 | 0 | 24 | 8
| LNG | Oakville | Valves - Pressure Safety | LAKESIDE PROCESS CONTROLS LTD. | 4500421917 | Flow Control | Metal Safety(relief) Valves | CAD | 8476 | USD | 8474 | 2 | Frame Agreements | 2021-01-27 | 2021-01-27 | 2020-08-12 | 2021-01-27 | 2021-04-07 | 2021-01-27 | 2021-01-27 | 2021-04-07 | 2021-01-27 | 2021-07-07 | 2021-07-14 | -7 | 24 | 70
| LNG | Oakville | Valves - Plug (Man) | SYLVAN AUTOMATION LTD | 4500407715 | Flow Control | Metal Isolation Valves | CAD | 42185 | CAD | 42185 | 0 | Size/ Weight/ Quantity Underestimated | 2021-01-29 | 2021-01-29 | 2020-11-30 | 2021-01-29 | 2021-01-05 | 2021-01-29 | 2021-01-29 | 2021-01-06 | 2021-01-29 | 2021-03-31 | 2021-03-24 | 7 | 18 | -23
| LNG | Oakville | Valves - Plug (Auto) | PROCESS & STEAM SPECIALTIES | 4500355869 | Flow Control | Metal Isolation Valves | CAD | 64617 | USD | 385714 | -321097 | Specs / Requirements Misinterpreted in Proposal | 2019-07-13 | 2020-02-14 | 2019-09-25 | 2019-09-06 | 2019-11-14 | 2020-02-14 | 2019-10-18 | 2020-01-07 | 2020-03-06 | 2020-07-07 | 2020-09-18 | -73 | 18 | -38
| LNG | Oakville | Piping Spools | SHANGHAI HILTON INTERNATIONAL TRADE CO LTD | 4500355253 | Fabrication | Metal Isolation Valves | CAD | 327418 | USD | 501332 | -173914 | Not included in Proposal / RFQ | 2019-10-18 | 2020-02-19 | 2019-11-22 | 2019-11-08 | 2019-12-11 | 2020-02-19 | 2019-11-29 | 2019-12-11 | 2020-03-06 | 2020-01-08 | 2020-06-23 | -167 | 18 | -70
| LNG | Oakville | Piping Spools | SHANGHAI HILTON INTERNATIONAL TRADE CO LTD | 4500369130 | Fabrication | Metal Isolation Valves | CAD | 438230 | CAD | 217323 | 220907 | Supplier Competitions / Negotiation | 2020-07-22 | 2020-07-22 | 2020-03-16 | 2020-07-22 | 2019-12-10 | 2020-07-22 | 2020-07-22 | 2020-03-15 | 2020-07-22 | 2020-03-15 | 2021-03-04 | -354 | 18 | -129
| LNG | Oakville | Piping Spools | FIL-TREK CORPORATION | 4500368900 | Fabrication | Metal Isolation Valves | CAD | 148149 | CAD | 465313 | -317164 | Estimate Without Market Reference(No Quote) | 2020-07-28 | 2020-07-28 | 2020-02-12 | 2020-07-28 | 2019-11-24 | 2020-07-28 | 2020-07-28 | 2020-03-08 | 2020-07-28 | 2020-03-08 | 2021-04-01 | -389 | 36 | -142
| LNG | Oakville | Piping Spools | FIL-TREK CORPORATION | 4500374519 | Fabrication | Metal Isolation Valves | CAD | 24642 | CAD | 155623 | -130981 | Single Sourced | 2020-09-19 | 2020-09-19 | 2020-04-22 | 2020-09-19 | 2020-04-26 | 2020-09-19 | 2020-09-19 | 2020-04-26 | 2020-09-19 | 2020-04-26 | 2021-02-17 | -297 | 36 | -146
| LNG | Oakville | Piping Spools - PVC/CPVC | BETA PLASTICS INC | 4500393365 | Fabrication | Carbon Steel | CAD | 140000 | CAD | 184464 | -44464 | Proposed Supplier Incapable Of Executing | 2020-10-07 | 2020-10-07 | 2020-07-31 | 2020-10-07 | 2020-08-04 | 2020-10-07 | 2020-10-07 | 2020-09-21 | 2020-10-07 | 2020-11-27 | 2020-12-14 | -17 | 18 | -16
| LNG | Oakville | Electrical Bulk - Fittings | PINACLE STAINLESS STEEL INC. | 4500388314 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 17000 | CAD | 51167 | -34167 | Not included in Proposal / RFQ | 2020-08-26 | 2020-08-11 | 2020-08-14 | 2020-08-26 | 2020-07-21 | 2020-08-26 | 2020-08-26 | 2020-08-11 | 2020-08-26 | 2020-08-18 | 2020-10-01 | -44 | 18 | 0
| LNG | Oakville | Electrical Bulk - Connectors | Texcan | 4500384440 | Electrical & Instrumentation | Ele-Electrical Others | CAD | 8128 | CAD | 71323 | -63195 | Estimate Without Market Reference(No Quote) | 2020-08-11 | 2020-08-11 | 2020-07-16 | 2020-08-11 | 2020-07-07 | 2020-08-11 | 2020-08-11 | 2020-07-14 | 2020-08-11 | 2020-08-25 | 2020-09-15 | -21 | 24 | -28
| LNG | Oakville | Desadeg Progressive Cavity Pumps | NETZSCH CANADA INC. | 4500363466 | Rotating Equipment | Centrifugal Pumps | CAD | 324827 | CAD | 257000 | 67827 | Frame Agreements | 2019-10-04 | 2020-05-02 | 2019-09-18 | 2019-10-25 | 2020-01-27 | 2020-05-02 | 2019-11-15 | 2020-01-27 | 2020-03-06 | 2020-07-27 | 2020-12-16 | -142 | 56 | -96
| LNG | Oakville | Tank - CS - Internals (Clarifier & Densadeg Internals - install onsite) | SHANGHAI HILTON INTERNATIONAL TRADE CO LTD | 4500391812 | Fabrication | Ele-Control Panels | CAD | 25820 | USD | 107840 | -82020 | Estimate Without Market Reference(No Quote) | 2019-11-01 | 2020-08-24 | 2020-09-02 | 2019-11-22 | 2020-09-11 | 2020-08-24 | 2019-12-13 | 2020-09-11 | 2020-03-06 | 2020-10-25 | 2021-06-18 | -236 | 18 | 18
| LNG | Oakville | Clarifier Drives | DBS MANUFACTURING INC. | 4500378899 | Rotating Equipment | Metal Isolation Valves | CAD | 26403 | USD | 55942 | -29539 | Single Sourced | 2019-09-20 | 2020-03-21 | 2020-05-21 | 2019-10-11 | 2020-06-04 | 2020-03-21 | 2019-11-01 | 2020-06-14 | 2020-03-06 | 2020-06-14 | 2020-09-21 | -99 | 18 | 85
| LNG | Oakville | AOD Pumps | York Hydraulics | 4500366393 | Rotating Equipment | Centrifugal Pumps | CAD | 40019 | CAD | 14174 | 25845 | Frame Agreements | 2019-09-20 | 2020-01-30 | 2019-09-24 | 2019-10-11 | 2020-01-29 | 2020-01-30 | 2019-11-01 | 2020-02-26 | 2020-03-06 | 2020-05-22 | 2020-06-11 | -20 | 60 | 27
| LNG | Oakville | Air Compressor | INGERSOLL-RAND CO | 4500369614 | Rotating Equipment | Compressors | CAD | 115796 | CAD | 94059 | 21737 | Supplier Competitions / Negotiation | 2019-08-03 | 2020-01-03 | 2020-02-28 | 2019-08-24 | 2020-01-02 | 2020-01-03 | 2019-09-14 | 2020-03-17 | 2020-03-06 | 2020-03-17 | 2020-06-05 | -80 | 18 | 74
| Broward County, FL - WWAM | Richmond | COPRESSORS | GARDNER DENVER NASH LLC | 4500364419 | Rotating Equipment | Carbon Steel | USD | 1915284 | USD | 1027793 | 887491 | Frame Agreements | 2020-02-11 | 2020-04-28 | 2020-02-13 | 2020-02-25 | 2020-02-12 | 2020-04-28 | 2020-03-17 | 2020-02-12 | 2020-07-15 | 2020-06-03 | 2020-06-24 | -21 | 30 | -76
| Broward County, FL - WWAM | Richmond | MIXER TUBES | POSEIDON, INC | 4503759001 | Fabrication | Metal Isolation Valves | USD | 405313 | USD | 556974 | -151661 | Specs / Requirements Misinterpreted in Proposal | 2020-04-26 | 2020-06-11 | 2020-05-07 | 2020-05-03 | 2020-05-07 | 2020-06-11 | 2020-05-06 | 2020-05-12 | 2020-07-15 | 2020-07-28 | 2020-07-21 | 7 | 12 | -30
| Broward County, FL - WWAM | Richmond | ISOLATION VALVES | AC CONTROLS INC. | 4500375900 | Flow Control | Metal Isolation Valves | USD | 12213 | USD | 5040 | 7173 | Supplier Competitions / Negotiation | 2020-05-12 | 2020-06-06 | 2020-04-29 | 2020-05-26 | 2020-05-12 | 2020-06-06 | 2020-06-09 | 2020-05-12 | 2020-07-15 | 2020-06-09 | 2020-06-27 | -18 | 12 | -25
| Broward County, FL - WWAM | Richmond | GLOBE VALVE | HAJOCA CORP | 4503732801 | Flow Control | Metal Isolation Valves | USD | 71444 | USD | 55604 | 15840 | Supplier Competitions / Negotiation | 2020-05-12 | 2020-05-31 | 2020-04-17 | 2020-05-26 | 2020-04-17 | 2020-05-31 | 2020-06-09 | 2020-05-31 | 2020-07-15 | 2020-06-19 | 2020-07-02 | -13 | 12 | 0
| Broward County, FL - WWAM | Richmond | FLOW METER | BROOKS AUTOMATION | 4500375395 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 135060 | USD | 90960 | 44100 | Frame Agreements | 2020-05-12 | 2020-06-10 | 2020-05-07 | 2020-05-26 | 2020-05-06 | 2020-06-10 | 2020-06-09 | 2020-05-06 | 2020-07-15 | 2020-06-17 | 2020-07-01 | -14 | 18 | -35
| Broward County, FL - WWAM | Richmond | GLYCERIN FILLED PRESSURE GAUGE | AC CONTROLS INC. | 450374529 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 38772 | USD | 17460 | 21312 | Supplier Competitions / Negotiation | 2020-05-12 | 2020-06-06 | 2020-04-29 | 2020-05-26 | 2020-06-02 | 2020-06-06 | 2020-06-09 | 2020-06-06 | 2020-07-15 | 2020-06-02 | 2020-06-23 | -21 | 18 | 0
| Broward County, FL - WWAM | Richmond | GAS MANIFOLD ASSEMBL | SHARP IRON GROUP | 4500374884 | Electrical & Instrumentation | Carbon Steel | USD | 229005 | USD | 128005 | 101000 | Frame Agreements | 2020-04-26 | 2020-06-05 | 2020-05-05 | 2020-05-03 | 2020-05-05 | 2020-06-05 | 2020-05-06 | 2020-06-05 | 2020-07-15 | 2020-06-05 | 2020-06-25 | -20 | 18 | 0
| Annacis Island - WWTP | Richmond | Climber Screen, Model 3AS, ALL 316SS | RICHLAND LLC | 4503391765 | Fabrication | Carbon Steel | USD | 133526 | USD | 198805 | -65279 | Estimate Without Market Reference(No Quote) | 2020-04-01 | 2020-06-03 | 2020-04-04 | 2020-04-13 | 2020-05-08 | 2020-06-03 | 2020-04-17 | 2020-04-15 | 2020-07-10 | 2020-08-05 | 2020-07-23 | 13 | 12 | -49
| Annacis Island - WWTP | Richmond | Main Control Panel, Local, NEMA 4X, ALL 316SS | REVERE CONTROLS | 450339072 | Electrical & Instrumentation | Ele-Control Panels | USD | 15485 | USD | 21081 | -5596 | Specs / Requirements Misinterpreted in Proposal | 2020-04-10 | 2020-05-22 | 2020-04-07 | 2020-04-23 | 2020-05-22 | 2020-05-22 | 2020-04-30 | 2020-04-14 | 2020-06-26 | 2020-07-07 | 2020-07-01 | 6 | 18 | -38
| Annacis Island - WWTP | Richmond | Sub. Motor Enclosure, ALL 316SS | HALL INDUSTRIES (ELLWOOD CITY) | 4503391803 | Electrical & Instrumentation | Ele-Control Panels | USD | 7233 | USD | 15935 | -8702 | Specs / Requirements Misinterpreted in Proposal | 2020-04-20 | 2020-06-05 | 2020-04-11 | 2020-04-30 | 2020-06-05 | 2020-06-05 | 2020-05-04 | 2020-04-14 | 2020-07-30 | 2020-06-23 | 2020-07-11 | -18 | 18 | -52
| Sha Tin Water Treatment Works | Leonia | Inductors | SINTERMETALLE PROMETHEUS | 4500441448 | Electrical & Instrumentation | Ele-Transformers, Power Supplies | CAD | 20496 | EUR | 20496 | 0 | Size/ Weight/ Quantity Underestimated | 2022-01-07 | 2022-01-27 | 2021-09-15 | 2022-01-14 | 2022-01-27 | 2022-01-27 | 2022-01-21 | 2021-09-15 | 2022-06-10 | 2021-09-15 | 2022-01-27 | -134 | 18 | -134
| Sha Tin Water Treatment Works | Leonia | Transformers | BCV Technologies | 4500441456 | Electrical & Instrumentation | Ele-Transformers, Power Supplies | CAD | 40988 | EUR | 40988 | 0 | Size/ Weight/ Quantity Underestimated | 2022-01-07 | 2022-01-27 | 2021-09-15 | 2022-01-14 | 2022-01-27 | 2022-01-27 | 2022-01-21 | 2021-09-15 | 2022-06-10 | 2022-01-11 | 2022-03-27 | -75 | 18 | -134
510014 | Blue Sky Biotreatment | Bellevue | Control Panels (MCP) | KELTOUR CONTROLS INC. | 4504084797 | Electrical & Instrumentation | Ele-Control Panels | USD | 50000 | CAD | 37648 | 12352 | Supplier Competitions / Negotiation | 2023-03-01 | 2023-09-08 | 2023-09-28 | 2023-03-29 | 2023-09-18 | 2023-08-04 | 2023-04-05 | 2023-10-16 | 2023-09-27 | 2024-01-08 | 2023-11-17 | 52 | 24 | 38
510014 | Blue Sky Biotreatment | Guelph | Control Panels (RIO Panel) | ENGINEERING ELECTRIC CONTROLS | 4504087199 | Electrical & Instrumentation | Ele-Control Panels | USD | 135000 | CAD | 113842 | 21158 | Single Sourced | 2023-03-01 | 2023-07-20 | 2023-08-28 | 2023-03-29 | 2023-08-29 | 2023-07-23 | 2023-04-05 | 2023-10-19 | 2023-09-27 | 2023-12-14 | 2023-12-08 | 6 | 18 | 91
510014 | Blue Sky Biotreatment | Bellevue | HMI + Software | Wonderware Canada | 4504068420 | Electrical & Instrumentation | Ele-Control Panels | USD | 20000 | CAD | 10660 | 9340 | Single Sourced | 2023-03-01 | 2023-07-07 | 2023-07-28 | 2023-03-29 | 2023-07-31 | 2023-07-07 | 2023-04-05 | 2023-09-18 | 2023-09-27 | 2023-11-13 | 2023-10-20 | 24 | 18 | 73
510014 | Blue Sky Biotreatment | Bellevue | E-Stop | INTEGRATED SYSTEMS GROUP | 4504071099 | Electrical & Instrumentation | Ele-Control Panels | USD | 32550 | USD | 51556 | -19006 | Size/ Weight/ Quantity Underestimated | 2023-03-01 | 2023-09-08 | 2023-09-27 | 2023-03-29 | 2023-09-12 | 2023-07-31 | 2023-04-05 | 2023-09-24 | 2023-09-27 | 2023-12-31 | 2023-11-13 | 48 | 18 | 16
510014 | Blue Sky Biotreatment | Oakville | Control System / PLC Components | Gerrie Electric | 4503979138 | Electrical & Instrumentation | Ele-Industrial Controls | USD | 385660 | CAD | 207737 | 177923 | Single Sourced | 2023-03-01 | 2023-02-24 | 2023-04-21 | 2023-03-29 | 2023-04-19 | 2023-04-16 | 2023-04-05 | 2023-04-16 | 2023-11-08 | 2023-04-16 | 2023-07-28 | -103 | 12 | 51
510014 | Blue Sky Biotreatment | Bellevue | VFD's | ENGINEERING ELECTRIC CONTROLS | 4504025919 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 41339 | CAD | 88167 | -46828 | Size/ Weight/ Quantity Underestimated | 2023-03-03 | 2023-04-17 | 2023-06-27 | 2023-02-17 | 2023-06-27 | 2023-06-30 | 2023-02-24 | 2023-07-06 | 2023-10-13 | 2023-12-14 | 2023-11-13 | 31 | 24 | 80
510014 | Blue Sky Biotreatment | Guelph | Frames | 3D MECHANICAL | 4504019610 | Fabrication | Skid Assembly Outsourced | USD | 269993 | CAD | 60690 | 209303 | Supplier Competitions / Negotiation | 2023-04-14 | 2023-05-09 | 2023-05-26 | 2023-05-12 | 2023-06-04 | 2023-06-26 | 2023-05-19 | 2023-06-25 | 2023-10-13 | 2023-09-03 | 2023-10-27 | -54 | 12 | 47
510014 | Blue Sky Biotreatment | Bellevue | FRP Tank | DIAMOND FIBERGLASS | 4504014091 | Flow Control | Plastic Tanks | USD | 41160 | USD | 68840 | -27680 | Design Optimizations | 2023-03-31 | 2023-03-23 | 2023-06-05 | 2023-04-28 | 2023-05-30 | 2023-06-15 | 2023-05-05 | 2023-06-16 | 2023-10-13 | 2023-12-15 | 2023-12-07 | 8 | 36 | 85
510014 | Blue Sky Biotreatment | Bellevue | Hanger & Support | 3D MECHANICAL | 4504035628 | Fabrication | Platform & Module | USD | 498132 | CAD | 192666 | 305466 | Supplier Competitions / Negotiation | 2023-04-14 | 2023-05-09 | 2023-07-12 | 2023-05-12 | 2023-07-10 | 2023-07-25 | 2023-05-19 | 2023-07-23 | 2023-10-13 | 2023-11-05 | 2023-10-24 | 12 | 12 | 75
510014 | Blue Sky Biotreatment | Bellevue | Platforms Walkways and Ladders | 3D MECHANICAL | 4504019621 | Fabrication | Platform & Module | USD | 251295 | CAD | 180371 | 70924 | Supplier Competitions / Negotiation | 2023-06-01 | 2023-05-09 | 2023-06-19 | 2023-06-29 | 2023-06-03 | 2023-06-26 | 2023-07-06 | 2023-06-25 | 2023-11-30 | 2023-10-22 | 2023-12-11 | -50 | 12 | 47
510014 | Blue Sky Biotreatment | Bellevue | Air Diffuser | ENVIRONMENTAL DYNAMICS INTERNATIONAL | 4503990496 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 486098 | USD | 695800 | -209702 | Specs / Requirements Misinterpreted in Proposal | 2023-01-27 | 2023-01-27 | 2023-04-26 | 2023-02-24 | 2023-04-04 | 2023-05-05 | 2023-03-03 | 2023-05-08 | 2023-06-30 | 2023-09-25 | 2023-12-18 | -84 | 36 | 101
510014 | Blue Sky Biotreatment | Oakville | Pressure Gauge | CONVAL PROCESS SOLUTIONS | 4504055917 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 20000 | USD | 13016 | 6984 | Single Sourced | 2023-06-30 | 2023-07-14 | 2023-07-17 | 2023-07-28 | 2023-08-17 | 2023-08-30 | 2023-08-04 | 2023-08-28 | 2023-10-13 | 2023-10-30 | 2023-10-21 | 9 | 18 | 45
510014 | Blue Sky Biotreatment | Leonia | Pressure Gauge | CONVAL PROCESS SOLUTIONS | 4504055924 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 50000 | USD | 46906 | 3094 | Single Sourced | 2023-06-30 | 2023-07-14 | 2023-08-08 | 2023-07-28 | 2023-08-21 | 2023-09-02 | 2023-08-04 | 2023-08-28 | 2023-10-13 | 2023-11-06 | 2023-10-25 | 12 | 18 | 45
510014 | Blue Sky Biotreatment | Leonia | Flow Switch | EVEREST AUTOMATION INC. | 4504054341 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 7930 | USD | 22116 | -14186 | Single Sourced | 2023-06-30 | 2023-06-26 | 2023-06-26 | 2023-07-28 | 2023-08-08 | 2023-10-18 | 2023-08-04 | 2023-08-25 | 2023-10-13 | 2024-02-09 | 2023-12-11 | 60 | 18 | 60
510014 | Blue Sky Biotreatment | Leonia | Tank Level Switch | XYLEM CANADA COMPANY | 4504084801 | Electrical & Instrumentation | Inst-Level (Inst. & Switches) | USD | 36360 | CAD | 7511 | 28849 | Single Sourced | 2023-07-21 | 2023-07-14 | 2023-09-18 | 2023-08-18 | 2023-09-18 | 2023-09-13 | 2023-08-25 | 2023-10-17 | 2023-10-13 | 2023-11-14 | 2023-10-29 | 16 | 18 | 95
510014 | Blue Sky Biotreatment | Leonia | Analyzers | ENDRESS & HAUSER MN | 4504067831 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 514124 | USD | 89086 | 425038 | Frame Agreements | 2023-05-12 | 2023-05-09 | 2023-09-15 | 2023-06-09 | 2023-09-14 | 2023-08-18 | 2023-06-16 | 2023-09-19 | 2023-10-13 | 2023-11-28 | 2023-11-05 | 23 | 18 | 133
510014 | Blue Sky Biotreatment | Guelph | Analyzers - Turbidity Meter | Hach Company | 4504051609 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 26214 | USD | 95266 | -69052 | Frame Agreements | 2023-05-12 | 2023-05-07 | 2023-07-21 | 2023-06-09 | 2023-07-23 | 2023-07-29 | 2023-06-16 | 2023-08-25 | 2023-10-13 | 2023-10-20 | 2023-10-16 | 4 | 18 | 110
510014 | Blue Sky Biotreatment | Leonia | Instrumentaion (FT) | ENDRESS & HAUSER MN | 4504054476 | Electrical & Instrumentation | Inst-Multiparam Transmitters, Controllers | USD | 119057 | USD | 107976 | 11081 | Frame Agreements | 2023-05-12 | 2023-05-31 | 2023-07-28 | 2023-06-09 | 2023-06-12 | 2023-08-21 | 2023-06-16 | 2023-08-25 | 2023-10-13 | 2023-12-01 | 2023-11-06 | 25 | 18 | 86
510014 | Blue Sky Biotreatment | Leonia | Instrumentaion (PT) | ENDRESS & HAUSER MN | 4504076480 | Electrical & Instrumentation | Inst-Multiparam Transmitters, Controllers | USD | 62634 | USD | 7401 | 55233 | Frame Agreements | 2023-05-12 | 2023-05-31 | 2023-09-19 | 2023-06-09 | 2023-09-18 | 2023-07-30 | 2023-06-16 | 2023-10-03 | 2023-10-13 | 2023-10-17 | 2023-10-15 | 2 | 18 | 125
510014 | Blue Sky Biotreatment | Leonia | Instrumentaion (LT) | ENDRESS & HAUSER MN | 4504056168 | Electrical & Instrumentation | Inst-Multiparam Transmitters, Controllers | USD | 34615 | USD | 26296 | 8319 | Frame Agreements | 2023-05-12 | 2023-05-31 | 2023-08-23 | 2023-06-09 | 2023-08-22 | 2023-07-28 | 2023-06-16 | 2023-08-29 | 2023-10-13 | 2023-10-03 | 2023-10-08 | -5 | 18 | 90
510014 | Blue Sky Biotreatment | Leonia | Instrumentaion (TT) | ENDRESS & HAUSER MN | 4504076466 | Electrical & Instrumentation | Inst-Multiparam Transmitters, Controllers | USD | 21673 | USD | 6504 | 15169 | Frame Agreements | 2023-05-12 | 2023-05-31 | 2023-09-19 | 2023-06-09 | 2023-09-19 | 2023-08-13 | 2023-06-16 | 2023-10-03 | 2023-10-13 | 2023-11-14 | 2023-10-29 | 16 | 18 | 125
510014 | Blue Sky Biotreatment | Guelph | Instrumentaion (FT) | ENDRESS & HAUSER MN | 4504044834 | Electrical & Instrumentation | Inst-Multiparam Transmitters, Controllers | USD | 17435 | USD | 21450 | -4015 | Frame Agreements | 2023-05-12 | 2023-05-31 | 2023-07-28 | 2023-06-09 | 2023-06-14 | 2023-08-23 | 2023-06-16 | 2023-08-08 | 2023-10-13 | 2023-09-19 | 2023-12-05 | -77 | 18 | 69
510014 | Blue Sky Biotreatment | Bellevue | Piping - SS | PANDA PIPING LTD | 4504040533 | Fabrication | Stainless Steel | USD | 159602 | CAD | 104743 | 54859 | Supplier Competitions / Negotiation | 2023-04-14 | 2023-05-10 | 2023-07-18 | 2023-05-12 | 2023-06-04 | 2023-08-01 | 2023-05-19 | 2023-08-01 | 2023-10-13 | 2023-10-10 | 2023-11-20 | -41 | 12 | 83
510014 | Blue Sky Biotreatment | Guelph | Piping - SS | PANDA PIPING LTD | 4504040519 | Fabrication | Stainless Steel | USD | 106401 | CAD | 54360 | 52041 | Supplier Competitions / Negotiation | 2023-04-14 | 2023-05-10 | 2023-07-18 | 2023-05-12 | 2023-06-04 | 2023-08-01 | 2023-05-19 | 2023-08-01 | 2023-10-13 | 2023-10-10 | 2023-11-01 | -22 | 12 | 83
510014 | Blue Sky Biotreatment | Leonia | Metallic Valves - Manual (Ball, BF, S.C Valves) | BRAY CONTROLS CANADA LTD | 4504044903 | Flow Control | Metal Isolation Valves | USD | 125460 | USD | 340258 | -214798 | Frame Agreements | 2023-05-12 | 2023-06-02 | 2023-06-28 | 2023-06-09 | 2023-07-17 | 2023-08-22 | 2023-06-16 | 2023-08-05 | 2023-10-13 | 2023-12-02 | 2023-11-07 | 25 | 12 | 64
510014 | Blue Sky Biotreatment | Guelph | Metallic Valves - Manual (Ball, BF, S.C Valves) | BRAY CONTROLS CANADA LTD | 4504044890 | Flow Control | Metal Isolation Valves | USD | 16528 | USD | 11887 | 4641 | Frame Agreements | 2023-05-12 | 2023-06-02 | 2023-06-28 | 2023-06-09 | 2023-07-19 | 2023-08-23 | 2023-06-16 | 2023-08-08 | 2023-10-13 | 2023-12-05 | 2023-11-02 | 33 | 36 | 67
510014 | Blue Sky Biotreatment | Leonia | Metallic Valves - Manual (Wafer Check Valve) | Duncan Co. | 4504071104 | Flow Control | Metal Isolation Valves | USD | 44569 | USD | 41320 | 3249 | Single Sourced | 2023-05-12 | 2023-04-03 | 2023-04-05 | 2023-06-09 | 2023-08-10 | 2023-07-20 | 2023-06-16 | 2023-09-25 | 2023-10-13 | 2023-11-06 | 2023-10-25 | 12 | 12 | 175
510014 | Blue Sky Biotreatment | Bellevue | Membrane Tank Cover | CST Covers | 4504047190 | Fabrication | Stainless Steel | USD | 196724 | USD | 375500 | -178776 | Specs / Requirements Misinterpreted in Proposal | 2023-03-31 | 2023-05-19 | 2023-08-01 | 2023-04-28 | 2023-06-29 | 2023-09-01 | 2023-05-05 | 2023-08-11 | 2023-11-10 | 2024-02-02 | 2023-12-22 | 42 | 12 | 84
510014 | Blue Sky Biotreatment | Bellevue | Plate Heat Exchanger | ALFA LAVAL | 4503990672 | Rotating Equipment | Heat Exchangers | USD | 115050 | USD | 102000 | 13050 | Supplier Competitions / Negotiation | 2023-03-23 | 2023-02-06 | 2023-03-13 | 2023-04-20 | 2023-03-23 | 2023-04-25 | 2023-04-27 | 2023-05-08 | 2023-11-30 | 2023-12-04 | 2023-12-02 | 2 | 36 | 91
510014 | Blue Sky Biotreatment | Bellevue | Blowers | AERZEN CANADA INC | 4503963108 | Rotating Equipment | Blowers & Fans | USD | 609050 | CAD | 544178 | 64872 | Frame Agreements | 2023-01-27 | 2023-03-08 | 2023-05-26 | 2023-02-21 | 2023-03-07 | 2023-03-13 | 2023-02-28 | 2023-03-16 | 2023-11-28 | 2023-12-07 | 2023-12-02 | 5 | 36 | 8
510014 | Blue Sky Biotreatment | Bellevue | Process Mixers | KSB Pumps Inc. | 4504005815 | Rotating Equipment | Mixers | USD | 905593 | USD | 199235 | 706358 | Supplier Competitions / Negotiation | 2023-02-10 | 2023-02-10 | 2023-04-13 | 2023-03-23 | 2023-05-16 | 2023-06-01 | 2023-03-30 | 2023-06-01 | 2023-10-19 | 2023-12-28 | 2023-11-23 | 35 | 36 | 111
510014 | Blue Sky Biotreatment | Bellevue | Centrifugal Pumps | SULZER PUMP SOLUTIONS - USA | 4503986464 | Rotating Equipment | Centrifugal Pumps | USD | 263229 | USD | 388551 | -125322 | Size/ Weight/ Quantity Underestimated | 2023-01-25 | 2023-02-03 | 2023-04-27 | 2023-02-22 | 2023-03-23 | 2023-04-28 | 2023-03-01 | 2023-04-30 | 2023-11-08 | 2023-10-29 | 2023-11-03 | -5 | 36 | 86
510014 | Blue Sky Biotreatment | Bellevue | Propeller Pumps | KSB Pumps Inc. | 4504005746 | Rotating Equipment | Centrifugal Pumps | USD | 424912 | USD | 253877 | 171035 | Single Sourced | 2023-02-08 | 2023-02-03 | 2023-05-24 | 2023-03-27 | 2023-05-25 | 2023-05-30 | 2023-04-03 | 2023-06-02 | 2023-10-23 | 2024-01-26 | 2023-12-09 | 48 | 36 | 119
510014 | Blue Sky Biotreatment | Guelph | Rotary Lobe Pumps | Boerger LLC | 4503971124 | Rotating Equipment | PD Pumps | USD | 411524 | USD | 279106 | 132418 | Supplier Competitions / Negotiation | 2023-02-16 | 2023-02-13 | 2023-03-28 | 2023-03-16 | 2023-03-19 | 2023-03-31 | 2023-03-23 | 2023-04-01 | 2023-10-12 | 2023-10-11 | 2023-12-05 | -55 | 24 | 47
510014 | Blue Sky Biotreatment | Guelph | Metallic Valves - On/OFF BF-CV | BRAY CONTROLS CANADA LTD | 4504033391 | Flow Control | Metal Isolation Valves | USD | 7754 | USD | 33114 | -25360 | Frame Agreements | 2023-05-12 | 2023-05-12 | 2023-07-13 | 2023-06-09 | 2023-06-13 | 2023-07-17 | 2023-06-16 | 2023-07-19 | 2023-10-13 | 2023-11-15 | 2023-11-02 | 13 | 36 | 68
510882 | 1PointFive DAC-1 RWTU | Oakville | Metallic Piping Spools | NV PIPING SYSTEMS INC. | 4504110075 | Fabrication | Platform & Module | USD | 409772 | CAD | 382841 | 26931 | Supplier Competitions / Negotiation | 2023-09-22 | 2023-09-25 | 2023-09-27 | 2023-10-19 | 2024-10-26 | 2023-11-30 | 2023-11-02 | 2023-11-29 | 2024-03-14 | 2024-03-27 | 2024-03-20 | 7 | 12 | 65
510882 | 1PointFive DAC-1 RWTU | Oakville | Non-Metallic Piping Spools | PRECISIONEERING | 4504177972 | Fabrication | Platform & Module | USD | 72813 | CAD | 410260 | -337447 | Specs / Requirements Misinterpreted in Proposal | 2023-09-22 | 2024-01-22 | 2024-03-07 | 2023-10-19 | 2024-03-11 | 2024-03-11 | 2023-11-02 | 2024-03-28 | 2024-03-14 | 2024-08-01 | 2024-05-23 | 70 | 12 | 66
510882 | 1PointFive DAC-1 RWTU | Oakville | Frames | LAKESIDE PROCESS CONTROLS LTD. | 4504114465 | Fabrication | Carbon Steel | USD | 374146 | USD | 404577 | -30431 | Market Impact | 2023-10-03 | 2023-10-13 | 2023-11-07 | 2023-08-30 | 2023-12-04 | 2023-12-04 | 2023-11-13 | 2023-12-08 | 2024-02-12 | 2023-12-08 | 2024-01-10 | -33 | 12 | 56
510882 | 1PointFive DAC-1 RWTU | Oakville | Soda Ash System | Con-V-Air | 4504046949 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 1941847 | USD | 912044 | 1029803 | Design Optimizations | 2023-05-26 | 2023-06-08 | 2023-06-29 | 2023-06-09 | 2023-08-13 | 2023-08-15 | 2023-08-23 | 2023-08-11 | 2024-07-02 | 2024-03-28 | 2024-05-15 | -48 | 30 | 64
510882 | 1PointFive DAC-1 RWTU | Oakville | DensaDeg - Fabrication incl platforms & ladders | SHARP IRON GROUP | 4504124334 | Fabrication | Carbon Steel | USD | 1587550 | USD | 1617125 | -29575 | Not included in Proposal / RFQ | 2023-10-10 | 2023-11-22 | 2023-12-11 | 2023-11-06 | 2023-12-19 | 2023-12-19 | 2023-11-20 | 2024-01-04 | 2024-08-05 | 2024-03-01 | 2024-05-18 | -78 | 12 | 43
510882 | 1PointFive DAC-1 RWTU | Oakville | MMF Vessel & Lining | ENPRO INDUSTRIES PVT LTD | 4504057923 | Fabrication | Carbon Steel | USD | 1072748 | USD | 718000 | 354748 | Frame Agreements | 2023-05-24 | 2023-05-24 | 2023-07-29 | 2023-09-01 | 2023-08-24 | 2023-08-29 | 2023-08-08 | 2023-09-01 | 2024-10-08 | 2024-01-29 | 2024-06-03 | -126 | 12 | 100
510882 | 1PointFive DAC-1 RWTU | Oakville | FRP Tank | DIAMOND FIBERGLASS | 4504103646 | Fabrication | Non-Metal Equipment | USD | 735893 | USD | 697105 | 38788 | Supplier Competitions / Negotiation | 2023-09-11 | 2023-09-12 | 2023-09-19 | 2023-10-09 | 2023-10-31 | 2023-10-27 | 2023-11-06 | 2023-11-15 | 2024-04-29 | 2024-05-31 | 2024-05-15 | 16 | 12 | 64
510882 | 1PointFive DAC-1 RWTU | Oakville | HCL Scrubber | PRECISIONEERING | 4504093839 | Fabrication | Non-Metal Equipment | USD | 28616 | CAD | 29054 | -438 | Proposed Supplier Incapable Of Executing | 2023-08-17 | 2023-08-18 | 2023-09-07 | 2023-10-06 | 2024-10-20 | 2023-10-19 | 2023-11-03 | 2024-11-01 | 2024-03-01 | 2024-11-21 | 2024-07-11 | 133 | 12 | 441
510882 | 1PointFive DAC-1 RWTU | Oakville | Air Vent Treatment excluding Carbon Scrubber (Carbon Tower System) | Biorem Environmental (US) | 4504121054 | Fabrication | Platform & Module | USD | 1198800 | USD | 1198800 | 0 | Specs / Requirements Misinterpreted in Proposal | 2023-07-12 | 2023-07-14 | 2023-12-01 | 2023-10-13 | 2024-12-14 | 2023-12-15 | 2023-10-27 | 2024-01-03 | 2024-07-08 | 2024-08-09 | 2024-07-24 | 16 | 12 | 173
510882 | 1PointFive DAC-1 RWTU | Oakville | Cartridge Filter Vessels | FIL-TREK CORPORATION | 4504060294 | Fabrication | Carbon Steel | USD | 163267 | USD | 251300 | -88033 | Not included in Proposal / RFQ | 2023-06-15 | 2023-06-16 | 2023-07-05 | 2023-09-06 | 2023-07-31 | 2023-08-02 | 2023-09-08 | 2023-09-08 | 2024-05-17 | 2024-02-19 | 2024-04-03 | -44 | 12 | 84
510882 | 1PointFive DAC-1 RWTU | Oakville | Filter Press | EVOQUA WATER TECHNOLOGIES, LLC | 4504082885 | Fabrication | Platform & Module | USD | 1984605 | USD | 2132088 | -147483 | Market Impact | 2023-05-09 | 2023-05-09 | 2023-09-13 | 2023-06-09 | 2023-10-11 | 2023-09-21 | 2023-10-02 | 2023-10-13 | 2024-10-14 | 2024-10-21 | 2024-10-17 | 4 | 12 | 157
510882 | 1PointFive DAC-1 RWTU | Oakville | Centrifugal Pumps | SULZER PUMP SOLUTIONS - USA | 4504025581 | Rotating Equipment | Centrifugal Pumps | USD | 2058682 | USD | 2058682 | 0 | Not included in Proposal / RFQ | 2023-04-21 | 2023-04-21 | 2023-05-10 | 2023-06-02 | 2023-06-27 | 2023-06-29 | 2023-07-07 | 2023-07-04 | 2024-08-09 | 2024-02-21 | 2024-05-16 | -85 | 30 | 74
510882 | 1PointFive DAC-1 RWTU | Oakville | Progressive Cavity Pumps | SEEPEX - USA | 4504046982 | Rotating Equipment | PD Pumps | USD | 162282 | USD | 87117 | 75165 | Design Optimizations | 2023-05-03 | 2023-05-03 | 2023-08-02 | 2023-06-02 | 2023-08-11 | 2023-08-11 | 2023-09-08 | 2023-08-15 | 2024-08-09 | 2024-02-15 | 2024-05-13 | -88 | 30 | 104
510882 | 1PointFive DAC-1 RWTU | Oakville | OSM Skid Fabrication - 3 Skids (Remainder) | TRIVACO | 4504147445 | Fabrication | Skid Assembly Outsourced | USD | 354828 | USD | 258449 | 96379 | Supplier Competitions / Negotiation | 2023-09-25 | 2023-12-11 | 2024-01-17 | 2023-10-18 | 2024-01-28 | 2024-01-29 | 2023-11-15 | 2024-02-02 | 2024-06-19 | 2024-02-02 | 2024-04-11 | -69 | 12 | 53
510882 | 1PointFive DAC-1 RWTU | Oakville | OSM Skid Fabrication - Main Order | TRIVACO | 4504117625 | Fabrication | Skid Assembly Outsourced | USD | 1645172 | USD | 1674009 | -28837 | Not included in Proposal / RFQ | 2023-09-25 | 2023-09-21 | 2023-10-30 | 2023-10-18 | 2023-11-14 | 2023-11-26 | 2023-11-15 | 2023-12-12 | 2024-06-19 | 2024-03-05 | 2024-04-27 | -53 | 12 | 82
510882 | 1PointFive DAC-1 RWTU | Oakville | Blowers | AERZEN | 4504070011 | Rotating Equipment | Blowers & Fans | USD | 1078120 | USD | 513320 | 564800 | Design Optimizations | 2023-07-19 | 2023-07-19 | 2023-09-20 | 2023-08-18 | 2024-09-20 | 2023-09-21 | 2023-08-25 | 2023-09-21 | 2024-05-06 | 2024-03-11 | 2024-04-08 | -28 | 30 | 64
510882 | 1PointFive DAC-1 RWTU | Oakville | Chemical Metering System | PROMINENT FLUID CONTROLS LTD. | 4504140264 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 533974 | CAD | 1280114 | -746140 | Market Impact | 2023-09-12 | 2023-09-12 | 2024-01-12 | 2023-10-09 | 2024-01-17 | 2024-01-08 | 2023-11-06 | 2024-01-23 | 2024-04-15 | 2024-11-18 | 2024-08-01 | 109 | 30 | 133
510882 | 1PointFive DAC-1 RWTU | Oakville | Tank Mixers | NOV PROCESS & FLOW TECH | 4504117632 | Rotating Equipment | Mixers | USD | 114354 | USD | 120140 | -5786 | Single Sourced | 2023-07-21 | 2023-07-22 | 2023-12-01 | 2023-10-06 | 2023-11-01 | 2023-11-09 | 2023-11-03 | 2023-12-22 | 2024-05-24 | 2024-07-19 | 2024-06-21 | 28 | 30 | 153
510882 | 1PointFive DAC-1 RWTU | Oakville | DensaDeg - Reactor Drive | BALDWIN SUPPLY COMPANY | 4504098090 | Rotating Equipment | Electric Motors | USD | 69214 | USD | 45170 | 24044 | Supplier Competitions / Negotiation | 2023-07-21 | 2023-07-26 | 2023-10-07 | 2023-10-06 | 2023-10-23 | 2023-11-10 | 2023-11-03 | 2023-11-07 | 2024-05-24 | 2024-03-07 | 2024-04-15 | -39 | 30 | 104
510882 | 1PointFive DAC-1 RWTU | Oakville | DensaDeg - Clarifier Drive | DBS MANUFACTURING INC. | 4504074435 | Rotating Equipment | Electric Motors | USD | 44000 | USD | 60780 | -16780 | Not included in Proposal / RFQ | 2023-07-21 | 2023-07-26 | 2023-08-09 | 2023-08-18 | 2023-09-15 | 2023-09-15 | 2023-08-25 | 2023-09-29 | 2024-03-11 | 2024-03-08 | 2024-03-09 | -1 | 30 | 65
510882 | 1PointFive DAC-1 RWTU | Oakville | PLC Components | GERRIE ELECTRIC LIMITED | 4504035612 | Electrical & Instrumentation | Ele-Control Panels | USD | 220461 | CAD | 231760 | -11299 | Not included in Proposal / RFQ | 2023-05-01 | 2023-05-01 | 2023-07-24 | 2023-06-02 | 2024-07-23 | 2023-07-24 | 2023-06-16 | 2023-07-24 | 2023-11-30 | 2024-01-04 | 2023-12-17 | 18 | 18 | 84
510882 | 1PointFive DAC-1 RWTU | Oakville | High Performance Butterfly Valves | BRAY CONTROLS CANADA LTD | 4504025973 | Flow Control | Metal Isolation Valves | USD | 265445 | USD | 265445 | 0 | Supplier Competitions / Negotiation | 2023-05-15 | 2023-05-15 | 2023-05-24 | 2023-06-15 | 2023-06-28 | 2023-06-29 | 2023-06-29 | 2023-07-05 | 2024-02-14 | 2024-02-23 | 2024-02-18 | 5 | 12 | 51
510882 | 1PointFive DAC-1 RWTU | Oakville | Metallic Auto and manual Ball Valves (Guelph) | Duncan Co. | 4504134598 | Flow Control | Metal Isolation Valves | USD | 60098 | USD | 67066 | -6968 | Not included in Proposal / RFQ | 2023-09-22 | 2023-10-06 | 2023-12-19 | 2023-10-19 | 2024-01-10 | 2024-01-10 | 2023-11-03 | 2024-01-22 | 2024-02-01 | 2024-03-05 | 2024-02-17 | 17 | 12 | 108
510882 | 1PointFive DAC-1 RWTU | Oakville | Check Valves (Guelph) | BRAY CONTROLS CANADA LTD | 4504141093 | Flow Control | Metal Isolation Valves | USD | 37893 | USD | 37893 | 0 | Not included in Proposal / RFQ | 2023-09-22 | 2023-11-08 | 2023-11-08 | 2023-10-19 | 2024-01-16 | 2024-01-16 | 2023-11-03 | 2024-01-25 | 2024-02-01 | 2024-02-26 | 2024-02-13 | 13 | 12 | 78
510882 | 1PointFive DAC-1 RWTU | Oakville | Plug Valves (OSM) | EVEREST AUTOMATION INC. | 4504121610 | Flow Control | Metal Isolation Valves | USD | 161177 | USD | 161177 | 0 | Estimate Without Market Reference(No Quote) | 2023-09-12 | 2023-09-12 | 2023-12-01 | 2023-11-29 | 2024-01-08 | 2024-01-08 | 2023-10-23 | 2024-01-09 | 2024-04-29 | 2024-04-30 | 2024-04-29 | 1 | 12 | 119
510882 | 1PointFive DAC-1 RWTU | Oakville | Recovery RO Reject Valves | EVEREST AUTOMATION INC. | 4504116617 | Flow Control | Metal Isolation Valves | USD | 11728 | USD | 11728 | 0 | Single Sourced | 2023-09-22 | 2023-10-17 | 2023-12-02 | 2023-10-19 | 2023-11-30 | 2023-11-30 | 2023-11-03 | 2023-12-11 | 2024-02-01 | 2024-09-30 | 2024-06-01 | 121 | 12 | 55
510882 | 1PointFive DAC-1 RWTU | Oakville | Modulating Butterfly (Fisher)-Guelph | LAKESIDE PROCESS CONTROLS LTD. | 4504062685 | Flow Control | Metal Control Valves | USD | 189355 | USD | 189355 | 0 | Supplier Competitions / Negotiation | 2023-06-19 | 2023-06-22 | 2023-08-23 | 2023-06-16 | 2023-08-29 | 2023-08-23 | 2023-06-23 | 2023-09-07 | 2024-03-01 | 2024-01-15 | 2024-02-07 | -23 | 12 | 77
510882 | 1PointFive DAC-1 RWTU | Oakville | Modulating Butterfly (Fisher)-3W | LAKESIDE PROCESS CONTROLS LTD. | 4504134463 | Flow Control | Metal Control Valves | USD | 61813 | USD | 61813 | 0 | Design Optimizations | 2023-08-04 | 2023-11-20 | 2023-10-24 | 2023-10-19 | 2024-01-04 | 2024-01-04 | 2023-11-03 | 2024-01-12 | 2024-02-01 | 2024-03-22 | 2024-02-26 | 25 | 12 | 53
510882 | 1PointFive DAC-1 RWTU | Oakville | Modulating Butterfly (Bray)-3W | BRAY CONTROLS CANADA LTD | 4504144967 | Flow Control | Metal Control Valves | USD | 36215 | USD | 29874 | 6341 | Design Optimizations | 2023-09-22 | 2023-11-20 | 2023-11-27 | 2023-10-19 | 2024-01-04 | 2024-01-04 | 2023-11-03 | 2024-01-30 | 2024-02-01 | 2024-07-19 | 2024-04-25 | 85 | 12 | 71
510882 | 1PointFive DAC-1 RWTU | Oakville | Instruments (Flowmeters) -Guelph | ENDRESS & HAUSER MN | 4504134261 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 73848 | USD | 110265 | -36417 | Proposed Supplier Incapable Of Executing | 2023-11-20 | 2023-10-05 | 2024-01-05 | 2023-12-15 | 2024-01-05 | 2024-01-05 | 2023-12-29 | 2024-01-12 | 2024-05-10 | 2024-02-23 | 2024-04-01 | -38 | 18 | 99
510882 | 1PointFive DAC-1 RWTU | Oakville | Instruments (Analyzers-pH, Cl2, ORP, Cond.) - Guelph | ENDRESS & HAUSER MN | 4504153461 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 21467 | USD | 23127 | -1660 | Estimate Without Market Reference(No Quote) | 2023-11-20 | 2023-10-13 | 2024-01-31 | 2023-12-15 | 2024-01-31 | 2024-02-01 | 2023-12-29 | 2024-02-13 | 2024-05-10 | 2024-02-13 | 2024-03-27 | -43 | 18 | 123
510882 | 1PointFive DAC-1 RWTU | Oakville | Instruments (H2S Analyzers-Gas Type)- 3W | Biorem Environmental (US) | 4504231000 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 228050 | USD | 228050 | 0 | Specs / Requirements Misinterpreted in Proposal | 2023-11-20 | 2023-10-13 | 2024-06-21 | 2023-12-15 | 2024-02-25 | 2024-02-25 | 2024-02-21 | 2024-07-02 | 2024-05-10 | 2024-10-31 | 2024-08-05 | 87 | 18 | 263
510882 | 1PointFive DAC-1 RWTU | Oakville | Instruments (Pressure gauges) - OSM | Winters Instruments | 4504152216 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 16483 | CAD | 16483 | 0 | Proposed Supplier Incapable Of Executing | 2023-11-20 | 2023-11-08 | 2023-11-08 | 2023-12-15 | 2024-02-07 | 2024-02-01 | 2023-12-29 | 2024-02-14 | 2024-05-10 | 2024-04-04 | 2024-04-22 | -18 | 18 | 98
510882 | 1PointFive DAC-1 RWTU | Oakville | Instruments (Pressure gauges) - 3W | Wika Instruments Ltd | 4504179626 | Electrical & Instrumentation | Ele-Control Panels | USD | 23210 | CAD | 17865 | 5345 | Frame Agreements | 2023-12-15 | 2024-02-02 | 2024-02-09 | 2024-01-12 | 2024-03-27 | 2024-03-27 | 2024-01-26 | 2024-03-28 | 2024-04-26 | 2024-08-15 | 2024-06-20 | 56 | 18 | 55
510882 | 1PointFive DAC-1 RWTU | Oakville | Static Mixer | KOFLO CORPORATION | 4504165756 | Flow Control | Static Mixer | USD | 78500 | USD | 79839 | -1339 | Not included in Proposal / RFQ | 2023-10-09 | 2024-01-16 | 2024-03-08 | 2023-11-03 | 2024-03-14 | 2024-03-14 | 2023-12-01 | 2024-03-17 | 2024-05-24 | 2024-04-08 | 2024-05-01 | -23 | 12 | 61
510882 | 1PointFive DAC-1 RWTU | Oakville | Electrical Heater | ASB HEATING ELEMENTS LIMITED | 4504069122 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | USD | 26857 | USD | 5710 | 21147 | Design Optimizations | 2023-07-28 | 2023-07-31 | 2023-08-18 | 2023-08-18 | 2023-08-22 | 2023-09-19 | 2023-08-25 | 2023-09-19 | 2024-02-12 | 2024-02-27 | 2024-02-19 | 8 | 18 | 50
510882 | 1PointFive DAC-1 RWTU | Oakville | Conical Strainer (OSM) | Harrington Industrial Plastics | 4504130540 | Flow Control | Filters And Strainers (Incl Housings) | USD | 28316 | USD | 28316 | 0 | Supplier Competitions / Negotiation | 2023-11-01 | 2023-10-04 | 2023-12-08 | 2023-11-22 | 2024-01-03 | 2024-01-03 | 2023-12-06 | 2024-01-09 | 2024-04-18 | 2024-03-25 | 2024-04-06 | -12 | 12 | 97
510882 | 1PointFive DAC-1 RWTU | Oakville | Calcite Silo System | Con-V-Air | 4504082884 | Flow Control | Filters And Strainers (Incl Housings) | USD | 471825 | USD | 457000 | 14825 | Frame Agreements | 2023-08-17 | 2023-08-17 | 2023-09-08 | 2023-09-29 | 2023-08-09 | 2023-10-12 | 2023-10-18 | 2023-10-13 | 2024-07-17 | 2024-06-17 | 2024-07-02 | -15 | 12 | 57
510882 | 1PointFive DAC-1 RWTU | Oakville | CLS Polymer Tank | PROMINENT FLUID CONTROLS LTD. | 4504157882 | Fabrication | Carbon Steel | USD | 174761 | CAD | 134822 | 39939 | Supplier Competitions / Negotiation | 2023-09-11 | 2023-09-11 | 2024-01-25 | 2023-10-09 | 2024-02-13 | 2024-10-01 | 2023-11-06 | 2024-02-22 | 2024-04-20 | 2024-11-29 | 2024-08-09 | 112 | 12 | 164
510882 | 1PointFive DAC-1 RWTU | Oakville | CO2 System | Tomco2 Systems | 4504143106 | Flow Control | Filters And Strainers (Incl Housings) | USD | 437119 | USD | 490623 | -53504 | Market Impact | 2023-10-02 | 2023-10-06 | 2023-11-03 | 2023-10-20 | 2023-12-08 | 2023-12-11 | 2023-11-07 | 2024-01-31 | 2024-07-26 | 2024-09-27 | 2024-08-26 | 32 | 12 | 117
510882 | 1PointFive DAC-1 RWTU | Oakville | Motor Disconnects & Operator Stations | ENGINEERING ELECTRIC CONTROLS | 4504176432 | Electrical & Instrumentation | Ele-Electrical Others | USD | 280269 | CAD | 326243 | -45974 | Estimate Without Market Reference(No Quote) | 2024-03-10 | 2023-09-15 | 2024-02-05 | 2024-03-10 | 2024-09-04 | 2024-02-05 | 2024-03-10 | 2024-02-11 | 2024-03-10 | 2024-02-11 | 2024-02-25 | -14 | 18 | 149
510882 | 1PointFive DAC-1 RWTU | Oakville | Sludge Forwarding Pumps | A.R. WILFLEY & SONS, INC. | 4504105258 | Flow Control | Filters And Strainers (Incl Housings) | USD | 612338 | USD | 137931 | 474407 | Design Optimizations | 2024-01-28 | 2023-10-04 | 2023-11-08 | 2024-01-28 | 2023-11-21 | 2023-11-21 | 2024-01-28 | 2023-11-21 | 2024-01-28 | 2024-05-23 | 2024-03-26 | 58 | 12 | 48
510882 | 1PointFive DAC-1 RWTU | Oakville | Remin Vessels | ENPRO INDUSTRIES PVT LTD | 4504130543 | Fabrication | Platform & Module | USD | 879889 | USD | 294750 | 585139 | Design Optimizations | 2024-05-25 | 2023-11-09 | 2023-11-03 | 2024-05-25 | 2024-12-15 | 2023-12-15 | 2024-05-25 | 2024-01-16 | 2024-05-25 | 2024-10-14 | 2024-08-04 | 71 | 12 | 68
510882 | 1PointFive DAC-1 RWTU | Oakville | Pressure Relief Valves (Guelph) | westech | 4504140221 | Flow Control | Filters And Strainers (Incl Housings) | USD | 71014 | USD | 63175 | 7839 | Supplier Competitions / Negotiation | 2024-02-21 | 2023-09-22 | 2023-11-09 | 2024-02-21 | 2024-01-11 | 2024-01-11 | 2024-02-21 | 2024-01-22 | 2024-02-21 | 2024-07-23 | 2024-05-07 | 77 | 12 | 122
510882 | 1PointFive DAC-1 RWTU | Oakville | Knife Gate Valves (3W) | BRAY CONTROLS CANADA LTD | 4504130131 | Flow Control | Filters And Strainers (Incl Housings) | USD | 10437 | USD | 11268 | -831 | Specs / Requirements Misinterpreted in Proposal | 2024-01-21 | 2023-12-05 | 2023-12-12 | 2024-01-21 | 2023-12-22 | 2023-12-22 | 2024-01-21 | 2024-01-08 | 2024-01-21 | 2024-03-08 | 2024-02-13 | 24 | 12 | 34
510882 | 1PointFive DAC-1 RWTU | Oakville | TSE Controller (PC Pumps) | SEEPEX | 4504091540 | Rotating Equipment | PD Pumps | USD | 5400 | USD | 5400 | 0 | Proposed Supplier Incapable Of Executing | 2023-07-10 | 2023-05-03 | 2023-10-05 | 2023-07-10 | 2023-08-08 | 2023-08-08 | 2023-07-10 | 2023-10-26 | 2023-07-10 | 2023-03-24 | 2023-05-17 | -54 | 30 | 176
510882 | 1PointFive DAC-1 RWTU | Oakville | Manual On-Off Butterfly Valves (On-skid Guelph) | BRAY CONTROLS CANADA LTD | 4504089711 | Rotating Equipment | PD Pumps | USD | 21613 | USD | 21613 | 0 | Market Impact | 2022-05-04 | 2023-09-23 | 2023-10-11 | 2022-05-04 | 2023-10-26 | 2020-11-03 | 2022-05-04 | 2023-11-03 | 2022-05-04 | 2023-04-14 | 2022-10-23 | 173 | 30 | 41
510882 | 1PointFive DAC-1 RWTU | Oakville | Manual On-Off Butterfly Valves (On-skid-OSM) | BRAY CONTROLS CANADA LTD | 4504092975 | Rotating Equipment | PD Pumps | USD | 75874 | USD | 80367 | -4493 | Market Impact | 2022-10-30 | 2023-09-23 | 2023-10-11 | 2022-10-30 | 2024-10-26 | 2020-11-03 | 2022-10-30 | 2023-11-03 | 2022-10-30 | 2023-12-27 | 2023-05-29 | 212 | 30 | 41
510882 | 1PointFive DAC-1 RWTU | Oakville | Manual On-Off Butterfly Valves (Off-skid-3W) | BRAY CONTROLS CANADA LTD | 4504145757 | Rotating Equipment | PD Pumps | USD | 66524 | USD | 89423 | -22899 | Estimate Without Market Reference(No Quote) | 2024-03-28 | 2023-11-27 | 2023-11-27 | 2024-03-28 | 2023-11-27 | 2023-11-27 | 2024-03-28 | 2024-02-11 | 2024-03-28 | 2024-07-29 | 2024-05-28 | 62 | 30 | 76
510882 | 1PointFive DAC-1 RWTU | Oakville | Pressure Relief Valves (OSM) | westech | 4504140292 | Flow Control | Filters And Strainers (Incl Housings) | USD | 5000 | USD | 9812 | -4812 | Market Impact | 2024-02-22 | 2023-09-22 | 2023-11-09 | 2024-02-22 | 2024-01-16 | 2024-01-16 | 2024-02-22 | 2024-01-25 | 2024-02-22 | 2024-07-24 | 2024-05-08 | 77 | 12 | 125
510882 | 1PointFive DAC-1 RWTU | Oakville | Metallic Auto and manual Ball Valves (OSM) | Duncan Co. | 4504134643 | Flow Control | Metal Isolation Valves | USD | 60098 | USD | 55758 | 4340 | Frame Agreements | 2024-01-12 | 2023-10-06 | 2023-12-19 | 2024-01-12 | 2024-01-10 | 2024-01-10 | 2024-01-12 | 2024-01-22 | 2024-01-12 | 2024-04-19 | 2024-03-01 | 49 | 12 | 108
510882 | 1PointFive DAC-1 RWTU | Oakville | Instruments (Flowmeters)-OSM | ENDRESS & HAUSER MN | 4504134222 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 24905 | USD | 25652 | -747 | Specs / Requirements Misinterpreted in Proposal | 2023-12-04 | 2023-10-05 | 2024-01-05 | 2023-12-04 | 2024-01-05 | 2024-01-05 | 2023-12-04 | 2024-01-15 | 2023-12-04 | 2024-02-02 | 2024-01-03 | 30 | 18 | 102
510882 | 1PointFive DAC-1 RWTU | Oakville | Instruments (Flowmeters)-3W | ENDRESS & HAUSER | 4504134596 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 13973 | USD | 13973 | 0 | Frame Agreements | 2023-12-10 | 2023-10-05 | 2024-01-05 | 2023-12-10 | 2024-01-05 | 2024-01-05 | 2023-12-10 | 2024-01-15 | 2023-12-10 | 2024-02-14 | 2024-01-12 | 33 | 18 | 102
510882 | 1PointFive DAC-1 RWTU | Oakville | Field RIO + MCP (DS to Site) | KELTOUR CONTROLS INC. | 4504196915 | Electrical & Instrumentation | Ele-Electrical Others | USD | 320028 | USD | 351924 | -31896 | Specs / Requirements Misinterpreted in Proposal | 2024-06-06 | 2024-03-22 | 2024-04-15 | 2024-06-06 | 2024-04-13 | 2024-04-13 | 2024-06-06 | 2024-04-29 | 2024-06-06 | 2024-08-22 | 2024-07-14 | 39 | 18 | 38
510882 | 1PointFive DAC-1 RWTU | Oakville | JBs,SVCP, CIP Heater Panel (OSM) | KELTOUR CONTROLS INC. | 4504171860 | Electrical & Instrumentation | Ele-Electrical Others | USD | 123123 | USD | 123123 | 0 | Specs / Requirements Misinterpreted in Proposal | 2024-03-29 | 2024-01-10 | 2024-03-15 | 2024-03-29 | 2024-03-15 | 2024-03-15 | 2024-03-29 | 2024-03-19 | 2024-03-29 | 2024-06-17 | 2024-05-08 | 40 | 18 | 69
510882 | 1PointFive DAC-1 RWTU | Oakville | RIO Panels (Guelph) | 206186 - Ardea Technologies | 4504157876 | Electrical & Instrumentation | Ele-Control Panels | USD | 109777 | CAD | 109777 | 0 | Design Optimizations | 2024-03-05 | 2024-01-10 | 2024-01-26 | 2024-03-05 | 2024-02-06 | 2024-02-06 | 2024-03-05 | 2024-03-04 | 2024-03-05 | 2024-04-30 | 2024-04-02 | 28 | 18 | 54
510882 | 1PointFive DAC-1 RWTU | Oakville | Carbon Scrubbers (Air Vent Treatment System) | BION LLC | 4504128902 | Fabrication | Carbon Steel | USD | 131000 | USD | 377673 | -246673 | Not included in Proposal / RFQ | 2024-03-29 | 2023-07-12 | 2023-12-15 | 2024-03-29 | 2024-12-15 | 2023-12-19 | 2024-03-29 | 2024-11-19 | 2024-03-29 | 2024-11-19 | 2024-07-24 | 118 | 12 | 496
510882 | 1PointFive DAC-1 RWTU | Oakville | Pressure Transmitter - Guelph | ENDRESS & HAUSER | 4504144822 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 26152 | USD | 50653 | -24501 | Estimate Without Market Reference(No Quote) | 2023-12-21 | 2023-10-13 | 2024-01-04 | 2023-12-21 | 2024-01-16 | 2024-01-16 | 2023-12-21 | 2024-01-31 | 2023-12-21 | 2024-02-29 | 2024-01-25 | 35 | 12 | 110
510882 | 1PointFive DAC-1 RWTU | Oakville | Pressure Transmitter - OSM | ENDRESS & HAUSER | 4504144936 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 50137 | USD | 50137 | 0 | Market Impact | 2023-12-21 | 2023-10-13 | 2024-01-15 | 2023-12-21 | 2024-01-16 | 2024-01-16 | 2023-12-21 | 2024-01-31 | 2023-12-21 | 2024-02-28 | 2024-01-24 | 35 | 12 | 110
510882 | 1PointFive DAC-1 RWTU | Oakville | Injection Quill | SAF-T-FLO | 4504198184 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 100000 | USD | 49483 | 50517 | Frame Agreements | 2024-05-31 | 2024-04-15 | 2024-04-22 | 2024-05-31 | 2024-04-22 | 2024-04-22 | 2024-05-31 | 2024-05-02 | 2024-05-31 | 2024-07-17 | 2024-06-23 | 24 | 12 | 17
510882 | 1PointFive DAC-1 RWTU | Oakville | Pressure Switches- Guelph | CONVAL EQUIPMENT LIMITED | 4504166051 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 8304 | USD | 8304 | 0 | Specs / Requirements Misinterpreted in Proposal | 2024-01-13 | 2023-11-08 | 2024-01-22 | 2024-01-13 | 2024-02-22 | 2024-02-22 | 2024-01-13 | 2024-03-11 | 2024-01-13 | 2024-03-20 | 2024-02-15 | 34 | 12 | 124
510882 | 1PointFive DAC-1 RWTU | Oakville | Pressure Switches- OSM | FLOMEC INC | 4504166041 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 24282 | USD | 24282 | 0 | Single Sourced | 2024-02-07 | 2023-11-08 | 2024-02-29 | 2024-02-07 | 2024-03-01 | 2024-03-01 | 2024-02-07 | 2024-03-08 | 2024-02-07 | 2024-05-09 | 2024-03-24 | 46 | 12 | 121
510882 | 1PointFive DAC-1 RWTU | Oakville | Pressure Switches- 3W | CONVAL PROCESS SOLUTIONS | 4504210482 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 66653 | USD | 66653 | 0 | Not included in Proposal / RFQ | 2024-04-27 | 2024-01-15 | 2024-01-22 | 2024-04-27 | 2024-05-14 | 2024-05-14 | 2024-04-27 | 2024-05-23 | 2024-04-27 | 2024-08-09 | 2024-06-18 | 52 | 12 | 129
510882 | 1PointFive DAC-1 RWTU | Oakville | Level Transmitter 3W | ENDRESS & HAUSER MN | 4504211128 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 78533 | USD | 115655 | -37122 | Estimate Without Market Reference(No Quote) | 2024-07-22 | 2024-05-14 | 2024-05-21 | 2024-07-22 | 2024-05-20 | 2024-05-20 | 2024-07-22 | 2024-05-22 | 2024-07-22 | 2024-09-29 | 2024-08-25 | 35 | 18 | 8
510882 | 1PointFive DAC-1 RWTU | Oakville | Cat-ox Internal Spools | Rigid Welding Inc. | 4504225709 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 748246 | CAD | 391157 | 357089 | Frame Agreements | 2024-07-14 | 2024-05-31 | 2024-06-07 | 2024-07-14 | 2024-06-14 | 2024-06-14 | 2024-07-14 | 2024-06-25 | 2024-07-14 | 2024-08-27 | 2024-08-05 | 22 | 18 | 25
510882 | 1PointFive DAC-1 RWTU | Oakville | Remin Strainers | ORTHOS LIQUID SYSTEMS, INC. | 4504198455 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 8652 | USD | 9380 | -728 | Size/ Weight/ Quantity Underestimated | 2024-05-19 | 2024-05-04 | 2024-05-11 | 2024-05-19 | 2024-05-01 | 2024-05-01 | 2024-05-19 | 2024-05-02 | 2024-05-19 | 2024-06-07 | 2024-05-28 | 10 | 18 | -2
510882 | 1PointFive DAC-1 RWTU | Oakville | H2S Analyzer Plate Assembly | ENDRESS & HAUSER MN | 4504236010 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 294034 | USD | 294034 | 0 | Single Sourced | 2024-07-31 | 2024-05-30 | 2024-06-06 | 2024-07-31 | 2024-05-28 | 2024-05-28 | 2024-07-31 | 2024-07-04 | 2024-07-31 | 2024-10-03 | 2024-09-01 | 32 | 18 | 35
510882 | 1PointFive DAC-1 RWTU | Oakville | Cat Ox Hardwares | NICKEL SYSTEMS, INC | 4504250761 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 200000 | USD | 183512 | 16488 | Design Optimizations | 2024-08-12 | 2024-07-01 | 2024-07-07 | 2024-08-12 | 2024-07-29 | 2024-07-29 | 2024-08-12 | 2024-08-02 | 2024-08-12 | 2024-09-24 | 2024-09-02 | 22 | 18 | 32
510882 | 1PointFive DAC-1 RWTU | Oakville | ISB Electrical Panels | KELTOUR CONTROLS INC. | 4504276080 | Flow Control | Metal Control Valves | USD | 278362 | USD | 144787 | 133575 | Design Optimizations | 2024-10-14 | 2024-09-06 | 2024-09-13 | 2024-10-14 | 2024-09-13 | 2024-09-13 | 2024-10-14 | 2024-09-17 | 2024-10-14 | 2024-11-22 | 2024-11-02 | 20 | 12 | 11
510882 | 1PointFive DAC-1 RWTU | Oakville | Pressure Transmitter | ENDRESS & HAUSER MN | 4504223024 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 31673 | USD | 32177 | -504 | Not included in Proposal / RFQ | 2024-07-31 | 2024-05-21 | 2024-05-28 | 2024-07-31 | 2024-05-27 | 2024-05-27 | 2024-07-31 | 2024-06-12 | 2024-07-31 | 2024-10-10 | 2024-09-04 | 36 | 18 | 22
511294 | Nutrien - UF Skid Expansion | Guelph | Modulating CV | DUNCAN CO | 4504106690 | Flow Control | Metal Control Valves | USD | 35000 | USD | 36998 | -1998 | Single Sourced | 2023-08-05 | 2023-10-17 | 2023-11-07 | 2023-08-20 | 2023-11-14 | 2023-12-22 | 2023-08-30 | 2023-11-22 | 2024-02-28 | 2024-01-17 | 2024-05-10 | -114 | 18 | 36
511294 | Nutrien - UF Skid Expansion | Guelph | V-Ball CV | Great Lakes Industrial Controls | 4504118181 | Flow Control | Metal Control Valves | USD | 10000 | CAD | 6804 | 3196 | Single Sourced | 2023-08-05 | 2023-10-17 | 2023-11-24 | 2023-08-20 | 2023-11-27 | 2023-11-16 | 2023-08-30 | 2023-12-12 | 2024-02-28 | 2024-02-06 | 2024-02-17 | -11 | 12 | 56
511294 | Nutrien - UF Skid Expansion | Guelph | Pressure Relief Valve (PRV) | LAKESIDE PROCESS CONTROLS LTD. | 4504106694 | Flow Control | Metal Safety(relief) Valves | USD | 9000 | USD | 7598 | 1402 | Single Sourced | 2023-10-14 | 2023-10-25 | 2023-11-13 | 2023-10-29 | 2023-10-22 | 2024-01-25 | 2023-11-08 | 2023-11-23 | 2024-02-28 | 2024-02-29 | 2024-05-08 | -69 | 18 | 29
511294 | Nutrien - UF Skid Expansion | Guelph | Instrumentation | LAKESIDE PROCESS CONTROLS LTD. | 4504106672 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 17895 | USD | 19090 | -1195 | Single Sourced | 2023-10-14 | 2023-10-25 | 2023-10-13 | 2023-10-29 | 2023-10-22 | 2024-01-28 | 2023-11-08 | 2023-11-23 | 2024-02-28 | 2024-01-18 | 2024-05-15 | -118 | 18 | 29
511294 | Nutrien - UF Skid Expansion | Guelph | Self Cleaning Strainer (Basket Type) | BOLL FILTER CORPORATION | 4504106648 | Flow Control | Filters And Strainers (Incl Housings) | USD | 26465 | USD | 21110 | 5355 | Single Sourced | 2023-08-19 | 2023-08-19 | 2023-11-16 | 2023-09-03 | 2023-11-13 | 2024-01-22 | 2023-09-13 | 2023-11-21 | 2024-02-28 | 2024-03-26 | 2024-06-26 | -92 | 12 | 94
511294 | Nutrien - UF Skid Expansion | Guelph | Skid Frame | 3D MECHANICAL | 4504118186 | Fabrication | Carbon Steel | USD | 11862 | CAD | 11413 | 449 | Supplier Competitions / Negotiation | 2023-10-14 | 2023-11-06 | 2023-12-07 | 2023-10-29 | 2023-12-07 | 2023-12-13 | 2023-12-17 | 2023-12-12 | 2023-12-17 | 2024-02-20 | 2024-01-18 | 33 | 12 | 36
511294 | Nutrien - UF Skid Expansion | Guelph | Metallic Spools | PANDA PIPING LTD | 4504118184 | Fabrication | Stainless Steel | USD | 65625 | CAD | 16636 | 48989 | Supplier Competitions / Negotiation | 2023-10-14 | 2023-11-06 | 2023-12-08 | 2023-10-29 | 2023-12-07 | 2023-12-13 | 2024-01-14 | 2023-12-12 | 2024-01-14 | 2024-04-16 | 2024-02-29 | 47 | 12 | 36
511294 | Nutrien - UF Skid Expansion | Guelph | Control and Pneumatic Panel | 206186 - Ardea Technologies | 4504156605 | Electrical & Instrumentation | Ele-Control Panels | USD | 26692 | CAD | 9924 | 16768 | Supplier Competitions / Negotiation | 2023-10-14 | 2024-01-15 | 2024-02-15 | 2023-10-29 | 2024-02-15 | 2024-02-20 | 2024-01-10 | 2024-02-19 | 2024-01-10 | 2024-04-08 | 2024-02-23 | 45 | 18 | 35
508114 | Town of Erin | Guelph | MCP & General Purpose Panel | ENGINEERING ELECTRIC CONTROLS | 4504050739 | Electrical & Instrumentation | Ele-Industrial Controls | CAD | 67979 | CAD | 60970 | 7009 | Supplier Competitions / Negotiation | 2023-05-30 | 2023-05-31 | 2023-06-23 | 2023-06-20 | 2023-06-22 | 2023-08-28 | 2023-06-27 | 2023-09-25 | 2023-10-24 | 2023-11-01 | 2023-11-27 | -26 | 24 | 117
508114 | Town of Erin | Guelph | PLC Components | Gerrie Electric | 4504028994 | Electrical & Instrumentation | Ele-Industrial Controls | CAD | 80000 | CAD | 74684 | 5316 | Single Sourced | 2023-05-30 | 2023-05-31 | 2023-07-06 | 2023-06-20 | 2023-06-21 | 2023-07-06 | 2023-06-27 | 2023-07-12 | 2023-10-24 | 2023-11-29 | 2023-11-15 | 14 | 12 | 42
508114 | Town of Erin | Guelph | RIO Panel | ENGINEERING ELECTRIC CONTROLS | 4504070967 | Electrical & Instrumentation | Ele-Industrial Controls | CAD | 26069 | CAD | 27900 | -1831 | Size/ Weight/ Quantity Underestimated | 2023-09-12 | 2023-09-12 | 2023-06-23 | 2023-09-12 | 2023-06-22 | 2023-09-12 | 2023-09-12 | 2023-09-25 | 2023-09-12 | 2023-11-01 | 2023-12-04 | -33 | 24 | 13
508114 | Town of Erin | Guelph | Outsourcing ( Framing + Spools) | TITAN PIPING SYSTEMS INC. | 4504050741 | Fabrication | Skid Assembly Outsourced | CAD | 329923 | CAD | 283686 | 46237 | Supplier Competitions / Negotiation | 2023-05-30 | 2023-04-03 | 2023-07-04 | 2023-06-20 | 2023-07-03 | 2023-08-11 | 2023-06-27 | 2023-08-31 | 2023-10-24 | 2023-11-23 | 2023-12-20 | -27 | 30 | 150
508114 | Town of Erin | Guelph | Electrical Heater | ASB HEATING ELEMENTS LIMITED | 4504045689 | Flow Control | Other | CAD | 9675 | CAD | 8584 | 1091 | Single Sourced | 2023-07-25 | 2023-04-03 | 2023-08-04 | 2023-08-15 | 2023-05-04 | 2023-08-25 | 2023-08-22 | 2023-08-09 | 2023-10-24 | 2023-12-27 | 2024-01-16 | -20 | 12 | 128
508114 | Town of Erin | Guelph | Instruments Devices | ENDRESS & HAUSER | 4504060933 | Electrical & Instrumentation | Inst-Multiparam Transmitters, Controllers | CAD | 8251 | USD | 24037 | -15786 | Frame Agreements | 2023-06-13 | 2023-05-31 | 2023-08-22 | 2023-07-04 | 2023-08-12 | 2023-08-12 | 2023-07-11 | 2023-09-06 | 2023-10-24 | 2023-10-11 | 2023-10-12 | -1 | 24 | 98
508114 | Town of Erin | Guelph | Automatic Strainer | BOLL FILTER CORPORATION | 4504048592 | Flow Control | Other | CAD | 70537 | USD | 110025 | -39488 | Market Impact | 2023-05-16 | 2023-03-31 | 2023-08-07 | 2023-06-06 | 2023-05-03 | 2023-08-10 | 2023-06-13 | 2023-08-16 | 2023-10-24 | 2023-12-20 | 2023-11-30 | 20 | 30 | 138
508114 | Town of Erin | Guelph | Air Compressor and Dryer | GTA Compressor Solutions Inc | 4504048581 | Rotating Equipment | Compressors | CAD | 18815 | USD | 27057 | -8242 | Market Impact | 2023-06-27 | 2023-04-05 | 2023-08-04 | 2023-07-18 | 2023-05-04 | 2023-07-25 | 2023-07-25 | 2023-08-16 | 2023-10-24 | 2023-11-08 | 2023-11-14 | -6 | 30 | 133
508114 | Town of Erin | Guelph | Air Blower | AERZEN CANADA INC | 4504048587 | Rotating Equipment | Blowers & Fans | CAD | 26000 | CAD | 58220 | -32220 | Design Optimizations | 2023-06-13 | 2023-03-31 | 2023-08-08 | 2023-07-04 | 2023-05-04 | 2023-08-05 | 2023-07-11 | 2023-08-16 | 2023-10-24 | 2023-11-22 | 2023-12-11 | -19 | 36 | 138
508114 | Town of Erin | Guelph | Dosing Pump | FINISH THOMPSON, INC | 4504057159 | Rotating Equipment | Dosing Pump | CAD | 15870 | USD | 5576 | 10294 | Single Sourced | 2023-07-25 | 2023-03-31 | 2023-04-26 | 2023-08-15 | 2023-05-04 | 2023-07-12 | 2023-08-22 | 2023-08-30 | 2023-10-24 | 2023-09-13 | 2023-10-13 | -30 | 12 | 152
508114 | Town of Erin | Guelph | Centrifugal Pumps | SULZER PUMPS (CANADA) IN | 4504047827 | Rotating Equipment | Centrifugal Pumps | CAD | 503115 | CAD | 596332 | -93217 | Market Impact | 2023-03-07 | 2023-03-09 | 2023-06-29 | 2023-03-28 | 2023-07-11 | 2023-06-30 | 2023-04-04 | 2023-08-13 | 2023-10-24 | 2024-02-04 | 2024-02-29 | -25 | 36 | 157
508114 | Town of Erin | Guelph | HDPE Tank | ACO CONTAINER SYSTEMS LTD. | 4504048373 | Flow Control | Plastic Pipe and Fittings | CAD | 15900 | CAD | 21142 | -5242 | Single Sourced | 2023-07-11 | 2023-06-07 | 2023-08-04 | 2023-08-01 | 2023-07-19 | 2023-08-15 | 2023-08-08 | 2023-08-15 | 2023-10-24 | 2023-10-03 | 2023-10-20 | -17 | 12 | 69
508114 | Town of Erin | Guelph | Metallic Valve - ON/OFF Ball CV | LAKESIDE PROCESS CONTROLS LTD. | 4504061191 | Flow Control | Metal Control Valves | CAD | 67000 | USD | 62945 | 4055 | Frame Agreements | 2023-05-30 | 2023-05-31 | 2023-06-16 | 2023-06-20 | 2023-08-19 | 2023-08-19 | 2023-06-27 | 2023-09-06 | 2023-10-24 | 2023-11-08 | 2023-11-07 | 1 | 24 | 98
508114 | Town of Erin | Guelph | Metallic Valves - ON/OFF CV (Valve Rack Skid) | BRAY CONTROLS CANADA LTD | 4504061218 | Flow Control | Metal Control Valves | CAD | 15096 | USD | 13952 | 1144 | Frame Agreements | 2023-09-07 | 2023-09-07 | 2023-08-11 | 2023-09-07 | 2023-09-07 | 2023-09-07 | 2023-09-07 | 2023-09-06 | 2023-09-07 | 2023-10-04 | 2023-10-03 | 1 | 36 | -1
508114 | Town of Erin | Guelph | Static Mixers | KOFLO CORP | 4504050483 | Flow Control | Static Mixer | CAD | 14000 | USD | 18371 | -4371 | Supplier Competitions / Negotiation | 2023-07-25 | 2023-05-19 | 2023-05-31 | 2023-08-15 | 2023-05-31 | 2023-08-07 | 2023-08-22 | 2023-08-18 | 2023-10-24 | 2023-09-22 | 2023-10-27 | -35 | 18 | 91
510087 | Abilene Hambby 2 Train Expansion | Minnetonka | RIO Panel | ENGINEERING ELECTRIC CONTROLS | 4503957096 | Electrical & Instrumentation | Ele-Control Panels | USD | 20719 | CAD | 22181 | -1462 | Supplier Competitions / Negotiation | 2023-03-24 | 2023-02-06 | 2023-02-22 | 2023-04-14 | 2023-02-27 | 2023-03-06 | 2023-04-21 | 2023-03-08 | 2023-06-30 | 2023-05-10 | 2023-08-30 | -112 | 12 | 30
510087 | Abilene Hambby 2 Train Expansion | Minnetonka | Spools & Brackets | ARC SERVICES | 4503972576 | Fabrication | Stainless Steel | USD | 76669 | USD | 119700 | -43031 | Supplier Competitions / Negotiation | 2022-08-19 | 2023-03-03 | 2023-04-04 | 2022-09-09 | 2023-03-31 | 2023-04-04 | 2022-09-16 | 2023-04-04 | 2023-04-07 | 2023-06-27 | 2023-07-30 | -33 | 12 | 32
510087 | Abilene Hambby 2 Train Expansion | Minnetonka | Instruments | ENDRESS & HAUSER CANADA LTD | 4503960783 | Electrical & Instrumentation | Inst-Flow (Inst. & Switches) | USD | 6450 | USD | 11234 | -4784 | Frame Agreements | 2022-11-25 | 2023-01-09 | 2023-03-09 | 2022-12-16 | 2023-02-14 | 2023-03-13 | 2022-12-23 | 2023-03-14 | 2023-03-24 | 2023-05-23 | 2023-06-15 | -23 | 36 | 64
510087 | Abilene Hambby 2 Train Expansion | Minnetonka | Desiccant Dryer | QUINCY COMPRESSORS | 4503957107 | Rotating Equipment | Compressors | USD | 17501 | USD | 5881 | 11620 | Single Sourced | 2023-02-03 | 2023-01-09 | 2023-02-15 | 2023-02-24 | 2023-02-19 | 2023-03-03 | 2023-03-03 | 2023-03-08 | 2023-04-07 | 2023-04-05 | 2023-05-04 | -29 | 15 | 58
510087 | Abilene Hambby 2 Train Expansion | Minnetonka | Membrane Blower | PSI PROLEW INC. | 4503958955 | Rotating Equipment | Blowers & Fans | USD | 62936 | CAD | 94804 | -31868 | Single Sourced | 2022-08-05 | 2023-01-09 | 2023-03-08 | 2022-08-26 | 2023-02-14 | 2023-03-03 | 2022-09-02 | 2023-03-09 | 2023-04-07 | 2023-10-05 | 2023-10-20 | -15 | 12 | 59
510087 | Abilene Hambby 2 Train Expansion | Minnetonka | Permeate Pump | Flowserve US Inc. | 4503954686 | Rotating Equipment | Centrifugal Pumps | USD | 47566 | USD | 54672 | -7106 | Single Sourced | 2022-12-23 | 2022-12-28 | 2023-03-03 | 2023-01-13 | 2023-02-08 | 2023-03-03 | 2023-01-20 | 2023-03-03 | 2023-05-05 | 2023-06-09 | 2023-09-20 | -103 | 12 | 65
510087 | Abilene Hambby 2 Train Expansion | Minnetonka | Vertical Turbine Pump | CASCADE INSULATION COMPAN | 4503997922 | Rotating Equipment | Centrifugal Pumps | USD | 140000 | USD | 187500 | -47500 | Single Sourced | 2022-09-02 | 2023-01-09 | 2023-03-07 | 2022-09-23 | 2023-02-02 | 2023-03-10 | 2022-09-30 | 2023-05-19 | 2023-05-05 | 2023-12-01 | 2023-11-06 | 25 | 12 | 130
510087 | Abilene Hambby 2 Train Expansion | Minnetonka | Swing Check Valve | Ferguson Waterworks | 4503960692 | Flow Control | Metal Isolation Valves | USD | 6420 | USD | 30750 | -24330 | Single Sourced | 2022-09-16 | 2023-02-02 | 2023-03-02 | 2022-10-07 | 2023-03-01 | 2023-03-13 | 2022-10-14 | 2023-03-14 | 2023-05-05 | 2023-09-26 | 2023-10-01 | -5 | 12 | 40
510087 | Abilene Hambby 2 Train Expansion | Minnetonka | Butterfly Valve | BRAY CONTROLS CANADA LTD | 4503954784 | Flow Control | Metal Control Valves | USD | 34400 | USD | 49001 | -14601 | Frame Agreements | 2022-09-16 | 2023-02-01 | 2023-03-03 | 2022-10-07 | 2023-02-14 | 2023-02-22 | 2022-10-14 | 2023-03-03 | 2023-05-05 | 2023-09-15 | 2023-04-14 | 154 | 24 | 30
511879 | FRAC XIV with DIB III | Leonia | Rotor Impeller Drive | Norfolk Bearing | 4504195405 | Rotating Equipment | Electric Motors | USD | 5134 | USD | 12038 | -6904 | Estimate Without Market Reference(No Quote) | 2024-02-12 | 2024-01-05 | 2024-01-25 | 2024-03-11 | 2024-04-21 | 2024-06-03 | 2024-03-25 | 2024-04-23 | 2024-08-26 | 2024-06-18 | 2024-10-31 | -135 | 18 | 109
511879 | FRAC XIV with DIB III | Leonia | Submersible Pump | SULZER PUMP SOLUTIONS - USA | 4504199084 | Rotating Equipment | Centrifugal Pumps | USD | 83728 | USD | 77636 | 6092 | Supplier Competitions / Negotiation | 2023-12-25 | 2023-12-22 | 2024-05-02 | 2024-01-22 | 2024-04-23 | 2024-06-01 | 2024-02-05 | 2024-04-30 | 2024-08-26 | 2024-04-30 | 2024-11-10 | -194 | 18 | 130
511879 | FRAC XIV with DIB III | Leonia | Agitator | SPX FLOW US LLC | 4504197944 | Rotating Equipment | Mixers | USD | 42873 | USD | 21690 | 21183 | Supplier Competitions / Negotiation | 2024-03-18 | 2023-12-22 | 2024-04-30 | 2024-04-15 | 2024-04-25 | 2024-05-01 | 2024-04-29 | 2024-04-30 | 2024-08-26 | 2024-09-09 | 2024-09-09 | 0 | 18 | 130
511879 | FRAC XIV with DIB III | Bellevue | Sludge Thickener | SPS Engineering Inc. | 4504138492 | Rotating Equipment | Others | USD | 260842 | USD | 253456 | 7386 | Supplier Competitions / Negotiation | 2023-10-03 | 2023-12-22 | 2024-01-11 | 2023-10-31 | 2024-01-17 | 2024-01-19 | 2023-11-14 | 2024-01-18 | 2024-09-03 | 2024-10-03 | 2024-11-10 | -38 | 18 | 27
511879 | FRAC XIV with DIB III | Leonia | Impeller Pump | ITT GOULDS PUMPS INC | 4504197811 | Rotating Equipment | Centrifugal Pumps | USD | 49408 | USD | 56244 | -6836 | Estimate Without Market Reference(No Quote) | 2024-01-01 | 2024-01-04 | 2024-04-17 | 2024-01-29 | 2024-04-24 | 2024-05-21 | 2024-02-12 | 2024-04-28 | 2024-08-26 | 2024-09-29 | 2024-10-10 | -11 | 18 | 115
511879 | FRAC XIV with DIB III | Bellevue | Filter Press + Diaphragm Pump | EVOQUA WATER TECHNOLOGIES, LLC | 4504157168 | Rotating Equipment | Filter Press | USD | 107825 | USD | 108312 | -487 | Supplier Competitions / Negotiation | 2024-01-09 | 2023-12-22 | 2024-01-29 | 2024-02-06 | 2024-01-29 | 2024-02-26 | 2024-02-20 | 2024-02-24 | 2024-09-03 | 2024-07-20 | 2024-11-24 | -127 | 18 | 64
511879 | FRAC XIV with DIB III | Bellevue | Accelator | Sharp Iron | 4504157174 | Fabrication | Process Equipment | USD | 371242 | USD | 323284 | 47958 | Supplier Competitions / Negotiation | 2024-02-06 | 2024-01-25 | 2024-02-21 | 2024-03-05 | 2024-02-21 | 2024-02-26 | 2024-03-19 | 2024-02-27 | 2024-09-03 | 2024-06-18 | 2024-09-10 | -84 | 18 | 33
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | RO & UF Heaters | ASB HEATING ELEMENTS LIMITED | 4504031760 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | USD | 23334 | CAD | 24356 | -1022 | Size/ Weight/ Quantity Underestimated | 2023-08-11 | 2023-06-13 | 2023-06-12 | 2023-09-08 | 2023-07-01 | 2023-11-01 | 2023-09-22 | 2023-07-17 | 2024-03-22 | 2023-11-28 | 2024-01-24 | -57 | 24 | 34
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | PLC Components UF, IX, RO | GERRIE ELECTRIC LIMITED | 4503981537 | Electrical & Instrumentation | Ele-Industrial Controls | USD | 700000 | CAD | 713716 | -13716 | Specs / Requirements Misinterpreted in Proposal | 2023-02-10 | 2023-02-24 | 2023-03-10 | 2023-03-10 | 2023-04-05 | 2023-07-17 | 2023-03-24 | 2023-04-17 | 2023-12-22 | 2023-04-17 | 2023-08-19 | -124 | 12 | 52
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | PLC Components Thermal | EECO | 4503982179 | Electrical & Instrumentation | Ele-Industrial Controls | USD | 200000 | USD | 182360 | 17640 | Supplier Competitions / Negotiation | 2023-02-10 | 2023-02-24 | 2023-03-10 | 2023-03-10 | 2023-04-06 | 2023-07-17 | 2023-03-24 | 2023-04-18 | 2023-12-22 | 2023-04-18 | 2023-08-20 | -124 | 12 | 53
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Thermal Ducts | HARRIS THERMAL TRANSFER | 4503979427 | Fabrication | Stainless Steel | USD | 1893994 | USD | 1773500 | 120494 | Design Optimizations | 2023-03-10 | 2023-02-06 | 2023-03-14 | 2023-04-07 | 2023-03-18 | 2023-10-11 | 2023-04-21 | 2023-04-16 | 2024-06-14 | 2024-06-09 | 2024-06-11 | -2 | 24 | 69
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Concentrator & Crystallizer Tubes | HUNAN XIANGTOU GOLDSKY NEW MATERIAL | 4503934623 | Fabrication | Alloy Steel | USD | 1043450 | USD | 650228 | 393222 | Design Optimizations | 2023-01-13 | 2022-12-16 | 2023-02-05 | 2023-02-10 | 2023-01-13 | 2023-01-31 | 2023-02-24 | 2023-01-28 | 2023-08-11 | 2023-05-08 | 2023-06-24 | -47 | 24 | 43
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | FPRO & SPRO Cartridge Filter Housings | FIL-TREK CORPORATION | 4504008345 | Flow Control | Filters And Strainers (Incl Housings) | USD | 263990 | USD | 245952 | 18038 | Supplier Competitions / Negotiation | 2023-03-31 | 2023-02-28 | 2023-03-17 | 2023-05-12 | 2023-05-12 | 2023-06-28 | 2023-05-12 | 2023-06-08 | 2023-10-27 | 2023-09-14 | 2023-10-05 | -21 | 24 | 100
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | RO CIP Cartridge Filter Housings | FIL-TREK CORPORATION | 4504014160 | Flow Control | Filters And Strainers (Incl Housings) | USD | 42126 | USD | 56936 | -14810 | Estimate Without Market Reference(No Quote) | 2023-03-31 | 2023-02-28 | 2023-03-17 | 2023-05-12 | 2023-05-11 | 2023-07-01 | 2023-05-12 | 2023-06-15 | 2023-10-27 | 2023-11-02 | 2023-10-30 | 3 | 24 | 107
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | FRP Cartridge Filter Housings | Fluytec Filtration Technology | 4504046303 | Flow Control | Filters And Strainers (Incl Housings) | USD | 10000 | EUR | 7842 | 2158 | Frame Agreements | 2023-06-16 | 2023-06-16 | 2023-06-19 | 2023-07-14 | 2023-07-23 | 2023-08-31 | 2023-07-28 | 2023-08-09 | 2023-10-27 | 2023-11-15 | 2023-11-05 | 10 | 12 | 54
510021 | ZLD Blue Sky Sundt Kiewit JV | Leonia | FRP Cartridge Filter Housings | Fluytec Filtration Technology | 4504046289 | Flow Control | Filters And Strainers (Incl Housings) | USD | 24406 | EUR | 13755 | 10651 | Supplier Competitions / Negotiation | 2023-06-16 | 2023-06-16 | 2023-06-19 | 2023-07-14 | 2023-07-23 | 2023-09-04 | 2023-07-28 | 2023-08-10 | 2023-10-27 | 2023-11-23 | 2023-11-09 | 14 | 12 | 55
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Static Mixer (Thermal) | KOFLO CORPORATION | 4504005825 | Flow Control | Static Mixer | USD | 24679 | USD | 12155 | 12524 | Frame Agreements | 2023-10-27 | 2023-02-03 | 2023-02-27 | 2023-11-24 | 2023-05-16 | 2023-09-01 | 2023-12-08 | 2023-06-02 | 2024-03-29 | 2023-08-08 | 2023-12-03 | -117 | 24 | 119
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Static Mixer (UF-IX-RO) | KOFLO CORPORATION | 4504046218 | Flow Control | Static Mixer | USD | 38471 | USD | 40460 | -1989 | Proposed Supplier Incapable Of Executing | 2023-08-30 | 2023-06-16 | 2023-06-23 | 2023-09-27 | 2023-07-05 | 2023-11-07 | 2023-10-11 | 2023-08-10 | 2024-03-30 | 2023-10-19 | 2024-01-08 | -81 | 12 | 55
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Thermal - Level Switches | AVENSYS | 4504007655 | Electrical & Instrumentation | Inst-Gauges | USD | 36740 | USD | 36740 | 0 | Size/ Weight/ Quantity Underestimated | 2023-05-26 | 2023-04-26 | 2023-05-05 | 2023-06-23 | 2023-05-13 | 2023-08-24 | 2023-07-07 | 2023-06-05 | 2023-12-22 | 2023-08-07 | 2023-10-14 | -68 | 12 | 40
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | IX - Magmeters | ENDRESS & HAUSER MN | 4504040680 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 34100 | USD | 34055 | 45 | Supplier Competitions / Negotiation | 2023-05-26 | 2023-05-01 | 2023-05-25 | 2023-06-23 | 2023-07-05 | 2023-08-26 | 2023-07-07 | 2023-07-31 | 2023-12-22 | 2023-10-09 | 2023-11-15 | -37 | 18 | 91
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | IX - Conductivity Analyzers | LAKESIDE PROCESS CONTROLS LTD. | 4504014399 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 11000 | USD | 10904 | 96 | Supplier Competitions / Negotiation | 2023-05-26 | 2023-05-12 | 2023-05-12 | 2023-06-23 | 2023-06-06 | 2023-09-08 | 2023-07-07 | 2023-06-19 | 2023-12-22 | 2024-01-05 | 2023-12-29 | 7 | 24 | 38
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | IX - Analyzers | ENDRESS & HAUSER MN | 4504048263 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 20755 | USD | 20755 | 0 | Not included in Proposal / RFQ | 2023-05-26 | 2023-05-12 | 2023-06-16 | 2023-06-23 | 2023-07-20 | 2023-09-01 | 2023-07-07 | 2023-08-15 | 2023-12-22 | 2023-10-10 | 2023-11-15 | -36 | 18 | 95
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | IX - Conductivity Analyzers | LAKESIDE PROCESS CONTROLS LTD. | 4504014439 | Electrical & Instrumentation | Inst-Temperature (Inst. & Switches) | USD | 24000 | USD | 22228 | 1772 | Design Optimizations | 2023-05-26 | 2023-05-12 | 2023-06-12 | 2023-06-23 | 2023-06-06 | 2023-09-07 | 2023-07-07 | 2023-06-18 | 2023-12-22 | 2024-01-04 | 2023-12-28 | 7 | 24 | 37
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | UF - Magmeters | ENDRESS & HAUSER MN | 4504048302 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 26737 | USD | 26737 | 0 | Market Impact | 2023-05-26 | 2023-03-27 | 2023-04-13 | 2023-06-23 | 2023-07-11 | 2023-08-09 | 2023-07-07 | 2023-08-14 | 2023-12-22 | 2023-10-31 | 2023-11-26 | -26 | 18 | 140
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | UF - Chlorine Analyzer Panels | ENDRESS & HAUSER MN | 4504048311 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 6336 | USD | 6336 | 0 | Frame Agreements | 2023-05-26 | 2023-06-22 | 2023-08-01 | 2023-06-23 | 2023-07-25 | 2023-09-08 | 2023-07-07 | 2023-08-15 | 2023-12-22 | 2023-10-03 | 2023-11-12 | -40 | 18 | 54
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | RO - Magmeters | ENDRESS & HAUSER MN | 4504045448 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 40200 | USD | 40162 | 38 | Design Optimizations | 2023-05-26 | 2023-03-27 | 2023-04-20 | 2023-06-23 | 2023-06-28 | 2023-08-09 | 2023-07-07 | 2023-08-09 | 2023-12-22 | 2023-10-04 | 2023-11-12 | -39 | 18 | 135
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | RO - Conductivity Analyzers | LAKESIDE PROCESS CONTROLS LTD. | 4504223344 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 222000 | USD | 200292 | 21708 | Design Optimizations | 2023-05-26 | 2023-04-19 | 2023-05-24 | 2023-06-23 | 2023-06-02 | 2023-08-23 | 2023-07-07 | 2023-06-14 | 2023-12-22 | 2023-12-27 | 2023-12-24 | 3 | 24 | 56
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | RO - Vortex Flow Meters | ENDRESS & HAUSER MN | 4504045427 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 176960 | USD | 176951 | 9 | Design Optimizations | 2023-05-26 | 2023-03-30 | 2023-06-01 | 2023-06-23 | 2023-07-04 | 2023-07-02 | 2023-07-07 | 2023-08-09 | 2023-07-02 | 2023-10-04 | 2023-08-18 | 47 | 18 | 132
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | RO - Analyzers Plates | ENDRESS & HAUSER MN | 4504045403 | Electrical & Instrumentation | Inst-Pressure (Transimitter & Switches) | USD | 50870 | USD | 50870 | 0 | Market Impact | 2023-05-26 | 2023-04-19 | 2023-06-01 | 2023-06-23 | 2023-07-26 | 2023-07-12 | 2023-07-07 | 2023-08-09 | 2023-07-12 | 2023-10-04 | 2023-08-23 | 42 | 18 | 112
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Instruments and Analyzers - Instruments Panel Assembly | Hach Company | 4504011612 | Electrical & Instrumentation | Ele-Control Panels | USD | 388310 | USD | 410184 | -21874 | Not included in Proposal / RFQ | 2023-05-26 | 2023-03-20 | 2023-04-12 | 2023-06-23 | 2023-05-21 | 2023-08-05 | 2023-07-07 | 2023-06-12 | 2023-12-22 | 2023-11-02 | 2023-11-27 | -25 | 24 | 84
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Centrifuges | Flottweg | 4503965590 | Rotating Equipment | Centrifuge | USD | 3334070 | USD | 2701380 | 632690 | Supplier Competitions / Negotiation | 2023-01-11 | 2022-12-23 | 2023-02-02 | 2023-02-08 | 2023-02-22 | 2023-08-26 | 2023-02-22 | 2023-03-10 | 2024-04-17 | 2024-04-29 | 2024-04-23 | 6 | 24 | 77
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Thermal Recirculation Pumps | ITT GOULDS PUMPS INC | 4503958983 | Rotating Equipment | Centrifugal Pumps | USD | 1723852 | USD | 1604038 | 119814 | Design Optimizations | 2022-12-05 | 2022-12-23 | 2023-02-13 | 2023-01-02 | 2023-02-22 | 2023-07-14 | 2023-01-16 | 2023-03-10 | 2024-01-15 | 2024-02-20 | 2024-02-02 | 18 | 24 | 77
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Concentrator Vessel | NORTHWEST COPPER WORKS | 4503952286 | Fabrication | Alloy Steel | USD | 1239170 | USD | 1171615 | 67555 | Frame Agreements | 2023-04-21 | 2022-12-28 | 2023-01-18 | 2023-05-19 | 2023-01-11 | 2023-08-31 | 2023-06-02 | 2023-02-21 | 2024-05-03 | 2023-12-12 | 2024-02-21 | -71 | 18 | 55
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Plate Heat Exchangers (Thermal) | Danfoss LLC | 4503990650 | Rotating Equipment | Heat Exchangers | USD | 353669 | USD | 263950 | 89719 | Frame Agreements | 2023-10-06 | 2023-01-18 | 2023-02-20 | 2023-11-03 | 2023-04-19 | 2023-09-17 | 2023-11-17 | 2023-05-07 | 2024-05-16 | 2023-12-17 | 2024-03-01 | -75 | 24 | 109
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | WAC Vessel | Alps Welding Ltd. | 4503988958 | Fabrication | Stainless Steel | USD | 1158290 | USD | 1363440 | -205150 | Single Sourced | 2023-07-07 | 2023-02-06 | 2023-04-04 | 2023-08-04 | 2023-05-01 | 2023-08-26 | 2023-08-18 | 2023-05-03 | 2024-03-15 | 2023-12-07 | 2024-01-25 | -49 | 18 | 86
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | WAC Vessel internal | NV PIPING SYSTEMS INC. | 4504001608 | Fabrication | Stainless Steel | USD | 776115 | USD | 673480 | 102635 | Frame Agreements | 2023-06-09 | 2023-02-06 | 2023-03-20 | 2023-07-07 | 2023-05-14 | 2023-08-12 | 2023-07-21 | 2023-05-25 | 2024-02-16 | 2023-09-15 | 2023-12-01 | -77 | 24 | 108
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | WAC Ladders & Platforms | MARCON CUSTOM METALS, INC. | 4504030705 | Fabrication | Stainless Steel | USD | 141908 | USD | 174360 | -32452 | Single Sourced | 2023-07-07 | 2023-02-06 | 2023-07-06 | 2023-08-04 | 2023-07-06 | 2023-08-26 | 2023-07-21 | 2023-07-14 | 2024-03-15 | 2023-12-01 | 2024-01-22 | -52 | 24 | 158
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Vent Condenser | CORWEST | 4504011931 | Fabrication | Stainless Steel | USD | 95500 | USD | 95000 | 500 | Supplier Competitions / Negotiation | 2023-08-07 | 2023-01-31 | 2023-03-22 | 2023-09-04 | 2023-04-26 | 2023-09-08 | 2023-09-18 | 2023-06-14 | 2024-04-15 | 2023-09-11 | 2023-12-28 | -108 | 24 | 134
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Strainer System (Buy Out) | BOLL FILTER CORPORATION | 4504010088 | Fabrication | Stainless Steel | USD | 96676 | USD | 83500 | 13176 | Supplier Competitions / Negotiation | 2023-04-27 | 2023-05-17 | 2023-06-01 | 2023-05-25 | 2023-06-07 | 2023-08-31 | 2023-06-08 | 2023-06-09 | 2024-01-04 | 2023-12-08 | 2023-12-21 | -13 | 24 | 23
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Vapor Compressors | PILLER BLOWERS & COMPRESSORS GMBH | 4503967016 | Rotating Equipment | Vapor Compressor | USD | 3338276 | EUR | 3372586 | -34310 | Market Impact | 2023-02-22 | 2022-12-23 | 2023-02-22 | 2023-03-22 | 2023-03-02 | 2023-08-06 | 2023-04-05 | 2023-03-24 | 2024-03-20 | 2024-03-04 | 2024-03-12 | -8 | 18 | 91
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Crystallizer Feed Tank | NORTHWEST COPPER WORKS | 4503112233 | Fabrication | Alloy Steel | USD | 1760920 | USD | 1850073 | -89153 | Proposed Supplier Incapable Of Executing | 2023-01-23 | 2022-12-28 | 2023-01-11 | 2023-02-20 | 2023-01-11 | 2023-07-18 | 2023-03-06 | 2023-02-20 | 2024-02-05 | 2024-01-22 | 2024-01-29 | -7 | 18 | 54
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Decarbonator Fans | CANADA BLOWER | 4504041388 | Rotating Equipment | Blowers & Fans | USD | 76063 | USD | 31944 | 44119 | Design Optimizations | 2023-09-18 | 2023-06-15 | 2023-07-05 | 2023-10-16 | 2023-11-14 | 2023-11-14 | 2023-10-30 | 2023-08-02 | 2024-04-15 | 2023-11-22 | 2024-02-02 | -72 | 30 | 48
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Motorized Mixers | SHARPE MIXERS | 4504001954 | Rotating Equipment | Mixers | USD | 182776 | USD | 261163 | -78387 | Market Impact | 2023-08-09 | 2023-01-31 | 2023-03-02 | 2023-09-06 | 2023-04-22 | 2023-08-26 | 2023-09-20 | 2023-05-25 | 2024-03-20 | 2023-11-09 | 2024-01-14 | -66 | 24 | 114
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Thermal Pumps | ITT GOULDS PUMPS INC | 4504013367 | Rotating Equipment | Centrifugal Pumps | USD | 453381 | USD | 453948 | -567 | Specs / Requirements Misinterpreted in Proposal | 2023-04-14 | 2023-04-18 | 2023-05-11 | 2023-05-12 | 2023-05-24 | 2023-08-18 | 2023-06-02 | 2023-06-15 | 2023-12-22 | 2023-12-20 | 2023-12-21 | -1 | 24 | 58
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | UF, IX, RO Pumps (Site) | SULZER PUMPS (CANADA) INC. | 4504024139 | Rotating Equipment | Centrifugal Pumps | USD | 2550899 | USD | 2361701 | 189198 | Frame Agreements | 2023-04-14 | 2023-04-25 | 2023-05-26 | 2023-05-12 | 2023-06-16 | 2023-09-25 | 2023-05-26 | 2023-07-03 | 2023-12-22 | 2024-03-07 | 2024-01-29 | 38 | 24 | 69
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Chemical Transfer Pumps - IX | ITT GOULDS PUMPS INC | 4504018455 | Rotating Equipment | Centrifugal Pumps | USD | 55404 | USD | 24750 | 30654 | Design Optimizations | 2023-04-14 | 2023-04-25 | 2023-05-19 | 2023-05-12 | 2023-06-18 | 2023-08-18 | 2023-05-26 | 2023-06-23 | 2023-12-22 | 2023-11-24 | 2023-12-08 | -14 | 24 | 59
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | Chemical Transfer Pumps - IX | ITT GOULDS PUMPS INC | 4504018547 | Rotating Equipment | Centrifugal Pumps | USD | 161616 | USD | 99000 | 62616 | Supplier Competitions / Negotiation | 2023-04-14 | 2023-04-25 | 2023-05-18 | 2023-05-12 | 2023-06-18 | 2023-08-18 | 2023-05-26 | 2023-06-23 | 2023-12-22 | 2023-11-24 | 2023-12-08 | -14 | 24 | 59
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | UF, IX, RO Pumps (Third Party Assembler) | SULZER PUMPS (CANADA) INC. | 4504024151 | Rotating Equipment | Centrifugal Pumps | USD | 830102 | USD | 593121 | 236981 | Frame Agreements | 2023-04-14 | 2023-04-25 | 2023-05-23 | 2023-05-12 | 2023-06-17 | 2023-08-18 | 2023-05-26 | 2023-07-03 | 2023-12-22 | 2023-12-14 | 2023-12-18 | -4 | 24 | 69
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | RO, UF Pumps | SULZER PUMPS (CANADA) INC. | 4504024166 | Rotating Equipment | Centrifugal Pumps | USD | 75000 | USD | 64008 | 10992 | Frame Agreements | 2023-04-14 | 2023-04-25 | 2023-05-23 | 2023-05-12 | 2023-06-17 | 2023-08-18 | 2023-05-26 | 2023-07-03 | 2023-12-22 | 2023-12-14 | 2023-12-18 | -4 | 24 | 69
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Process Tanks (Crystallizer Distillate,Centrate,Fines Storage,Concentrator Distillate, Distillate Collection) | Arrow Tanks | 4503992115 | Fabrication | Stainless Steel | USD | 1214684 | USD | 1118758 | 95926 | Supplier Competitions / Negotiation | 2023-09-08 | 2023-02-02 | 2023-04-13 | 2023-10-06 | 2023-04-22 | 2023-09-24 | 2023-10-20 | 2023-05-10 | 2024-05-16 | 2024-01-17 | 2024-03-17 | -60 | 24 | 97
510021 | ZLD Blue Sky Sundt Kiewit JV | Guelph | Butterfly & Ball Manual Valves | BRAY CONTROLS CANADA LTD | 4504033492 | Flow Control | Metal Isolation Valves | USD | 353727 | USD | 342307 | 11420 | Design Optimizations | 2023-05-12 | 2023-04-24 | 2023-05-11 | 2023-06-16 | 2023-06-18 | 2023-09-07 | 2023-06-23 | 2023-07-16 | 2023-12-22 | 2024-01-21 | 2024-01-06 | 15 | 12 | 83
510021 | ZLD Blue Sky Sundt Kiewit JV | Leonia | Butterfly & Ball Manual Valves | BRAY CONTROLS CANADA LTD | 4504038944 | Flow Control | Metal Isolation Valves | USD | 200000 | USD | 212376 | -12376 | Specs / Requirements Misinterpreted in Proposal | 2023-05-12 | 2023-04-24 | 2023-05-11 | 2023-06-16 | 2023-06-19 | 2023-08-23 | 2023-06-23 | 2023-07-26 | 2023-12-22 | 2023-12-14 | 2023-12-18 | -4 | 12 | 93
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | Valves Diaphragm | GEMU Valves, Inc. | 4504016857 | Flow Control | Metal Isolation Valves | USD | 40000 | USD | 19924 | 20076 | Frame Agreements | 2023-03-31 | 2023-03-02 | 2023-03-16 | 2023-04-28 | 2023-05-09 | 2023-07-27 | 2023-05-12 | 2023-06-21 | 2023-12-22 | 2023-10-31 | 2023-11-26 | -26 | 24 | 111
510021 | ZLD Blue Sky Sundt Kiewit JV | Leonia | RO - Modulating Control Valves | LAKESIDE PROCESS CONTROLS LTD. | 4504022856 | Flow Control | Metal Control Valves | USD | 55000 | USD | 53366 | 1634 | Supplier Competitions / Negotiation | 2023-05-26 | 2023-03-21 | 2023-06-15 | 2023-06-23 | 2023-06-18 | 2023-08-06 | 2023-07-07 | 2023-06-30 | 2023-12-22 | 2023-12-22 | 2023-12-22 | 0 | 24 | 101
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | IX - ON/OFF Butterfly Valves | BRAY CONTROLS CANADA LTD | 4504026084 | Flow Control | Metal Control Valves | USD | 316000 | USD | 315606 | 394 | Supplier Competitions / Negotiation | 2023-05-26 | 2023-04-10 | 2023-05-25 | 2023-06-23 | 2023-07-05 | 2023-08-16 | 2023-07-07 | 2023-07-07 | 2023-12-22 | 2023-10-10 | 2023-11-15 | -36 | 24 | 88
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Thermal - Modulating Control Valves | Samson Controls Inc. | 4504006399 | Flow Control | Metal Control Valves | USD | 145000 | USD | 140740 | 4260 | Frame Agreements | 2023-05-26 | 2023-04-07 | 2023-04-24 | 2023-06-23 | 2023-05-14 | 2023-08-14 | 2023-07-07 | 2023-06-05 | 2023-12-22 | 2023-12-05 | 2023-12-13 | -8 | 24 | 59
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | UF - Modulating Control Valves | LAKESIDE PROCESS CONTROLS LTD. | 4504013268 | Flow Control | Metal Control Valves | USD | 125000 | USD | 123336 | 1664 | Design Optimizations | 2023-05-26 | 2023-04-10 | 2023-04-26 | 2023-06-23 | 2023-06-12 | 2023-08-16 | 2023-07-07 | 2023-06-15 | 2023-12-22 | 2023-11-11 | 2023-12-01 | -20 | 24 | 66
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | IX - Modulating Control Valves (Butterfly) | LAKESIDE PROCESS CONTROLS LTD. | 4504010101 | Flow Control | Metal Control Valves | USD | 145000 | USD | 144808 | 192 | Supplier Competitions / Negotiation | 2023-05-26 | 2023-04-14 | 2023-05-10 | 2023-06-23 | 2023-06-18 | 2023-08-18 | 2023-07-07 | 2023-06-30 | 2023-12-22 | 2023-12-22 | 2023-12-22 | 0 | 24 | 77
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | UF - ON/OFF Butterfly Valves | BRAY CONTROLS CANADA LTD | 4504024228 | Flow Control | Metal Control Valves | USD | 172000 | USD | 118095 | 53905 | Design Optimizations | 2023-05-26 | 2023-04-14 | 2023-05-05 | 2023-06-23 | 2023-06-20 | 2023-08-18 | 2023-07-07 | 2023-07-03 | 2023-12-22 | 2023-11-13 | 2023-12-02 | -19 | 24 | 80
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | RO - ON/OFF Valves (Butterfly Type) | BRAY CONTROLS CANADA LTD | 4504030805 | Flow Control | Metal Control Valves | USD | 427000 | USD | 445286 | -18286 | Specs / Requirements Misinterpreted in Proposal | 2023-05-26 | 2023-04-14 | 2023-05-26 | 2023-06-23 | 2023-06-27 | 2023-08-18 | 2023-07-07 | 2023-07-13 | 2023-12-22 | 2023-11-23 | 2023-12-07 | -14 | 24 | 90
510021 | ZLD Blue Sky Sundt Kiewit JV | Leonia | Thermal - ON/OFF Ball Valves | LAKESIDE PROCESS CONTROLS LTD. | 4504030650 | Flow Control | Metal Control Valves | USD | 84100 | USD | 84090 | 10 | Supplier Competitions / Negotiation | 2023-05-26 | 2023-04-14 | 2023-06-14 | 2023-06-23 | 2023-06-13 | 2023-08-18 | 2023-07-07 | 2023-07-14 | 2023-12-22 | 2023-10-13 | 2023-11-17 | -35 | 24 | 91
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | RO - Modulating Control Valves | LAKESIDE PROCESS CONTROLS LTD. | 4504022857 | Flow Control | Metal Control Valves | USD | 13500 | USD | 13226 | 274 | Design Optimizations | 2023-05-26 | 2023-04-14 | 2023-06-15 | 2023-06-23 | 2023-06-18 | 2023-08-18 | 2023-07-07 | 2023-06-29 | 2023-12-22 | 2023-10-05 | 2023-11-13 | -39 | 24 | 76
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | RO - Modulating Control Valves | LAKESIDE PROCESS CONTROLS LTD. | 4504022840 | Flow Control | Metal Control Valves | USD | 686000 | USD | 685499 | 501 | Design Optimizations | 2023-05-26 | 2023-04-14 | 2023-06-15 | 2023-06-23 | 2023-06-19 | 2023-08-18 | 2023-07-07 | 2023-06-30 | 2023-12-22 | 2023-12-22 | 2023-12-22 | 0 | 24 | 77
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | RO - ON/OFF Valves (Ball Type) | LAKESIDE PROCESS CONTROLS LTD. | 4504031752 | Flow Control | Metal Control Valves | USD | 215800 | USD | 215800 | 0 | Market Impact | 2023-05-26 | 2023-04-14 | 2023-07-06 | 2023-06-23 | 2023-07-04 | 2023-08-29 | 2023-07-07 | 2023-07-16 | 2023-12-22 | 2024-01-14 | 2024-01-02 | 12 | 24 | 93
510021 | ZLD Blue Sky Sundt Kiewit JV | Leonia | Thermal - ON/OFF & Modulating Plug Valves | EVEREST AUTOMATION INC. | 4504030950 | Flow Control | Metal Control Valves | USD | 88600 | USD | 88574 | 26 | Supplier Competitions / Negotiation | 2023-05-26 | 2023-04-14 | 2023-04-13 | 2023-06-23 | 2023-06-10 | 2023-08-17 | 2023-07-07 | 2023-07-14 | 2023-12-22 | 2023-12-04 | 2023-12-13 | -9 | 24 | 91
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Crystallizers Vapor Body & Heaters | HARRIS THERMAL TRANSFER | 4503951883 | Fabrication | Alloy Steel | USD | 4458000 | USD | 4578300 | -120300 | Size/ Weight/ Quantity Underestimated | 2023-01-11 | 2022-12-28 | 2023-01-18 | 2023-02-08 | 2023-01-11 | 2023-02-09 | 2023-02-22 | 2023-02-08 | 2024-04-17 | 2024-03-24 | 2024-04-05 | -12 | 24 | 42
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | WAC Vessel Lining and Painting | BRANT CORROSION CONTROL, | 4503995626 | Fabrication | Non-Metal Equipment | USD | 447402 | USD | 424536 | 22866 | Supplier Competitions / Negotiation | 2023-08-18 | 2023-02-06 | 2023-03-15 | 2023-09-15 | 2023-05-07 | 2023-08-26 | 2023-09-29 | 2023-05-16 | 2024-03-15 | 2024-01-17 | 2024-02-15 | -29 | 12 | 99
510021 | ZLD Blue Sky Sundt Kiewit JV | Oakville | RO Pressure Vessels | PENTAIR FILTRATION SOLUTIONS, LLC | 4504000295 | Flow Control | RO membrane housings | USD | 938100 | USD | 850000 | 88100 | Frame Agreements | 2023-04-14 | 2023-02-07 | 2023-03-02 | 2023-05-12 | 2023-04-22 | 2023-07-16 | 2023-05-26 | 2023-05-26 | 2023-12-22 | 2023-12-11 | 2023-12-16 | -5 | 24 | 108
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Concentrator Mist Eliminators | COSTACURTA SPA - VICO | 4503986194 | Fabrication | Alloy Steel | USD | 20000 | USD | 10729 | 9271 | Design Optimizations | 2023-07-21 | 2023-02-02 | 2023-03-07 | 2023-08-18 | 2023-03-16 | 2023-08-17 | 2023-09-01 | 2023-04-27 | 2024-03-01 | 2023-08-17 | 2023-11-23 | -98 | 18 | 84
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Crystallizer Vapor Bodies Mist Eliminators | COSTACURTA SPA - VICO | 4503986214 | Fabrication | Alloy Steel | USD | 71324 | USD | 21140 | 50184 | Supplier Competitions / Negotiation | 2023-07-21 | 2023-02-02 | 2023-03-07 | 2023-08-18 | 2023-03-16 | 2023-08-17 | 2023-09-01 | 2023-04-27 | 2024-03-01 | 2023-08-17 | 2023-11-23 | -98 | 18 | 84
510021 | ZLD Blue Sky Sundt Kiewit JV | Bellevue | Decarbonator | DIAMOND FIBERGLASS | 4504042371 | Fabrication | Stainless Steel | USD | 169800 | USD | 228440 | -58640 | Estimate Without Market Reference(No Quote) | 2023-07-21 | 2023-02-07 | 2023-02-24 | 2023-08-18 | 2023-07-25 | 2023-08-20 | 2023-09-01 | 2023-08-03 | 2024-03-01 | 2024-01-18 | 2024-02-08 | -21 | 12 | 177
510012 | Blue Sky Azoles | Richmond | AOP Ozone Generator Vessels | JNBV | 4503983599 | Fabrication | Stainless Steel | USD | 244160 | USD | 142500 | 101660 | Supplier Competitions / Negotiation | 2023-03-24 | 2023-03-10 | 2023-03-27 | 2023-04-07 | 2023-03-25 | 2023-07-14 | 2023-04-21 | 2023-04-25 | 2023-11-17 | 2023-09-22 | 2023-10-20 | -28 | 12 | 46
510012 | Blue Sky Azoles | Richmond | AOP Tubes | Li Yang Si Fang STAINLESS STEEL PRODU | 4503983569 | Fabrication | Stainless Steel | USD | 99931 | USD | 63831 | 36100 | Design Optimizations | 2023-03-03 | 2023-01-17 | 2023-01-17 | 2023-03-17 | 2023-01-16 | 2023-04-06 | 2023-03-31 | 2023-04-24 | 2023-06-16 | 2023-06-26 | 2023-06-21 | 5 | 12 | 97
510012 | Blue Sky Azoles | Richmond | AOP OG internals (inventory) | 3W - Infilco Warehouse | 4503983871 | Fabrication | Stainless Steel | USD | 276064 | USD | 197582 | 78482 | Supplier Competitions / Negotiation | 2023-10-13 | 2023-04-23 | 2023-04-25 | 2023-10-27 | 2023-04-23 | 2023-08-05 | 2023-11-10 | 2023-04-25 | 2023-11-17 | 2023-11-02 | 2023-11-09 | -7 | 12 | 2
510012 | Blue Sky Azoles | Richmond | AOP Injectors | Korting Hannover GmbH | 4504022065 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 37500 | EUR | 33825 | 3675 | Supplier Competitions / Negotiation | 2023-06-30 | 2023-05-15 | 2023-06-19 | 2023-07-14 | 2023-06-07 | 2023-09-13 | 2023-07-28 | 2023-06-28 | 2024-01-12 | 2023-10-09 | 2023-11-25 | -47 | 12 | 44
510012 | Blue Sky Azoles | Richmond | AOP Contact Tank & Ancillaries | CAID | 4503957956 | Fabrication | Stainless Steel | USD | 965319 | USD | 583900 | 381419 | Design Optimizations | 2023-02-10 | 2023-02-10 | 2023-03-09 | 2023-02-24 | 2023-03-03 | 2023-08-28 | 2023-03-10 | 2023-03-09 | 2024-03-15 | 2023-10-16 | 2023-12-30 | -75 | 12 | 27
510012 | Blue Sky Azoles | Richmond | Centrifugal Pumps (MMF Feed/Backwash/Backwash Waste /AOP Ozone Feed / MBR Feed/RAS/WAS) - Skid Assembler | SULZER PUMP SOLUTIONS - USA | 4504017096 | Rotating Equipment | Centrifugal Pumps | USD | 240312 | USD | 257054 | -16742 | Market Impact | 2023-04-21 | 2023-04-21 | 2023-06-22 | 2023-05-05 | 2023-06-19 | 2023-08-31 | 2023-05-19 | 2023-06-27 | 2023-12-15 | 2024-01-11 | 2023-12-28 | 14 | 30 | 67
510012 | Blue Sky Azoles | Richmond | Centrifugal Pumps (AOP CW, Injection, Drain Booster Pumps) - Ancaster | SULZER PUMP SOLUTIONS - USA | 4504019444 | Rotating Equipment | Centrifugal Pumps | USD | 148426 | USD | 148426 | 0 | Supplier Competitions / Negotiation | 2023-04-21 | 2023-04-21 | 2023-06-22 | 2023-05-05 | 2023-06-20 | 2023-08-20 | 2023-05-19 | 2023-06-28 | 2023-12-15 | 2023-12-20 | 2023-12-17 | 3 | 30 | 68
510012 | Blue Sky Azoles | Richmond | AOP Heat Exchanger (CLCW) | ALFA LAVAL | 4504019625 | Rotating Equipment | Heat Exchangers | USD | 48000 | USD | 20900 | 27100 | Design Optimizations | 2023-06-09 | 2022-12-13 | 2023-06-12 | 2023-06-23 | 2023-06-12 | 2023-06-18 | 2023-07-07 | 2023-06-26 | 2023-12-22 | 2023-12-08 | 2023-12-15 | -7 | 30 | 195
510012 | Blue Sky Azoles | Richmond | AOP PSU Enclosure | Metafab Inc | 4504010917 | Electrical & Instrumentation | Ele-nclosures | USD | 91234 | CAD | 91234 | 0 | Single Sourced | 2023-06-09 | 2023-05-03 | 2023-05-16 | 2023-06-23 | 2023-06-11 | 2023-08-06 | 2023-07-07 | 2023-06-11 | 2023-11-10 | 2023-10-01 | 2023-10-21 | -20 | 18 | 39
510012 | Blue Sky Azoles | Richmond | AOP PSU Heat Exchangers and Chillers | RefPlus | 4504012325 | Electrical & Instrumentation | Ele-Thermal Mgmt (Heater, A/C, Fan) | USD | 31706 | CAD | 31706 | 0 | Single Sourced | 2023-07-13 | 2023-03-31 | 2023-06-28 | 2023-07-27 | 2023-06-09 | 2023-07-31 | 2023-08-10 | 2023-06-10 | 2023-11-30 | 2023-08-19 | 2023-10-09 | -51 | 18 | 71
510012 | Blue Sky Azoles | Richmond | AOP PSU Transformers and Inductors | 3W - Infilco Warehouse | 4503970712 | Electrical & Instrumentation | Ele-Transformers, Power Supplies | USD | 48253 | USD | 48253 | 0 | Specs / Requirements Misinterpreted in Proposal | 2023-04-06 | 2023-03-31 | 2023-03-31 | 2023-04-20 | 2023-03-30 | 2023-07-30 | 2023-05-04 | 2023-03-30 | 2023-11-30 | 2023-09-21 | 2023-10-26 | -35 | 18 | -1
510012 | Blue Sky Azoles | Richmond | Overall PLC | ELECTRICAL EQUIPMENT COMP | 4503973755 | Electrical & Instrumentation | Ele-PLCs, HMIs | USD | 568796 | USD | 458184 | 110612 | Design Optimizations | 2023-01-19 | 2023-03-06 | 2023-03-20 | 2023-02-02 | 2023-07-14 | 2023-07-14 | 2023-02-16 | 2023-04-02 | 2023-11-30 | 2024-01-07 | 2023-12-19 | 19 | 18 | 27
510012 | Blue Sky Azoles | Richmond | MBR Analyzer-HACH | HACH CO - LOVELAND | 4504040595 | Electrical & Instrumentation | Inst-Analytical Instruments | USD | 139594 | USD | 47943 | 91651 | Frame Agreements | 2023-05-05 | 2023-05-29 | 2023-07-24 | 2023-05-19 | 2023-07-23 | 2023-08-10 | 2023-06-02 | 2023-08-02 | 2023-11-03 | 2023-11-16 | 2023-11-09 | 7 | 18 | 65
510012 | Blue Sky Azoles | Richmond | DD MAG Flow Meters | ENDRESS & HAUSER MN | 4504037198 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 14435 | USD | 14435 | 0 | Design Optimizations | 2023-05-05 | 2023-03-30 | 2023-06-26 | 2023-05-19 | 2023-07-26 | 2023-07-17 | 2023-06-02 | 2023-07-26 | 2023-11-03 | 2023-08-31 | 2023-10-02 | -32 | 18 | 118
510012 | Blue Sky Azoles | Richmond | AOP T-Mass Flow meter | ENDRESS & HAUSER MN | 4504047849 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 25863 | USD | 25863 | 0 | Design Optimizations | 2023-06-16 | 2023-05-01 | 2023-07-27 | 2023-06-30 | 2023-07-28 | 2023-08-23 | 2023-07-14 | 2023-08-14 | 2023-12-15 | 2023-12-01 | 2023-12-08 | -7 | 18 | 105
510012 | Blue Sky Azoles | Richmond | MBR MAG Flow Meter | ENDRESS & HAUSER MN | 4504042166 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 45437 | USD | 7564 | 37873 | Supplier Competitions / Negotiation | 2023-05-05 | 2023-05-20 | 2023-07-20 | 2023-05-19 | 2023-07-23 | 2023-08-04 | 2023-06-02 | 2023-08-02 | 2023-11-03 | 2023-11-03 | 2023-11-03 | 0 | 18 | 74
510012 | Blue Sky Azoles | Richmond | AOP Dew Point Analyzers (Skidded) | VERONICS INSTRUMENTS INC. | 4504040165 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 14675 | CAD | 14675 | 0 | Proposed Supplier Incapable Of Executing | 2023-06-16 | 2023-07-19 | 2023-07-19 | 2023-06-30 | 2023-07-21 | 2023-09-15 | 2023-07-14 | 2023-08-01 | 2023-12-15 | 2023-12-01 | 2023-12-08 | -7 | 18 | 13
510012 | Blue Sky Azoles | Richmond | AOP Mass Flow Controller | SRB Controls | 4504048074 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 16553 | CAD | 16553 | 0 | Design Optimizations | 2023-06-16 | 2023-05-01 | 2023-08-02 | 2023-06-30 | 2023-08-02 | 2023-08-23 | 2023-07-14 | 2023-08-15 | 2023-12-15 | 2023-12-01 | 2023-12-08 | -7 | 18 | 106
510012 | Blue Sky Azoles | Richmond | DD Modulating Control Valves | LAKESIDE PROCESS CONTROLS LTD. | 4504009340 | Flow Control | Metal Control Valves | USD | 37368 | USD | 37368 | 0 | Specs / Requirements Misinterpreted in Proposal | 2023-04-28 | 2023-03-13 | 2023-05-11 | 2023-05-12 | 2023-05-13 | 2023-08-22 | 2023-05-26 | 2023-06-07 | 2024-02-01 | 2024-01-14 | 2024-01-23 | -9 | 12 | 86
510012 | Blue Sky Azoles | Richmond | DD ON/OFF Plug Valves | EVEREST AUTOMATION INC. | 4504025184 | Flow Control | Metal Control Valves | USD | 71326 | USD | 71326 | 0 | Not included in Proposal / RFQ | 2023-04-28 | 2023-04-11 | 2023-06-21 | 2023-05-12 | 2023-06-23 | 2023-08-23 | 2023-05-26 | 2023-07-04 | 2024-01-05 | 2023-12-21 | 2023-12-28 | -7 | 12 | 84
510012 | Blue Sky Azoles | Richmond | MBR Skidded ON/OFF BFVs | BRAY CONTROLS CANADA LTD | 4504032072 | Flow Control | Metal Control Valves | USD | 10486 | USD | 10486 | 0 | Design Optimizations | 2023-04-28 | 2023-05-09 | 2023-07-05 | 2023-05-18 | 2023-07-16 | 2023-09-01 | 2023-05-26 | 2023-07-17 | 2024-01-05 | 2023-12-21 | 2023-12-28 | -7 | 12 | 69
510012 | Blue Sky Azoles | Richmond | AOP AUTOMATED ON/OFF BFVs (UV Skid) | BRAY CONTROLS CANADA LTD | 4504038631 | Flow Control | Metal Control Valves | USD | 7493 | USD | 7493 | 0 | Specs / Requirements Misinterpreted in Proposal | 2023-06-30 | 2023-06-07 | 2023-07-18 | 2023-07-14 | 2023-07-18 | 2023-09-14 | 2023-07-28 | 2023-07-28 | 2023-12-15 | 2023-12-22 | 2023-12-18 | 4 | 12 | 51
510012 | Blue Sky Azoles | Richmond | MBR Modulating Control Valves | LAKESIDE PROCESS CONTROLS LTD. | 4504038947 | Flow Control | Metal Control Valves | USD | 32986 | USD | 32986 | 0 | Market Impact | 2023-04-28 | 2023-05-12 | 2023-07-11 | 2023-05-18 | 2023-07-17 | 2023-09-01 | 2023-05-26 | 2023-07-28 | 2024-01-05 | 2023-12-22 | 2023-12-29 | -7 | 12 | 77
510012 | Blue Sky Azoles | Richmond | AOP Automated ON/OFF BVs (Skidded) | LAKESIDE PROCESS CONTROLS LTD. | 4504042393 | Flow Control | Metal Control Valves | USD | 8514 | USD | 8514 | 0 | Design Optimizations | 2023-06-30 | 2023-05-23 | 2023-08-03 | 2023-07-14 | 2023-08-01 | 2023-09-06 | 2023-07-28 | 2023-08-03 | 2023-12-15 | 2023-12-21 | 2023-12-18 | 3 | 12 | 72
510012 | Blue Sky Azoles | Richmond | AOP Modulating Control Valves (Skidded) | LAKESIDE PROCESS CONTROLS LTD. | 4504048034 | Flow Control | Metal Control Valves | USD | 121138 | USD | 121138 | 0 | Proposed Supplier Incapable Of Executing | 2023-06-30 | 2023-06-07 | 2023-08-04 | 2023-07-14 | 2023-08-04 | 2023-09-10 | 2023-07-28 | 2023-08-15 | 2023-12-15 | 2023-11-28 | 2023-12-06 | -8 | 12 | 69
510012 | Blue Sky Azoles | Richmond | AOP AUTOMATED ON/OFF BFVs (Ancaster Skids) | BRAY CONTROLS CANADA LTD | 4504038681 | Flow Control | Metal Control Valves | USD | 30762 | USD | 30762 | 0 | Design Optimizations | 2023-06-30 | 2023-09-25 | 2023-07-18 | 2023-07-14 | 2023-07-18 | 2023-09-25 | 2023-07-28 | 2023-07-28 | 2023-12-15 | 2023-12-22 | 2023-12-18 | 4 | 12 | -59
510012 | Blue Sky Azoles | Richmond | AOP UV Deozonation Unit | Trojan Technologies INC. | 4504026423 | Fabrication | Process Equipment | USD | 204980 | USD | 168533 | 36447 | Design Optimizations | 2023-06-02 | 2023-06-02 | 2023-06-28 | 2023-06-16 | 2023-06-27 | 2023-09-08 | 2023-06-30 | 2023-07-07 | 2023-12-15 | 2023-12-01 | 2023-12-08 | -7 | 12 | 35
510012 | Blue Sky Azoles | Richmond | DD Filter Press | Andritz Separation Technologies Inc. | 4504000975 | Rotating Equipment | Filter Press | USD | 742084 | USD | 685400 | 56684 | Frame Agreements | 2023-03-03 | 2023-03-03 | 2023-05-24 | 2023-03-17 | 2023-05-22 | 2023-09-08 | 2023-03-31 | 2023-05-24 | 2024-03-15 | 2024-02-29 | 2024-03-07 | -7 | 30 | 82
510012 | Blue Sky Azoles | Richmond | DD Reactor Drives | SEW EURODRIVE | 4503997946 | Rotating Equipment | Electric Motors | USD | 19695 | USD | 10455 | 9240 | Supplier Competitions / Negotiation | 2023-03-10 | 2023-03-02 | 2023-05-12 | 2023-03-24 | 2023-05-15 | 2023-07-13 | 2023-04-07 | 2023-05-18 | 2023-11-03 | 2023-11-23 | 2023-11-13 | 10 | 30 | 77
510012 | Blue Sky Azoles | Richmond | DD Scraper Drives | DBS MANUFACTURING INC. | 4503966240 | Rotating Equipment | Electric Motors | USD | 65635 | USD | 51348 | 14287 | Design Optimizations | 2023-03-10 | 2023-03-02 | 2023-03-03 | 2023-03-24 | 2023-03-20 | 2023-07-03 | 2023-04-07 | 2023-03-22 | 2023-11-03 | 2023-09-20 | 2023-10-12 | -22 | 30 | 20
510012 | Blue Sky Azoles | Richmond | DD Rapid, Backwash waste mixers, sludge holding tank mixers | SPX FLOW US LLC | 4503993033 | Rotating Equipment | Mixers | USD | 100190 | USD | 109426 | -9236 | Proposed Supplier Incapable Of Executing | 2023-03-31 | 2023-03-10 | 2023-05-05 | 2023-04-14 | 2023-05-04 | 2023-06-26 | 2023-04-28 | 2023-05-08 | 2023-10-13 | 2023-08-28 | 2023-09-20 | -23 | 30 | 59
510012 | Blue Sky Azoles | Richmond | MBR Pre-Anoxic (Submersible) Mixers | KSB Pumps Inc. | 4504008679 | Rotating Equipment | Mixers | USD | 75466 | USD | 31091 | 44375 | Supplier Competitions / Negotiation | 2023-03-31 | 2023-03-23 | 2023-05-19 | 2023-04-14 | 2023-05-21 | 2023-07-29 | 2023-04-28 | 2023-06-05 | 2023-10-13 | 2023-12-04 | 2023-11-08 | 26 | 30 | 74
510012 | Blue Sky Azoles | Richmond | MBR/MMF Blowers | AERZEN CANADA INC. | 4504010087 | Rotating Equipment | Blowers & Fans | USD | 100337 | CAD | 120835 | -20498 | Proposed Supplier Incapable Of Executing | 2023-03-31 | 2023-03-23 | 2023-05-26 | 2023-04-14 | 2023-05-24 | 2023-07-25 | 2023-04-28 | 2023-06-08 | 2023-11-10 | 2023-11-26 | 2023-11-18 | 8 | 30 | 77
510012 | Blue Sky Azoles | Richmond | DD Sludge Recycle(8 EA)/Blowdown pumps(8 EA) - Progressive Cavity Pumps | SEEPEX - USA | 4503973304 | Rotating Equipment | PD Pumps | USD | 145165 | USD | 130988 | 14177 | Supplier Competitions / Negotiation | 2023-03-31 | 2023-03-02 | 2023-07-13 | 2023-04-14 | 2023-03-30 | 2023-06-22 | 2023-04-28 | 2023-04-05 | 2023-10-13 | 2023-09-29 | 2023-10-06 | -7 | 30 | 34
510012 | Blue Sky Azoles | Richmond | MMF Fabrication | Arrow Tanks | 4504025990 | Fabrication | Alloy Steel | USD | 276322 | USD | 255000 | 21322 | Design Optimizations | 2023-06-30 | 2023-05-09 | 2023-06-05 | 2023-07-14 | 2023-06-18 | 2023-11-05 | 2023-07-28 | 2023-07-04 | 2024-05-03 | 2023-12-19 | 2024-02-25 | -68 | 12 | 56
510012 | Blue Sky Azoles | Richmond | MBR Rotary Lobe Pumps (Z-Mod Skid) | BOERGER LLC | 4504000346 | Rotating Equipment | PD Pumps | USD | 76351 | USD | 40837 | 35514 | Supplier Competitions / Negotiation | 2023-03-31 | 2023-03-30 | 2023-05-17 | 2023-04-14 | 2023-05-21 | 2023-07-06 | 2023-04-28 | 2023-05-26 | 2023-10-13 | 2023-08-31 | 2023-09-21 | -21 | 30 | 57
510012 | Blue Sky Azoles | Richmond | MBR Diffusion Grid | ENVIRONMENTAL DYNAMICS INTERNATIONAL | 4504013484 | Flow Control | Injection Quills, Ejectors, Diffusers | USD | 30000 | USD | 47100 | -17100 | Market Impact | 2023-06-30 | 2023-03-29 | 2023-05-22 | 2023-07-14 | 2023-05-28 | 2023-07-30 | 2023-07-28 | 2023-06-14 | 2023-12-01 | 2023-11-16 | 2023-11-23 | -7 | 12 | 77
510012 | Blue Sky Azoles | Richmond | Membrane HX | ALFA LAVAL | 4504009978 | Rotating Equipment | Heat Exchangers | USD | 25000 | USD | 20550 | 4450 | Frame Agreements | 2023-06-09 | 2023-03-15 | 2023-05-19 | 2023-06-23 | 2023-06-08 | 2023-08-03 | 2023-07-07 | 2023-06-08 | 2023-12-22 | 2023-10-05 | 2023-11-13 | -39 | 30 | 85
510670 | Blue Sky FabWW | Richmond | Densadeg fabricated items - tanks, impeller, scraper, falk coupling, sludge handling, sample system | SHARP IRON GROUP | 4504004132 | Fabrication | Carbon Steel | USD | 2918740 | USD | 2254800 | 663940 | Frame Agreements | 2023-04-21 | 2023-05-19 | 2023-05-25 | 2023-05-05 | 2023-05-25 | 2023-09-10 | 2023-05-19 | 2023-05-31 | 2023-09-22 | 2024-01-31 | 2023-11-26 | 66 | 12 | 12
510670 | Blue Sky FabWW | Richmond | Densadeg Anchor Channels | SHARP IRON GROUP | 4503981262 | Fabrication | Carbon Steel | USD | 56331 | USD | 56331 | 0 | Not included in Proposal / RFQ | 2023-04-21 | 2023-04-06 | 2023-04-18 | 2023-05-05 | 2023-04-15 | 2023-06-29 | 2023-05-19 | 2023-04-20 | 2023-09-22 | 2023-06-02 | 2023-07-28 | -56 | 12 | 14
510670 | Blue Sky FabWW | Richmond | Lime/Soda Ash Feed System | CTS Global Systems | 4504033041 | Rotating Equipment | Chem. Feed Skids (Turnkey) | USD | 2103762 | USD | 306523 | 1797239 | Design Optimizations | 2023-03-31 | 2023-04-21 | 2023-06-08 | 2023-04-14 | 2023-05-27 | 2023-08-26 | 2023-04-28 | 2023-07-09 | 2023-12-22 | 2024-01-21 | 2024-01-06 | 15 | 30 | 79
510670 | Blue Sky FabWW | Richmond | Reactor Drives | SEW EURODRIVE | 4504000072 | Rotating Equipment | Electric Motors | USD | 59528 | USD | 34163 | 25365 | Design Optimizations | 2023-06-21 | 2023-01-26 | 2023-05-23 | 2023-07-05 | 2023-05-13 | 2023-07-16 | 2023-07-19 | 2023-05-24 | 2024-01-03 | 2023-09-13 | 2023-11-08 | -56 | 30 | 118
510670 | Blue Sky FabWW | Richmond | Scraper Drives | DBS MANUFACTURING INC. | 4503965544 | Rotating Equipment | Electric Motors | USD | 112763 | USD | 140059 | -27296 | Not included in Proposal / RFQ | 2023-06-21 | 2023-01-26 | 2023-03-03 | 2023-07-05 | 2023-03-06 | 2023-07-16 | 2023-07-19 | 2023-03-21 | 2024-01-03 | 2023-09-20 | 2023-11-11 | -52 | 30 | 54
510670 | Blue Sky FabWW | Richmond | Rapid, pH adjust tank, effluent break tank and lime reaction tank mixers | SPX FLOW US LLC | 4503992892 | Rotating Equipment | Mixers | USD | 468428 | USD | 342405 | 126023 | Frame Agreements | 2023-06-21 | 2023-03-10 | 2023-05-04 | 2023-07-05 | 2023-04-28 | 2023-08-06 | 2023-07-19 | 2023-05-07 | 2024-01-03 | 2023-10-24 | 2023-11-28 | -35 | 30 | 58
510670 | Blue Sky FabWW | Richmond | Sludge Recycle/Blowdown pumps - Progressive Cavity Pumps | SEEPEX - USA | 4503960630 | Rotating Equipment | PD Pumps | USD | 118609 | USD | 181247 | -62638 | Estimate Without Market Reference(No Quote) | 2023-03-08 | 2023-02-03 | 2023-07-13 | 2023-03-22 | 2023-02-28 | 2023-08-04 | 2023-04-05 | 2023-03-14 | 2023-09-20 | 2024-02-02 | 2023-11-26 | 68 | 30 | 39
510670 | Blue Sky FabWW | Richmond | HMI + Software | Wonderware Canada | 4504039721 | Electrical & Instrumentation | Ele-Control Panels | USD | 17155 | CAD | 17155 | 0 | Supplier Competitions / Negotiation | 2023-03-29 | 2023-07-18 | 2023-07-26 | 2023-04-12 | 2023-07-30 | 2023-07-26 | 2023-04-26 | 2023-07-30 | 2023-11-22 | 2023-09-10 | 2023-10-16 | -36 | 18 | 12
510670 | Blue Sky FabWW | Richmond | VFDs | ENGINEERED ELECTRIC CONTROLS LIMITED | 4504029815 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 774226 | CAD | 230757 | 543469 | Frame Agreements | 2023-05-10 | 2023-05-26 | 2023-06-27 | 2023-05-24 | 2023-06-27 | 2023-08-31 | 2023-06-07 | 2023-07-13 | 2023-11-22 | 2023-12-22 | 2023-12-07 | 15 | 18 | 48
510670 | Blue Sky FabWW | Richmond | PLC Components | ELECTRICAL EQUIPMENT COMP | 4503973734 | Electrical & Instrumentation | Ele-VFDs, DC Drives, Rectifiers | USD | 235372 | USD | 235372 | 0 | Estimate Without Market Reference(No Quote) | 2023-05-10 | 2023-03-06 | 2023-03-21 | 2023-05-24 | 2023-03-16 | 2023-07-14 | 2023-06-07 | 2023-04-03 | 2023-11-22 | 2023-11-15 | 2023-11-18 | -3 | 18 | 28
510670 | Blue Sky FabWW | Richmond | Modulating Control Valves | LAKESIDE PROCESS CONTROLS LTD. | 4504000928 | Flow Control | Metal Control Valves | USD | 119100 | USD | 119100 | 0 | Market Impact | 2023-05-10 | 2023-03-13 | 2023-05-11 | 2023-05-24 | 2023-05-15 | 2023-07-18 | 2023-06-07 | 2023-05-25 | 2023-11-22 | 2023-08-25 | 2023-10-08 | -44 | 12 | 73
510670 | Blue Sky FabWW | Richmond | Automated ON/OFF Plug Valves | EVEREST AUTOMATION INC. | 4504025551 | Flow Control | Metal Control Valves | USD | 101088 | USD | 101088 | 0 | Size/ Weight/ Quantity Underestimated | 2023-05-10 | 2023-04-11 | 2023-06-15 | 2023-05-24 | 2023-07-24 | 2023-08-01 | 2023-06-07 | 2023-07-06 | 2023-11-22 | 2023-10-12 | 2023-11-01 | -20 | 12 | 86
510670 | Blue Sky FabWW | Richmond | Manual Plug Valves | EVEREST AUTOMATION INC. | 4504027568 | Flow Control | Metal Control Valves | USD | 40949 | USD | 40949 | 0 | Not included in Proposal / RFQ | 2023-05-10 | 2023-05-19 | 2023-07-05 | 2023-05-24 | 2023-07-06 | 2023-08-16 | 2023-06-07 | 2023-07-10 | 2023-11-22 | 2023-10-30 | 2023-11-10 | -11 | 12 | 52
510670 | Blue Sky FabWW | Richmond | Manual Valves (Ball, Butterfly, Check, Diaphragm) - Skidded | BRAY CONTROLS CANADA LTD | 4504046353 | Flow Control | Metal Control Valves | USD | 9282 | USD | 9282 | 0 | Design Optimizations | 2023-05-10 | 2023-05-19 | 2023-08-01 | 2023-05-24 | 2023-08-02 | 2023-08-23 | 2023-06-07 | 2023-08-10 | 2023-11-22 | 2023-12-07 | 2023-11-29 | 8 | 12 | 83
510670 | Blue Sky FabWW | Richmond | MAG Flow Meters | ENDRESS & HAUSER | 4504014508 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 68996 | USD | 68996 | 0 | Market Impact | 2023-04-12 | 2023-03-24 | 2023-06-22 | 2023-04-26 | 2023-05-30 | 2023-08-18 | 2023-05-10 | 2023-06-23 | 2023-10-25 | 2024-01-12 | 2023-12-03 | 40 | 18 | 91
510670 | Blue Sky FabWW | Richmond | Pressure Switches | CONVAL PROCESS SOLUTIONS | 4504046882 | Electrical & Instrumentation | Inst-Instrumentation Others | USD | 26901 | USD | 26901 | 0 | Size/ Weight/ Quantity Underestimated | 2023-04-12 | 2023-07-28 | 2023-08-11 | 2023-04-26 | 2023-08-08 | 2023-07-19 | 2023-05-10 | 2023-08-11 | 2023-10-25 | 2023-09-18 | 2023-10-06 | -18 | 18 | 14
510670 | Blue Sky FabWW | Richmond | Recycle Pump Skid assembly (outsource) | H+M Industrial EPC | 4504034694 | Fabrication | Skid Assembly Outsourced | USD | 397500 | USD | 352775 | 44725 | Frame Agreements | 2023-05-24 | 2023-06-12 | 2023-07-19 | 2023-06-07 | 2023-07-20 | 2023-11-30 | 2023-06-21 | 2023-07-21 | 2024-01-17 | 2024-06-07 | 2024-03-28 | 71 | 12 | 39
510670 | Blue Sky FabWW | Richmond | Static Mixers | KOFLO CORP | 4504034213 | Rotating Equipment | Mixers | USD | 16425 | USD | 16425 | 0 | Proposed Supplier Incapable Of Executing | 2023-06-22 | 2023-06-22 | 2023-06-30 | 2023-06-29 | 2023-07-19 | 2023-09-25 | 2023-07-13 | 2023-07-24 | 2023-12-30 | 2023-09-18 | 2023-11-08 | -51 | 30 | 32